## Activity Schedule_Updated (2)
Pipelines Asset Activity Plan
|  |  | Initial |  | New
| Activities | Duration | Start Date | End Date |  |  | 2021 | [6 empty] | 2022 | [11 empty] | Remarks | Action Parties
[7 empty] | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Evaluate all Safeguarding information
| Data/Information Gathering. | 3 weeks | 2021-09-06 | 30/06/2021 | bar: 2021 Jun
| Scope Definition | 1 week | 2021-01-07 | 2021-09-07 | bar: 2021 Jul
| Get/Agree CTR from SCiNDO | 1 week | 2021-12-07 | 16/07/2021 | bar: 2021 Jul
| Secure Budget from Pipeline Asset | 1 week | 19/7/2021 | 23/7/2021 | bar: 2021 Jul
| Contractor Identification, Selection and PO creation & delivery | 3 weeks | 26/7/2021 | 13/08/2021 | bar: 2021 Jul to 2021 Aug
| Execute SGM (Staggered for TRP, TNP & TEP) | 6 weeks | 16/08/2021 | 30/09/2021 | [21 empty] | TRP SGM Completed Oct. 2021 Other Pipeline networks oustanding. | TRP Completed | bar: 2021 Aug to 2021 Oct
| Final Report Completion | 2 weeks | 2021-04-10 | 18/10/2021 | bar: 2021 Oct
| Execute TEP SGM |  | 2021-01-12 | 28/02/2022 | 2021-01-12 | 28/02/2022 | [19 empty] | Discounting for leave days | Suanu (Asset Support) | bar: 2021 Oct; 2021 Dec to 2022 Feb
| Execute TNP SGM |  | 2021-01-12 | 28/02/2022 | 2021-01-12 | 28/02/2022 | [19 empty] | Discounting for leave days | Unwana (Asset Support) | bar: 2021 Oct; 2021 Dec to 2022 Feb
| Execute EGGS SGM | [24 empty] | Schedule to be provided after consultation with Pipelines Asset. | Suano (Asset Support) and Ayo (Pipelines)
2 | Conduct HAZOP
| Data/Information Gathering, List of all P&ID. | 3 weeks | 2021-09-06 | 30/06/2021 | bar: 2021 Jun
| Scope Definition, TOR Preparation | 2 week | 2021-01-07 | 16/7/2021 | bar: 2021 Jul
| Get/Agree CTR from SCiNDO | 1 week | 19/7/2021 | 23/07/2021 | bar: 2021 Jul
| Secure Budget from Pipeline Asset | 1 week | 26/7/2021 | 31/7/2021 | bar: 2021 Jul
| Identify/ Engage HAZOP Consultant, PO created & delivered | 3 weeks | 2021-02-08 | 23/08/2021 | bar: 2021 Jul to 2021 Aug
| Execute HAZOP (Staggered for TRP, TNP & TEP). | 8 weeks | 25/10/2021 | 20/12/2022 | 2022-07-03 | 22/04/2022 | bar: 2021 Oct to 2021 Dec; 2022 Mar to 2022 Apr
| HAZOP Report | 3 weeks | 2022-07-01 | 28/01/2022 | 25/04/2022 | 13/05/2022 | bar: 2022 Jan; 2022 May
3 | Develop and complete PSBR Compliance Report
| PSBR Gap Closure. Identification & Deployment of requisite resources to close the PSBR gaps. Staggered for the three pipelines. | 6 weeks | 2022-01-02 | 18/03/2022 | [22 empty] | Oluoma | bar: 2022 Feb to 2022 Mar
4 | Update BowTie Report
| BowTie Report. Stggered for the three pipelines. | 6 weeks | 21/03/2022 | 2022-05-05 | [22 empty] | Oluoma | bar: 2022 Mar to 2022 May
5 | Update ALARP Demonstration Report
| To be updated on completion of all other preceding studies which will feed into the ALARP Demonstration Report. | 4 weeks | 13/05/2022 | 15/06/2022 | 2022-01-08 | 31/08/2022 | bar: 2022 Jun
6 | Track Existing HEMP Actions and Closeout
| HEMP actions tracking and closure happening continuously. Focus will be on PS related Actions | Continuous | [24 empty] | Chizube
Legend
Initial Schedule
New Schedule
Completed Activity
Uncertainties
1 | Data/ Information Availability
2 | Completion of CTR agreement as per plan
3 | Contractor/ Vendor identification, selection and engegemnent as per plan
Support Required
1 | Dedicated staff from Pipelines Asset to provide support.
Assumptions:
1 | These are initial estimated dates/plans, which will be further refined once the CTR is agreed/completed.
2 | Available Budget to execute all activities
3 | HAZOP Execution to start after SGM completion. Relevant stakeholders to be used for HAZOP of each pipeline section.
4 | The activities are to be conducted on the three Pipelines - TRP (Trans-Ramos Pipeline), TNP (Trans-Niger Pipeline) and TEP (Trans-Escravos Pipeline). Studies to be conducted in a staggered manner.
5 | HEMP Actions: Focus will be on PS related Actions and requirements for closeout

## Activity Schedule
Pipelines Asset Activity Plan
| Activities | Duration | Start Date | End Date | 2021 | [6 empty] | 2022 | [11 empty] | Remarks
[5 empty] | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Evaluate all Safeguarding information
| Data/Information Gathering. | 3 weeks | 2021-09-06 | 30/06/2021 | bar: 2021 Jun
| Scope Definition | 1 week | 2021-01-07 | 2021-09-07 | bar: 2021 Jul
| Get/Agree CTR from SCiNDO | 1 week | 2021-12-07 | 16/07/2021 | bar: 2021 Jul
| Secure Budget from Pipeline Asset | 1 week | 19/7/2021 | 23/7/2021 | bar: 2021 Jul
| Contractor Identification, Selection and PO creation & delivery | 3 weeks | 26/7/2021 | 13/08/2021 | bar: 2021 Jul to 2021 Aug
| Execute SGM (Staggered for TRP, TNP & TEP) | 6 weeks | 16/08/2021 | 30/09/2021 | [19 empty] | Scenarios done. Calc. YTS Safety systems studies done | bar: 2021 Aug to 2021 Sep
| Final Report Completion | 2 weeks | 2021-04-10 | 18/10/2021 | bar: 2021 Oct
2 | Conduct HAZOP
| Data/Information Gathering, List of all P&ID. | 3 weeks | 2021-09-06 | 30/06/2021 | bar: 2021 Jun
| Scope Definition, TOR Preparation | 2 week | 2021-01-07 | 16/7/2021 | bar: 2021 Jul
| Get/Agree CTR from SCiNDO | 1 week | 19/7/2021 | 23/07/2021 | bar: 2021 Jul
| Secure Budget from Pipeline Asset | 1 week | 26/7/2021 | 31/7/2021 | bar: 2021 Jul
| Identify/ Engage HAZOP Consultant, PO created & delivered | 3 weeks | 2021-02-08 | 23/08/2021 | bar: 2021 Jul to 2021 Aug
| Execute HAZOP (Staggered for TRP, TNP & TEP). | 8 weeks | 25/10/2021 | 20/12/2022 | bar: 2021 Oct to 2021 Dec
| HAZOP Report | 3 weeks | 2022-07-01 | 28/01/2022 | bar: 2022 Jan
3 | Develop and complete PSBR Compliance Report
| PSBR Gap Closure. Identification & Deployment of requisite resources to close the PSBR gaps. Staggered for the three pipelines. | 6 weeks | 2022-01-02 | 18/03/2022 | bar: 2022 Feb to 2022 Mar
4 | Update BowTie Report
| BowTie Report. Stggered for the three pipelines. | 6 weeks | 21/03/2022 | 2022-05-05 | bar: 2022 Mar to 2022 May
5 | Update ALARP Demonstration Report
| To be updated on completion of all other preceding studies which will feed into the ALARP Demonstration Report. | 4 weeks | 13/05/2022 | 15/06/2022 | bar: 2022 Jun
6 | Track Existing HEMP Actions and Closeout
| HEMP actions tracking and closure happening continuously. Focus will be on PS related Actions | Continuous
Uncertainties
1 | Data/ Information Availability
2 | Completion of CTR agreement as per plan
3 | Contractor/ Vendor identification, selection and engegemnent as per plan
Support Required
1 | Dedicated staff from Pipelines Asset to provide support.
Assumptions:
1 | These are initial estimated dates/plans, which will be further refined once the CTR is agreed/completed.
2 | Available Budget to execute all activities
3 | HAZOP Execution to start after SGM completion. Relevant stakeholders to be used for HAZOP of each pipeline section.
4 | The activities are to be conducted on the three Pipelines - TRP (Trans-Ramos Pipeline), TNP (Trans-Niger Pipeline) and TEP (Trans-Escravos Pipeline). Studies to be conducted in a staggered manner.
5 | HEMP Actions: Focus will be on PS related Actions and requirements for closeout