## Sheet1
CRITICAL EQUIPMENT /MATERIAL TO AID MER TEST
S/No. | Equipment/Materials | Recommendation | Frequency | Action Party
1 | Rotronmeters (Sizes dependent on PUs) | Ensure calibrations are up to date prior to MER test | 3 months to MER test | Maintenance Team Leader
2 | Barton Meters/charts/ink | Confirm Barton Meter calibrations are up to date; source for Barton meter Charts and Ink prior to MER test | 3 months to MER test | Maintenance TL
3 | Pressure gauges (0 to 250bar, 0 to 100bar and 0 to 25bar) | Calibrated Pressure gauges to be on site. | 2 months to MER test | Operations Team Leader
4 | Gas meters (Ultrasonic) | Confirm Calibrations are up to date | 3 months to MER test | Maintenance Team Leader
5 | Adjustable spanners | 12 inch, 6 inch (Must be available) | 2 month to MER test | Operations Team Leader
6 | Pipe Wrench | 14 inch and 18 inch | 2 month to MER test | Operations Team Leader
7 | Operator's tools bag | Ensure there is a fit for purpose tool bag to contain all necessary tools | 3 Months to MER test | Operations Team Leader
8 | Bean (Sizes and makes depends on PUs) | Ensure to stock the common bean sizes to enable carrying out two MER per day with ease. | 4 months to MER test | Operations Team Leader
Some PU’s use adjustable choke, hence no issues on bean procurement but confirm adjustable choke calibration.
9 | Bean Gauges | Procure Bean gauges to ascertain actual bean sizes to be used. | 3 months to MER test. | Operations Team Leader
10 | Orifice plates (Sizes depends on PUs) | Ensure required Orifice plate sizes are on site | 2 months to MER test. | Operations Team Leader
11 | Water cut meters | Ensure Water cut meters are calibrated prior to MER test | 3 Months to MER test | Maintenance Team Leader
12 | Sample Cans and label/tag | Ensure adequate sample cans and labels are on site. To avoid wrong labeling, all wellhead sample taken should be labeled in-situ. | 1Month to MER test | Operations TL