## Slide 1
“As is” Material requisition and Marine Logistics process.
PUM/OIM approves request <$5k USD
AMIL support required if >$5k
Field request (Materials, PMS, water) compiled by planner or activity owner on a weekly basis one week ahead of need.
CRP reviews and approves request by field/ including Marine request.
Planner raise PR in SAP
CP raise PO
Marine Logistics provides Vessels/deliver request.
Issues with “As –Is” Process:
Late/no forward planning makes integration/central optimisation impossible.
Marine budget resides in individual field and is mostly subject to PUM/OIM approval
Assets that use current milk run pay for voyage- Those who opt out have no financial commitment/loose nothing.
STIA Operations plan/firm plan not used as basis for material planning & delivery
Backloading is not coordinated as frequency of marine vessels in field is high
Single PO utilization for charge whereas cargo belong to multiple teams

## Slide 2
“Time-Based Milk-run for Material requisition and Marine Logistics process.
Time based Milk run key actions
Field Operations plan as basis for material request and Milk run (Min. 30 days firm plan required)
Central plan optimisation based on Milk run capacity
No adhoc/emergency request outside Milk run schedule without AM approval
Centralised Marine budget & Marine planning
Re-introduce PO split or central point of accountability to adequately back charge all the teams with materials
Introduce time-based deployment with charge split to Asset, FMT’s, etc even where they don’t use the mill-run.
Marine Logistics provides Vessels/deliver request.
PUM/OIM approves request <$5k USD
AMIL support required if >$5k
Field request (Materials, PMS, water) compiled by planner or activity owner at least 30 days ahead of need.
CP,AMIL, Finance reviews and approves request by field/ including Marine request.
Planner raise PR in SAP
CP raise PO
Marine Logistics provides the charge back advise to the requestors
Defer request to next available Milk-run schedule
YES
NO
End
Marine logistics confirms availability of “Time-
Based” Milk run schedule
BIG RULES
Restrict authority to hire to AM only post Marine milk run unavailability notification
Cascade request for milk run 3 week to demand pre-CLP approval
Roll out 30-day plan to align with Milk run schedule/IAP
Ensure WBS is received for all items for teams latching to milk-run based on space utilized