## APRIL 23
Avoidance of Cost and Risk exposure for APRIL 2023
| Week | Logistics Service Request description | Amount Saved through Integrated Scheduling Decisions |  | Amount of Hours Risk Exposure reduced through Integrated Scheduling Decisions
MMR NO |  |  | N | $ |  | Remark
2725 | 16 | MARINE EQUIPMENT TO MOVE PROJECT MATERIALS, CRANE AND SELF LOADER FROM OGUNU TO TUNU. PLEASE CHARGE | 514504.6 | 26625.1 | 840 | Barge mobilized for Tunu TAM was used to demobilize crane that supported project work at Tunu. Saved cost of hiring separate tug at (N70327.98, $654.08) Ramp at (N32572.94, $302.94) for 5 days, 5,000 Liters of AGO for Tug and 7,000 liters of AGO for MPV at $1.82
2607 | 16 | CRANE FOR SHUT DOWN | 1085700 |  |  | Through ILS decision, Crane mobilized for project work was moved over to Ogbotobo for shut down while waiting. Saved 5 crane days at N217,140 per day
2879 | 16 | PROVIDE MARINE EQUIPMENT (TUG AND BARGE) TO MOVE SCAFFOLDING MATERIALS FROM TUNU TO BENISEDE | 205801.84 | 1914.04 | 336 | Through ILS decision, barge mobilized for shut down was used to deliver project materials to Benisede. Saved cost of hiring separate tug at (N70327.98, $654.08) Ramp at (N32572.94, $302.94) for 2 days, 5,000 Liters of AGO for Tug and 7,000 liters of AGO for MPV at $1.82
2881 | 16 | PROVIDE MATERIAL HANDLING EQUIPMENT TO MOVE DURABASS MATS FROM TUNU TO OGBOTOBO | 205801.84 | 1914.04 | 336 | Through ILS decision, barge mobilized for shut down was used to deliver project materials to Ogbotobo. Saved cost of hiring separate tug at (N70327.98, $654.08) Ramp at (N32572.94, $302.94) for 2 days, 5,000 Liters of AGO for Tug and 7,000 liters of AGO for MPV at $1.82 per litre
2926 | 17 | PROVIDE PMS FUEL TANKER OF 30,000 LITRES CAPACITY for TUNU FOR A PERIOD OF 2-MONTHSESCORT USED FOR PROJECT | 913119.99 | 12740 |  | Through ILS decision, escort mobilized to move Tunu PMS combo to Tunu was used to drop off project houseboat Esjay 6 at Benisede. Saved cost of MPV at N304,373.33 per day for 3 days and cost of 7,000 liters of GAO at $1.82 per litre
2670 | 15 | BARGE TO MOBILISE FOT DYNAMIC METERING EQUIPMENT 20FT CARAVAN FROM OGUNU IA JETTY TO FORCADOS TERMINAL . INCLUDE REQUEST FOR BARGE TO DEMOBILISE FOT DYNAMIC METERING EQUIPMENT | 411603.68 | 25668.08 | 672 | Through ILS decision, caravan for dynamic metering was mobilized to FOT using Princess Tamar and demoibilized using Erin bay. Saved cost of hiring separate tug at (N70327.98, $654.08) Ramp at (N32572.94, $302.94) for 4 days, 3,800 Liters of AGO for Tug and 5,000 liters of AGO for MPV at $1.82
Mail request | 16 | PRINCESS TAMAR FOR LOADING hose changeout activity on FSPM-1 from Ogunnu to HDE at forcados | 102900.92 | 22797.02 | 672 | Materials urgently needed for hose changeout activity on FSPM-1 was loaded on Pricess Tamar for delivery to Forcados. Saved cost of hiring separate tug at (N70327.98, $654.08) Ramp at (N32572.94, $302.94) for 1 day, 3,800 Liters of AGO for Tug and 5,000 liters of AGO for MPV at $1.82
2897 | 16 | Valves, Rotor, Engine, and Gear boxes and others materials to be loaded - | 205801.84 | 1914.04 | 336 | Barge mobilized to recover solar engine was used to deliver these materials to Otumara . Saved cost of hiring separate tug at (N70327.98, $654.08) Ramp at (N32572.94, $302.94) for 5 days, 3,800 Liters of AGO for Tug and 5,000 liters of AGO for MPV at $1.82
ERT | 16 | Deliver ERT materials to Escravos incident site | 411603.68 | 3828.08 | 336 | Tunu PMS Combo awaiting bunkering was used to deliver ERT materials to Escravos. Saved cost of hiring separate tug at (N70327.98, $654.08) Ramp at (N32572.94, $302.94) for 3 days,
|  |  | 4056838.39 | 97400.4 | 3528
8113.6768
105514.0768

## MAY 23
Avoidance of Cost and Risk exposure for MAY 2023
| Week | Logistics Service Request description | Amount Saved through Integrated Scheduling Decisions |  | Amount of Hours Risk Exposure reduced through Integrated Scheduling Decisions
MMR NO |  |  | N | $ |  | Remark
3007 | 20 | ComUnits transfer to Tunu from PH IA Warehouse to Ogunu then move to Tunu | 308702.76 | 24711.06 | 504 | This urgent materials for Wells reopening at Tunu were delivered with CWI barge. Saved cost of hiring separate tug at (N70327.98, $654.08) Ramp at (N32572.94, $302.94) for 3 days, 5,000 Liters of AGO for Tug and 7,000 liters of AGO for MPV at $1.82
2979 | 19 | REQUEST FOR 1 BARGE, 1 TUG & 1 CRANE; MOBILISATION TO ESCRAVOS FLOW STATION | 205801.84 | 23754.04 | 336 | Materials for water treatment plan at Escravos were loaded on ERT barges. Saved cost of hiring separate tug at (N70327.98, $654.08) Ramp at (N32572.94, $302.94) for 2 days, 3,800 Liters of AGO for Tug and 5,000 liters of AGO for MPV at $1.82
2824_ | 21 | EQUIPMENT TO MOVE FYIP MATERIALS 2ND LEG TO NORTH BANK | 205801.84 | 17930.04 | 336 | Asset materials were loaded on project convoy to North bank. Saved cost of hiring separate tug at (N70327.98, $654.08) Ramp at (N32572.94, $302.94) for 2 days, 3,800 Liters of AGO for Tug and 5,000 liters of AGO for MPV at $1.82
2966 | 21 | To convey Vehicle(Bus) for Forcados Airstrip Runway Friction test | 205801.84 | 23754.04 | 336 | Aviation bus was delivered to FOT using PMS combo . Saved cost of hiring separate tug at (N70327.98, $654.08) Ramp at (N32572.94, $302.94) for 2 days, 3,800 Liters of AGO for Tug and 5,000 liters of AGO for MPV at $1.82
3073 | 22 | tipper truck to load drums of lubt oil and chemicals from warehouse to the jetty, to be loaded on the barge for onward movement to TUNU. | 308702.76 | 24711.06 | 504 | 80 drums of chemicals for Tunu Asset operations were loaded on project PMS combo. Saved cost of hiring separate tug at (N70327.98, $654.08) Ramp at (N32572.94, $302.94) for 3 days, 5,000 Liters of AGO for Tug and 7,000 liters of AGO for MPV at $1.82
|  |  | 1234811.04 | 114860.24 | 2016
2469.6221
117329.8621

## JUNE 23
Avoidance of Cost and Risk exposure for JUNE 2023
| Week | Logistics Service Request description | Amount Saved through Integrated Scheduling Decisions |  | Amount of Hours Risk Exposure reduced through Integrated Scheduling Decisions
MMR NO |  |  | N | $ |  | Remark
Mail | 26 | Request to support FOT hose stringing job | 308702.76 | 2871.06 | 504 | FOT tug and ramp barg were deployed for urgent hose stringing job at the terminal. Saved cost of hiring separate tug at (N70327.98, $654.08) Ramp at (N32572.94, $302.94) for 3 days
3229_philo.akpovwovwo | 26 | To load drums of chemicals, boxes of filters and a box contain scaffolding equipment from the warehouse to the barge | 308702.76 | 24711.06 | 336 | Asset materials were loaded on project PMS Combo to Tunu. Saved cost of hiring separate tug at (N70327.98, $654.08) Ramp at (N32572.94, $302.94) for 3 days, 5,000 Liters of AGO for Tug and 7,000 liters of AGO for MPV at $1.82
|  |  | 617405.52 | 27582.12 | 840
1234.811
28816.931

## Qtr 2 Summary
| MONTH | COST F$
1 | 2023-04-01 | 105514.08
2 | 2023-05-01 | 117329.86
3 | 2023-06-01 | 28816.93
| TOTAL | 251660.87