## Slide 1: Eliminate Demurrage from SPDC Terminals
Sponsors briefing – Sprint Week 03

## Slide 2: Initiative Title: Eliminating Demurrage in SPDC Terminals
Understand what it takes to deliver a ‘perfect’ offtake Close identified gaps/root causes that contribute to demurrage cost Implement a performance measurement and monitoring system to sustain improvement
Fig: Demurrage Reduction Staircase
Target | Zero demurrage cost incurred |  | 
 |  |  | Production forecast stability
 |  | Enhanced tanker turnaround time | 
Current State | Baseline Performance |  | 
SPDC experienced increased value erosion from demurrage claims in the past four years. Total claims rose from ~$6.4m in 2020 to ~$23m in 2023 largely due to slower loading at Forcados Terminal caused by SPM integrity issues/outage and awaiting cargo in Bonny Terminal due to lower receipts from TNP. In line with the drive to improve cost competitiveness, an ambitious 2024 business plan was endorsed with a provision for demurrage capped at $7.2m With the restoration of FSPM1 and proven functionality of the Tri Catenary Mooring system, more focus and cross-functional integration is required to achieve and sustain “offtake ready everyday” across SPDC Terminals. Ambition is to incur ZERO demurrage claims charge in 2024.
Deliver ~$7m OPEX cost savings in 2024 Prevent > $20million/annum value erosion Lower unit operating cost for SPDC Export Terminals
Objectives
Benefits
Business Case

## Slide 3: Initiative Update
  Analysis of 2023 demurrage claims to understand the reasons with the biggest claims amount
  Root cause analysis for the demurrage claims
  High level solutions for the biggest contributory causes
  Progress initiative from L0 to L3 in Fit4
  ~$1M demurrage incurred in 2024 YTD ($0.4M BOGT; $0.5M FOT; $72k SE)
  $306K - TCMS related demurrage YTD
  Basis for impact: $7M budget figure less the actuals incurred in 2024 YTD less the estimated annual demurrage from slower loading with TCMS.
  Detailed solution planning – implementation plans for solutions in need of further development
  Determine cost-benefit for proposed solution: Provide additional Personnel Carrier for Terminal Ops.
  Estimate the annual demurrage claim associated with exporting from TCMS = $57,278*no of loading from TCMS
  None
Promise for next week
Support required/Key decisions
Previous Weeks
Expected impact
2024: $6M*
I-2889155: Eliminating Demurrage in SPDC Terminals
Notes: Impact – 7Mbudget figure less the actuals incurred in 2024 YTD less the estimated annual demurrage from slower loading with TCMS

## Slide 4: RCA – Slow loading at FOT
Slow Loading at FOT
Loading on TCMS
Loading from SBM1 with one floating hose or one subsea hose
FOT export flow constraints from onshore systems i.e. loading at rates below shore max.
SBM2 was replaced by TCMS
TCMS was installed with design limitations
SBM1 and accessories failure/repair
Floating Hose - Lacerations on sections of the floating hose string.
Subsea Hose failure- leak developed
Equipment required for shore max: 3 Power Turbines + 5 booster pumps + 4 Export pumps + 5 meter runs.
Equipment Nos installed: 6 Power Turbines + 5 booster pumps + 5 Export pumps + 6 meter runs
4oo5 Export pumps available. Failure of any one of the available export pumps means FOT is unable to load at shore max.
Flow rate at 50% of Shore Max loading rates; Full parcel of 1million bbls will take circa 28hrs @ 35kbbls/hr Loading at TCMS requires much calmer weather conditions than the SBM can withstand - offtake will be delayed or suspended if already in progress when weather conditions deteriorate.
LEGEND
FOT & BOGT
BOGT only
FOT only

## Slide 5: RCA – FOT SBM1 Outage
FSBM1 Outage
FSBM1 was past end of life and failed in service.
OEM recommended 7yrs of service.
Shell-RBI study outcome extended field service to 10yrs.
FSBM1 was in service for >12yrs.
LEGEND
FOT & BOGT
BOGT only
FOT only

## Slide 6: RCA - Awaiting Berthing
Awaiting Berthing
Grommet entanglement
Support vessels propellers getting entangled with hawser
Delayed Tanker Inward clearance.
Daylight Constraints
Berth occupied
Adverse weather condition/wave action
Line handling during mooring ops
Human error during mooring ops
Adverse weather condition.
Unavailability of PC to convey officials to embark/disembark vessel.
Adverse weather
Limited experience/capability of vessel captain.
Limited experience/capability of vessel captain.
Activities requiring PC movement is subject to arduous scheduling with little flexibility.
When the sole PC is reassigned to other activities based on prioritization, this has resulted in delayed disembarking of officials with resultant delay in tanker inward clearance.
Unable to berth on TCMS or SBM during adverse weather conditions beyond permissible limits
Terminals are set up contractually as 24hr. Ship can tender Notice of Readiness at any time within the laycan.
Disruption of tanker schedule for all other previous causes. Delay in concluding preceeding tanker's export documentation after offtake- experienced more with some NUPRC officials.
BOGT - GOs -Port Health, NDLEA- reside outside the terminal and are available in the day only.
Vessels are limited to daylight sailing.
Security concerns for night sailing.
FOT: River channel is unlit - absence buoys indicating the safe waters for vessels to prevent running aground. E.g. Presence of shipwreck in river channel
FOT: Fouling of the propellers by fishing nets; Fishing activities.
LEGEND
FOT & BOGT
BOGT only
FOT only

## Slide 7: RCA - Awaiting cargo
Awaiting Cargo
Protracted cargo preparation time
1.Low/No Receipt
2.Inadequate Ullage – FOT
3.High Emulsion content in receipt
4.Quality – SBM3 intake – BOGT
5.Pressure restriction in incoming lines – BOGT
Receipt unpredictability e.g. UPS or upstream facilities issues
Unscheduled unavailability of trunklines - TNP, TFP e.g. Sabotage etc.
Available ullage vs design capacity vs receipt: 5CSTs vs 9CSTs Tanker programming has little room for flexibility. Tank top (leading to production cutback) Tank bottom - demurrage outcome
Upstream stations fail to inject sufficient demulsifiers into production stream
High volume of Untreated water e.g. UPS
Effluent generated into production downstream of producing facilities
Unavailability of FOT Emulsion treatment system - Height of sludge already resident in Crude Storage tanks
Liquids from Soku is predominantly higher API - condensate. Less Low API crude available to blend.
Salt content above threshold >25ptb - EMERGING
Suspected restriction in common header.
LEGEND
FOT & BOGT
BOGT only
FOT only

## Slide 8
1 | Improve Capability of vessel crew.
2 | Provide another PC to support Terminals – steady state or call-off contract options for contingency/redundancy
3 | Review night sailing policy. Make adequate security arrangements for vessel convoy. Provide another PC to support terminal ops. FOT - 'Lit' the river channel -Provide buoys to illuminate the channel. FOT - Remove ship-wreck and mark-up navigational charts. BOGT - Make arrangements for GOs to reside in BOGT.
4 | Transfer claims to the upstream 3P producers.
5 | Enforce the emulsion content specification for receipt.
6 | Chemical treatment at source to reduce salt content.
7 | Remove accumulation of debris in elbow section.
8 | Realign maintenance schedule for all SBMs to OEM recommended intervals.
SOLUTIONS IN FLIGHT
1 | Timely maintenance of installed FSBM1, BSBM1.
2 | Execute BSPM2 change-out as scheduled. LEC 16-Apr-2024
3 | Replace TCMS with new FSBM2.
4 | Timely maintenance of floating hoses and subsea hoses. Readiness check with Underwater Mtce - Check availability of materials required for activities.
5 | Procure new electric motor and overhaul Export Pump P-403.
6 | Pipeline security improvement.
7 | Accelerate FOT Floating roof crude storage tanks rehab program.
8 | Restore FOT Emulsion treatment system.
SOLUTIONS FOR FURTHER DEVELOPMENT

## Slide 9: RCA - Summary
Contributors | Why | Why | Why
Slow Loading | 1.Loading on TCMS | 1.SBM2 was replaced by TCMS 2.TCMS was installed with design limitations 3.SBM1 and accessories failure/repair | Flow rate at 50% of Shore Max loading rates.which means full parcel of 1million barells will take Loading at TCMS requires much calmer weather conditions than the SBM can withstand - offtake will be delayed or suspended if already in progress when weather conditions deteriorate.
 | 2.Loading from SBM1 with one floating hose or one subsea hose | 1. Floating Hose - Lacerations on sections of the floating hose string. | 1. Floating hose sustained damage - likely impact from vessels
 |  | 2. Subsea Hose failure- leak developed | 2. SSH - failed in service at 7.5yrs beyond OEM recommended replacement interval of 5years. Shell-RBI study outcome led to service extension of 7.5yrs.
 | 3.FOT export flow constraints from onshore systems i.e. loading at rates below shore max. | Equipment required for shore max: 3 Power Turbines + 5 booster pumps + 4 Export pumps + 5 meter runs. Equipment Nos installed: 6 Power Turbines + 5 booster pumps + 5 Export pumps + 6 meter runs | 4oo5 Export pumps available. Failure of any one of the available export pumps means FOT is unable to load at shore max.
SBM Outage | SBM1 was past end of life and failed in service. | OEM recommended 7yrs of service. Shell-RBI study outcome extended field service to 10yrs. SBM1 was in service for >12yrs. | 
Awaiting Berthing | Grommet entanglement | Adverse weather condition/wave action | 
 |  | Line handling during mooring ops | Limited experience/capability of vessel captain.
 | Support vessels propellers getting entangled with hawser | Human error during mooring ops | Limited experience/capability of vessel captain.
 |  | Adverse weather condition. | 
 | Delayed Tanker Inward clearance. | Unavailability of PC to convey officials to embark/disembark vessel. | Activities requiring PC movement is subject to arduous scheduling with little flexibility. When the sole PC is reassigned to other activities based on prioritization, this has resulted in delayed disembarking of officials with resultant delay in tanker inward clearance.
 | Delayed Regulatory clearance | NUPRC, NNPC Plc issuing clearance after delay between vessel nomination: documentary instruction for SWEST parcels. | 
 | Adverse Weather | Unable to berth on TCMS or SBM during adverse weather conditions beyond permissible limits. | 
 | Daylight constraints | Terminals are set up contractually as 24hr, whereas vessels are limited to daylight sailing. Vessels can tender Notice of Readiness at any time within the laycan. BOGT - GOs -Customs, NIS, Port Health, NDLEA- reside outside the terminal and are available in the day time. | Security concerns for night sailing. Safety concern: River channel is unlit - absence buoys indicating the safe waters for vessels to prevent running aground. E.g. Presence of shipwreck in river channel Safety concern: Fouling of the propellers by fishing nets; Fishing activities.
 | Berth occupied. | Disruption of tanker schedulefor all other previous causes. Delay in concluding preceeding tanker's export documentation after offtake- experienced more with some NUPRC officials. | 
Awaiting Cargo | Protracted cargo preparation time. | 1.Low/No Receipt | Receipt unpredictability e.g. UPS or upstream facilities issues
 |  |  | Unscheduled unavailability of trunklines - TNP, TFP e.g. Sabotage etc.
 |  | 2.Inadequate Ullage - FOT | Available ullage vs design capacity vs receipt: 5CSTs vs 9CSTs Tanker programming has little room for flexibility. Tank top (leading to production cutbacks) Tank bottom - demurrage outcome
 |  | 3.High Emulsion content in receipt – FOT & BOGT | Upstream stations fail to inject sufficient demulsifiers into production stream
 |  |  | High volume of Untreated water e.g. UPS
 |  |  | Effluent generated into production downstream of producing facilities
 |  |  | Unavailability of FOT Emulsion treatment system - Height of sludge already resident in Crude Storage tanks
 |  | 4.Quality – SBM3 intake - BOGT | Liquids from Soku is predominantly higher API - condensate. Less Low API crude available to blend.
 |  |  | Salt content above threshold >25ptb – EMERGING
 |  | 5.Pressure restriction in incoming lines - BOGT | Suspected restriction in common header.