## OABP Q1 2021 Savings
DATE | PROJECT | PE / SPONSOR | WBS | COST SAVINGS Q1 | [5 empty] | Remarks
|  |  |  | LAND | CENTRAL | SWAMP WEST | CIVIL | OABP ASSET, 100% Savings | FCF Savings
2021-01-01 | No Submission(s)
| Opukushi 34T Flowline Replacement | Otavie, G | 102155 |  |  | 65000 |  |  |  | Renegotiated excavation rates, use of only one vendor reduced double mobilization and associated catering costs
| Opukushi W26T Flowline Replacement (4" x 2km | Otavie, G | 102155 |  |  | 35000 |  |  |  | Campaign mobilization will enable the sharing of Marine logistic resources like hosueboat
| Rehabilitation of 800m failed sections of Obigbo flow station road. | Ezenduka, D | C.NG.PAE.IC.21.001 |  |  |  | 29844.89 |  |  | 6.5 % LOP Discount
| Addendum to Construction of 1 No. Well bay location Assa-North | Ezenduka, D | C.NG.ANO.DG.17.004.1231 |  |  |  | 7589.49 |  |  | 5 % LOP Discount
| Sectional Replacement of (a) ImoR 59T (6-inch) (b) ImoR 25L (4-inch) | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | 8280.04 | [5 empty] | THERE IS A SAVINGS OF 8,280.04 USD WHICH SHOULD HAVE COVERED MOB & DEMOB USING A NEW CONTRACTOR
| Full Replacement of ImoR 58T (4- inch x 3.4km) | Aderiye, A | C.NG.PAE.DL.21.001 | [6 empty] | THERE IS A SAVINGS OF 12,508.36 FROM THE MATERIALS THAT WILL BE COLLECTED FROM THE SPDC WAREHOUSE
2021-02-01 | LOCATION DREDGING WORKS AT BENISEDE EAUA-2. | Onyejekwe, C | C.NG.AFS.DD.19.009.9401 |  |  |  | 115543.79 |  |  | Low Oil Price LoP discounts (i.e. 22%).
| FULL REPLACEMENT OF IMOR 58T (4-INCH x 3.4KM) | Aderiye, A | C.NG.PAE.DL.21.001 | 14800 | [5 empty] | Warehouse Materials
| K2S Simultaneous Flow Project | Akoma, I | C.NG.PBE.DF.21.005 |  | 22416.83 |  |  |  |  | Savings on Mob and De-mob by using same contractor for Mechanical/ Instrumentation works, etc
| Replacement of LP header of Yokri flow station. | Obiakor, O | O.NG.PCW.YKF.FAC.71300 |  |  | 23907.23 |  |  |  | saved for combining mobilization of Forcados Yokri 127T flowline sectional replacement and replacement of Yokri LP header
| LEAK REPAIR OF FORCADOS 127T FLOWLINE | Obiakor, O | 102155 |  |  | 39515.51 |  |  |  | Mob and De-mob, Houseboat
| SECTIONAL REPLACEMENT OF OTUMARA 42LS, 16T FLOWLINES AND FABRICATION OF HOOK-UP ARM OF OTUMARA 4L. | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  |  | 159000 |  |  |  | F$82,000 (Shared marine logistics) + F$77,000 (Single mob/demob)
2021-03-01 | UZU MANIFOLD LOCATION PREPARATION | Oludare, S | P.NG.PAE.DG.17.001 |  |  |  | 107225.24 |  |  | 5 % LOP Discount
| FORC 111T Flowline Replacement (6" sch 40 x 2.7 km bulkline) & (4" sch 40 x 0.25 km flowline) | Orji, C | C.NG.PAE.DL.21.001.1230 |  |  | 33891.12 |  |  |  | From Materials to be taken from Hot Desk
| FULL REPLACEMENT OF IMOR 36L (4-INCH x 1.0 KM) | Aderiye, A | C.NG.PAE.DL.21.001 | 12500 | [5 empty] | MATERIALS FROM THE SPDC WAREHOUSE.
| SECTIONAL REPLACEMENT OF (a) IMOR 4-inch TEST LINE (48M) (b) IMOR RIVER 26S (48M) © IMO RIVER 44S (48M) (d) IMO RIVER 55S (48M) (e) IMO RIVER 43T (48M) (f) IMOR 60T (48M) | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | 11525.18 | [5 empty] | MOB & DEMOB. ALL MATERIALS FOR THESE SECTIONAL REPLACEMENT SHALL BE SOURCED FROM SPDC WAREHOUSE
| SECTIONAL REPLACEMENT OF (a) IMOR RIVER 6-INCH BULKLINE (IMO 2 -1) X 1500 M (Additional leak points) | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | 8280.04 | [5 empty] | MOB & DEMOB IF USING A NEW CONTRACTOR
| Provision of lay barge for installation of CCUs at Kanbo W5L/S | Ehizonyan, O | C.NG.AFS.DF.18.025.1202 |  |  | 10062 |  |  |  | Shared marine logistics and security deployment
| Seibou 3 and 4 bulkline JIV and clamping. -Reviewed offline | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | 9050.71 |  |  |  | cost saving on inter-area move instead of mobilizing a new contractor.
| Bonny W14 Maintenance Dredging works | Onyejekwe, C | 110744 |  |  |  | 56227.33 |  |  | Cost saving is from Low Oil Price LoP discounts (i.e. 7.5%).
| Bonny W13 Maintenance Dredging works | Onyejekwe, C | 110744 |  |  |  | 54055.53 |  |  | Cost saving is from Low Oil Price LoP discounts (i.e. 7.5%).
| Kanbo W7S (6’’ x 0.1Km) & W6T (6’’ x 0.1Km) Flowline Sectional Replacement | Otavie, G | O.NG.STG.PBE.KAN.007FL O.NG.STG.PBE.KAN.006FL |  |  | 20000 |  |  |  | Elimination of Mob and De-mob of Houseboat, by latching onto existing houseboat already in Tunu
| TUNU BQRT-3 Flowline Replacement (6" Sch 80 x 6.1km) | Otavie, G | C.NG.AFS.DL.19.006.1230 |  |  | 24284.08 |  |  |  | House boat sharing and materials discounted
| Total |  |  | 55385.26 | 22416.83 | 419710.65 | 370486.27 | 867999.01 | 252587.7119
|  |  |  | 67893.62 | 22416.83 | 375426.57 | 370486.27 | 836223.29 | 243340.9774