## Summary OABP H2 Savings
| LAND | CENTRAL | SWAMP WEST | CIVIL | OABP ASSET | AF | 100% (F$ ‘000) | FCF (100% x 0.3 x 0.97) (F$ ‘000)
|  |  | 20056.18 |  |  |  | 20056.18 | 5836.3484 | July
|  | 96713.65 | 359060.762 | 21696.008 |  |  | 477470.4201 | 138943.8922 | Aug
[7 empty] | 0 | 0 | Sept
Total | 0 | 96713.65 | 379116.942 | 21696.008 | 0 | 0 | 497526.6001 | 144780.2406
Remark

## Q3 Savings
DATE | PROJECT | TYPE | WORP DECISION | STATUS | PE / SPONSOR | WBS | TOTAL VALUE/COST | [5 empty] | COST SAVINGS (F$) | Remarks | CONTRACT
[7 empty] | LAND | CENTRAL | SWAMP WEST | CIVIL | OABP ASSET | AF
2021-01-07 | No Submission
2021-01-14 | Replacement of 2” water equalization of Soku cluster B | Fresh | Conditional Approval: Complete the actions below and revert offline - Confirmation availability of signed work request - Finalise the procurement process - MCIA: Baseline integrity request to be carried out. - Engage C&P to negotiate the swamp buggy cost. - Engage C&P on procurement of 2” line pipes - Update all documents as related to contractor change | Conditional Approval | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  | $ 155,435.95 N 7,195,661.10 F$ 174,396.85 |  |  |  |  | Nil |  | KEMUD INT’L
| FORCADOS 127T Flowline Sectional Replacement – (6’’ x 0.05km) | Fresh | Approved. - Update total cost column to reflect realities - Ensure an elaborate kick off meeting with contractor due to change in work environment. | Approved | Obiakor, O | 102155 |  |  | $ 58,352.89 N 1,953,504.45 F$ 63,500.46 |  |  |  | Nil |  | TONYMA INVESTMENT
| Provision of Security/surveillance and Downtime for Tunu BQRT-4 Flowline | Fresh | Approved | Approved | Otavie, G | C.NG.AFS.DL.19.004.1230 |  |  | $49,124.21 N 25,544,732.98 F$116,435.76 |  |  |  | Nil |  | IKONIBO NIG
| Provision of support to CWI for open-up of Tunu BQRT-4(W5ST) | Fresh | Approved. - Reconfirm that there is not/wouldn’t be a double charge on equipment due to resource sharing. - Confirm that all necessary plans, HSE, Security etc are in place and signed off | Approved | Otavie, G | C.NG.AFS.DD.19.005.9411 |  |  | $11,713.68 N10,860,399.09 F$40,331.33 |  |  |  | Nil |  | IKONIBO NIG
| Opukushi 34T Flowline Replacement | Fresh | Approved - Update the narrative in the submission to indicate initial PO will be deleted - Update in the submission G&H to CTS | Approved | Otavie, G | 102155 |  |  | FUSD:390,382.95 NGN:6,387,108.86 USD: 373,574.27 |  |  |  | FUSD: 65,000 | Renegotiated excavation rates, use of only one vendor reduced double mobilization and associated catering costs | WILANDSON
| Opukushi W26T Flowline Replacement (4" x 2km | Fresh | Conditional Approval: Complete the actions below and revert offline - Contract extension to be updated in SAP - Engage PST to reconcile cost - Update submission to reflect risk, work schedule etc | Conditional Approval | Otavie, G | 102155 |  |  | $ 182,085.5 N 66,885,002.36 F$ 401,380.6 |  |  |  | F$: 35,000 | Campaign mobilization will enable the sharing of Marine logistic resources like hosueboat | SEVOIL
| GENERAL |  | Change all submission from OP19 to OP20 Activity owners to confirm support of activities in OP20 before commencing activities. Work allocation spreadsheet to be updated and current at all times.
2021-01-21 | Opukushi W26T Flowline Replacement (4" x 2km) - Resubmission & Reviewed offline | Resubmission | Approved | Approved | Otavie, G | 102155 |  |  | $ 177,590.51 N 65,234,247.10 F$ 349,485.76 |  |  |  | F$: 35,000 | Campaign mobilization will enable the sharing of Marine logistic resources like hosueboat | SEVOIL
| Diebu Creek 9T Flowline Replacement – 4” x 4.2km | Resubmission | Deferred: Complete item below and revert offline - Reconcile materials list with materials HotDesk and EST | Deferred | Uwaezuoke, D | 102155 |  | $337,905.66 N124,092,863.66 F$664,896.08 |  |  |  |  | Nil |  | ANASAMI CONSTRUCTION
| Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km | Fresh | Deferred: Complete items below and revert offline - Reconcile materials list with materials HotDesk and EST - Review work distribution to vendors equitably. | Deferred | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 69,057.09 N 19,127,794.00 F$ 119,459.71 |  |  |  |  | Nil |  | PECKON NIGERIA
| Sectional Replacement Of IMOR Well 32L & GLL Flowlines | Fresh |  |  | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 8,876.10 N 2,214,970.80 F$ 14,712.65 | [5 empty] | Nil |  | ADLAND PROJECTS
| Sectional Replacement Of IMOR4- Inch Delivery Line/57GLL/36S/22S | Fresh |  |  | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 48,732.29 N 14,993,395.11 F$ 88,240.58 | [5 empty] | Nil |  | GAMSTEC INTEGRATED
| DBCU W12T Flowline Replacement (4" Sch 80 x 5km) | Fresh | Deferred: Complete items below and revert offline - Reconcile materials list with materials HotDesk and EST - Review work distribution to vendors equitably. | Deferred | Azaka, G | NIL |  | $ 337,588.93 N 127,747,467.01 F$674,209.40 |  |  |  |  | Nil |  | MIDEN SERVICES
| FORC 126S Flowline Replacement (6” sch 80 x 1.2 km) | Fresh | Deferred: Complete items below and revert offline - Reconcile materials list with materials HotDesk and EST - Review work distribution to vendors equitably. | Deferred | Orji, C | C.NG.PAE.DL.21.001 |  |  | $ 132,054.33 N 48,500,624.65 F$ 259,687.56 |  |  |  | Nil |  | STEVE INEGRATED
| Rehabilitation of 800m failed sections of Obigbo flow station road. | Fresh | Deferred: Complete item below and revert offline - Engage the Asset team to get confirmation from divestment BOM on the execution of this project | Deferred | Ezenduka, D | C.NG.PAE.IC.21.001 |  |  |  | F$: 429,307.22 |  |  | F$: 29,844.89 | 6.5 % LOP Discount | BENCOV NIG
| GENERAL |  | All submissions are be subject to DRB approval EST to share a standard hook up arm materials list template to all
2021-01-28 | Sectional Replacement of Afam 25T Flowline (8” x 12m) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Engage Asset team, EST, HSE, Technical Safety and Security teams to review and sign off method statement. II. Include clamping as a mitigation against spill in the 5 top risks | Conditional Approval | Akinbiyi, A | O.NG.PAE.I1F.FAC.724FC | $ 27,733.14 + 35,712.58 N 46,114,670.79 + 11,048,655.19 F$ 149,247.42 + 64,826.30 | [5 empty] | Nil |  | BG TECHNICAL NIG LTD
| Rehabilitation of 800m failed sections of Obigbo flow station road. -Resubmission | Resubmission | Approved. WORP steers from previous sitting 21-01-21 have been incorporated. | Approved | Ezenduka, D | 110854 |  |  |  | F$: 429,307.22 |  |  | F$: 29,844.89 | 6.5 % LOP Discount | BENCOV NIG
| Addendum to Construction of 1 No. Well bay location Assa-North | Fresh | Approved. I. Resolve ACV balance in SAP II. Update 5 top risks to include Covid19 | Approved | Ezenduka, D | C.NG.ANO.DG.17.004.1231 |  |  |  | F$: 144,200.22 |  |  | F$: 7,589.49 | 5 % LOP Discount | RAFFOULNIG.LIMITED
| FORC 126S Flowline Replacement (6” sch 80 x 1.2 km) -Resubmission & Reviewed Offline | Resubmission | Approved. WORP steers from previous sitting 21-01-21 and 28-01-21 have been incorporated. | Approved | Orji, C | C.NG.PAE.DL.21.001 |  |  | $ 132,054.33 N 48,500,624.65 F$ 259,687.56 |  |  |  | Nil |  | HENSTEEL ENGINEERING
| Sectional Replacement of ImoR Well 32L & GLL | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Update cost saving column with proposed cost savings. II. Reconcile materials list with Hotdesk and expunge cost of available materials from cost estimate. | Conditional Approval | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 8,876.10 N 2,214,970.80 F$ 14,712.65 | [5 empty] | Nil |  | ADLAND PROJECTS
| Sectional Replacement of (a) ImoR 4-inch Delivery line (b) ImoR 57GLL (c) ImoR 36S (d) ImoR 23L (e) ImoR 14L (f) ImoR 6-inch Bulkline (g) ImoR 63T Manifold | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Update cost saving column with cost saved from inter-field move. II. Reconcile materials list with Hotdesk and expunge cost of available materials from cost estimate. | Conditional Approval | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 48,732.29 N 14,993,395.11 F$ 88,240.58 | [5 empty] | Nil |  | GAMSTEC INTEGRATED
| Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km -Resubmission & Reviewed Offline | Resubmission | Approved. WORP steers from previous sitting 21-01-21 have been incorporated. | Approved | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 72,553.73 N 5,439,173.57 F$ 86,886.20 |  |  |  |  | Nil |  | ABBEYCOURT ENERGY
| DBCU W12T Flowline Replacement (4" Sch 80 x 4.8km) -Resubmission & Reviewed Offline | Resubmission | Approved. WORP steers from previous sitting 21-01-21 have been incorporated. | Approved | Azaka, G | NIL |  | $ 324,004.09 N 121,078,352 F$727,442.65 |  |  |  |  | Nil |  | MIDEN SERVICES LTD
2021-02-04 | BONNY WELL 12S & OLOMA FS LIGAMENT VALVES CHANGE -OUT | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Update WBS for this activity. II. Attach an approved e-AEWR. III. Ensure all equipment have valid premob certificates. IV. Specify crew boat type in the cost estimate. V. Ensure detailed security plan review. VI. Update OP’19 to OP’20 in the submission | Conditional Approval | Ehizoyanyan, O | NIL |  | $ 17,399.52 N 2,002,876.74 F$ 22,677.19 |  |  |  |  | Nil |  | SURVEILLANCE 2000
2021-02-11 | Saghara 3S and 5L Flowline Replacement – 4” Sch. 40 x 850m Each (Total = 4” Sch. 40 x 1.7km) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Include fabrication of hook up arm in the work scope. II. Expunge CP survey and balancing from cost estimate. III. Expedite materials availability check with Hotdesk IV. Engage PS for a review of cost estimate. | Conditional Approval | Uwaezuoke, D | O.NG.PBW.SHF.03S.713FL/O.NG.PBW.SHF.05L713FL |  |  | $ 211,509.27 N 77,405,267.22 F$ 415,475.72 |  |  |  | Nil |  | ANASAMI
| Sectional Replacement of (a) ImoR 59T (6-inch) (b) ImoR 25L (4-inch) | Fresh | Approved. I. Include line length in the Project Title | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 12,297.25 N 3,357,092.47 F$ 21,143.34 | [5 empty] | 8280.04 | THERE IS A SAVINGS OF 8,280.04 USD WHICH SHOULD HAVE COVERED MOB & DEMOB USING A NEW CONTRACTOR | GAMSTEC INTEGRATED
| Full Replacement of ImoR 58T (4- inch x 3.4km) | Fresh | Approved. | Approved | Aderiye, A | C.NG.PAE.DL.21.001 | $ 110,900.38 N 26,084,203.78 F$ 179,633.46 | [5 empty] | 12508.36 | THERE IS A SAVINGS OF 12,508.36 FROM THE MATERIALS THAT WILL BE COLLECTED FROM THE SPDC WAREHOUSE | THOMPSON AND GRACE
| Sectional Replacement of Afam 25T flowline (8” x 12m) -Resubmission & reviewed offline | Resubmission | Approved. WORP steers from previous sitting 28/01/21 have been incorporated. | Approved | Dienagha, I | O.NG.PAE.I1F.FAC.724FC | $ 30,998.84 + 35,712.58 N 52,409,398.79 + 11,048,655.19 F$ 169,100.02 + 64,826.30 | [5 empty] | Nil |  | GAMSTEC INTEGRATED
| GENERAL |  | Ensure all cost are independently assured by PS. • Advise the team on when to commence movement of bare pipes to coating vendors (SOLEWANT & PCN). • Confirm availability of coated pipes from stockist. • Send sample of disused spool piece from Saghara 3S & 5L to MCI for analysis. • Expunge CP survey and balancing from cost estimate and where necessary, reports should be provided for documentation • Early request for Houseboat to the marine team • Ensure kickoff meetings are held prior mobilizations.
2021-02-18 | : LOCATION DREDGING WORKS AT BENISEDE EAUA-2. | Fresh | Approved. I. Liase with OABP focal persons to confirm ETC/OTC availability. | Approved | Onyejekwe, C | C.NG.AFS.DD.19.009.9401 |  |  |  | $: 103,003.11 N: 267,683,624.79 F$: 808,361.80 |  |  | F$: 115,543.79 | Low Oil Price LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| FULL REPLACEMENT OF OGUTA 16S FLOWLINE (4” X 2.9KM) | Fresh | NOT TREATED |  | Akinbiyi, A | 102155 | $ 91,808.64 N 26,740,513.71 F$ 179,482.45 | [5 empty] | Nil |  | MORRAY SERVICES
| FULL REPLACEMENT OF OGUTA 25T FLOWLINE (4” X 5.6KM) | Fresh | NOT TREATED |  | Akinbiyi, A | 102155 | $ 227,072.62 N 51,829,929.49 F$ 363,646.87 | [5 empty] | Nil |  | GESON INVESTMENT
| FULL REPLACEMENT OF OGUTA 12T FLOWLINE (4” X 4.3KM) | Fresh | NOT TREATED |  | Akinbiyi, A | 102155 | $ 140,649.15 N 17,728,986.10 F$ 187,365.85 | [5 empty] | Nil |  | ABBEYCOURT
| INTEGRITY CHECK OF AGBADA 67T GAS LINE | Fresh | Conditional Approval Update and resubmit upon completion of these conditions: I. Update WBS for this activity. II. Formal engagement with the Pipeline Contract Holder and review contract line items. III. Review work method statement with the vendor IV. Recourse option of engaging a flowline vendor to manage the overall activity. | Conditional Approval | Dienagha, I | NIL | $ 47,136.48 N 76,378,129.79 F$ 248,131.56 | [5 empty] | Nil |  | BG TECHNICAL
| BONNY W30T Flowline Replacement (4" Sch 80 x 1km) | Fresh | Deferred. I. Stepped down for a proper internal review by Project Lead. | Stepped Down | Azaka, G | NIL |  | $ 104,781.24 N 38,486,464.52 F$206,194.85 |  |  |  |  | Nil |  | VANDRESSER NIG
| Tunu CDRY-3 Flowline Construction (6" x 2.1km) & Tunu CDRY-4 Wellhead Platform Installation and hookup | Fresh | Approved. I. Update cost saving column with the proposed cost savings. II. Liase with C&P to affirm benchmark rates | Approved | Azaka, G | C.NG.AFS.DF.19.003.1200 |  |  | $324,929.80 N 118,704,995.67 F$ 637,697.73 |  |  |  | Nil |  | IKONIBO NIG
| Replacement of 1,75KM of 2” water equalization of Soku cluster D | Fresh | Deferred. I. Provide and attach basis for the additional 1.75km scope. II. Engage EST & Geomatics for a proper review III. Review and simplify execution strategy. | Deferred | Obioakor, O | NIL |  | $ 225,297.74 N 13,915,985.80 F$ 261,967.01 |  |  |  |  | Nil |  | HENZOL, KEMUD, VISCA
| FULL REPLACEMENT OF IMOR 58T (4-INCH x 3.4KM) | Fresh | Approved. I. Proceed to execution with the proposed new vendor (WILKRISS NIG. LTD) II. Ensure the MoM and offer decline letter from Thompson & Grace Investment Ltd is duly signed for documentation | Approved | Aderiye, A | C.NG.PAE.DL.21.001 | $ 137,763.36 N 12,884,978.45 F$ 179,633.46 | [5 empty] | 14800 | Warehouse Materials | WILKRISS
| SAGHARA 3S & 5L FLOWLINE REPLACEMENT – 4” Sch. 40 x 850m each (Total = 4” Sch. 40 x 1.7km). Resubmission & Reviewed offline | Resubmission | Approved. WORP steers from previous sitting 11/02/21 have been incorporated | Approved | Uwaezuoke, D | O.NG.PBW.SHF.03S.713FL/O.NG.PBW.SHF.05L.713FL |  |  | $ 204,508.67 N 74,834,367.87 F$ 401,700.68 |  |  |  | Nil |  | ANASAMI CONSTRUCTION
2021-02-25 | BONNY W30T Flowline Replacement (4" Sch 80 x 1km) | Resubmission | Conditional Approval. WORP steers from previous sitting 18/02 have not been fully incorporated. I. Engage WRFM to provide WBS for this activity and resubmit offline | Conditional Approval | Azaka, G | NIL |  | $ 101,126.24 N 37,144,159.42 F$199,002.81 |  |  |  |  | Nil |  | VANDRESSER NIG
| OTUMARA FLOW STATION GANTRY WORKS | Fresh | Deferred. I. Update WBS for this activity. II. Engage EST to review existing structural frame and attach schematic drawing. III. Confirm Gantry maximum load. | Deferred | Azaka, G | NIL |  |  | $ 187,308.06 N 6,577,567.94 F$206,814.41 |  |  |  | Nil |  | NAPEBI CONSTRUCTION
| KOCR 22T Flowline Sectional Replacement – 4” sch. 40 x 0.06km and 8” Sch 160 x 0.012km | Fresh | Approved. I. Forward approved e-WR to the Secretariat and Manager. II. Plan for mitigation against Vendors under performance due to low project cost. | Approved | Arowosafe, T | O.NG.PAE.GBG.FAC.724FC |  | $ 55,973.34 N 4,979,690.78 F$ 69,,095.05 |  |  |  |  | Nil |  | ABBEYCOURT ENERGY
| K2S Simultaneous Flow Project | Fresh | Approved. I. Engage CH to update ACV split currency values. II. Carry out materials check with Hotdesk. III. Emphasize criticality of this activity with the Vendor. | Approved | Akoma, I | C.NG.PBE.DF.21.005 |  | $ - 104,725.16 N - 36,794,719.22 F$ - 201,680.94 |  |  |  |  | F$: 22,416.83 | Savings on Mob and De-mob by using same contractor for Mechanical/ Instrumentation works, etc | GRAMEN PETROSERVE
| Replacement of LP header of Yokri flow station. -Reviewed offline | Fresh | Approved | Approved | Obiakor, O | O.NG.PCW.YKF.FAC.71300 |  |  | $ 31,865.72 N 375,865.72 F$ 32,854.55 |  |  |  | 23907.23 | saved for combining mobilization of Forcados Yokri 127T flowline sectional replacement and replacement of Yokri LP header | TONYMAR INVESTMENT
| GENERAL |  | Review materials reconciliation tracking system and communicate to leadership: ▪ Flowlines ▪ Facilities
2021-03-04 | FODPA and NEFS Boatlanding Rehabilitation Works | Fresh | Approved. I. Confirm full budget availability for these activities. II. Carry out materials reconciliation with Hotdesk. III. Ensure security plan is properly reviewed and assurance provided for adequate cover at site | Approved | Uwaezuoke, D | F$: C.NG.PBW.DF.212.001 – FODPA F$: C.NG.PCW.DF.98.706.1230 - NEFS |  |  | Total: FODPA + NEFS = F$394,395.64 |  |  |  | Nil |  | Gramen Petroserve
| FULL REPLACEMENT OF OGUTA 12T FLOWLINE(4” X 4.3KM) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Confirm WBS for this activity. II. Carry out materials reconciliation with Hotdesk and discount available materials. III. Update Project Schedule to current plan. IV. Include Fabrication & Hook up in the scope summary. V. Confirm linepipes availability for this activity. VI. Align POB requirement with OABP Central Team | Conditional Approval | Akinbiyi, A | 102155 | $ 132,486.76 N 37,684,516.42 F$ 231,787.20 | [5 empty] | Nil |  | WILKRISS
| FULL REPLACEMENT OF OGUTA 16S FLOWLINE(4” X 2.9KM) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Confirm WBS for this activity. II. Carry out materials reconciliation with Hotdesk and discount available materials. III. Update Project Schedule to current plan. IV. Include Fabrication & Hook up in the scope summary. V. Confirm linepipes availability for this activity. VI. Align POB requirement with OABP Central Team | Conditional Approval | Akinbiyi, A | 102155 | $ 91,808.64 N 26,740,513.71 F$ 179,482.45 | [5 empty] | Nil |  | MORRAY SERVICES
| FULL REPLACEMENT OF OGUTA 25T FLOWLINE(4” X 5.6KM) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Confirm WBS for this activity. II. Carry out materials reconciliation with Hotdesk and discount available materials. III. Update Project Schedule to current plan. IV. Include Fabrication & Hook up in the scope summary. V. Confirm linepipes availability for this activity. VI. Align POB requirement with OABP Central Team | Conditional Approval | Akinbiyi, A | 102155 | $ 165,827.86 N 46,524,990.84 F$ 288,423.35 | [5 empty] | Nil |  | GUIZ AND COMPANY
| LEAK REPAIR OF FORCADOS 127T FLOWLINE | Fresh | Approved. I. Engage WRFM to confirm WBS for this activity. II. Update Project title to include “Optimization of Line size” III. Update Project Schedule to current plan. | Approved | Obiakor, O | 102155 |  |  | $ 47,933.39 N 1,545,750.79 F$ 52,006.51 |  |  |  | F$39,515.51 | Mob and De-mob, Houseboat | TONYMA INVESTMENT
| SECTIONAL REPLACEMENT OF OTUMARA 42LS, 16T FLOWLINES AND FABRICATION OF HOOK-UP ARM OF OTUMARA 4L. | Fresh | Approved. I. Carry out materials reconciliation with hotdesk and discount available materials. | Approved | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  |  | $ 160,601.21 N 61,143,932.41 F$ 321,718.29 |  |  |  | F$82,000 & F$77,000 | F$82,000 (Shared marine logistics) + F$77,000 (Single mob/demob) | ANASAMI
| Diebu Creek 8T Flowline Replacement – 4” x 3.07km | Fresh | Stepped down by the team | Stepped down | Ehizoyanyan, O | WRFM 102155 |  | $228,572.93 N 83,941,422.41 F$449,762.45 |  |  |  |  | Nil |  | SEVOIL LTD
| BONN 12S Flowline Replacement – 4” x 1.7km | Fresh | Stepped down by the team | Stepped down | Ehizoyanyan, O
| BONNY W30T Flowline Replacement (4" Sch 80 x 1km) -Resubmission & Reviewed offline | Resubmission & Reviewed Offline | Approved. WORP steer from previous sitting 25/02/21 have been incorporated. | Approved | Azaka, G | NIL |  | $ 101,126.24 N 37,144,159.42 F$199,002.81 |  |  |  |  | Nil |  | VANDRESSER NIG
| GENERAL |  | Ensure timely checks on materials availability prior to WORP submission. • Only funded activities should be brought into plan and ensure alignment of execution with IAP central team. • Proper security plan review / HSE documentation for each project before mobilization. • Early engagement on marine request to avoid delayed mobilization to sites.
2021-03-11 | UZU MANIFOLD LOCATION PREPARATION | Fresh | Approved. I. Limit PO value to the contractor to available ACV balance in SAP. II. Engage C&P to update remaining ACV III. Ensure combination of controls is in place for managing community workers. IV. Liase with the planning team to align schedule & demand requirements for IAP | Approved | Oludare, S | P.NG.PAE.DG.17.001 |  |  |  | F$: 2,037,279.64 (N: 473,610,898.60, $: 789,293.09) |  |  | F$:107,225.24 | 5 % LOP Discount | RAFFOUL NIG. LIMITED
| FORC 111T Flowline Replacement (6" sch 40 x 2.7 km bulkline) & (4" sch 40 x 0.25 km flowline) | Fresh | Approved. I. Ensure combination of controls is in place for managing community workers. II. Decomit previously issued PO for Forcados 126S before issuing the new PO for 111T to the Vendor. III. Update Project Schedule to current plan. | Approved | Orji, C | C.NG.PAE.DL.21.001.1230 |  |  | $ 251,239.91 N 92,278,553.00 F$ 494,398.16 |  |  |  | 33891.12 | From Materials to be taken from Hot Desk | HENSTEEL ENGINEERING
| FULL REPLACEMENT OF IMOR 36L (4-INCH x 1.0 KM) | Fresh | Approved. I. Carry out proper material reconciliation with hotdesk. | Approved | Aderiye, A | C.NG.PAE.DL.21.001 | $ 47,000.69 N 11,269,553.88 F$ 76,696.49 | [5 empty] | F$: 12,500 | MATERIALS FROM THE SPDC WAREHOUSE. | ROMEK AND COMPANY
| SECTIONAL REPLACEMENT OF (a) IMOR 4-inch TEST LINE (48M) (b) IMOR RIVER 26S (48M) © IMO RIVER 44S (48M) (d) IMO RIVER 55S (48M) (e) IMO RIVER 43T (48M) (f) IMOR 60T (48M) | Fresh | Approved. I. Prompt engagement with Asset PUM’s to provide enhanced security surveillance for these lines. II. Update Project Schedule to current plan. | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 35,160.13 N 10,617,977.01 F$ 63,138.99 | [5 empty] | FS11,525.18 | MOB & DEMOB. ALL MATERIALS FOR THESE SECTIONAL REPLACEMENT SHALL BE SOURCED FROM SPDC WAREHOUSE | GAMSTEC
| SECTIONAL REPLACEMENT OF (a) IMOR RIVER 6-INCH BULKLINE (IMO 2 -1) X 1500 M (Additional leak points) | Fresh | Approved. | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 17,777.50 N 5,370,063.42 F$ 31,927.86 | [5 empty] | 8,280.04 USD | MOB & DEMOB IF USING A NEW CONTRACTOR | GAMSTEC
| Diebu Creek 8T Flowline Replacement – 4” x 3.07km | Fresh | Conditional Approval. Subject to NAPIMS engagement on contract expiration date extension. | Conditional Approval | Ehizonyan, O | O.NG.PBE.DBC.09T.713FL |  | $238,624..58 N 87,632,760.32 F$469,540.94 |  |  |  |  | Nil |  | SEVOIL LTD
| FULL REPLACEMENT OF ETELEBOU 3S FLOWLINE (4” X 1.2KM) | Fresh | Approved: Premised on early mobilization. I. Update contract end date and engage NAPIMS. II. Forward cost savings to I&A for documentation. | Approved | Otavie, G | O.NG.PAE.ETL.03S.713FL |  | $ 57,925.84 N 13,410,314.07 F$ 85,626.42 |  |  |  |  | Nil |  | PECKON NIGERIA
| BONNY W18S Flowline Replacement (4" Sch 40 x 1.2km) | Fresh | Conditional Approval. I. Carry out work distribution alignment across team. II. Confirm Contractors capacity to execute | Conditional Approval | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  | $ 133,308.68 N 48,964,351.92 F$262,332.00 |  |  |  |  | Nil |  | IKONIBO
| Provision of lay barge for installation of CCUs at Kanbo W5L/S -Reviewed Offline | Fresh | Approved. | Approved | Ehizonyan, O | C.NG.AFS.DF.18.025.1202 |  |  | $ 22,320.8 N 602,305.87 F$ 23,907.9 |  |  |  | F$: 10,062.00 | Shared marine logistics and security deployment | HENZOL GLOBAL
2021-03-18 | Replacement of 1,75KM of 2” water equalization of Soku cluster D | Resubmission | Conditional Approval. WORP steers from previous sitting 18/02/21 have been incorporated. Further steers: I. Attach signed MoM of review meeting held with EST & Geomatics. II. Update WBS for this activity. III. Engage vendor & secure commitment to execute work accordingly. IV. Liase with C&P to load contract in SAP. | Conditional Approval | Obiakor, O | Nil |  | $ 107,282.92 N 39,409,715.49 F$211,129.34 |  |  |  |  | Nil |  | VANDREZZER NIG. LTD
| BOGT SHORE PROTECTION – PHASE1 | Fresh | Approved. I. Focused attention on vendor HSE risk management before and during site works. II. Review & accelerate project schedule. III. Proceed with interim plan to safeguard shoreline before actual work execution. IV. Kick off meeting to include Vendor top management in view of the nature of work. | Approved | Ogunkunle, M | C.NG.PBE.IC.07.001 |  |  |  | F$ 875,727.01 N69,244,408.04 + $693,264.80 |  |  | Nil |  | PILE FOUNDATION LIMITED
| Seibou 3 and 4 bulkline JIV and clamping. -Reviewed offline | Fresh | Approved. I. Update project schedule to current plan | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $ 27,976.94 N 511,967.62 F$ 29,326.00 |  |  |  | 9050.71 | cost saving on inter-area move instead of mobilizing a new contractor. | HENZOL GLOBAL
| GENERAL |  | Engage the relevant authorities with proposal to include equalization lines in FIMS for ease of line tracking and integrity monitoring.
2021-03-25 | Bonny W14 Maintenance Dredging works | Fresh | Approved. I. Reiterate the responsibility of the main contractor despite invoice partnering option. II. Ensure safe work completion before contract expiration date. III. Update project schedule to align with current plan IV. 5no top risk to include “Interface management risk” V. Align cost breakdown descriptions with cost summary sheet. VI. Ensure proper HSE & Security plan review. VII. Kick off meeting to emphasize Covid’19 protocols at site. | Approved | Onyejekwe, C | 110744 |  |  |  | $: 428,558.82 N: 192,570,123.89 F$: 935,989.97 |  |  | F$: 56,227.33 | Cost saving is from Low Oil Price LoP discounts (i.e. 7.5%). | SHORELINE DREDGING
| Bonny W13 Maintenance Dredging works | Fresh | Approved. I. Reiterate the responsibility of the main contractor despite invoice partnering option. II. Ensure safe work completion before contract expiration date. III. Update project schedule to align with current plan IV. 5no top risk to include “Interface management risk” V. Align cost breakdown descriptions with cost summary sheet. VI. Ensure proper HSE & Security plan review. VII. Kick off meeting to emphasize Covid’19 protocols at site. | Approved | Onyejekwe, C | 110744 |  |  |  | $: 412,055.67 N: 188,667,970.36 F$: 909,204.47 |  |  | F$: 54,055.53 | Cost saving is from Low Oil Price LoP discounts (i.e. 7.5%). | SHORELINE DREDGING
| Enwhe East Flare Test Pit and Bundwall Construction Work | Fresh | Approved. I. Capture cost savings and forward to I&A for reporting. II. Update project schedule to align with current plan III. Update appropriately the remaining ACV for this submission. | Approved | Otavie, G | C.NG.LNG.DG.19.004.1230 |  | $ 54,465.13 N 113,596,678.73 F$ 353,797.61 |  |  |  |  | Nil |  | Gramen Petroserve
| Enwhe West Flare Test Pit and Bundwall Construction Work | Fresh | Approved. I. Update project schedule to align with current plan. II. Update appropriately the remaining ACV for this submission III. Ensure vendor has adequate resources to deliver according to schedule. | Approved | Uwaezuoke, D | C.NG.LNG.DG.19.004.1230 |  | $ 49,888.81 N 95,735,716.20 F$ 302,156.84 |  |  |  |  | Nil |  | Gramen Petroserve
| Estuary Cluster 51 Ring A Replacement Work ahead of FORC73 Workover | Fresh | Approved. I. Ensure safe work completion before contract expiration date. II. Update project schedule to align with current plan. III. Harmonize project title with other relevant documentation. | Approved | Uwaezuoke, D | O.NG.STG.PBE.FOR.072FL |  |  | $ 102,377.04 N 26,433,707.21 F$ 172,031.08 |  |  |  | Nil |  | Miden Systems Ltd
| Kanbo 5LS TRP Outage surveillance cover. | Fresh | Approved. I. Vendor to deploy adequate resources for security surveillance. | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $ 31,947.75 N 372,012.45 F$ 32,928.02 |  |  |  | Nil |  | HENZOL GLOBA
| Kanbo W7S (6’’ x 0.1Km) & W6T (6’’ x 0.1Km) Flowline Sectional Replacement | Fresh | Deferred. I. Liase with C&P to update remaining ACV for this activity. II. Update summary description of cost saving initiative. | Deferred | Otavie, G | O.NG.STG.PBE.KAN.007FL O.NG.STG.PBE.KAN.006FL |  |  | $ 122,276.73 N 3,736,362.47 F$ 132,122.22 |  |  |  | F$: $20,000 | Elimination of Mob and De-mob of Houseboat, by latching onto existing houseboat already in Tunu | FEIMA
| FORC 110T & FORC 112T Integrity Checks | Fresh | Deferred. I. Liase with C&P to update remaining ACV for this activity | Deferred | Orji, C | C.NG.PCW.DL.21.001 |  |  | $ 64,269.17 N 1,986,542.12 F$ 69,503.80 |  |  |  | Nil |  | TUSOJA MARINE
| Tunu BQRT-3 Flowline Replacement (6" SCH 80 x 6.1km) | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Carry out material reconciliation with hotdesk. II. Update 5no top risk to include “Interface management risk” III. Update summary | Conditional Approval | Otavie, G | C.NG.AFS.DL.19.006.1230 |  |  | $ 306,292.32 N 117,178,807.88 F$ 615,063.88 |  |  |  | F$: 20,000 | Campaign mobilization will enable the sharing of Marine logistic resources like houseboat which are already in the field | SEVOIL & OSAKS INTEQ
| GENERAL |  | Escalate security challenges in Kanbo and Seibou axis to Security LT.
2021-04-01 | FORC 110T & FORC 112T INTEGRITY CHECKS | Resubmission | Approved. I. Update Contractor’s name with the correct spelling in the submission. II. Include value proposition (bopd) for both lines. III. Indicate all the WBS provided for this project and charge each flowline cost to specific WBS provided IV. Review and update risk No3 in the top risks. | Approved | Orji, C | O.NG.STG.PBE.FOR.110FL |  |  | $ 64,269.17 N 1,986,542.12 F$ 69,503.80 |  |  |  | Nil |  | ELKON INTEGRATED
| TUNU BQRT-3 Flowline Replacement (6" Sch 80 x 6.1km) -Resubmission & Reviewed offline | Resubmission | Approved. WORP steers from previous sitting 25/03/21 have been incorporated. | Approved | Otavie, G | C.NG.AFS.DL.19.006.1230 |  |  | $ 304,115.16 N 116,379,232 F$ 610,779.8 |  |  |  | F$: 20,000 F$: 4,284.08 | House boat sharing and materials discounted | SEVOIL & OSAKS INTEQ
| BONNY W18S Flowline Replacement (4" Sch 40 x 1.2km) -Resubmission & Reviewed offline | Resubmission | Approved. WORP steers from previous sitting 11/03/21 have been incorporated. | Approved | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  | $ 132,180.84 N 48,550,109.36 F$260,112.61 |  |  |  |  | Nil |  | IKONIBO NIG
| GENERAL |  | Always ensure equitable work allocation.
2021-04-08 | SECTIONAL REPLACEMENT OF (a) IMOR RIVER 6-INCH BULKLINE (IMO 2 -1) X 800 M (Additional leak points) (b) IMOR RIVER 26S (300 M) © IMO RIVER 60T (2200M) | Fresh | Deferred. I. Evaluate all additional work scope for each conduit, hold an alignment meeting with the Vendor and attach MoM to the resubmission. | Deferred | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 36,849.85 N 11,959,792.85 F$ 68,364.45 | [5 empty] | 8,280.04 USD | MOB & DEMOB USING A NEW CONTRACTOR. | GAMSTEC INTEGRATED
| GENERAL |  | Engage Asset team to provide enhanced security surveillance for these lines.
2021-04-15 | AFAM VI VENT GATHERING PROJECT | Fresh | Conditional Approval. I. Update value of work order in split currency. II. Include security risk in the 5nos top risks. III. Attach email confirmation of materials reconciliation carried out with Hotdesk. IV. Confirm and document contractor’s readiness and capability to mobilize according to schedule. V. Engage C&P to provide steers on the provision of accommodation by the contractor at site. | Conditional Approval | Dienagha, I | C.NG.PCE.NO.21.004 | USD 88,709.22 NGN 8,425,414.35 F$: 111,835.53 | [5 empty] | F$: 7,824.72 | (Nonstock materials) | ADVANCED COATING TECH
| SCAFFOLDING OKGP DRYER PROJECT | Fresh | Conditional Approval. I. Update value of work order in split currency. II. Liaise with C&P to seek support on the proposed mode of payment to the contractor. III. Engage BSU to confirm budget availability for this activity. | Conditional Approval | Ewenike, M | C.NG.PCE.NO.21.004 | NGN 3,111,284.44 USD 4,372.58 F$: 14,582.31 | [5 empty] | NIL |  | GRAMEN PETRO-SERV
| CRACK REPAIR OF SOKU GP AG2 TURBINE EXHAUST COLLECTOR | Fresh | Approved. I. Engage Contract Holder to confirm adequate ACV ceiling for this activity. II. Update Project title to properly describe activity. | Approved | Obiakor, O | O.NG.PBE.SKG.FAC.72FC |  | $ 8,346.46 N 6,773171.82 F$26,194.08 |  |  |  |  | NIL |  | GRAMEN PETRO-SERV
| GENERAL |  | Engage NAPIMS to discuss Mechanical modification contracts. • Expedite action on ceiling increase and time extension for GRAMEN PETRO-SERVE contract. • Liase with C&P to resolve contract ACV split value issues and revert to Manager.
2021-04-22 | AFAM VI VENT GATHERING PROJECT - Resubmission | Resubmission | Approved. WORP steers from previous sitting 15/04/21 have been incorporated. I. Proceed to execution and follow through on steers from C&P. | Approved | Dienagha, I | C.NG.PCE.NO.21.004 | USD 88,709.22 NGN 8,425,414.35 F$: 111,835.53 | [5 empty] | 7824.72 | (Nonstock materials) | ADVANCED COATING TECH
| DELETED SEs FOR OPUKUSHI 2T FLOWLINE REPLACEMENT - Resubmission | Resubmission | Approved. I. This payment is for provision of services rendered in 2019. Invoice could not be provided by the Vendor due to their internal constraints. II. This P.O is to enable creation of S.E for invoice payment. | Approved | Ehizoyanyan, O | C.NG.PCW.DL.21.001.1230 |  |  | $ 10,983.23 N 4,041,941.25 F$ 21,633.93 |  |  |  | NIL |  | VANDREZZER ENERGY SERVICES
| SECTIONAL REPLACEMENT OF (a) IMOR RIVER 6-INCH BULKLINE (IMO 2 -1) X 800 M (Additional leak points) (b) IMOR RIVER 26S (300 M) © IMO RIVER 60T (1850M) (d) IMO RIVER 32L/GLL (e) IMO RIVER 4-INCH BULKLINE (f) IMO RIVER 57GLL (g) IMO RIVER 36S (h) IMO RIVER 63T (i) IMO RIVER 4-INCH TEST LINE - Resubmission | Resubmission | Approved. WORP steers from previous sitting 15/04/21 have not been fully incorporated. I. Ensure C&P and PS participation in the alignment meeting with the contractor and document MoM to WORP secretariat. | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 38,413.62 N 12,943,786.38 F$ 72,521.09 | [5 empty] | NIL |  | GAMSTEC INTEGRATED
| SECTIONAL REPLACEMENT OF AFAM 27T FLOWLINE (8” x 12m) | Fresh | Approved | Approved | Akinbiyi, A | O.NG.PAE.I1F.FAC.724FC | $ 30,177.06 + 98,171.47 N 51,406,830.37 + 2,393,303.75 F$ 165,636.43 + 104,477.93 | [5 empty] | F$: 11,596.18 | Mob and De-mob from the two Contractors | GAMSTEC INTEGRATED
| ESTUARY CLUSTER 9 RING AND 2 Nos. BULKLINE RISER REPLACEMENT WORK. | Fresh | Approved | Approved | Uwaezuoke, D | C.NG.PBW.DF.212.001 |  |  | $ 119,090.63 N 31,814,175.20 F$ 202,922.45 |  |  |  | NIL |  | Miden Systems Limited
| SECTIONAL REPLACEMENT OF NKALI 10S – (4” Sch.80 X 120M) NKALI 13L – (4” Sch.80 X 120M) NKALI 13S – (4” Sch.80 X 120M) | Fresh | Approved. I. Reference percentage of commitment to date as part of the reasons for choice of contractor. | Approved | Aderiye, A | O.NG.PAE.NKF.FAC.724FC | $ 41,624.94 N 4,030,118.50 F$ 52,244.49 | [5 empty] | FS 22,162.92 | MOB & DEMOB BY USING ONE CONTRACTOR TO EXECUTE THE REPAIRS OF THE THREE (3) FLOWLINE REPAIRS. | WILKRISS NIGERIA
| NUN RIVER WELL 13T MAINTENANCE DREDGING WORKS. | Fresh | Approved | Approved | Onjejekwe, C | 110744 |  |  |  | $: 391,403.14 N: 225,529,048.35 F$: 985,682.59 |  |  | F$: 111,908.44 | Cost saving is from Low Oil Price LoP discounts (i.e. 15%). | FW DREDGING LTD
| GENERAL |  | Ensure C&P participation in all alignment meetings with contractors. • Always reference percentage of commitment to date as part of the reasons for choice of contractor. • Document contractor’s performance at site for referencing.
2021-04-29 | LOCATION DREDGING WORKS AT BENISEDE EAUA-2 – ADDITIONAL RIG PAD AREA SAND FILLING WORKS | Fresh | Conditional Approval. Update and revert upon completion of the following: I. Engage PS to finalize review on the estimated volume/cost of additional sandfill works. | Conditional Approval | Onjejekwe, C | C.NG.AFS.DD.19.009.9401 |  |  |  | $: 18,696.66 N: 59,495,875.75 F$: 175,471.03 |  |  | F$: 44,242.44 | Cost saving is from Low Oil Price LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| NUN RIVER DIEBU CREEK BULKLINE TO GBARAN - Civil Structural Scope. | Fresh | Conditional Approval. Update and revert upon completion of the followings: I. Update Project title to appropriately describe activity. II. Forward project MTO to PS for review. III. Engage C&P to review and update omitted contract line items in ARIBA / SAP | Conditional Approval | Ehizoyanyan, O | C.NG.PAE.DL.21.002.1230 |  | $ - 267,723..54 N – 146,066,686.79 F$ - 652,616,00 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| GBARAN 5T FLOWLINE INTEGRITY CHECK | Fresh | Approved. I. In the event of line failure, revert to EST to review the pipe schedule for replacement works | Approved | Okeke, N | C.NG.PAE.DL.21.002.1230 |  | $ 12,158.02 N 3,511,033.32 F$ 21,409.68 |  |  |  |  | NIL |  | THOMPSON AND GRACE LTD
2021-05-06 | CONSTRUCTION OF AIR COMPRESSOR FOUNDATION BAY & SHED AT ESCRAVOS FS FOR THE IG - IA PROJECT – Additional work | Fresh | Approved. I. Update the remaining ACV for this submission II. CH to liaise with C&P and resolve contract ACV split value issues. | Approved | Ehizoyanyan, O | C.NG.PAE.DL.21.002.1230 |  |  | $ - 7,171.22 N – 18,981,937.62 F$ - 57,187.92 |  |  |  | NIL |  | GRAMEN PETROSERVE
| SEIBOU BULKLINE 3 AND 4 JIV - 2ND JIV AND SEIBOU BULKLINE 3 AND 4 JIV - Proposed 3rd JIV. | Fresh | Deferred. I. Engage C&P to support execution strategy and revert. | Deferred | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300 |  |  | $ 75,346.14 N 1,168,966.47 F$ 78,426.42 |  |  |  | NIL |  | TONYMAR INVESTMENT
| BONNY WELL 12S JIV SUPPORT TO THE ASSET TEAM. | Fresh | Approved. I. Update WBS for this activity to Asset account. II. Update the remaining ACV for this submission. | Approved | Ehizoyanyan, O | C.NG.PAE.DL.20.001.1230 |  | $ 14,073.00 N 718,429.33 F$ 15,966.89 |  |  |  |  | NIL |  | SURVEILLANCE 2000 LTD
| APARA 10 BORROW PIT RECLAMATION PROJECT- ADDITIONAL WORK | Fresh | Deferred. I. Secure approval from Divestment finance team to carry out this activity and revert. | Deferred | Agbonsalo, O | O.NG.PAE.OBP.MFC.71300 |  |  |  | $ 89,508.25 N 53,704,949.76 F$ 231,023.27 |  |  | F$: 31,503.17 | Lop,re-negotiated rates | EA TEMILE
| SECTIONAL REPLACEMENT OF IMOR (a) 63T (3-INCH x 80M) – IMO 1 AREA (b) 21S (4-INCH X 24M) – IMO 2 AREA | Fresh | Approved | Approved | Aderiye, A | O.NG.PAE.UCF.FAC724FC | $ 13,612.36 N 3,308,636.05 F$ 23,169.24 | [5 empty] | FS8,282.04 | MOB & DEMOB SINCE THE SAME CONTRACTOR IS ALREADY ON THE SITE | ROMEK AND COMPANY
| LOCATION DREDGING WORKS AT BENISEDE EAUA-2 – ADDITIONAL RIG PAD AREA SAND FILLING WORKS. -Resubmission & reviewed offline | Resubmission & Reviewed offline | Approved. WORP steer from previous sitting 29/04/21 have been incorporated | Approved | Onyejekwe, C | C.NG.AFS.DD.19.009.9401 |  |  |  | $: 18,696.66 N: 59,495,875.75 F$: 175,471.03 |  |  | F$: 44,242.44 | Cost saving is from Low Oil Price LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| GENERAL |  | Forward to ALL the procedure on managing emergency/urgent works. • Harmonize template for standard list of materials for hook up/flowline works and circulate to team.
2021-05-14 | Provision of Engineering support for JIV to SEIBOU bulklines 3 and 4 (Repeat JIV and access new leak points) - Resubmission | Resubmission | Approved. WORP steer from previous sitting 06/05/21 have been incorporated. I. Engage Asset team for an enhanced surveillance cover. | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $ 75,518.29 N 1,188,378.37 F$ 78,649.72 |  |  |  | NIL |  | TONYMAR INVESTMENT
| Deleted SEs for Soku Relocation of Emergency Spill Reponses Caravan, Construction of Chemical Shed and procurement and Installation of Jib Crane | Resubmission | Approved. | Approved | Ehizoyanyan, O | O.NG.PBE.SKF.FAC.724FP |  | $ 136,725.22 N 29,734,583.43 F$ 215,077.218 |  |  |  |  | NIL |  | VANDREZZER ENERGY SERVICES
| Bonny 12S Flowline Replacement – (4” x 1.75km). | Fresh | Approved. I. Engage BSU to provide adequate budget for this activity. II. Ensure linepipe cost is transferred from previous activity to Bonny 12S. III. Provide assurance of Vendors ability to carry out work in this community. IV. Capture cost savings secured from discounting houseboat to the use of hotel accommodation and forward to I&A for documentation. | Approved | Ehizoyanyan, O | C.NG.PAE.DL.21.001.1230 |  | $ 246,444.75 N 6,442,651.14 F$ 263,421.44 |  |  |  |  | NIL |  | JOSBANI CONSTRUCTION
| Repair of cracked 2” sampling line to Atmospheric flare of Soku GP GRU train 3. | Fresh | Conditional Approval. I. Update ACV for this activity. II. Review interim mobilization to “Distance below 100km” and revert with updated cost. | Conditional Approval | Obiakor, O | O.NG.PBE.SKG.FAC.72FC |  | $ 5,043.65 N 3,689,043.98 F$14,764.45 |  |  |  |  | 25456.77 | Cost saving initiative -savings for not doing full mobilization and no demobilization | GRAMEN PETRO-SERV
| GENERAL |  | Proper materials tracking & reconciliation procedure.
2021-05-20 | OTUMARA FLOW STATION GANTRY WORKS -Resubmission | Resubmission | Deferred. WORP steers from previous sitting 25/02/21 have been incorporated. Further steers: I. Engage C&P to review vendor rates and benchmark with PS to ensure process is in line with approved contracting procedures. II. Update risk register to include “Scaffolding” and review procedure with SME in EST prior mobilization. III. Ensure active participation of the Quality team to avoid equipment & materials failure. | Deferred | Azaka, G | C.NG.PBW.IM.17.005.1230 |  |  | $ 224,535.15 N 15,882,943.33 F$266,387.44 |  |  |  | NIL |  | NAPEBI CONSTRUCTION
| TUNU CDRY-3 FLOWLINE CONSTRUCTION -2 days standby | Fresh |  | Deferred | Azaka, G | C.NG.AFS.DF.19.003.1200 |  |  | $3,847.34 N 2,103,075.15 F$ 9,389.04 |  |  |  | NIL |  | IKONIBO NIG LTD
| REPLACEMENT OF CORRODED RISER FORCADOS 127T FLOWLINE. | Fresh | Approved. I. Update contract expiration date. II. Update business case and specify that this activity is different from previously completed work. III. Full adherence to CSSS requirements at site. IV. Always attach QAQC reports to justify additional work submissions. | Approved | Obiakor, O | 102155 |  |  | $ 75,911.23 N 1,393,860.79 F$ 78,425.57 |  |  |  | F$29,515.51 | Mob and De-mob, Houseboat | TONYMA INVESTMENT
| ABRICATION/INSTALLATION OF OBELLE 3L HOOK-UP ARM (a) 3T (3-INCH x 12 M) | Fresh | Approved. I. Update ACV for this activity. II. Always ensure risk assessment is carried out for all submissions prior to WORP submission. III. Update Project Schedule to current plan. | Approved | Aderiye, A | O.NG.PAE.OLF.FAC.724FC | $ 6,007.13 N 1,414,531.68 F$ 9,734.48 | [5 empty] | FS8.801.96 | MOB & DEMOB SINCE THE SAME CONTRACTOR IS ALREADY ON THE SITE | ROMEK
| GENERAL |  | Proper reporting of all non-compliance at sites by HSE inspectors. • Full adherence to CSSS requirements at all OABP sites. • Free-issue materials to be included as savings and differentiated in the remarks.
2021-05-27 | Repair of Cracked 2” sampling line to atmospheric flare of Soku GP GRU Train 3 -Resubmission | Resubmission | Approved. WORP steers from previous sitting 14/05/21 have been implemented. | Approved | Obiakor, O | O.NG.PBE.SKG.FAC.72FC |  | $ 3,669.00 N 2,710,751.95 F$10,811.96 |  |  |  |  | 25456.77 | savings for not doing full mobilization and no demobilization | GRAMEN PETRO-SERV
| Unblocking of Etelebou Test line to Gbaran (6” X 8km Bulk line) - Resubmission | Resubmission | Deferred. WORP steers from previous sitting 25/06/20 have not been fully implemented. Further steers: I. Engage PS to further review cost optimization on Inter area spread and As-built survey. II. Confirm Vendors CAP assessment status. III. Engage hotdesk for materials reconciliation. IV. Prioritize Inventory spill / environmental impact in the 5no top risks. | Deferred | Obiakor, O | C.NG.PCE.NO.21.002.1230 |  | $ 70,330.40 N 20,070,011.95 F$ 126,105.43 |  |  |  |  | NIL |  | ROMEK & COMPANY
| Sectional Replacement of Afam 25T flowline (Additional Work) | Fresh | Approved. I. Always include line length in the project title. | Approved | Akinbiyi, A | O.NG.PAE.I1F.FAC.724FC | $ 40,336.43 N 11,879,588.32 F$ 71,639.69 | [5 empty] | NIL |  | GAMSTEC INTEGRATED
| Gbaran Produced Water Flowline Construction – 6” sch. 40 x 1.72km | Fresh | Deferred. I. Carry out proper corrosion management study to determine required linepipe schedule for this activity. II. Engage hotdesk for materials reconciliation. | Deferred | Arowosafe, T | C.NG.PBE.IM.21.001.1230 |  | $ 76,928.46 N 19,082,949.85 F$ 127,212.92 |  |  |  |  | NIL |  | GUIZ AND COMPANY
| Fabrication and Installation of Ubie 8T Hook Up Arm | Fresh | Approved | Approved | Azaka, G | C.NG.AFS.DF.19.003.1200 |  | $ 643.30 N 225,164 F$ 1,381.55 |  |  |  |  | NIL |  | MORRAY SERVICES
| Enwhe East Miscellaneous Civil Works. | Fresh | Approved. I. Include resource sharing as cost savings and forward to I&A. II. Ensure proper HSE supervision and adequate security cover at site. | Approved | Ebirim, M | C.NG.LNG.17.003.1230 |  |  |  | F$: 219,812.14 |  |  | F$: 15,281.06 | 6.5 % LOP Discount | BENCOV NIG.LIMITED
| GENERAL |  | Shrink Sleeves now available for collection at the warehouse.
2021-06-03 | Sectional Replacement of ImoR 36L (3” x 80m) from Gathering manifold to Inlet manifold. | Fresh | Conditional Approval. Subject to pending resolution of contract time extension by NAPIMS. | Conditional Approval | Aderiye, A | O.NG.PAE.UCF.FAC724FC | $ 10,654.64 N 2,021,999.35 F$ 15,982.70 | [5 empty] | FS6,617.11 | Free Issue materials | ROMEK
| Re-routing of NUNR 3S, 13T, 16T Flowline (4” sch 80 x 1.1km) | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Capture cost savings from shared resources. II. Engage C&P to reconcile ACV figures. | Conditional Approval | Uwaezuoke, D | P.NG.PAE.OP.19.005.9401 |  | $ 248,215.97 N 7,477,220.95 F$ 267,918.80 |  |  |  |  | NIL |  | Tonymar Investment
| Re-routing of NUNR 12LS Flowline (4” sch. 80 x 700m) | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Capture cost savings from shared resources. II. Engage C&P to reconcile ACV figures. | Conditional Approval | Uwaezuoke, D | P.NG.PAE.OP.19.005.9401 |  | $ 183,798.51 N 5,919,883.68 F$ 203,207.96 |  |  |  |  | NIL |  | Surveillance 2000 Limited
| Unblocking of Etelebou Test line to Gbaran (6” X 8km Bulk line) -Resubmission | Resubmission | Approved. WORP steers from previous sitting 27/05/21 have been incorporated. I. Ensure top-level risk of potential spill to the environment and mitigation are well adhered to at site. | Approved | Obiakor, O | C.NG.PCE.NO.21.002.1230 |  | $ 76,114.92 N 20,641,979.95 F$ 133,453.75 |  |  |  |  | NIL |  | ROMEK & COMPANY
| FORC 111T Flowline Replacement (4" sch 40 x 0.411km Additional scope) -Reviewed offline | Fresh | Approved. | Approved | Orji, C | C.NG.PCW.DL.21.001.1230 |  |  | $ 38,383.78 N 14,097,183.85 F$ 75,530.51 |  |  |  | NIL |  | HENSTEEL ENGINEERING
| Otumara flow station Gantry work. -Reviewed offline. | Resubmission | Approved. WORP steers from previous sitting 20/05/21 have been incorporated. | Approved | Azaka, G | C.NG.PBW.IM.17.005.1230 |  |  | $ 82,470.03 N 2,409,002.58 F$88,817.86 |  |  |  | NIL |  | NAPEBI & PECOM
| GENERAL |  | Project Leads to ensure all submissions are reviewed prior WORP sitting.
2021-06-10 | Gbaran Produced Water Flowline Construction – 6” sch. 80 x 1.72km -Resubmission | Resubmission | Approved. WORP steers from previous sitting 27/05/21 have been incorporated. I. Engage NAPIMS for approval to raise P.O. II. Confirm linepipes availability & location. | Approved | Arowosafe, T | C.NG.PBE.IM.21.001.1230 |  | $ 72,928.93 N 17,434,041.54 F$ 115,450.98 |  |  |  |  | NIL |  | GUIZ AND COMPANY
| Re-routing of NUNR 12LS Flowline (4” sch. 80 x 700m) -Resubmission | Resubmission | WORP steers from previous sitting 03/06/21 have been incorporated | Approved | Uwaezuoke, D | P.NG.PAE. OP.19.005.9401 |  | $ 179,829.74 N 5,297,237.66 F$ 192,749.83 |  |  |  |  | F$: 87,447.78 | Shared Resources – houseboat | Surveillance 2000 Limited
| Re-routing of NUNR 3S, 13T, 16T Flowline (4” sch 80 x 1.1km) -Resubmission | Resubmission | WORP steers from previous sitting 03/06/21 have been incorporated. | Approved | Uwaezuoke, D | P.NG.PAE.OP.19.005.9401 |  | $ 241,645.94 N 6,316,713.09 F$ 257,052.56 |  |  |  |  | NIL |  | Tonymar Investment
| Estuary Cluster 51: Installation of Forcados. 73LS Hook-up Arm | Fresh | Progress manual deletion of previous PO for Opukushi 32T flowline. | Approved | Uwaezuoke, D | C.NG.AFS.DL.18.004.1218 |  |  | $ 67,038.61 N 2,973,825.23 F$ 74,874.78 |  |  |  | NIL |  | Gawason Integrated
| Bonny W12S JIV Support Services to the Asset Team – Additional work. | Fresh | Approved. I. Attach e-mail confirmation of additional work at site & forward to the Secretariat. | Approved | Ehizoyanyan, O | O.NG.PCE.BNF.FAC.71300 |  | $ 9,171.00 N 286,524.00 F$ 9,926.00 |  |  |  |  | NIL |  | SURVEILLANCE 2000 LTD
| Otumara flowstation Replacement of corroded drip pan. | Fresh | Approved. I. Progress manual deletion of previous PO for Otumara W20, 25 & 27 WHP rehabilitation. II. Ensure proper kick-off meeting | Approved | Obiakor, O | C.NG.PBW.IM.17.005.1230 |  |  | $ 108,500.00 N 3,350,000 F$116,670.73 |  |  |  | NIL |  | ROESON NIG
2021-06-17 | K2S Simultaneous Flow Project - Materials for Workshop Fabrication | Fresh | Deferred. I. Carry out further engagement with Procurement team to expedite materials delivery and revert with outcome. II. Document delays encountered from Procurement team and involve Asset team in the engagement. III. Liase with C&P to reconcile ACV figures. | Deferred | Akoma, I | C.NG.PBE.DF.21.005 |  | $11,908.95 N F$11,908.95 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Gbaran Produce Water Re-injection Project – Preliminary Works (Phase 1) | Fresh | Approved. I. Liase with C&P to reconcile ACV figures. II. Start early documentation of project pictures & forward to SE Lead. | Approved | Akoma, I | C.NG.PBE.IM.21.001.1230 |  | $ 13,865.02 N 10,453,136.83 F$ 39,360.48 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Kanbo 3L Flow line Sectional Replacement – (6’’ SCH 40 x 0.2km) | Fresh | Stepped Down. Project Lead to reconcile contracting issue and revert. | Stepped Down | Ehizoyanyan, O
| Replacement of Otumara 4L GLL (4" Sch 40 x 1.0km) | Fresh | Stepped Down. Project Lead to reconcile contracting issue and revert. | Stepped Down | Obiakor, O
| GENERAL |  | Always ensure strict adherence to SPDC procedures.
2021-06-24 | Diebu Creek FS Shutdown activities. | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Update WBS for this activity. II. Attach an approved OABP-WR. III. Carry out materials reconciliation with Hotdesk. IV. Update Project title to appropriately describe work scope. V. Engage CH for contract ceiling increase. VI. Liase with EST to ascertain Asset Integrity scope. | Conditional Approval | Uwaezuoke, D | TBA |  | $ 38,880.07 N 16,955.578.78 F$ 80,235.14 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Gbaran Produce Water Re-injection Project. -Reviewed offline | Fresh | Approved | Approved | Akoma, I | C.NG.PBE.IM.21.001.1230 |  | 800661.49 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
2021-07-01 | Kanbo 3L Flow line Sectional Replacement – (6’’ sch 40 x 0.2km) | Fresh | Approved. I. Set up an interface management meeting with the vendors and document MoM. II. Update CTS cost in the cost breakdown summary. | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $35,265.98 - N 2,357,063.1 F$41,014.91 - ELKON $31,746.32 N 1,024,554.20 F$34,245.23 - PALTOJEN |  |  |  | NIL |  | PALTOJEN NIG ELKON INTEGRATED
| Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km – Additional work | Fresh | Deferred. I. Engage C&P and other relevant project teams (NLNG) to ascertain company decision on vendors hotel accommodation payment during Covid’19 at site. | Deferred | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 1,115.74 N 198,497.00 F$ 1,638.79 |  |  |  |  | NIL |  | ABBEYCOURT ENERGY
2021-07-08 | Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km – Additional work -Resubmission | Resubmission | Deferred. WORP steers from previous sitting 01/07/21 have not been closed out. I. Engage C&P with outcome of discussions held with NLNG team to ascertain company decision on vendors hotel accommodation payment during covid’19 at site and revert. | Deferred | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 1,115.74 N 198,497.00 F$ 1,638.79 |  |  |  |  | NIL |  | ABBEYCOURT ENERGY
| Re-routing of NUNR 3S & 13T Flowline (4” Sch 80 x 700m) - SLOT Re-routing of NUNR 16T Flowline (4” sch 80 x 350m) – TONYMAR -Resubmission | Resubmission | Deferred. I. Advised to propose a single Vendor to reduce cost implication. | Deferred | Uwaezuoke, D | P.NG.PAE.OP.19.005.9401 |  | Slot $ 173,807.54 N 4,600,382.20 F$ 185,027.98 Tonymar $ 119,438.25 N 4,047,964.33 F$ 129,311.34 |  |  |  |  | NIL |  | Slot Engineering Tonymar Investment
| Provision of TRP scale inhibition injection points in Tunu, Opukushi & Benisede flow stations. | Fresh | Deferred. I. Engage CH to update ACV. II. Attach an approved e-WR | Deferred | Obiakor, O | C.NG.PBW.DF.21.003 |  |  | $ - 65,451.78 N – 22,088,4444.87 F$ - 119,326.04 |  |  |  | F$: 42,345.22 | Inter area mobilization instead of full mob to two facilities and domobilization | GRAMEN PETROSERVE
| Nun River Diebu Creek Bulkline to Gbaran - Civil Structural Scope. (missed out scope) | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Engage CH to update ACV. II. Update submission to clearly explain “Inter area move” as specified in the contract. III. Attach an updated Project schedule IV. Ensure provision for proper crew change to avoid personnel overstay at site | Conditional Approval | Obiakor, O / Ehizoyanyan, O | C.NG.PAE.DL.21.002.1230 |  | $ - 48,263.45 N – 48,639,602.94 F$ - 166,896.63 |  |  |  |  | F$: 21,151.12 | inter area move to Nun river manifold instead of full mob plus demob charge. | GRAMEN PETROSERVE
| Location Dredging works at Ogbotobo ANTM-1 & Ogbotobo AOTM-1. | Fresh | Conditional Approval I. Project Lead to reconcile contracting issue and revert. II. Update 5no top risk | Conditional Approval | Onyejekwe, C | TBA |  |  |  | $: 982,895.93 N: 585,168,641.77 F$: 2,410,136.52 |  |  | F$: 538,142.04 | Low Oil Price LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| GENERAL |  | Ensure proper review of submissions prior WORP
2021-07-15 | Re-routing of NUNR 3S, 13T, 16T Flowline (4” sch 80 x 1.1km) -Resubmission | Resubmission | Conditional Approval. WORP steer from previous sitting 08/07/21 have been incorporated. Further steer: I. Carry out contract alignment with NAPIMS and attach evidence of engagement to the resubmission. | Conditional Approval | Uwaezuoke, D | P.NG.PAE. OP.19.005.9401 |  | $ 241,645.94 N 6,316,713.09 F$ 257,052.56 |  |  |  |  | NIL |  | Slot Engineering
| Kanbo 3S JIV Asset Support. | Fresh | Approved | Approved | Ehizoyanya, O | O.NG.PCW.OKF.FAC.71300. |  |  | $23,535.13 N 787,950.12 F$27,456.96 |  |  |  | NIL |  | ELKON INTEGRATED
| Gbaran Produce Water Re-injection Project: Provision of Filtering Unit | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Build-up a detailed scope/cost to justify ceiling increase & secure TA2 assurance before engaging MTB. II. Carry out contract alignment with NAPIMS and attach evidence of engagement. III. Update 5no top risk to include “Possible procurement delay” and provide mitigations. IV. Update “Payment on behalf of SPDC” in the cost breakdown to “Reimbursable” | Conditional Approval | Akoma, I / Jimba, O | C.NG.PBE.IM.21.001.1230 |  | $ 560,099.71 N 33,501,980.40 F$ 646,948.56 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Otumara 55T Flowline Replacement (4” Sch 40 x 3.3km). -Reviewed offline | Fresh | Approved | Approved | Uwaezuoke, D | C.NG.PCW.DL.21.001.1230 |  |  | $ 459,067.57 N 8,974,812.70 F$ 480,957.36 | [5 empty] | Tomba Resources
| Otumara 30L Flowline Replacement (4” x 2.8km). -Reviewed offline | Fresh | Approved | Approved | Azaka, G | C.NG.PCW.DL.21.001.1230 |  |  | $404,380.20 N6,341,841.27 F$419,848.11 |  |  |  | 20056.18 | Houseboat sharing with another vendor working on OTUM55T | WILANDSON INTERNATIONAL
2021-07-22 | No Submission
2021-07-29 | Gbaran Produced Water Flowline Construction – 6” sch. 80 x 1.72km | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Attach mail confirmation of contract alignment meeting held with NAPIMS. II. Review the Contract ceiling availability and ensure is sufficient to accommodate this work. III. Capture cost savings from resource sharing. IV. Engage PS to review surveillance cost. V. Update Project schedule. | Conditional Approval | Arowosafe, T | C.NG.PBE.IM.21.001.1230 |  | $141,857.81 N 2,510,439.45 F$ 148,472.93 |  |  |  |  | NIL |  | JOSBANI
| Gbaran Produce Water Re-injection Project – Balance of Plant Works | Fresh | Approved. I. Ensure proper materials inspection by QAQC team. | Approved | Akoma, I | C.NG.PBE.IM.21.001.1230 |  | $ 909,985.52 N 298,402,543.02 F$ 1,637,796.60 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| KANBO 3S Flow line Sectional Replacement – (6’’ SCH 40 x 0.2km) | Fresh | Approved. I. Carry out interface management meeting with other vendors working on same RoW and ensure HSE & Security presence in the meeting. II. Engage HSE | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $.97,898.40 N 2,050,545.09 F$102,899.73 |  |  |  | NIL |  | EPOXY SERVICES
| Replacement of Otumara 4L GLL (4" Sch 40 x 1.0km). | Fresh | Approved. I. Carry out interface management meeting with the vendors and ensure HSE & Security presence in the meeting. | Approved | Obiakor, O | O.NG.STG.PBE.OTM.004FL |  |  | GAWASON $ 99,128.67 N 2,770.114.70 F$105,885.05 KEMUD $101,979.55 N 2,749,753.93 F$108,686.27 |  |  |  | NIL |  | GAWASON INTEGRATED. KEMUD INTERNATIONAL
| Afam VI Vent Gathering Project | Fresh | Approved | Approved | Dienagha, I | C.NG.PCE.NO.21.004 | USD 3,328.15 NGN 32,970 F$: 4,125.64 | [5 empty] | NIL |  | ADVANCED COATING TECH
| Resubmission: Re-routing of NUNR 3S, 13T, 16T Flowline (4” sch 80 x 1.1km) - Resubmission & Reviewed offline | Resubmission | Approved. WORP steer from previous sitting 15/07/21 have been incorporated. | Approved | Uwaezuoke, D | P.NG.PAE. OP.19.005.9401 |  | $ 241,645.94 N 6,316,713.09 F$ 257,052.56 |  |  |  |  | NIL |  | Slot Engineering
2021-08-05 | AJATITON W01L HOOK UP ARM REPLACEMENT. | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Attach an approved e-WR to the resubmission. II. Capture cost savings from resource sharing. III. Confirm vendors capability to execute work according to schedule. | Conditional Approval | Azaka, G | O.NG.STG.PBE.AJA.001FL |  |  | $67,692.69 N3,179,278.93 F$75,447.03 | [5 empty] | ELEKING W.W. SERVICES
| GENERAL |  | • Always document Contractors work performance. • Carry out a post-execution materials reconciliation review and report out with recommendations for improvement. • General HSE stand down in all OABP teams.
2021-08-12 | Ajatiton W01L Hook up Arm Replacement. -Resubmission | Resubmission | Approved. WORP steers from previous sitting 05/08/21 have been incorporated. I. Carry out a proper kick-off meeting and ensure HSE & Security presence, document MoM. | Approved | Azaka, G | O.NG.STG.PBE.AJA.001FL |  |  | $67,692.69 N3,179,278.93 F$75,447.03 |  |  |  | 48272.37 | (No cost for houseboat) | ELEKING W.W. SERVICES
| Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km – Additional work -Resubmission | Resubmission | Approved | Approved | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 1,819.93 N 160,592.00 F$ 2,211.62 |  |  |  |  | NIL |  | ABBEYCOURT ENERGY
| Provision of TRP Scale Inhibition Injection Points in Tunu, Opukushi & Benisede flowstation. -Resubmission | Resubmission | Conditional Approval WORP steers from previous sitting 08/07/21 have not been fully incorporated. I. Further engagement with the CH to secure additional eLDL to accommodate works on the Gramen Contract. | Conditional Approval | Obiakor, O | C.NG.PBW.DF.21.003 |  |  | $ 65,451.78 N 22,088,4444.87 F$ - 119,326.04 |  |  |  | F$: 42,345.22 | For doing inter area mobilization instead of full mob to two facilities and demobilization | GRAMEN PETROSERVE
| Installation of Flare tip & RIS at Agbada & Ahia FS. | Fresh | Deferred. I. Engage Asset team to decide funding procedure for divested OML17 activity. II. Update WBS for this activity. | Deferred | Ewenike, M | NIL | F$: 894.87 | [7 empty] | KEMUD INTERNATIONAL
| Kanbo 5S flowline JIV Asset Support. |  | Stepped Down by PMT
| Leak Repair of approach line of Nun River W13T Flowline. | Fresh | Deferred. I. Update WBS for this activity II. Engage CH to secure additional eLDL to accommodate works on the Gramen Contract | Deferred | Obiakor, O | C.NG.PAE.DL.21.001 |  | $ 14,338.89 N 9,489,577.88 F$ 37,484.20 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Nun River Diebu Creek Bulkline to Gbaran – Mechanical, Electrical & Instrumentation scopes. | Fresh | Deferred. I. Engage CH to secure additional eLDL to accommodate works on the Gramen Contract | Deferred | Ehizoyanyan, O | C.NG.PAE.DL.21.002.1230 |  | MECHANICAL PACO ELECTRICAL TOTAL COST $ 599,603.70 $ 268,558.89 $ 5,480.82 $ 873,643.34 N 252,401,417.93 N 13,288,610.75 N 10,392,665.63 N276,082,694.31 F$ 1,215,216.91 F$ 300,970.14 F$ 30,828.78 F$ 1,547,015.83 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Enwhe West 3.5km Location Access Road Additional Scope / Local content. | Fresh | Approved. I. Engage ER and ensure proper processes are deployed in the payment. | Approved | Ezenduka, D | C.NG.LNG.19.004.1230 |  |  |  | N38,871,180 +$ 3,660.94, F$:98,468.70 |  |  | NIL |  | MIFE CONSTRUCTION
| Gbaran Produced Water Flowline Construction – 6” sch. 80 x 1.72km -Resubmission & Reviewed offline | Fresh | Approved | Approved | Arowosafe, T | C.NG.PBE.IM.21.001.1230 |  | $ 143,031.76 N 2,550,416.89 F$ 149,252.29 |  |  |  |  | 96713.65 | Cost saving for not mobilizing tie-in barge and lay barge, also savings from cost of surveillance. (reduced from 43days to 15days) | JOSBANI
| Replacement of Otumara 4L GLL (4" Sch 40 x 1.0km) -Resubmission & Reviewed offline | Resubmission | Approved | Approved | Obiakor, O | O.NG.STG.PBE.OTM.004FL |  |  | $ 166,934.26 N 3,924,654.46 F$176,506.59 |  |  |  | NIL |  | TONYMAR
| Estuary Cluster 51: Forc. 73LS Hook-up Arm Modification – Reviewed offline | Fresh | Approved | Approved | Uwaezuoke, D | C.NG.AFS.DL.18.004.1218 |  |  | $58,153.30 N 2,432,214.52 F$ 64,085.53 |  |  |  | 25726.45 | Shared Resources, Scaffold | Gawason
2021-08-19 | Installation of flare tip & RIS at Agbada and Ahia flowstation Resubmission | Resubmission | Approved. WORP steers from previous sitting 12/08/21 have been incorporated. I. Erase Agbada from the Project title. II. Document payment agreement with the vendor to forestall future claims. | Approved | Ewenike, M | C.NG.PCE.N0.20.001.1230 | F$: 885.54 | [5 empty] | NIL |  | KEMUD INTERNATIONAL
| Construction of Enwhe West Location, By-pass, and Concrete Bridge. Additional Scope. | Fresh | Approved | Approved | Ezenduka, D | C.NG.LNG.19.004.1230 |  |  |  | N56,723,927.76 +$ 34,431.58, F$:172,782.62 |  |  |  |  | ENERCO NIG
| Geotechnical Investigation for Oloibiri Oil and Gas Museum and Research Center (OMRC) | Fresh | Approved. I. Update Risk item 2 title appropriately. | Approved | Edoh, C | 110866 |  |  |  | N 6,005,140.00 |  |  | 770.878 | 5% Discount on the Contract Rates | Eadro Geotechnics
| Gbaran 26 Location Rehabilitation Project (Gbaran 14 Replacement Well) | Fresh | Approved. I. Engage the contractor on the criticality of the schedule with regards to working during December period. II. Engage Wells team on the need for Well test location and revert to WORP for approval of the extra work scope if needed. | Approved | Chioke, K | C.NG.LNG.DG.19.006.1231 |  |  |  | $ 161,394.54 N 96,834,975.99 F$ 397,577.41 |  |  | 20925.13 | (LoP) | RAFFOUL NIG
| Disconnection of Afremo 6T Hook-up Arm (Afremo B) | Fresh | Approved. I. Align OABP security plan with CWI team. II. Hold a proper kick off meeting and ensure Security, HSE & Marine presence. | Approved | Uwaezuoke, D | P.NG.PAE. OP.19.004.1230 |  |  | $59,166.78 N 1,507,497.96 F$ 62,843.60 |  |  |  | 123952.48 | Shared Resources (Logistics and Security etc) | Kemud International
| Kanbo 5S flowline JIV Asset Support / Flowline Sectional Replacement (6’’ x 0.2Km) | Fresh | Approved | Approved | Otavie, G | O.NG.STG.PBE.KAN.005FL |  |  | $ 103,554.77 N 2,100,446.5 F$ 108,677.81 |  |  |  | NIL |  | WIRELINK SERVICES
| Repair of Cracked 3” Weldolet of Soku GP spiking pump discharge header. | Fresh | Approved. I. Engage CH to update ACV split values in the submission. | Approved | Obiakor, O | O.NG.PBE.SKG.FAC.724FC |  | $ 13,634.14 N 10,119,593.96 F$ 38,316.08 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Leak Detection System Project (Installation of Coriolis Meter at Kolo Creek and Rumuekpe Manifolds) – Provision of Shortfall Materials | Fresh | Approved. I. Engage CH to update ACV split values in the submission. | Approved | Odey, E | O.NG.PPE.MAN.MAN.71300 | $ 275,665.28 N 25,091,470.98 F$ 336,863.99 | [5 empty] | NIL |  | GRAMEN PETROSERVE
| Forcados 73LS Hook-up Arm Replacement. -Reviewed offline | Resubmission | Approved | Approved | Uwaezuoke, D | C.NG.AFS.DL.18.004.1218 |  |  | $ 31,605.99 N 1,103,594.09 F$ 34,297.68 |  |  |  | 117417.71 | Shared Resources, Logistics, Security and Scaffold etc) | Gawason
| GENERAL |  | Always ensure vendor supplied materials are inspected by the QAQC team.
2021-08-26 | Nun River Diebu Creek Bulkline to Gbaran – Mechanical, Electrical & Instrumentation scope. -Resubmission | Resubmission | Approved. WORP steers from previous sitting 12/08/21 have been incorporated. | Approved | Ehizoyanyan, O | C.NG.PAE.DL.21.002.1230 |  | MECHANICAL PACO ELECTRICAL TOTAL COST $ 599,603.70 $ 268,558.89 $ 5,480.82 $ 873,643.34 N 252,401,417.93 N 13,288,610.75 N 10,392,665.63 N276,082,694.31 F$ 1,215,216.91 F$ 300,970.14 F$ 30,828.78 F$ 1,547,015.83 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Provision of TRP Scale Inhibition Injection points in Tunu, Opukushi & Benisede flow stations. -Resubmission. | Resubmission | Approved. WORP steers from previous sitting 12/08/21 have been incorporated. | Approved | Obiakor, O | C.NG.PBW.DF.21.003 |  |  | $ 65,451.78 N 22,088,4444.87 F$ - 119,326.04 |  |  |  | 42345.22 | For doing inter area mobilization instead of full mob to two facilities and demobilization. | GRAMEN PETROSERVE
| Geotechnical Investigation for Gbaran NLNG Project/EPU Phase 2 Gas Dev. | Fresh | Approved. I. Update Project schedule to current plan. II. Engage C&P on clarification of rates application on this contract. | Approved | Edoh, C | P.NG.PAE.DG.20.001.1238 |  |  |  | N 10,489,484.49 |  |  | 1346.532 | Low Oil Price {LOP} | EADRO GEOTECHNICS
2021-09-02 | GBARAN PRODUCE WATER RE-INJECTION PROJECT – Materials | Fresh | Approved. I. Attach e-mail evidence of materials search carried out with Hotdesk. | Approved | Akoma, I | C.NG.PBE.IM.21.001.1230 |  | F$ 213,689.52 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| TUNU CPF INLET LINE TO TWISTER TUBE LEAK REPAIR | Fresh | Approved. I. Update WBS for this activity to AF. | Approved | Obiakor, O | C.NG.PBW.DF.21.003 |  |  | $ 19,031.56 N 9,402,872.46 F$41,965.40 |  |  |  | NIL |  | GRAMEN PETROSERVE
| TUNU HP GAS RE-ROUTING PROJECT | Fresh | Approved. I. Confirm WBS is from SSAGS team. | Approved | Obiakor, O | C.NG.PBW.DF.21.004.1230 |  |  | $ 170,906.29 N 70,497,828.59 F$342,852.21 |  |  |  | NIL |  | GRAMEN PETROSERVE
| GENERAL |  | • Strict adherence to SPDC policy of “NO PO = NO WORK” • Imbibe an aggressive cost saving initiative in all OABP activities.
2021-09-09 | Gbaran Produced Water Flowline Construction – 6” sch. 80 x 1.72km additional scope | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Update Project Schedule to current plan. II. Engage Security to mitigate exposure during river crossing. III. Confirm water depth to ascertain equipment requirement. IV. Review work method statement & certifications required. V. Update Project title to indicate the 50m additional scope VI. Review risks and update 5nos top risks. | Conditional Approval | Arowosafe, T | C.NG.PBE.IM.21.001.1230 |  | $ 35,653.72 N 3,444,186.22 F$ 44,054.17 |  |  |  |  | NIL |  | JOSBANI CONST
2021-09-16 | K2S Simultaneous Flow Project - Materials for Workshop Fabrication -Resubmission | Resubmission | Conditional Approval. WORP steers from previous sitting 17/06/21 have been incorporated. Further steer: I. Reconfirm materials availability from the Hotdesk and revert offline | Conditional Approval | Jimba, O | C.NG.PBE.DF.21.005 |  | $ 3,526.61 N F$ 3,526.61 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Gbaran Produce Water Re-injection Project: Provision of Safety Shutdown Valve | Fresh | Stepped down by PMT | Stepped down by PMT | Jimba, O
| Leak Detection System Project (Installation of Coriolis Meter at Kolo Creek and Rumuekpe Manifolds) – Provision of Shortfall Materials | Fresh | Conditional Approval I. Engage CH to reconcile ACV figures. II. Attach evidence of materials bench mark / moving average pricing from SAP. | Conditional Approval | Odey, E | C.NG.PPE.DP.21.012 |  | N 17,741,953.14 $ 3,507.71 F$46,780.77 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Enwhe East Drilling/Cellar Slot Retaining Walls and Underground Flare line Section (20m) | Fresh | Conditional Approval I. Engage CH to reconcile ACV figures. II. Update Project Schedule to current plan. | Conditional Approval | Uwaezuoke, D | C.NG.LNG.DG.19.004.1230 |  | $ 1,268.00 N 6,739,191.07 F$ 17,705.05 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| GENERAL |  | • Always ensure test results are attached to every material supplied by vendors.
23-Sep=21 | SECTIONAL REPLACEMENT OF AFAM 25T FLOWLINE- HYDROTEST (EXTRA WORK) AND AFAM 27T VOWD | Fresh | Approved. I. Attach the approved e-WR and previously secured WORP for Afam 25T and forward to the secretariat. | Approved | Akinbiyi, A | O.NG.PAE.I1F.FAC.724FC | $ 8,691.50 + 904.79 N 13,926,116.91 + 1,103,839.58 F$ 42,657.64 + 3,597.08 | [5 empty] | NIL |  | BG TECHNICAL LIMITED
| GENERAL |  | Always secure Leadership support/approval in writing for any emerging (additional) scope of work at site before execution.
[7 empty] | 0 | 96713.65 | 377770.41 | 23042.5401 | 497526.6001 | 144780.2406 | 497526.6001
497526.6001
144780.2406

## Q3 July - Sept 2021
DATE | PROJECT | TYPE | WORP DECISION | STATUS | PE / SPONSOR | WBS | TOTAL VALUE/COST | [5 empty] | COST SAVINGS (F$) | Remarks | CONTRACT
[7 empty] | LAND | CENTRAL | SWAMP WEST | CIVIL | OABP ASSET | AF
2021-01-07 | No Submission
2021-01-14 | Replacement of 2” water equalization of Soku cluster B | Fresh | Conditional Approval: Complete the actions below and revert offline - Confirmation availability of signed work request - Finalise the procurement process - MCIA: Baseline integrity request to be carried out. - Engage C&P to negotiate the swamp buggy cost. - Engage C&P on procurement of 2” line pipes - Update all documents as related to contractor change | Conditional Approval | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  | $ 155,435.95 N 7,195,661.10 F$ 174,396.85 |  |  |  |  | Nil |  | KEMUD INT’L
| FORCADOS 127T Flowline Sectional Replacement – (6’’ x 0.05km) | Fresh | Approved. - Update total cost column to reflect realities - Ensure an elaborate kick off meeting with contractor due to change in work environment. | Approved | Obiakor, O | 102155 |  |  | $ 58,352.89 N 1,953,504.45 F$ 63,500.46 |  |  |  | Nil |  | TONYMA INVESTMENT
| Provision of Security/surveillance and Downtime for Tunu BQRT-4 Flowline | Fresh | Approved | Approved | Otavie, G | C.NG.AFS.DL.19.004.1230 |  |  | $49,124.21 N 25,544,732.98 F$116,435.76 |  |  |  | Nil |  | IKONIBO NIG
| Provision of support to CWI for open-up of Tunu BQRT-4(W5ST) | Fresh | Approved. - Reconfirm that there is not/wouldn’t be a double charge on equipment due to resource sharing. - Confirm that all necessary plans, HSE, Security etc are in place and signed off | Approved | Otavie, G | C.NG.AFS.DD.19.005.9411 |  |  | $11,713.68 N10,860,399.09 F$40,331.33 |  |  |  | Nil |  | IKONIBO NIG
| Opukushi 34T Flowline Replacement | Fresh | Approved - Update the narrative in the submission to indicate initial PO will be deleted - Update in the submission G&H to CTS | Approved | Otavie, G | 102155 |  |  | FUSD:390,382.95 NGN:6,387,108.86 USD: 373,574.27 |  |  |  | FUSD: 65,000 | Renegotiated excavation rates, use of only one vendor reduced double mobilization and associated catering costs | WILANDSON
| Opukushi W26T Flowline Replacement (4" x 2km | Fresh | Conditional Approval: Complete the actions below and revert offline - Contract extension to be updated in SAP - Engage PST to reconcile cost - Update submission to reflect risk, work schedule etc | Conditional Approval | Otavie, G | 102155 |  |  | $ 182,085.5 N 66,885,002.36 F$ 401,380.6 |  |  |  | F$: 35,000 | Campaign mobilization will enable the sharing of Marine logistic resources like hosueboat | SEVOIL
| GENERAL |  | Change all submission from OP19 to OP20 Activity owners to confirm support of activities in OP20 before commencing activities. Work allocation spreadsheet to be updated and current at all times.
2021-01-21 | Opukushi W26T Flowline Replacement (4" x 2km) - Resubmission & Reviewed offline | Resubmission | Approved | Approved | Otavie, G | 102155 |  |  | $ 177,590.51 N 65,234,247.10 F$ 349,485.76 |  |  |  | F$: 35,000 | Campaign mobilization will enable the sharing of Marine logistic resources like hosueboat | SEVOIL
| Diebu Creek 9T Flowline Replacement – 4” x 4.2km | Resubmission | Deferred: Complete item below and revert offline - Reconcile materials list with materials HotDesk and EST | Deferred | Uwaezuoke, D | 102155 |  | $337,905.66 N124,092,863.66 F$664,896.08 |  |  |  |  | Nil |  | ANASAMI CONSTRUCTION
| Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km | Fresh | Deferred: Complete items below and revert offline - Reconcile materials list with materials HotDesk and EST - Review work distribution to vendors equitably. | Deferred | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 69,057.09 N 19,127,794.00 F$ 119,459.71 |  |  |  |  | Nil |  | PECKON NIGERIA
| Sectional Replacement Of IMOR Well 32L & GLL Flowlines | Fresh |  |  | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 8,876.10 N 2,214,970.80 F$ 14,712.65 | [5 empty] | Nil |  | ADLAND PROJECTS
| Sectional Replacement Of IMOR4- Inch Delivery Line/57GLL/36S/22S | Fresh |  |  | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 48,732.29 N 14,993,395.11 F$ 88,240.58 | [5 empty] | Nil |  | GAMSTEC INTEGRATED
| DBCU W12T Flowline Replacement (4" Sch 80 x 5km) | Fresh | Deferred: Complete items below and revert offline - Reconcile materials list with materials HotDesk and EST - Review work distribution to vendors equitably. | Deferred | Azaka, G | NIL |  | $ 337,588.93 N 127,747,467.01 F$674,209.40 |  |  |  |  | Nil |  | MIDEN SERVICES
| FORC 126S Flowline Replacement (6” sch 80 x 1.2 km) | Fresh | Deferred: Complete items below and revert offline - Reconcile materials list with materials HotDesk and EST - Review work distribution to vendors equitably. | Deferred | Orji, C | C.NG.PAE.DL.21.001 |  |  | $ 132,054.33 N 48,500,624.65 F$ 259,687.56 |  |  |  | Nil |  | STEVE INEGRATED
| Rehabilitation of 800m failed sections of Obigbo flow station road. | Fresh | Deferred: Complete item below and revert offline - Engage the Asset team to get confirmation from divestment BOM on the execution of this project | Deferred | Ezenduka, D | C.NG.PAE.IC.21.001 |  |  |  | F$: 429,307.22 |  |  | F$: 29,844.89 | 6.5 % LOP Discount | BENCOV NIG
| GENERAL |  | All submissions are be subject to DRB approval EST to share a standard hook up arm materials list template to all
2021-01-28 | Sectional Replacement of Afam 25T Flowline (8” x 12m) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Engage Asset team, EST, HSE, Technical Safety and Security teams to review and sign off method statement. II. Include clamping as a mitigation against spill in the 5 top risks | Conditional Approval | Akinbiyi, A | O.NG.PAE.I1F.FAC.724FC | $ 27,733.14 + 35,712.58 N 46,114,670.79 + 11,048,655.19 F$ 149,247.42 + 64,826.30 | [5 empty] | Nil |  | BG TECHNICAL NIG LTD
| Rehabilitation of 800m failed sections of Obigbo flow station road. -Resubmission | Resubmission | Approved. WORP steers from previous sitting 21-01-21 have been incorporated. | Approved | Ezenduka, D | 110854 |  |  |  | F$: 429,307.22 |  |  | F$: 29,844.89 | 6.5 % LOP Discount | BENCOV NIG
| Addendum to Construction of 1 No. Well bay location Assa-North | Fresh | Approved. I. Resolve ACV balance in SAP II. Update 5 top risks to include Covid19 | Approved | Ezenduka, D | C.NG.ANO.DG.17.004.1231 |  |  |  | F$: 144,200.22 |  |  | F$: 7,589.49 | 5 % LOP Discount | RAFFOULNIG.LIMITED
| FORC 126S Flowline Replacement (6” sch 80 x 1.2 km) -Resubmission & Reviewed Offline | Resubmission | Approved. WORP steers from previous sitting 21-01-21 and 28-01-21 have been incorporated. | Approved | Orji, C | C.NG.PAE.DL.21.001 |  |  | $ 132,054.33 N 48,500,624.65 F$ 259,687.56 |  |  |  | Nil |  | HENSTEEL ENGINEERING
| Sectional Replacement of ImoR Well 32L & GLL | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Update cost saving column with proposed cost savings. II. Reconcile materials list with Hotdesk and expunge cost of available materials from cost estimate. | Conditional Approval | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 8,876.10 N 2,214,970.80 F$ 14,712.65 | [5 empty] | Nil |  | ADLAND PROJECTS
| Sectional Replacement of (a) ImoR 4-inch Delivery line (b) ImoR 57GLL (c) ImoR 36S (d) ImoR 23L (e) ImoR 14L (f) ImoR 6-inch Bulkline (g) ImoR 63T Manifold | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Update cost saving column with cost saved from inter-field move. II. Reconcile materials list with Hotdesk and expunge cost of available materials from cost estimate. | Conditional Approval | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 48,732.29 N 14,993,395.11 F$ 88,240.58 | [5 empty] | Nil |  | GAMSTEC INTEGRATED
| Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km -Resubmission & Reviewed Offline | Resubmission | Approved. WORP steers from previous sitting 21-01-21 have been incorporated. | Approved | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 72,553.73 N 5,439,173.57 F$ 86,886.20 |  |  |  |  | Nil |  | ABBEYCOURT ENERGY
| DBCU W12T Flowline Replacement (4" Sch 80 x 4.8km) -Resubmission & Reviewed Offline | Resubmission | Approved. WORP steers from previous sitting 21-01-21 have been incorporated. | Approved | Azaka, G | NIL |  | $ 324,004.09 N 121,078,352 F$727,442.65 |  |  |  |  | Nil |  | MIDEN SERVICES LTD
2021-02-04 | BONNY WELL 12S & OLOMA FS LIGAMENT VALVES CHANGE -OUT | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Update WBS for this activity. II. Attach an approved e-AEWR. III. Ensure all equipment have valid premob certificates. IV. Specify crew boat type in the cost estimate. V. Ensure detailed security plan review. VI. Update OP’19 to OP’20 in the submission | Conditional Approval | Ehizoyanyan, O | NIL |  | $ 17,399.52 N 2,002,876.74 F$ 22,677.19 |  |  |  |  | Nil |  | SURVEILLANCE 2000
2021-02-11 | Saghara 3S and 5L Flowline Replacement – 4” Sch. 40 x 850m Each (Total = 4” Sch. 40 x 1.7km) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Include fabrication of hook up arm in the work scope. II. Expunge CP survey and balancing from cost estimate. III. Expedite materials availability check with Hotdesk IV. Engage PS for a review of cost estimate. | Conditional Approval | Uwaezuoke, D | O.NG.PBW.SHF.03S.713FL/O.NG.PBW.SHF.05L713FL |  |  | $ 211,509.27 N 77,405,267.22 F$ 415,475.72 |  |  |  | Nil |  | ANASAMI
| Sectional Replacement of (a) ImoR 59T (6-inch) (b) ImoR 25L (4-inch) | Fresh | Approved. I. Include line length in the Project Title | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 12,297.25 N 3,357,092.47 F$ 21,143.34 | [5 empty] | 8280.04 | THERE IS A SAVINGS OF 8,280.04 USD WHICH SHOULD HAVE COVERED MOB & DEMOB USING A NEW CONTRACTOR | GAMSTEC INTEGRATED
| Full Replacement of ImoR 58T (4- inch x 3.4km) | Fresh | Approved. | Approved | Aderiye, A | C.NG.PAE.DL.21.001 | $ 110,900.38 N 26,084,203.78 F$ 179,633.46 | [5 empty] | 12508.36 | THERE IS A SAVINGS OF 12,508.36 FROM THE MATERIALS THAT WILL BE COLLECTED FROM THE SPDC WAREHOUSE | THOMPSON AND GRACE
| Sectional Replacement of Afam 25T flowline (8” x 12m) -Resubmission & reviewed offline | Resubmission | Approved. WORP steers from previous sitting 28/01/21 have been incorporated. | Approved | Dienagha, I | O.NG.PAE.I1F.FAC.724FC | $ 30,998.84 + 35,712.58 N 52,409,398.79 + 11,048,655.19 F$ 169,100.02 + 64,826.30 | [5 empty] | Nil |  | GAMSTEC INTEGRATED
| GENERAL |  | Ensure all cost are independently assured by PS. • Advise the team on when to commence movement of bare pipes to coating vendors (SOLEWANT & PCN). • Confirm availability of coated pipes from stockist. • Send sample of disused spool piece from Saghara 3S & 5L to MCI for analysis. • Expunge CP survey and balancing from cost estimate and where necessary, reports should be provided for documentation • Early request for Houseboat to the marine team • Ensure kickoff meetings are held prior mobilizations.
2021-02-18 | : LOCATION DREDGING WORKS AT BENISEDE EAUA-2. | Fresh | Approved. I. Liase with OABP focal persons to confirm ETC/OTC availability. | Approved | Onyejekwe, C | C.NG.AFS.DD.19.009.9401 |  |  |  | $: 103,003.11 N: 267,683,624.79 F$: 808,361.80 |  |  | F$: 115,543.79 | Low Oil Price LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| FULL REPLACEMENT OF OGUTA 16S FLOWLINE (4” X 2.9KM) | Fresh | NOT TREATED |  | Akinbiyi, A | 102155 | $ 91,808.64 N 26,740,513.71 F$ 179,482.45 | [5 empty] | Nil |  | MORRAY SERVICES
| FULL REPLACEMENT OF OGUTA 25T FLOWLINE (4” X 5.6KM) | Fresh | NOT TREATED |  | Akinbiyi, A | 102155 | $ 227,072.62 N 51,829,929.49 F$ 363,646.87 | [5 empty] | Nil |  | GESON INVESTMENT
| FULL REPLACEMENT OF OGUTA 12T FLOWLINE (4” X 4.3KM) | Fresh | NOT TREATED |  | Akinbiyi, A | 102155 | $ 140,649.15 N 17,728,986.10 F$ 187,365.85 | [5 empty] | Nil |  | ABBEYCOURT
| INTEGRITY CHECK OF AGBADA 67T GAS LINE | Fresh | Conditional Approval Update and resubmit upon completion of these conditions: I. Update WBS for this activity. II. Formal engagement with the Pipeline Contract Holder and review contract line items. III. Review work method statement with the vendor IV. Recourse option of engaging a flowline vendor to manage the overall activity. | Conditional Approval | Dienagha, I | NIL | $ 47,136.48 N 76,378,129.79 F$ 248,131.56 | [5 empty] | Nil |  | BG TECHNICAL
| BONNY W30T Flowline Replacement (4" Sch 80 x 1km) | Fresh | Deferred. I. Stepped down for a proper internal review by Project Lead. | Stepped Down | Azaka, G | NIL |  | $ 104,781.24 N 38,486,464.52 F$206,194.85 |  |  |  |  | Nil |  | VANDRESSER NIG
| Tunu CDRY-3 Flowline Construction (6" x 2.1km) & Tunu CDRY-4 Wellhead Platform Installation and hookup | Fresh | Approved. I. Update cost saving column with the proposed cost savings. II. Liase with C&P to affirm benchmark rates | Approved | Azaka, G | C.NG.AFS.DF.19.003.1200 |  |  | $324,929.80 N 118,704,995.67 F$ 637,697.73 |  |  |  | Nil |  | IKONIBO NIG
| Replacement of 1,75KM of 2” water equalization of Soku cluster D | Fresh | Deferred. I. Provide and attach basis for the additional 1.75km scope. II. Engage EST & Geomatics for a proper review III. Review and simplify execution strategy. | Deferred | Obioakor, O | NIL |  | $ 225,297.74 N 13,915,985.80 F$ 261,967.01 |  |  |  |  | Nil |  | HENZOL, KEMUD, VISCA
| FULL REPLACEMENT OF IMOR 58T (4-INCH x 3.4KM) | Fresh | Approved. I. Proceed to execution with the proposed new vendor (WILKRISS NIG. LTD) II. Ensure the MoM and offer decline letter from Thompson & Grace Investment Ltd is duly signed for documentation | Approved | Aderiye, A | C.NG.PAE.DL.21.001 | $ 137,763.36 N 12,884,978.45 F$ 179,633.46 | [5 empty] | 14800 | Warehouse Materials | WILKRISS
| SAGHARA 3S & 5L FLOWLINE REPLACEMENT – 4” Sch. 40 x 850m each (Total = 4” Sch. 40 x 1.7km). Resubmission & Reviewed offline | Resubmission | Approved. WORP steers from previous sitting 11/02/21 have been incorporated | Approved | Uwaezuoke, D | O.NG.PBW.SHF.03S.713FL/O.NG.PBW.SHF.05L.713FL |  |  | $ 204,508.67 N 74,834,367.87 F$ 401,700.68 |  |  |  | Nil |  | ANASAMI CONSTRUCTION
2021-02-25 | BONNY W30T Flowline Replacement (4" Sch 80 x 1km) | Resubmission | Conditional Approval. WORP steers from previous sitting 18/02 have not been fully incorporated. I. Engage WRFM to provide WBS for this activity and resubmit offline | Conditional Approval | Azaka, G | NIL |  | $ 101,126.24 N 37,144,159.42 F$199,002.81 |  |  |  |  | Nil |  | VANDRESSER NIG
| OTUMARA FLOW STATION GANTRY WORKS | Fresh | Deferred. I. Update WBS for this activity. II. Engage EST to review existing structural frame and attach schematic drawing. III. Confirm Gantry maximum load. | Deferred | Azaka, G | NIL |  |  | $ 187,308.06 N 6,577,567.94 F$206,814.41 |  |  |  | Nil |  | NAPEBI CONSTRUCTION
| KOCR 22T Flowline Sectional Replacement – 4” sch. 40 x 0.06km and 8” Sch 160 x 0.012km | Fresh | Approved. I. Forward approved e-WR to the Secretariat and Manager. II. Plan for mitigation against Vendors under performance due to low project cost. | Approved | Arowosafe, T | O.NG.PAE.GBG.FAC.724FC |  | $ 55,973.34 N 4,979,690.78 F$ 69,,095.05 |  |  |  |  | Nil |  | ABBEYCOURT ENERGY
| K2S Simultaneous Flow Project | Fresh | Approved. I. Engage CH to update ACV split currency values. II. Carry out materials check with Hotdesk. III. Emphasize criticality of this activity with the Vendor. | Approved | Akoma, I | C.NG.PBE.DF.21.005 |  | $ - 104,725.16 N - 36,794,719.22 F$ - 201,680.94 |  |  |  |  | F$: 22,416.83 | Savings on Mob and De-mob by using same contractor for Mechanical/ Instrumentation works, etc | GRAMEN PETROSERVE
| Replacement of LP header of Yokri flow station. -Reviewed offline | Fresh | Approved | Approved | Obiakor, O | O.NG.PCW.YKF.FAC.71300 |  |  | $ 31,865.72 N 375,865.72 F$ 32,854.55 |  |  |  | 23907.23 | saved for combining mobilization of Forcados Yokri 127T flowline sectional replacement and replacement of Yokri LP header | TONYMAR INVESTMENT
| GENERAL |  | Review materials reconciliation tracking system and communicate to leadership: ▪ Flowlines ▪ Facilities
2021-03-04 | FODPA and NEFS Boatlanding Rehabilitation Works | Fresh | Approved. I. Confirm full budget availability for these activities. II. Carry out materials reconciliation with Hotdesk. III. Ensure security plan is properly reviewed and assurance provided for adequate cover at site | Approved | Uwaezuoke, D | F$: C.NG.PBW.DF.212.001 – FODPA F$: C.NG.PCW.DF.98.706.1230 - NEFS |  |  | Total: FODPA + NEFS = F$394,395.64 |  |  |  | Nil |  | Gramen Petroserve
| FULL REPLACEMENT OF OGUTA 12T FLOWLINE(4” X 4.3KM) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Confirm WBS for this activity. II. Carry out materials reconciliation with Hotdesk and discount available materials. III. Update Project Schedule to current plan. IV. Include Fabrication & Hook up in the scope summary. V. Confirm linepipes availability for this activity. VI. Align POB requirement with OABP Central Team | Conditional Approval | Akinbiyi, A | 102155 | $ 132,486.76 N 37,684,516.42 F$ 231,787.20 | [5 empty] | Nil |  | WILKRISS
| FULL REPLACEMENT OF OGUTA 16S FLOWLINE(4” X 2.9KM) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Confirm WBS for this activity. II. Carry out materials reconciliation with Hotdesk and discount available materials. III. Update Project Schedule to current plan. IV. Include Fabrication & Hook up in the scope summary. V. Confirm linepipes availability for this activity. VI. Align POB requirement with OABP Central Team | Conditional Approval | Akinbiyi, A | 102155 | $ 91,808.64 N 26,740,513.71 F$ 179,482.45 | [5 empty] | Nil |  | MORRAY SERVICES
| FULL REPLACEMENT OF OGUTA 25T FLOWLINE(4” X 5.6KM) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Confirm WBS for this activity. II. Carry out materials reconciliation with Hotdesk and discount available materials. III. Update Project Schedule to current plan. IV. Include Fabrication & Hook up in the scope summary. V. Confirm linepipes availability for this activity. VI. Align POB requirement with OABP Central Team | Conditional Approval | Akinbiyi, A | 102155 | $ 165,827.86 N 46,524,990.84 F$ 288,423.35 | [5 empty] | Nil |  | GUIZ AND COMPANY
| LEAK REPAIR OF FORCADOS 127T FLOWLINE | Fresh | Approved. I. Engage WRFM to confirm WBS for this activity. II. Update Project title to include “Optimization of Line size” III. Update Project Schedule to current plan. | Approved | Obiakor, O | 102155 |  |  | $ 47,933.39 N 1,545,750.79 F$ 52,006.51 |  |  |  | F$39,515.51 | Mob and De-mob, Houseboat | TONYMA INVESTMENT
| SECTIONAL REPLACEMENT OF OTUMARA 42LS, 16T FLOWLINES AND FABRICATION OF HOOK-UP ARM OF OTUMARA 4L. | Fresh | Approved. I. Carry out materials reconciliation with hotdesk and discount available materials. | Approved | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  |  | $ 160,601.21 N 61,143,932.41 F$ 321,718.29 |  |  |  | F$82,000 & F$77,000 | F$82,000 (Shared marine logistics) + F$77,000 (Single mob/demob) | ANASAMI
| Diebu Creek 8T Flowline Replacement – 4” x 3.07km | Fresh | Stepped down by the team | Stepped down | Ehizoyanyan, O | WRFM 102155 |  | $228,572.93 N 83,941,422.41 F$449,762.45 |  |  |  |  | Nil |  | SEVOIL LTD
| BONN 12S Flowline Replacement – 4” x 1.7km | Fresh | Stepped down by the team | Stepped down | Ehizoyanyan, O
| BONNY W30T Flowline Replacement (4" Sch 80 x 1km) -Resubmission & Reviewed offline | Resubmission & Reviewed Offline | Approved. WORP steer from previous sitting 25/02/21 have been incorporated. | Approved | Azaka, G | NIL |  | $ 101,126.24 N 37,144,159.42 F$199,002.81 |  |  |  |  | Nil |  | VANDRESSER NIG
| GENERAL |  | Ensure timely checks on materials availability prior to WORP submission. • Only funded activities should be brought into plan and ensure alignment of execution with IAP central team. • Proper security plan review / HSE documentation for each project before mobilization. • Early engagement on marine request to avoid delayed mobilization to sites.
2021-03-11 | UZU MANIFOLD LOCATION PREPARATION | Fresh | Approved. I. Limit PO value to the contractor to available ACV balance in SAP. II. Engage C&P to update remaining ACV III. Ensure combination of controls is in place for managing community workers. IV. Liase with the planning team to align schedule & demand requirements for IAP | Approved | Oludare, S | P.NG.PAE.DG.17.001 |  |  |  | F$: 2,037,279.64 (N: 473,610,898.60, $: 789,293.09) |  |  | F$:107,225.24 | 5 % LOP Discount | RAFFOUL NIG. LIMITED
| FORC 111T Flowline Replacement (6" sch 40 x 2.7 km bulkline) & (4" sch 40 x 0.25 km flowline) | Fresh | Approved. I. Ensure combination of controls is in place for managing community workers. II. Decomit previously issued PO for Forcados 126S before issuing the new PO for 111T to the Vendor. III. Update Project Schedule to current plan. | Approved | Orji, C | C.NG.PAE.DL.21.001.1230 |  |  | $ 251,239.91 N 92,278,553.00 F$ 494,398.16 |  |  |  | 33891.12 | From Materials to be taken from Hot Desk | HENSTEEL ENGINEERING
| FULL REPLACEMENT OF IMOR 36L (4-INCH x 1.0 KM) | Fresh | Approved. I. Carry out proper material reconciliation with hotdesk. | Approved | Aderiye, A | C.NG.PAE.DL.21.001 | $ 47,000.69 N 11,269,553.88 F$ 76,696.49 | [5 empty] | F$: 12,500 | MATERIALS FROM THE SPDC WAREHOUSE. | ROMEK AND COMPANY
| SECTIONAL REPLACEMENT OF (a) IMOR 4-inch TEST LINE (48M) (b) IMOR RIVER 26S (48M) © IMO RIVER 44S (48M) (d) IMO RIVER 55S (48M) (e) IMO RIVER 43T (48M) (f) IMOR 60T (48M) | Fresh | Approved. I. Prompt engagement with Asset PUM’s to provide enhanced security surveillance for these lines. II. Update Project Schedule to current plan. | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 35,160.13 N 10,617,977.01 F$ 63,138.99 | [5 empty] | FS11,525.18 | MOB & DEMOB. ALL MATERIALS FOR THESE SECTIONAL REPLACEMENT SHALL BE SOURCED FROM SPDC WAREHOUSE | GAMSTEC
| SECTIONAL REPLACEMENT OF (a) IMOR RIVER 6-INCH BULKLINE (IMO 2 -1) X 1500 M (Additional leak points) | Fresh | Approved. | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 17,777.50 N 5,370,063.42 F$ 31,927.86 | [5 empty] | 8,280.04 USD | MOB & DEMOB IF USING A NEW CONTRACTOR | GAMSTEC
| Diebu Creek 8T Flowline Replacement – 4” x 3.07km | Fresh | Conditional Approval. Subject to NAPIMS engagement on contract expiration date extension. | Conditional Approval | Ehizonyan, O | O.NG.PBE.DBC.09T.713FL |  | $238,624..58 N 87,632,760.32 F$469,540.94 |  |  |  |  | Nil |  | SEVOIL LTD
| FULL REPLACEMENT OF ETELEBOU 3S FLOWLINE (4” X 1.2KM) | Fresh | Approved: Premised on early mobilization. I. Update contract end date and engage NAPIMS. II. Forward cost savings to I&A for documentation. | Approved | Otavie, G | O.NG.PAE.ETL.03S.713FL |  | $ 57,925.84 N 13,410,314.07 F$ 85,626.42 |  |  |  |  | Nil |  | PECKON NIGERIA
| BONNY W18S Flowline Replacement (4" Sch 40 x 1.2km) | Fresh | Conditional Approval. I. Carry out work distribution alignment across team. II. Confirm Contractors capacity to execute | Conditional Approval | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  | $ 133,308.68 N 48,964,351.92 F$262,332.00 |  |  |  |  | Nil |  | IKONIBO
| Provision of lay barge for installation of CCUs at Kanbo W5L/S -Reviewed Offline | Fresh | Approved. | Approved | Ehizonyan, O | C.NG.AFS.DF.18.025.1202 |  |  | $ 22,320.8 N 602,305.87 F$ 23,907.9 |  |  |  | F$: 10,062.00 | Shared marine logistics and security deployment | HENZOL GLOBAL
2021-03-18 | Replacement of 1,75KM of 2” water equalization of Soku cluster D | Resubmission | Conditional Approval. WORP steers from previous sitting 18/02/21 have been incorporated. Further steers: I. Attach signed MoM of review meeting held with EST & Geomatics. II. Update WBS for this activity. III. Engage vendor & secure commitment to execute work accordingly. IV. Liase with C&P to load contract in SAP. | Conditional Approval | Obiakor, O | Nil |  | $ 107,282.92 N 39,409,715.49 F$211,129.34 |  |  |  |  | Nil |  | VANDREZZER NIG. LTD
| BOGT SHORE PROTECTION – PHASE1 | Fresh | Approved. I. Focused attention on vendor HSE risk management before and during site works. II. Review & accelerate project schedule. III. Proceed with interim plan to safeguard shoreline before actual work execution. IV. Kick off meeting to include Vendor top management in view of the nature of work. | Approved | Ogunkunle, M | C.NG.PBE.IC.07.001 |  |  |  | F$ 875,727.01 N69,244,408.04 + $693,264.80 |  |  | Nil |  | PILE FOUNDATION LIMITED
| Seibou 3 and 4 bulkline JIV and clamping. -Reviewed offline | Fresh | Approved. I. Update project schedule to current plan | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $ 27,976.94 N 511,967.62 F$ 29,326.00 |  |  |  | 9050.71 | cost saving on inter-area move instead of mobilizing a new contractor. | HENZOL GLOBAL
| GENERAL |  | Engage the relevant authorities with proposal to include equalization lines in FIMS for ease of line tracking and integrity monitoring.
2021-03-25 | Bonny W14 Maintenance Dredging works | Fresh | Approved. I. Reiterate the responsibility of the main contractor despite invoice partnering option. II. Ensure safe work completion before contract expiration date. III. Update project schedule to align with current plan IV. 5no top risk to include “Interface management risk” V. Align cost breakdown descriptions with cost summary sheet. VI. Ensure proper HSE & Security plan review. VII. Kick off meeting to emphasize Covid’19 protocols at site. | Approved | Onyejekwe, C | 110744 |  |  |  | $: 428,558.82 N: 192,570,123.89 F$: 935,989.97 |  |  | F$: 56,227.33 | Cost saving is from Low Oil Price LoP discounts (i.e. 7.5%). | SHORELINE DREDGING
| Bonny W13 Maintenance Dredging works | Fresh | Approved. I. Reiterate the responsibility of the main contractor despite invoice partnering option. II. Ensure safe work completion before contract expiration date. III. Update project schedule to align with current plan IV. 5no top risk to include “Interface management risk” V. Align cost breakdown descriptions with cost summary sheet. VI. Ensure proper HSE & Security plan review. VII. Kick off meeting to emphasize Covid’19 protocols at site. | Approved | Onyejekwe, C | 110744 |  |  |  | $: 412,055.67 N: 188,667,970.36 F$: 909,204.47 |  |  | F$: 54,055.53 | Cost saving is from Low Oil Price LoP discounts (i.e. 7.5%). | SHORELINE DREDGING
| Enwhe East Flare Test Pit and Bundwall Construction Work | Fresh | Approved. I. Capture cost savings and forward to I&A for reporting. II. Update project schedule to align with current plan III. Update appropriately the remaining ACV for this submission. | Approved | Otavie, G | C.NG.LNG.DG.19.004.1230 |  | $ 54,465.13 N 113,596,678.73 F$ 353,797.61 |  |  |  |  | Nil |  | Gramen Petroserve
| Enwhe West Flare Test Pit and Bundwall Construction Work | Fresh | Approved. I. Update project schedule to align with current plan. II. Update appropriately the remaining ACV for this submission III. Ensure vendor has adequate resources to deliver according to schedule. | Approved | Uwaezuoke, D | C.NG.LNG.DG.19.004.1230 |  | $ 49,888.81 N 95,735,716.20 F$ 302,156.84 |  |  |  |  | Nil |  | Gramen Petroserve
| Estuary Cluster 51 Ring A Replacement Work ahead of FORC73 Workover | Fresh | Approved. I. Ensure safe work completion before contract expiration date. II. Update project schedule to align with current plan. III. Harmonize project title with other relevant documentation. | Approved | Uwaezuoke, D | O.NG.STG.PBE.FOR.072FL |  |  | $ 102,377.04 N 26,433,707.21 F$ 172,031.08 |  |  |  | Nil |  | Miden Systems Ltd
| Kanbo 5LS TRP Outage surveillance cover. | Fresh | Approved. I. Vendor to deploy adequate resources for security surveillance. | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $ 31,947.75 N 372,012.45 F$ 32,928.02 |  |  |  | Nil |  | HENZOL GLOBA
| Kanbo W7S (6’’ x 0.1Km) & W6T (6’’ x 0.1Km) Flowline Sectional Replacement | Fresh | Deferred. I. Liase with C&P to update remaining ACV for this activity. II. Update summary description of cost saving initiative. | Deferred | Otavie, G | O.NG.STG.PBE.KAN.007FL O.NG.STG.PBE.KAN.006FL |  |  | $ 122,276.73 N 3,736,362.47 F$ 132,122.22 |  |  |  | F$: $20,000 | Elimination of Mob and De-mob of Houseboat, by latching onto existing houseboat already in Tunu | FEIMA
| FORC 110T & FORC 112T Integrity Checks | Fresh | Deferred. I. Liase with C&P to update remaining ACV for this activity | Deferred | Orji, C | C.NG.PCW.DL.21.001 |  |  | $ 64,269.17 N 1,986,542.12 F$ 69,503.80 |  |  |  | Nil |  | TUSOJA MARINE
| Tunu BQRT-3 Flowline Replacement (6" SCH 80 x 6.1km) | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Carry out material reconciliation with hotdesk. II. Update 5no top risk to include “Interface management risk” III. Update summary | Conditional Approval | Otavie, G | C.NG.AFS.DL.19.006.1230 |  |  | $ 306,292.32 N 117,178,807.88 F$ 615,063.88 |  |  |  | F$: 20,000 | Campaign mobilization will enable the sharing of Marine logistic resources like houseboat which are already in the field | SEVOIL & OSAKS INTEQ
| GENERAL |  | Escalate security challenges in Kanbo and Seibou axis to Security LT.
2021-04-01 | FORC 110T & FORC 112T INTEGRITY CHECKS | Resubmission | Approved. I. Update Contractor’s name with the correct spelling in the submission. II. Include value proposition (bopd) for both lines. III. Indicate all the WBS provided for this project and charge each flowline cost to specific WBS provided IV. Review and update risk No3 in the top risks. | Approved | Orji, C | O.NG.STG.PBE.FOR.110FL |  |  | $ 64,269.17 N 1,986,542.12 F$ 69,503.80 |  |  |  | Nil |  | ELKON INTEGRATED
| TUNU BQRT-3 Flowline Replacement (6" Sch 80 x 6.1km) -Resubmission & Reviewed offline | Resubmission | Approved. WORP steers from previous sitting 25/03/21 have been incorporated. | Approved | Otavie, G | C.NG.AFS.DL.19.006.1230 |  |  | $ 304,115.16 N 116,379,232 F$ 610,779.8 |  |  |  | F$: 20,000 F$: 4,284.08 | House boat sharing and materials discounted | SEVOIL & OSAKS INTEQ
| BONNY W18S Flowline Replacement (4" Sch 40 x 1.2km) -Resubmission & Reviewed offline | Resubmission | Approved. WORP steers from previous sitting 11/03/21 have been incorporated. | Approved | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  | $ 132,180.84 N 48,550,109.36 F$260,112.61 |  |  |  |  | Nil |  | IKONIBO NIG
| GENERAL |  | Always ensure equitable work allocation.
2021-04-08 | SECTIONAL REPLACEMENT OF (a) IMOR RIVER 6-INCH BULKLINE (IMO 2 -1) X 800 M (Additional leak points) (b) IMOR RIVER 26S (300 M) © IMO RIVER 60T (2200M) | Fresh | Deferred. I. Evaluate all additional work scope for each conduit, hold an alignment meeting with the Vendor and attach MoM to the resubmission. | Deferred | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 36,849.85 N 11,959,792.85 F$ 68,364.45 | [5 empty] | 8,280.04 USD | MOB & DEMOB USING A NEW CONTRACTOR. | GAMSTEC INTEGRATED
| GENERAL |  | Engage Asset team to provide enhanced security surveillance for these lines.
2021-04-15 | AFAM VI VENT GATHERING PROJECT | Fresh | Conditional Approval. I. Update value of work order in split currency. II. Include security risk in the 5nos top risks. III. Attach email confirmation of materials reconciliation carried out with Hotdesk. IV. Confirm and document contractor’s readiness and capability to mobilize according to schedule. V. Engage C&P to provide steers on the provision of accommodation by the contractor at site. | Conditional Approval | Dienagha, I | C.NG.PCE.NO.21.004 | USD 88,709.22 NGN 8,425,414.35 F$: 111,835.53 | [5 empty] | F$: 7,824.72 | (Nonstock materials) | ADVANCED COATING TECH
| SCAFFOLDING OKGP DRYER PROJECT | Fresh | Conditional Approval. I. Update value of work order in split currency. II. Liaise with C&P to seek support on the proposed mode of payment to the contractor. III. Engage BSU to confirm budget availability for this activity. | Conditional Approval | Ewenike, M | C.NG.PCE.NO.21.004 | NGN 3,111,284.44 USD 4,372.58 F$: 14,582.31 | [5 empty] | NIL |  | GRAMEN PETRO-SERV
| CRACK REPAIR OF SOKU GP AG2 TURBINE EXHAUST COLLECTOR | Fresh | Approved. I. Engage Contract Holder to confirm adequate ACV ceiling for this activity. II. Update Project title to properly describe activity. | Approved | Obiakor, O | O.NG.PBE.SKG.FAC.72FC |  | $ 8,346.46 N 6,773171.82 F$26,194.08 |  |  |  |  | NIL |  | GRAMEN PETRO-SERV
| GENERAL |  | Engage NAPIMS to discuss Mechanical modification contracts. • Expedite action on ceiling increase and time extension for GRAMEN PETRO-SERVE contract. • Liase with C&P to resolve contract ACV split value issues and revert to Manager.
2021-04-22 | AFAM VI VENT GATHERING PROJECT - Resubmission | Resubmission | Approved. WORP steers from previous sitting 15/04/21 have been incorporated. I. Proceed to execution and follow through on steers from C&P. | Approved | Dienagha, I | C.NG.PCE.NO.21.004 | USD 88,709.22 NGN 8,425,414.35 F$: 111,835.53 | [5 empty] | 7824.72 | (Nonstock materials) | ADVANCED COATING TECH
| DELETED SEs FOR OPUKUSHI 2T FLOWLINE REPLACEMENT - Resubmission | Resubmission | Approved. I. This payment is for provision of services rendered in 2019. Invoice could not be provided by the Vendor due to their internal constraints. II. This P.O is to enable creation of S.E for invoice payment. | Approved | Ehizoyanyan, O | C.NG.PCW.DL.21.001.1230 |  |  | $ 10,983.23 N 4,041,941.25 F$ 21,633.93 |  |  |  | NIL |  | VANDREZZER ENERGY SERVICES
| SECTIONAL REPLACEMENT OF (a) IMOR RIVER 6-INCH BULKLINE (IMO 2 -1) X 800 M (Additional leak points) (b) IMOR RIVER 26S (300 M) © IMO RIVER 60T (1850M) (d) IMO RIVER 32L/GLL (e) IMO RIVER 4-INCH BULKLINE (f) IMO RIVER 57GLL (g) IMO RIVER 36S (h) IMO RIVER 63T (i) IMO RIVER 4-INCH TEST LINE - Resubmission | Resubmission | Approved. WORP steers from previous sitting 15/04/21 have not been fully incorporated. I. Ensure C&P and PS participation in the alignment meeting with the contractor and document MoM to WORP secretariat. | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 38,413.62 N 12,943,786.38 F$ 72,521.09 | [5 empty] | NIL |  | GAMSTEC INTEGRATED
| SECTIONAL REPLACEMENT OF AFAM 27T FLOWLINE (8” x 12m) | Fresh | Approved | Approved | Akinbiyi, A | O.NG.PAE.I1F.FAC.724FC | $ 30,177.06 + 98,171.47 N 51,406,830.37 + 2,393,303.75 F$ 165,636.43 + 104,477.93 | [5 empty] | F$: 11,596.18 | Mob and De-mob from the two Contractors | GAMSTEC INTEGRATED
| ESTUARY CLUSTER 9 RING AND 2 Nos. BULKLINE RISER REPLACEMENT WORK. | Fresh | Approved | Approved | Uwaezuoke, D | C.NG.PBW.DF.212.001 |  |  | $ 119,090.63 N 31,814,175.20 F$ 202,922.45 |  |  |  | NIL |  | Miden Systems Limited
| SECTIONAL REPLACEMENT OF NKALI 10S – (4” Sch.80 X 120M) NKALI 13L – (4” Sch.80 X 120M) NKALI 13S – (4” Sch.80 X 120M) | Fresh | Approved. I. Reference percentage of commitment to date as part of the reasons for choice of contractor. | Approved | Aderiye, A | O.NG.PAE.NKF.FAC.724FC | $ 41,624.94 N 4,030,118.50 F$ 52,244.49 | [5 empty] | FS 22,162.92 | MOB & DEMOB BY USING ONE CONTRACTOR TO EXECUTE THE REPAIRS OF THE THREE (3) FLOWLINE REPAIRS. | WILKRISS NIGERIA
| NUN RIVER WELL 13T MAINTENANCE DREDGING WORKS. | Fresh | Approved | Approved | Onjejekwe, C | 110744 |  |  |  | $: 391,403.14 N: 225,529,048.35 F$: 985,682.59 |  |  | F$: 111,908.44 | Cost saving is from Low Oil Price LoP discounts (i.e. 15%). | FW DREDGING LTD
| GENERAL |  | Ensure C&P participation in all alignment meetings with contractors. • Always reference percentage of commitment to date as part of the reasons for choice of contractor. • Document contractor’s performance at site for referencing.
2021-04-29 | LOCATION DREDGING WORKS AT BENISEDE EAUA-2 – ADDITIONAL RIG PAD AREA SAND FILLING WORKS | Fresh | Conditional Approval. Update and revert upon completion of the following: I. Engage PS to finalize review on the estimated volume/cost of additional sandfill works. | Conditional Approval | Onjejekwe, C | C.NG.AFS.DD.19.009.9401 |  |  |  | $: 18,696.66 N: 59,495,875.75 F$: 175,471.03 |  |  | F$: 44,242.44 | Cost saving is from Low Oil Price LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| NUN RIVER DIEBU CREEK BULKLINE TO GBARAN - Civil Structural Scope. | Fresh | Conditional Approval. Update and revert upon completion of the followings: I. Update Project title to appropriately describe activity. II. Forward project MTO to PS for review. III. Engage C&P to review and update omitted contract line items in ARIBA / SAP | Conditional Approval | Ehizoyanyan, O | C.NG.PAE.DL.21.002.1230 |  | $ - 267,723..54 N – 146,066,686.79 F$ - 652,616,00 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| GBARAN 5T FLOWLINE INTEGRITY CHECK | Fresh | Approved. I. In the event of line failure, revert to EST to review the pipe schedule for replacement works | Approved | Okeke, N | C.NG.PAE.DL.21.002.1230 |  | $ 12,158.02 N 3,511,033.32 F$ 21,409.68 |  |  |  |  | NIL |  | THOMPSON AND GRACE LTD
2021-05-06 | CONSTRUCTION OF AIR COMPRESSOR FOUNDATION BAY & SHED AT ESCRAVOS FS FOR THE IG - IA PROJECT – Additional work | Fresh | Approved. I. Update the remaining ACV for this submission II. CH to liaise with C&P and resolve contract ACV split value issues. | Approved | Ehizoyanyan, O | C.NG.PAE.DL.21.002.1230 |  |  | $ - 7,171.22 N – 18,981,937.62 F$ - 57,187.92 |  |  |  | NIL |  | GRAMEN PETROSERVE
| SEIBOU BULKLINE 3 AND 4 JIV - 2ND JIV AND SEIBOU BULKLINE 3 AND 4 JIV - Proposed 3rd JIV. | Fresh | Deferred. I. Engage C&P to support execution strategy and revert. | Deferred | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300 |  |  | $ 75,346.14 N 1,168,966.47 F$ 78,426.42 |  |  |  | NIL |  | TONYMAR INVESTMENT
| BONNY WELL 12S JIV SUPPORT TO THE ASSET TEAM. | Fresh | Approved. I. Update WBS for this activity to Asset account. II. Update the remaining ACV for this submission. | Approved | Ehizoyanyan, O | C.NG.PAE.DL.20.001.1230 |  | $ 14,073.00 N 718,429.33 F$ 15,966.89 |  |  |  |  | NIL |  | SURVEILLANCE 2000 LTD
| APARA 10 BORROW PIT RECLAMATION PROJECT- ADDITIONAL WORK | Fresh | Deferred. I. Secure approval from Divestment finance team to carry out this activity and revert. | Deferred | Agbonsalo, O | O.NG.PAE.OBP.MFC.71300 |  |  |  | $ 89,508.25 N 53,704,949.76 F$ 231,023.27 |  |  | F$: 31,503.17 | Lop,re-negotiated rates | EA TEMILE
| SECTIONAL REPLACEMENT OF IMOR (a) 63T (3-INCH x 80M) – IMO 1 AREA (b) 21S (4-INCH X 24M) – IMO 2 AREA | Fresh | Approved | Approved | Aderiye, A | O.NG.PAE.UCF.FAC724FC | $ 13,612.36 N 3,308,636.05 F$ 23,169.24 | [5 empty] | FS8,282.04 | MOB & DEMOB SINCE THE SAME CONTRACTOR IS ALREADY ON THE SITE | ROMEK AND COMPANY
| LOCATION DREDGING WORKS AT BENISEDE EAUA-2 – ADDITIONAL RIG PAD AREA SAND FILLING WORKS. -Resubmission & reviewed offline | Resubmission & Reviewed offline | Approved. WORP steer from previous sitting 29/04/21 have been incorporated | Approved | Onyejekwe, C | C.NG.AFS.DD.19.009.9401 |  |  |  | $: 18,696.66 N: 59,495,875.75 F$: 175,471.03 |  |  | F$: 44,242.44 | Cost saving is from Low Oil Price LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| GENERAL |  | Forward to ALL the procedure on managing emergency/urgent works. • Harmonize template for standard list of materials for hook up/flowline works and circulate to team.
2021-05-14 | Provision of Engineering support for JIV to SEIBOU bulklines 3 and 4 (Repeat JIV and access new leak points) - Resubmission | Resubmission | Approved. WORP steer from previous sitting 06/05/21 have been incorporated. I. Engage Asset team for an enhanced surveillance cover. | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $ 75,518.29 N 1,188,378.37 F$ 78,649.72 |  |  |  | NIL |  | TONYMAR INVESTMENT
| Deleted SEs for Soku Relocation of Emergency Spill Reponses Caravan, Construction of Chemical Shed and procurement and Installation of Jib Crane | Resubmission | Approved. | Approved | Ehizoyanyan, O | O.NG.PBE.SKF.FAC.724FP |  | $ 136,725.22 N 29,734,583.43 F$ 215,077.218 |  |  |  |  | NIL |  | VANDREZZER ENERGY SERVICES
| Bonny 12S Flowline Replacement – (4” x 1.75km). | Fresh | Approved. I. Engage BSU to provide adequate budget for this activity. II. Ensure linepipe cost is transferred from previous activity to Bonny 12S. III. Provide assurance of Vendors ability to carry out work in this community. IV. Capture cost savings secured from discounting houseboat to the use of hotel accommodation and forward to I&A for documentation. | Approved | Ehizoyanyan, O | C.NG.PAE.DL.21.001.1230 |  | $ 246,444.75 N 6,442,651.14 F$ 263,421.44 |  |  |  |  | NIL |  | JOSBANI CONSTRUCTION
| Repair of cracked 2” sampling line to Atmospheric flare of Soku GP GRU train 3. | Fresh | Conditional Approval. I. Update ACV for this activity. II. Review interim mobilization to “Distance below 100km” and revert with updated cost. | Conditional Approval | Obiakor, O | O.NG.PBE.SKG.FAC.72FC |  | $ 5,043.65 N 3,689,043.98 F$14,764.45 |  |  |  |  | 25456.77 | Cost saving initiative -savings for not doing full mobilization and no demobilization | GRAMEN PETRO-SERV
| GENERAL |  | Proper materials tracking & reconciliation procedure.
2021-05-20 | OTUMARA FLOW STATION GANTRY WORKS -Resubmission | Resubmission | Deferred. WORP steers from previous sitting 25/02/21 have been incorporated. Further steers: I. Engage C&P to review vendor rates and benchmark with PS to ensure process is in line with approved contracting procedures. II. Update risk register to include “Scaffolding” and review procedure with SME in EST prior mobilization. III. Ensure active participation of the Quality team to avoid equipment & materials failure. | Deferred | Azaka, G | C.NG.PBW.IM.17.005.1230 |  |  | $ 224,535.15 N 15,882,943.33 F$266,387.44 |  |  |  | NIL |  | NAPEBI CONSTRUCTION
| TUNU CDRY-3 FLOWLINE CONSTRUCTION -2 days standby | Fresh |  | Deferred | Azaka, G | C.NG.AFS.DF.19.003.1200 |  |  | $3,847.34 N 2,103,075.15 F$ 9,389.04 |  |  |  | NIL |  | IKONIBO NIG LTD
| REPLACEMENT OF CORRODED RISER FORCADOS 127T FLOWLINE. | Fresh | Approved. I. Update contract expiration date. II. Update business case and specify that this activity is different from previously completed work. III. Full adherence to CSSS requirements at site. IV. Always attach QAQC reports to justify additional work submissions. | Approved | Obiakor, O | 102155 |  |  | $ 75,911.23 N 1,393,860.79 F$ 78,425.57 |  |  |  | F$29,515.51 | Mob and De-mob, Houseboat | TONYMA INVESTMENT
| ABRICATION/INSTALLATION OF OBELLE 3L HOOK-UP ARM (a) 3T (3-INCH x 12 M) | Fresh | Approved. I. Update ACV for this activity. II. Always ensure risk assessment is carried out for all submissions prior to WORP submission. III. Update Project Schedule to current plan. | Approved | Aderiye, A | O.NG.PAE.OLF.FAC.724FC | $ 6,007.13 N 1,414,531.68 F$ 9,734.48 | [5 empty] | FS8.801.96 | MOB & DEMOB SINCE THE SAME CONTRACTOR IS ALREADY ON THE SITE | ROMEK
| GENERAL |  | Proper reporting of all non-compliance at sites by HSE inspectors. • Full adherence to CSSS requirements at all OABP sites. • Free-issue materials to be included as savings and differentiated in the remarks.
2021-05-27 | Repair of Cracked 2” sampling line to atmospheric flare of Soku GP GRU Train 3 -Resubmission | Resubmission | Approved. WORP steers from previous sitting 14/05/21 have been implemented. | Approved | Obiakor, O | O.NG.PBE.SKG.FAC.72FC |  | $ 3,669.00 N 2,710,751.95 F$10,811.96 |  |  |  |  | 25456.77 | savings for not doing full mobilization and no demobilization | GRAMEN PETRO-SERV
| Unblocking of Etelebou Test line to Gbaran (6” X 8km Bulk line) - Resubmission | Resubmission | Deferred. WORP steers from previous sitting 25/06/20 have not been fully implemented. Further steers: I. Engage PS to further review cost optimization on Inter area spread and As-built survey. II. Confirm Vendors CAP assessment status. III. Engage hotdesk for materials reconciliation. IV. Prioritize Inventory spill / environmental impact in the 5no top risks. | Deferred | Obiakor, O | C.NG.PCE.NO.21.002.1230 |  | $ 70,330.40 N 20,070,011.95 F$ 126,105.43 |  |  |  |  | NIL |  | ROMEK & COMPANY
| Sectional Replacement of Afam 25T flowline (Additional Work) | Fresh | Approved. I. Always include line length in the project title. | Approved | Akinbiyi, A | O.NG.PAE.I1F.FAC.724FC | $ 40,336.43 N 11,879,588.32 F$ 71,639.69 | [5 empty] | NIL |  | GAMSTEC INTEGRATED
| Gbaran Produced Water Flowline Construction – 6” sch. 40 x 1.72km | Fresh | Deferred. I. Carry out proper corrosion management study to determine required linepipe schedule for this activity. II. Engage hotdesk for materials reconciliation. | Deferred | Arowosafe, T | C.NG.PBE.IM.21.001.1230 |  | $ 76,928.46 N 19,082,949.85 F$ 127,212.92 |  |  |  |  | NIL |  | GUIZ AND COMPANY
| Fabrication and Installation of Ubie 8T Hook Up Arm | Fresh | Approved | Approved | Azaka, G | C.NG.AFS.DF.19.003.1200 |  | $ 643.30 N 225,164 F$ 1,381.55 |  |  |  |  | NIL |  | MORRAY SERVICES
| Enwhe East Miscellaneous Civil Works. | Fresh | Approved. I. Include resource sharing as cost savings and forward to I&A. II. Ensure proper HSE supervision and adequate security cover at site. | Approved | Ebirim, M | C.NG.LNG.17.003.1230 |  |  |  | F$: 219,812.14 |  |  | F$: 15,281.06 | 6.5 % LOP Discount | BENCOV NIG.LIMITED
| GENERAL |  | Shrink Sleeves now available for collection at the warehouse.
2021-06-03 | Sectional Replacement of ImoR 36L (3” x 80m) from Gathering manifold to Inlet manifold. | Fresh | Conditional Approval. Subject to pending resolution of contract time extension by NAPIMS. | Conditional Approval | Aderiye, A | O.NG.PAE.UCF.FAC724FC | $ 10,654.64 N 2,021,999.35 F$ 15,982.70 | [5 empty] | FS6,617.11 | Free Issue materials | ROMEK
| Re-routing of NUNR 3S, 13T, 16T Flowline (4” sch 80 x 1.1km) | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Capture cost savings from shared resources. II. Engage C&P to reconcile ACV figures. | Conditional Approval | Uwaezuoke, D | P.NG.PAE.OP.19.005.9401 |  | $ 248,215.97 N 7,477,220.95 F$ 267,918.80 |  |  |  |  | NIL |  | Tonymar Investment
| Re-routing of NUNR 12LS Flowline (4” sch. 80 x 700m) | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Capture cost savings from shared resources. II. Engage C&P to reconcile ACV figures. | Conditional Approval | Uwaezuoke, D | P.NG.PAE.OP.19.005.9401 |  | $ 183,798.51 N 5,919,883.68 F$ 203,207.96 |  |  |  |  | NIL |  | Surveillance 2000 Limited
| Unblocking of Etelebou Test line to Gbaran (6” X 8km Bulk line) -Resubmission | Resubmission | Approved. WORP steers from previous sitting 27/05/21 have been incorporated. I. Ensure top-level risk of potential spill to the environment and mitigation are well adhered to at site. | Approved | Obiakor, O | C.NG.PCE.NO.21.002.1230 |  | $ 76,114.92 N 20,641,979.95 F$ 133,453.75 |  |  |  |  | NIL |  | ROMEK & COMPANY
| FORC 111T Flowline Replacement (4" sch 40 x 0.411km Additional scope) -Reviewed offline | Fresh | Approved. | Approved | Orji, C | C.NG.PCW.DL.21.001.1230 |  |  | $ 38,383.78 N 14,097,183.85 F$ 75,530.51 |  |  |  | NIL |  | HENSTEEL ENGINEERING
| Otumara flow station Gantry work. -Reviewed offline. | Resubmission | Approved. WORP steers from previous sitting 20/05/21 have been incorporated. | Approved | Azaka, G | C.NG.PBW.IM.17.005.1230 |  |  | $ 82,470.03 N 2,409,002.58 F$88,817.86 |  |  |  | NIL |  | NAPEBI & PECOM
| GENERAL |  | Project Leads to ensure all submissions are reviewed prior WORP sitting.
2021-06-10 | Gbaran Produced Water Flowline Construction – 6” sch. 80 x 1.72km -Resubmission | Resubmission | Approved. WORP steers from previous sitting 27/05/21 have been incorporated. I. Engage NAPIMS for approval to raise P.O. II. Confirm linepipes availability & location. | Approved | Arowosafe, T | C.NG.PBE.IM.21.001.1230 |  | $ 72,928.93 N 17,434,041.54 F$ 115,450.98 |  |  |  |  | NIL |  | GUIZ AND COMPANY
| Re-routing of NUNR 12LS Flowline (4” sch. 80 x 700m) -Resubmission | Resubmission | WORP steers from previous sitting 03/06/21 have been incorporated | Approved | Uwaezuoke, D | P.NG.PAE. OP.19.005.9401 |  | $ 179,829.74 N 5,297,237.66 F$ 192,749.83 |  |  |  |  | F$: 87,447.78 | Shared Resources – houseboat | Surveillance 2000 Limited
| Re-routing of NUNR 3S, 13T, 16T Flowline (4” sch 80 x 1.1km) -Resubmission | Resubmission | WORP steers from previous sitting 03/06/21 have been incorporated. | Approved | Uwaezuoke, D | P.NG.PAE.OP.19.005.9401 |  | $ 241,645.94 N 6,316,713.09 F$ 257,052.56 |  |  |  |  | NIL |  | Tonymar Investment
| Estuary Cluster 51: Installation of Forcados. 73LS Hook-up Arm | Fresh | Progress manual deletion of previous PO for Opukushi 32T flowline. | Approved | Uwaezuoke, D | C.NG.AFS.DL.18.004.1218 |  |  | $ 67,038.61 N 2,973,825.23 F$ 74,874.78 |  |  |  | NIL |  | Gawason Integrated
| Bonny W12S JIV Support Services to the Asset Team – Additional work. | Fresh | Approved. I. Attach e-mail confirmation of additional work at site & forward to the Secretariat. | Approved | Ehizoyanyan, O | O.NG.PCE.BNF.FAC.71300 |  | $ 9,171.00 N 286,524.00 F$ 9,926.00 |  |  |  |  | NIL |  | SURVEILLANCE 2000 LTD
| Otumara flowstation Replacement of corroded drip pan. | Fresh | Approved. I. Progress manual deletion of previous PO for Otumara W20, 25 & 27 WHP rehabilitation. II. Ensure proper kick-off meeting | Approved | Obiakor, O | C.NG.PBW.IM.17.005.1230 |  |  | $ 108,500.00 N 3,350,000 F$116,670.73 |  |  |  | NIL |  | ROESON NIG
2021-06-17 | K2S Simultaneous Flow Project - Materials for Workshop Fabrication | Fresh | Deferred. I. Carry out further engagement with Procurement team to expedite materials delivery and revert with outcome. II. Document delays encountered from Procurement team and involve Asset team in the engagement. III. Liase with C&P to reconcile ACV figures. | Deferred | Akoma, I | C.NG.PBE.DF.21.005 |  | $11,908.95 N F$11,908.95 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Gbaran Produce Water Re-injection Project – Preliminary Works (Phase 1) | Fresh | Approved. I. Liase with C&P to reconcile ACV figures. II. Start early documentation of project pictures & forward to SE Lead. | Approved | Akoma, I | C.NG.PBE.IM.21.001.1230 |  | $ 13,865.02 N 10,453,136.83 F$ 39,360.48 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Kanbo 3L Flow line Sectional Replacement – (6’’ SCH 40 x 0.2km) | Fresh | Stepped Down. Project Lead to reconcile contracting issue and revert. | Stepped Down | Ehizoyanyan, O
| Replacement of Otumara 4L GLL (4" Sch 40 x 1.0km) | Fresh | Stepped Down. Project Lead to reconcile contracting issue and revert. | Stepped Down | Obiakor, O
| GENERAL |  | Always ensure strict adherence to SPDC procedures.
2021-06-24 | Diebu Creek FS Shutdown activities. | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Update WBS for this activity. II. Attach an approved OABP-WR. III. Carry out materials reconciliation with Hotdesk. IV. Update Project title to appropriately describe work scope. V. Engage CH for contract ceiling increase. VI. Liase with EST to ascertain Asset Integrity scope. | Conditional Approval | Uwaezuoke, D | TBA |  | $ 38,880.07 N 16,955.578.78 F$ 80,235.14 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Gbaran Produce Water Re-injection Project. -Reviewed offline | Fresh | Approved | Approved | Akoma, I | C.NG.PBE.IM.21.001.1230 |  | 800661.49 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
2021-07-01 | Kanbo 3L Flow line Sectional Replacement – (6’’ sch 40 x 0.2km) | Fresh | Approved. I. Set up an interface management meeting with the vendors and document MoM. II. Update CTS cost in the cost breakdown summary. | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $35,265.98 - N 2,357,063.1 F$41,014.91 - ELKON $31,746.32 N 1,024,554.20 F$34,245.23 - PALTOJEN |  |  |  | NIL |  | PALTOJEN NIG ELKON INTEGRATED
| Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km – Additional work | Fresh | Deferred. I. Engage C&P and other relevant project teams (NLNG) to ascertain company decision on vendors hotel accommodation payment during Covid’19 at site. | Deferred | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 1,115.74 N 198,497.00 F$ 1,638.79 |  |  |  |  | NIL |  | ABBEYCOURT ENERGY
2021-07-08 | Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km – Additional work -Resubmission | Resubmission | Deferred. WORP steers from previous sitting 01/07/21 have not been closed out. I. Engage C&P with outcome of discussions held with NLNG team to ascertain company decision on vendors hotel accommodation payment during covid’19 at site and revert. | Deferred | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 1,115.74 N 198,497.00 F$ 1,638.79 |  |  |  |  | NIL |  | ABBEYCOURT ENERGY
| Re-routing of NUNR 3S & 13T Flowline (4” Sch 80 x 700m) - SLOT Re-routing of NUNR 16T Flowline (4” sch 80 x 350m) – TONYMAR -Resubmission | Resubmission | Deferred. I. Advised to propose a single Vendor to reduce cost implication. | Deferred | Uwaezuoke, D | P.NG.PAE.OP.19.005.9401 |  | Slot $ 173,807.54 N 4,600,382.20 F$ 185,027.98 Tonymar $ 119,438.25 N 4,047,964.33 F$ 129,311.34 |  |  |  |  | NIL |  | Slot Engineering Tonymar Investment
| Provision of TRP scale inhibition injection points in Tunu, Opukushi & Benisede flow stations. | Fresh | Deferred. I. Engage CH to update ACV. II. Attach an approved e-WR | Deferred | Obiakor, O | C.NG.PBW.DF.21.003 |  |  | $ - 65,451.78 N – 22,088,4444.87 F$ - 119,326.04 |  |  |  | F$: 42,345.22 | Inter area mobilization instead of full mob to two facilities and domobilization | GRAMEN PETROSERVE
| Nun River Diebu Creek Bulkline to Gbaran - Civil Structural Scope. (missed out scope) | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Engage CH to update ACV. II. Update submission to clearly explain “Inter area move” as specified in the contract. III. Attach an updated Project schedule IV. Ensure provision for proper crew change to avoid personnel overstay at site | Conditional Approval | Obiakor, O / Ehizoyanyan, O | C.NG.PAE.DL.21.002.1230 |  | $ - 48,263.45 N – 48,639,602.94 F$ - 166,896.63 |  |  |  |  | F$: 21,151.12 | inter area move to Nun river manifold instead of full mob plus demob charge. | GRAMEN PETROSERVE
| Location Dredging works at Ogbotobo ANTM-1 & Ogbotobo AOTM-1. | Fresh | Conditional Approval I. Project Lead to reconcile contracting issue and revert. II. Update 5no top risk | Conditional Approval | Onyejekwe, C | TBA |  |  |  | $: 982,895.93 N: 585,168,641.77 F$: 2,410,136.52 |  |  | F$: 538,142.04 | Low Oil Price LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| GENERAL |  | Ensure proper review of submissions prior WORP
2021-07-15 | Re-routing of NUNR 3S, 13T, 16T Flowline (4” sch 80 x 1.1km) -Resubmission | Resubmission | Conditional Approval. WORP steer from previous sitting 08/07/21 have been incorporated. Further steer: I. Carry out contract alignment with NAPIMS and attach evidence of engagement to the resubmission. | Conditional Approval | Uwaezuoke, D | P.NG.PAE. OP.19.005.9401 |  | $ 241,645.94 N 6,316,713.09 F$ 257,052.56 |  |  |  |  | NIL |  | Slot Engineering
| Kanbo 3S JIV Asset Support. | Fresh | Approved | Approved | Ehizoyanya, O | O.NG.PCW.OKF.FAC.71300. |  |  | $23,535.13 N 787,950.12 F$27,456.96 |  |  |  | NIL |  | ELKON INTEGRATED
| Gbaran Produce Water Re-injection Project: Provision of Filtering Unit | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Build-up a detailed scope/cost to justify ceiling increase & secure TA2 assurance before engaging MTB. II. Carry out contract alignment with NAPIMS and attach evidence of engagement. III. Update 5no top risk to include “Possible procurement delay” and provide mitigations. IV. Update “Payment on behalf of SPDC” in the cost breakdown to “Reimbursable” | Conditional Approval | Akoma, I / Jimba, O | C.NG.PBE.IM.21.001.1230 |  | $ 560,099.71 N 33,501,980.40 F$ 646,948.56 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Otumara 55T Flowline Replacement (4” Sch 40 x 3.3km). -Reviewed offline | Fresh | Approved | Approved | Uwaezuoke, D | C.NG.PCW.DL.21.001.1230 |  |  | $ 459,067.57 N 8,974,812.70 F$ 480,957.36 | [5 empty] | Tomba Resources
| Otumara 30L Flowline Replacement (4” x 2.8km). -Reviewed offline | Fresh | Approved | Approved | Azaka, G | C.NG.PCW.DL.21.001.1230 |  |  | $404,380.20 N6,341,841.27 F$419,848.11 |  |  |  | 20056.18 | Houseboat sharing with another vendor working on OTUM55T | WILANDSON INTERNATIONAL
2021-07-22 | No Submission
2021-07-29 | Gbaran Produced Water Flowline Construction – 6” sch. 80 x 1.72km | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Attach mail confirmation of contract alignment meeting held with NAPIMS. II. Review the Contract ceiling availability and ensure is sufficient to accommodate this work. III. Capture cost savings from resource sharing. IV. Engage PS to review surveillance cost. V. Update Project schedule. | Conditional Approval | Arowosafe, T | C.NG.PBE.IM.21.001.1230 |  | $141,857.81 N 2,510,439.45 F$ 148,472.93 |  |  |  |  | NIL |  | JOSBANI
| Gbaran Produce Water Re-injection Project – Balance of Plant Works | Fresh | Approved. I. Ensure proper materials inspection by QAQC team. | Approved | Akoma, I | C.NG.PBE.IM.21.001.1230 |  | $ 909,985.52 N 298,402,543.02 F$ 1,637,796.60 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| KANBO 3S Flow line Sectional Replacement – (6’’ SCH 40 x 0.2km) | Fresh | Approved. I. Carry out interface management meeting with other vendors working on same RoW and ensure HSE & Security presence in the meeting. II. Engage HSE | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $.97,898.40 N 2,050,545.09 F$102,899.73 |  |  |  | NIL |  | EPOXY SERVICES
| Replacement of Otumara 4L GLL (4" Sch 40 x 1.0km). | Fresh | Approved. I. Carry out interface management meeting with the vendors and ensure HSE & Security presence in the meeting. | Approved | Obiakor, O | O.NG.STG.PBE.OTM.004FL |  |  | GAWASON $ 99,128.67 N 2,770.114.70 F$105,885.05 KEMUD $101,979.55 N 2,749,753.93 F$108,686.27 |  |  |  | NIL |  | GAWASON INTEGRATED. KEMUD INTERNATIONAL
| Afam VI Vent Gathering Project | Fresh | Approved | Approved | Dienagha, I | C.NG.PCE.NO.21.004 | USD 3,328.15 NGN 32,970 F$: 4,125.64 | [5 empty] | NIL |  | ADVANCED COATING TECH
| Resubmission: Re-routing of NUNR 3S, 13T, 16T Flowline (4” sch 80 x 1.1km) - Resubmission & Reviewed offline | Resubmission | Approved. WORP steer from previous sitting 15/07/21 have been incorporated. | Approved | Uwaezuoke, D | P.NG.PAE. OP.19.005.9401 |  | $ 241,645.94 N 6,316,713.09 F$ 257,052.56 |  |  |  |  | NIL |  | Slot Engineering
2021-08-05 | AJATITON W01L HOOK UP ARM REPLACEMENT. | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Attach an approved e-WR to the resubmission. II. Capture cost savings from resource sharing. III. Confirm vendors capability to execute work according to schedule. | Conditional Approval | Azaka, G | O.NG.STG.PBE.AJA.001FL |  |  | $67,692.69 N3,179,278.93 F$75,447.03 | [5 empty] | ELEKING W.W. SERVICES
| GENERAL |  | • Always document Contractors work performance. • Carry out a post-execution materials reconciliation review and report out with recommendations for improvement. • General HSE stand down in all OABP teams.
2021-08-12 | Ajatiton W01L Hook up Arm Replacement. -Resubmission | Resubmission | Approved. WORP steers from previous sitting 05/08/21 have been incorporated. I. Carry out a proper kick-off meeting and ensure HSE & Security presence, document MoM. | Approved | Azaka, G | O.NG.STG.PBE.AJA.001FL |  |  | $67,692.69 N3,179,278.93 F$75,447.03 |  |  |  | 48272.37 | (No cost for houseboat) | ELEKING W.W. SERVICES
| Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km – Additional work -Resubmission | Resubmission | Approved | Approved | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 1,819.93 N 160,592.00 F$ 2,211.62 |  |  |  |  | NIL |  | ABBEYCOURT ENERGY
| Provision of TRP Scale Inhibition Injection Points in Tunu, Opukushi & Benisede flowstation. -Resubmission | Resubmission | Conditional Approval WORP steers from previous sitting 08/07/21 have not been fully incorporated. I. Further engagement with the CH to secure additional eLDL to accommodate works on the Gramen Contract. | Conditional Approval | Obiakor, O | C.NG.PBW.DF.21.003 |  |  | $ 65,451.78 N 22,088,4444.87 F$ - 119,326.04 |  |  |  | F$: 42,345.22 | For doing inter area mobilization instead of full mob to two facilities and demobilization | GRAMEN PETROSERVE
| Installation of Flare tip & RIS at Agbada & Ahia FS. | Fresh | Deferred. I. Engage Asset team to decide funding procedure for divested OML17 activity. II. Update WBS for this activity. | Deferred | Ewenike, M | NIL | F$: 894.87 | [7 empty] | KEMUD INTERNATIONAL
| Kanbo 5S flowline JIV Asset Support. |  | Stepped Down by PMT
| Leak Repair of approach line of Nun River W13T Flowline. | Fresh | Deferred. I. Update WBS for this activity II. Engage CH to secure additional eLDL to accommodate works on the Gramen Contract | Deferred | Obiakor, O | C.NG.PAE.DL.21.001 |  | $ 14,338.89 N 9,489,577.88 F$ 37,484.20 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Nun River Diebu Creek Bulkline to Gbaran – Mechanical, Electrical & Instrumentation scopes. | Fresh | Deferred. I. Engage CH to secure additional eLDL to accommodate works on the Gramen Contract | Deferred | Ehizoyanyan, O | C.NG.PAE.DL.21.002.1230 |  | MECHANICAL PACO ELECTRICAL TOTAL COST $ 599,603.70 $ 268,558.89 $ 5,480.82 $ 873,643.34 N 252,401,417.93 N 13,288,610.75 N 10,392,665.63 N276,082,694.31 F$ 1,215,216.91 F$ 300,970.14 F$ 30,828.78 F$ 1,547,015.83 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Enwhe West 3.5km Location Access Road Additional Scope / Local content. | Fresh | Approved. I. Engage ER and ensure proper processes are deployed in the payment. | Approved | Ezenduka, D | C.NG.LNG.19.004.1230 |  |  |  | N38,871,180 +$ 3,660.94, F$:98,468.70 |  |  | NIL |  | MIFE CONSTRUCTION
| Gbaran Produced Water Flowline Construction – 6” sch. 80 x 1.72km -Resubmission & Reviewed offline | Fresh | Approved | Approved | Arowosafe, T | C.NG.PBE.IM.21.001.1230 |  | $ 143,031.76 N 2,550,416.89 F$ 149,252.29 |  |  |  |  | 96713.65 | Cost saving for not mobilizing tie-in barge and lay barge, also savings from cost of surveillance. (reduced from 43days to 15days) | JOSBANI
| Replacement of Otumara 4L GLL (4" Sch 40 x 1.0km) -Resubmission & Reviewed offline | Resubmission | Approved | Approved | Obiakor, O | O.NG.STG.PBE.OTM.004FL |  |  | $ 166,934.26 N 3,924,654.46 F$176,506.59 |  |  |  | NIL |  | TONYMAR
| Estuary Cluster 51: Forc. 73LS Hook-up Arm Modification – Reviewed offline | Fresh | Approved | Approved | Uwaezuoke, D | C.NG.AFS.DL.18.004.1218 |  |  | $58,153.30 N 2,432,214.52 F$ 64,085.53 |  |  |  | 25726.45 | Shared Resources, Scaffold | Gawason
2021-08-19 | Installation of flare tip & RIS at Agbada and Ahia flowstation Resubmission | Resubmission | Approved. WORP steers from previous sitting 12/08/21 have been incorporated. I. Erase Agbada from the Project title. II. Document payment agreement with the vendor to forestall future claims. | Approved | Ewenike, M | C.NG.PCE.N0.20.001.1230 | F$: 885.54 | [5 empty] | NIL |  | KEMUD INTERNATIONAL
| Construction of Enwhe West Location, By-pass, and Concrete Bridge. Additional Scope. | Fresh | Approved | Approved | Ezenduka, D | C.NG.LNG.19.004.1230 |  |  |  | N56,723,927.76 +$ 34,431.58, F$:172,782.62 |  |  |  |  | ENERCO NIG
| Geotechnical Investigation for Oloibiri Oil and Gas Museum and Research Center (OMRC) | Fresh | Approved. I. Update Risk item 2 title appropriately. | Approved | Edoh, C | 110866 |  |  |  | N 6,005,140.00 |  |  | 770.878 | 5% Discount on the Contract Rates | Eadro Geotechnics
| Gbaran 26 Location Rehabilitation Project (Gbaran 14 Replacement Well) | Fresh | Approved. I. Engage the contractor on the criticality of the schedule with regards to working during December period. II. Engage Wells team on the need for Well test location and revert to WORP for approval of the extra work scope if needed. | Approved | Chioke, K | C.NG.LNG.DG.19.006.1231 |  |  |  | $ 161,394.54 N 96,834,975.99 F$ 397,577.41 |  |  | 20925.13 | (LoP) | RAFFOUL NIG
| Disconnection of Afremo 6T Hook-up Arm (Afremo B) | Fresh | Approved. I. Align OABP security plan with CWI team. II. Hold a proper kick off meeting and ensure Security, HSE & Marine presence. | Approved | Uwaezuoke, D | P.NG.PAE. OP.19.004.1230 |  |  | $59,166.78 N 1,507,497.96 F$ 62,843.60 |  |  |  | 123952.48 | Shared Resources (Logistics and Security etc) | Kemud International
| Kanbo 5S flowline JIV Asset Support / Flowline Sectional Replacement (6’’ x 0.2Km) | Fresh | Approved | Approved | Otavie, G | O.NG.STG.PBE.KAN.005FL |  |  | $ 103,554.77 N 2,100,446.5 F$ 108,677.81 |  |  |  | NIL |  | WIRELINK SERVICES
| Repair of Cracked 3” Weldolet of Soku GP spiking pump discharge header. | Fresh | Approved. I. Engage CH to update ACV split values in the submission. | Approved | Obiakor, O | O.NG.PBE.SKG.FAC.724FC |  | $ 13,634.14 N 10,119,593.96 F$ 38,316.08 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Leak Detection System Project (Installation of Coriolis Meter at Kolo Creek and Rumuekpe Manifolds) – Provision of Shortfall Materials | Fresh | Approved. I. Engage CH to update ACV split values in the submission. | Approved | Odey, E | O.NG.PPE.MAN.MAN.71300 | $ 275,665.28 N 25,091,470.98 F$ 336,863.99 | [5 empty] | NIL |  | GRAMEN PETROSERVE
| Forcados 73LS Hook-up Arm Replacement. -Reviewed offline | Resubmission | Approved | Approved | Uwaezuoke, D | C.NG.AFS.DL.18.004.1218 |  |  | $ 31,605.99 N 1,103,594.09 F$ 34,297.68 |  |  |  | 117417.71 | Shared Resources, Logistics, Security and Scaffold etc) | Gawason
| GENERAL |  | Always ensure vendor supplied materials are inspected by the QAQC team.
2021-08-26 | Nun River Diebu Creek Bulkline to Gbaran – Mechanical, Electrical & Instrumentation scope. -Resubmission | Resubmission | Approved. WORP steers from previous sitting 12/08/21 have been incorporated. | Approved | Ehizoyanyan, O | C.NG.PAE.DL.21.002.1230 |  | MECHANICAL PACO ELECTRICAL TOTAL COST $ 599,603.70 $ 268,558.89 $ 5,480.82 $ 873,643.34 N 252,401,417.93 N 13,288,610.75 N 10,392,665.63 N276,082,694.31 F$ 1,215,216.91 F$ 300,970.14 F$ 30,828.78 F$ 1,547,015.83 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Provision of TRP Scale Inhibition Injection points in Tunu, Opukushi & Benisede flow stations. -Resubmission. | Resubmission | Approved. WORP steers from previous sitting 12/08/21 have been incorporated. | Approved | Obiakor, O | C.NG.PBW.DF.21.003 |  |  | $ 65,451.78 N 22,088,4444.87 F$ - 119,326.04 |  |  |  | 42345.22 | For doing inter area mobilization instead of full mob to two facilities and demobilization. | GRAMEN PETROSERVE
| Geotechnical Investigation for Gbaran NLNG Project/EPU Phase 2 Gas Dev. | Fresh | Approved. I. Update Project schedule to current plan. II. Engage C&P on clarification of rates application on this contract. | Approved | Edoh, C | P.NG.PAE.DG.20.001.1238 |  |  |  | N 10,489,484.49 |  |  | 1346.532 | Low Oil Price {LOP} | EADRO GEOTECHNICS
2021-09-02 | GBARAN PRODUCE WATER RE-INJECTION PROJECT – Materials | Fresh | Approved. I. Attach e-mail evidence of materials search carried out with Hotdesk. | Approved | Akoma, I | C.NG.PBE.IM.21.001.1230 |  | F$ 213,689.52 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| TUNU CPF INLET LINE TO TWISTER TUBE LEAK REPAIR | Fresh | Approved. I. Update WBS for this activity to AF. | Approved | Obiakor, O | C.NG.PBW.DF.21.003 |  |  | $ 19,031.56 N 9,402,872.46 F$41,965.40 |  |  |  | NIL |  | GRAMEN PETROSERVE
| TUNU HP GAS RE-ROUTING PROJECT | Fresh | Approved. I. Confirm WBS is from SSAGS team. | Approved | Obiakor, O | C.NG.PBW.DF.21.004.1230 |  |  | $ 170,906.29 N 70,497,828.59 F$342,852.21 |  |  |  | NIL |  | GRAMEN PETROSERVE
| GENERAL |  | • Strict adherence to SPDC policy of “NO PO = NO WORK” • Imbibe an aggressive cost saving initiative in all OABP activities.
2021-09-09 | Gbaran Produced Water Flowline Construction – 6” sch. 80 x 1.72km additional scope | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Update Project Schedule to current plan. II. Engage Security to mitigate exposure during river crossing. III. Confirm water depth to ascertain equipment requirement. IV. Review work method statement & certifications required. V. Update Project title to indicate the 50m additional scope VI. Review risks and update 5nos top risks. | Conditional Approval | Arowosafe, T | C.NG.PBE.IM.21.001.1230 |  | $ 35,653.72 N 3,444,186.22 F$ 44,054.17 |  |  |  |  | NIL |  | JOSBANI CONST
2021-09-16 | K2S Simultaneous Flow Project - Materials for Workshop Fabrication -Resubmission | Resubmission | Conditional Approval. WORP steers from previous sitting 17/06/21 have been incorporated. Further steer: I. Reconfirm materials availability from the Hotdesk and revert offline | Conditional Approval | Jimba, O | C.NG.PBE.DF.21.005 |  | $ 3,526.61 N F$ 3,526.61 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Gbaran Produce Water Re-injection Project: Provision of Safety Shutdown Valve | Fresh | Stepped down by PMT | Stepped down by PMT | Jimba, O
| Leak Detection System Project (Installation of Coriolis Meter at Kolo Creek and Rumuekpe Manifolds) – Provision of Shortfall Materials | Fresh | Conditional Approval I. Engage CH to reconcile ACV figures. II. Attach evidence of materials bench mark / moving average pricing from SAP. | Conditional Approval | Odey, E | C.NG.PPE.DP.21.012 |  | N 17,741,953.14 $ 3,507.71 F$46,780.77 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Enwhe East Drilling/Cellar Slot Retaining Walls and Underground Flare line Section (20m) | Fresh | Conditional Approval I. Engage CH to reconcile ACV figures. II. Update Project Schedule to current plan. | Conditional Approval | Uwaezuoke, D | C.NG.LNG.DG.19.004.1230 |  | $ 1,268.00 N 6,739,191.07 F$ 17,705.05 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| GENERAL |  | • Always ensure test results are attached to every material supplied by vendors.
23-Sep=21 | SECTIONAL REPLACEMENT OF AFAM 25T FLOWLINE- HYDROTEST (EXTRA WORK) AND AFAM 27T VOWD | Fresh | Approved. I. Attach the approved e-WR and previously secured WORP for Afam 25T and forward to the secretariat. | Approved | Akinbiyi, A | O.NG.PAE.I1F.FAC.724FC | $ 8,691.50 + 904.79 N 13,926,116.91 + 1,103,839.58 F$ 42,657.64 + 3,597.08 | [5 empty] | NIL |  | BG TECHNICAL LIMITED
| GENERAL |  | Always secure Leadership support/approval in writing for any emerging (additional) scope of work at site before execution.
[7 empty] | 0 | 96713.65 | 377770.41 | 23042.5401 | 497526.6001 | 144780.2406 | 497526.6001

## WORP Jan-Sept 21
DATE | PROJECT | TYPE | WORP DECISION | STATUS | PE / SPONSOR | WBS | TOTAL VALUE/COST | [5 empty] | COST SAVINGS | Remarks | CONTRACT
[7 empty] | LAND | CENTRAL | SWAMP WEST | CIVIL | OABP ASSET | AF
2021-01-07 | No Submission
2021-01-14 | Replacement of 2” water equalization of Soku cluster B | Fresh | Conditional Approval: Complete the actions below and revert offline - Confirmation availability of signed work request - Finalise the procurement process - MCIA: Baseline integrity request to be carried out. - Engage C&P to negotiate the swamp buggy cost. - Engage C&P on procurement of 2” line pipes - Update all documents as related to contractor change | Conditional Approval | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  | $ 155,435.95 N 7,195,661.10 F$ 174,396.85 |  |  |  |  | Nil |  | KEMUD INT’L
| FORCADOS 127T Flowline Sectional Replacement – (6’’ x 0.05km) | Fresh | Approved. - Update total cost column to reflect realities - Ensure an elaborate kick off meeting with contractor due to change in work environment. | Approved | Obiakor, O | 102155 |  |  | $ 58,352.89 N 1,953,504.45 F$ 63,500.46 |  |  |  | Nil |  | TONYMA INVESTMENT
| Provision of Security/surveillance and Downtime for Tunu BQRT-4 Flowline | Fresh | Approved | Approved | Otavie, G | C.NG.AFS.DL.19.004.1230 |  |  | $49,124.21 N 25,544,732.98 F$116,435.76 |  |  |  | Nil |  | IKONIBO NIG
| Provision of support to CWI for open-up of Tunu BQRT-4(W5ST) | Fresh | Approved. - Reconfirm that there is not/wouldn’t be a double charge on equipment due to resource sharing. - Confirm that all necessary plans, HSE, Security etc are in place and signed off | Approved | Otavie, G | C.NG.AFS.DD.19.005.9411 |  |  | $11,713.68 N10,860,399.09 F$40,331.33 |  |  |  | Nil |  | IKONIBO NIG
| Opukushi 34T Flowline Replacement | Fresh | Approved - Update the narrative in the submission to indicate initial PO will be deleted - Update in the submission G&H to CTS | Approved | Otavie, G | 102155 |  |  | FUSD:390,382.95 NGN:6,387,108.86 USD: 373,574.27 |  |  |  | FUSD: 65,000 | Renegotiated excavation rates, use of only one vendor reduced double mobilization and associated catering costs | WILANDSON
| Opukushi W26T Flowline Replacement (4" x 2km | Fresh | Conditional Approval: Complete the actions below and revert offline - Contract extension to be updated in SAP - Engage PST to reconcile cost - Update submission to reflect risk, work schedule etc | Conditional Approval | Otavie, G | 102155 |  |  | $ 182,085.5 N 66,885,002.36 F$ 401,380.6 |  |  |  | F$: 35,000 | Campaign mobilization will enable the sharing of Marine logistic resources like hosueboat | SEVOIL
| GENERAL |  | Change all submission from OP19 to OP20 Activity owners to confirm support of activities in OP20 before commencing activities. Work allocation spreadsheet to be updated and current at all times.
2021-01-21 | Opukushi W26T Flowline Replacement (4" x 2km) - Resubmission & Reviewed offline | Resubmission | Approved | Approved | Otavie, G | 102155 |  |  | $ 177,590.51 N 65,234,247.10 F$ 349,485.76 |  |  |  | F$: 35,000 | Campaign mobilization will enable the sharing of Marine logistic resources like hosueboat | SEVOIL
| Diebu Creek 9T Flowline Replacement – 4” x 4.2km | Resubmission | Deferred: Complete item below and revert offline - Reconcile materials list with materials HotDesk and EST | Deferred | Uwaezuoke, D | 102155 |  | $337,905.66 N124,092,863.66 F$664,896.08 |  |  |  |  | Nil |  | ANASAMI CONSTRUCTION
| Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km | Fresh | Deferred: Complete items below and revert offline - Reconcile materials list with materials HotDesk and EST - Review work distribution to vendors equitably. | Deferred | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 69,057.09 N 19,127,794.00 F$ 119,459.71 |  |  |  |  | Nil |  | PECKON NIGERIA
| Sectional Replacement Of IMOR Well 32L & GLL Flowlines | Fresh |  |  | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 8,876.10 N 2,214,970.80 F$ 14,712.65 | [5 empty] | Nil |  | ADLAND PROJECTS
| Sectional Replacement Of IMOR4- Inch Delivery Line/57GLL/36S/22S | Fresh |  |  | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 48,732.29 N 14,993,395.11 F$ 88,240.58 | [5 empty] | Nil |  | GAMSTEC INTEGRATED
| DBCU W12T Flowline Replacement (4" Sch 80 x 5km) | Fresh | Deferred: Complete items below and revert offline - Reconcile materials list with materials HotDesk and EST - Review work distribution to vendors equitably. | Deferred | Azaka, G | NIL |  | $ 337,588.93 N 127,747,467.01 F$674,209.40 |  |  |  |  | Nil |  | MIDEN SERVICES
| FORC 126S Flowline Replacement (6” sch 80 x 1.2 km) | Fresh | Deferred: Complete items below and revert offline - Reconcile materials list with materials HotDesk and EST - Review work distribution to vendors equitably. | Deferred | Orji, C | C.NG.PAE.DL.21.001 |  |  | $ 132,054.33 N 48,500,624.65 F$ 259,687.56 |  |  |  | Nil |  | STEVE INEGRATED
| Rehabilitation of 800m failed sections of Obigbo flow station road. | Fresh | Deferred: Complete item below and revert offline - Engage the Asset team to get confirmation from divestment BOM on the execution of this project | Deferred | Ezenduka, D | C.NG.PAE.IC.21.001 |  |  |  | F$: 429,307.22 |  |  | F$: 29,844.89 | 6.5 % LOP Discount | BENCOV NIG
| GENERAL |  | All submissions are be subject to DRB approval EST to share a standard hook up arm materials list template to all
2021-01-28 | Sectional Replacement of Afam 25T Flowline (8” x 12m) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Engage Asset team, EST, HSE, Technical Safety and Security teams to review and sign off method statement. II. Include clamping as a mitigation against spill in the 5 top risks | Conditional Approval | Akinbiyi, A | O.NG.PAE.I1F.FAC.724FC | $ 27,733.14 + 35,712.58 N 46,114,670.79 + 11,048,655.19 F$ 149,247.42 + 64,826.30 | [5 empty] | Nil |  | BG TECHNICAL NIG LTD
| Rehabilitation of 800m failed sections of Obigbo flow station road. -Resubmission | Resubmission | Approved. WORP steers from previous sitting 21-01-21 have been incorporated. | Approved | Ezenduka, D | 110854 |  |  |  | F$: 429,307.22 |  |  | F$: 29,844.89 | 6.5 % LOP Discount | BENCOV NIG
| Addendum to Construction of 1 No. Well bay location Assa-North | Fresh | Approved. I. Resolve ACV balance in SAP II. Update 5 top risks to include Covid19 | Approved | Ezenduka, D | C.NG.ANO.DG.17.004.1231 |  |  |  | F$: 144,200.22 |  |  | F$: 7,589.49 | 5 % LOP Discount | RAFFOULNIG.LIMITED
| FORC 126S Flowline Replacement (6” sch 80 x 1.2 km) -Resubmission & Reviewed Offline | Resubmission | Approved. WORP steers from previous sitting 21-01-21 and 28-01-21 have been incorporated. | Approved | Orji, C | C.NG.PAE.DL.21.001 |  |  | $ 132,054.33 N 48,500,624.65 F$ 259,687.56 |  |  |  | Nil |  | HENSTEEL ENGINEERING
| Sectional Replacement of ImoR Well 32L & GLL | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Update cost saving column with proposed cost savings. II. Reconcile materials list with Hotdesk and expunge cost of available materials from cost estimate. | Conditional Approval | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 8,876.10 N 2,214,970.80 F$ 14,712.65 | [5 empty] | Nil |  | ADLAND PROJECTS
| Sectional Replacement of (a) ImoR 4-inch Delivery line (b) ImoR 57GLL (c) ImoR 36S (d) ImoR 23L (e) ImoR 14L (f) ImoR 6-inch Bulkline (g) ImoR 63T Manifold | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Update cost saving column with cost saved from inter-field move. II. Reconcile materials list with Hotdesk and expunge cost of available materials from cost estimate. | Conditional Approval | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 48,732.29 N 14,993,395.11 F$ 88,240.58 | [5 empty] | Nil |  | GAMSTEC INTEGRATED
| Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km -Resubmission & Reviewed Offline | Resubmission | Approved. WORP steers from previous sitting 21-01-21 have been incorporated. | Approved | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 72,553.73 N 5,439,173.57 F$ 86,886.20 |  |  |  |  | Nil |  | ABBEYCOURT ENERGY
| DBCU W12T Flowline Replacement (4" Sch 80 x 4.8km) -Resubmission & Reviewed Offline | Resubmission | Approved. WORP steers from previous sitting 21-01-21 have been incorporated. | Approved | Azaka, G | NIL |  | $ 324,004.09 N 121,078,352 F$727,442.65 |  |  |  |  | Nil |  | MIDEN SERVICES LTD
2021-02-04 | BONNY WELL 12S & OLOMA FS LIGAMENT VALVES CHANGE -OUT | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Update WBS for this activity. II. Attach an approved e-AEWR. III. Ensure all equipment have valid premob certificates. IV. Specify crew boat type in the cost estimate. V. Ensure detailed security plan review. VI. Update OP’19 to OP’20 in the submission | Conditional Approval | Ehizoyanyan, O | NIL |  | $ 17,399.52 N 2,002,876.74 F$ 22,677.19 |  |  |  |  | Nil |  | SURVEILLANCE 2000
2021-02-11 | Saghara 3S and 5L Flowline Replacement – 4” Sch. 40 x 850m Each (Total = 4” Sch. 40 x 1.7km) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Include fabrication of hook up arm in the work scope. II. Expunge CP survey and balancing from cost estimate. III. Expedite materials availability check with Hotdesk IV. Engage PS for a review of cost estimate. | Conditional Approval | Uwaezuoke, D | O.NG.PBW.SHF.03S.713FL/O.NG.PBW.SHF.05L713FL |  |  | $ 211,509.27 N 77,405,267.22 F$ 415,475.72 |  |  |  | Nil |  | ANASAMI
| Sectional Replacement of (a) ImoR 59T (6-inch) (b) ImoR 25L (4-inch) | Fresh | Approved. I. Include line length in the Project Title | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 12,297.25 N 3,357,092.47 F$ 21,143.34 | [5 empty] | 8280.04 | THERE IS A SAVINGS OF 8,280.04 USD WHICH SHOULD HAVE COVERED MOB & DEMOB USING A NEW CONTRACTOR | GAMSTEC INTEGRATED
| Full Replacement of ImoR 58T (4- inch x 3.4km) | Fresh | Approved. | Approved | Aderiye, A | C.NG.PAE.DL.21.001 | $ 110,900.38 N 26,084,203.78 F$ 179,633.46 | [5 empty] | 12508.36 | THERE IS A SAVINGS OF 12,508.36 FROM THE MATERIALS THAT WILL BE COLLECTED FROM THE SPDC WAREHOUSE | THOMPSON AND GRACE
| Sectional Replacement of Afam 25T flowline (8” x 12m) -Resubmission & reviewed offline | Resubmission | Approved. WORP steers from previous sitting 28/01/21 have been incorporated. | Approved | Dienagha, I | O.NG.PAE.I1F.FAC.724FC | $ 30,998.84 + 35,712.58 N 52,409,398.79 + 11,048,655.19 F$ 169,100.02 + 64,826.30 | [5 empty] | Nil |  | GAMSTEC INTEGRATED
| GENERAL |  | Ensure all cost are independently assured by PS. • Advise the team on when to commence movement of bare pipes to coating vendors (SOLEWANT & PCN). • Confirm availability of coated pipes from stockist. • Send sample of disused spool piece from Saghara 3S & 5L to MCI for analysis. • Expunge CP survey and balancing from cost estimate and where necessary, reports should be provided for documentation • Early request for Houseboat to the marine team • Ensure kickoff meetings are held prior mobilizations.
2021-02-18 | : LOCATION DREDGING WORKS AT BENISEDE EAUA-2. | Fresh | Approved. I. Liase with OABP focal persons to confirm ETC/OTC availability. | Approved | Onyejekwe, C | C.NG.AFS.DD.19.009.9401 |  |  |  | $: 103,003.11 N: 267,683,624.79 F$: 808,361.80 |  |  | F$: 115,543.79 | Low Oil Price LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| FULL REPLACEMENT OF OGUTA 16S FLOWLINE (4” X 2.9KM) | Fresh | NOT TREATED |  | Akinbiyi, A | 102155 | $ 91,808.64 N 26,740,513.71 F$ 179,482.45 | [5 empty] | Nil |  | MORRAY SERVICES
| FULL REPLACEMENT OF OGUTA 25T FLOWLINE (4” X 5.6KM) | Fresh | NOT TREATED |  | Akinbiyi, A | 102155 | $ 227,072.62 N 51,829,929.49 F$ 363,646.87 | [5 empty] | Nil |  | GESON INVESTMENT
| FULL REPLACEMENT OF OGUTA 12T FLOWLINE (4” X 4.3KM) | Fresh | NOT TREATED |  | Akinbiyi, A | 102155 | $ 140,649.15 N 17,728,986.10 F$ 187,365.85 | [5 empty] | Nil |  | ABBEYCOURT
| INTEGRITY CHECK OF AGBADA 67T GAS LINE | Fresh | Conditional Approval Update and resubmit upon completion of these conditions: I. Update WBS for this activity. II. Formal engagement with the Pipeline Contract Holder and review contract line items. III. Review work method statement with the vendor IV. Recourse option of engaging a flowline vendor to manage the overall activity. | Conditional Approval | Dienagha, I | NIL | $ 47,136.48 N 76,378,129.79 F$ 248,131.56 | [5 empty] | Nil |  | BG TECHNICAL
| BONNY W30T Flowline Replacement (4" Sch 80 x 1km) | Fresh | Deferred. I. Stepped down for a proper internal review by Project Lead. | Stepped Down | Azaka, G | NIL |  | $ 104,781.24 N 38,486,464.52 F$206,194.85 |  |  |  |  | Nil |  | VANDRESSER NIG
| Tunu CDRY-3 Flowline Construction (6" x 2.1km) & Tunu CDRY-4 Wellhead Platform Installation and hookup | Fresh | Approved. I. Update cost saving column with the proposed cost savings. II. Liase with C&P to affirm benchmark rates | Approved | Azaka, G | C.NG.AFS.DF.19.003.1200 |  |  | $324,929.80 N 118,704,995.67 F$ 637,697.73 |  |  |  | Nil |  | IKONIBO NIG
| Replacement of 1,75KM of 2” water equalization of Soku cluster D | Fresh | Deferred. I. Provide and attach basis for the additional 1.75km scope. II. Engage EST & Geomatics for a proper review III. Review and simplify execution strategy. | Deferred | Obioakor, O | NIL |  | $ 225,297.74 N 13,915,985.80 F$ 261,967.01 |  |  |  |  | Nil |  | HENZOL, KEMUD, VISCA
| FULL REPLACEMENT OF IMOR 58T (4-INCH x 3.4KM) | Fresh | Approved. I. Proceed to execution with the proposed new vendor (WILKRISS NIG. LTD) II. Ensure the MoM and offer decline letter from Thompson & Grace Investment Ltd is duly signed for documentation | Approved | Aderiye, A | C.NG.PAE.DL.21.001 | $ 137,763.36 N 12,884,978.45 F$ 179,633.46 | [5 empty] | 14800 | Warehouse Materials | WILKRISS
| SAGHARA 3S & 5L FLOWLINE REPLACEMENT – 4” Sch. 40 x 850m each (Total = 4” Sch. 40 x 1.7km). Resubmission & Reviewed offline | Resubmission | Approved. WORP steers from previous sitting 11/02/21 have been incorporated | Approved | Uwaezuoke, D | O.NG.PBW.SHF.03S.713FL/O.NG.PBW.SHF.05L.713FL |  |  | $ 204,508.67 N 74,834,367.87 F$ 401,700.68 |  |  |  | Nil |  | ANASAMI CONSTRUCTION
2021-02-25 | BONNY W30T Flowline Replacement (4" Sch 80 x 1km) | Resubmission | Conditional Approval. WORP steers from previous sitting 18/02 have not been fully incorporated. I. Engage WRFM to provide WBS for this activity and resubmit offline | Conditional Approval | Azaka, G | NIL |  | $ 101,126.24 N 37,144,159.42 F$199,002.81 |  |  |  |  | Nil |  | VANDRESSER NIG
| OTUMARA FLOW STATION GANTRY WORKS | Fresh | Deferred. I. Update WBS for this activity. II. Engage EST to review existing structural frame and attach schematic drawing. III. Confirm Gantry maximum load. | Deferred | Azaka, G | NIL |  |  | $ 187,308.06 N 6,577,567.94 F$206,814.41 |  |  |  | Nil |  | NAPEBI CONSTRUCTION
| KOCR 22T Flowline Sectional Replacement – 4” sch. 40 x 0.06km and 8” Sch 160 x 0.012km | Fresh | Approved. I. Forward approved e-WR to the Secretariat and Manager. II. Plan for mitigation against Vendors under performance due to low project cost. | Approved | Arowosafe, T | O.NG.PAE.GBG.FAC.724FC |  | $ 55,973.34 N 4,979,690.78 F$ 69,,095.05 |  |  |  |  | Nil |  | ABBEYCOURT ENERGY
| K2S Simultaneous Flow Project | Fresh | Approved. I. Engage CH to update ACV split currency values. II. Carry out materials check with Hotdesk. III. Emphasize criticality of this activity with the Vendor. | Approved | Akoma, I | C.NG.PBE.DF.21.005 |  | $ - 104,725.16 N - 36,794,719.22 F$ - 201,680.94 |  |  |  |  | F$: 22,416.83 | Savings on Mob and De-mob by using same contractor for Mechanical/ Instrumentation works, etc | GRAMEN PETROSERVE
| Replacement of LP header of Yokri flow station. -Reviewed offline | Fresh | Approved | Approved | Obiakor, O | O.NG.PCW.YKF.FAC.71300 |  |  | $ 31,865.72 N 375,865.72 F$ 32,854.55 |  |  |  | 23907.23 | saved for combining mobilization of Forcados Yokri 127T flowline sectional replacement and replacement of Yokri LP header | TONYMAR INVESTMENT
| GENERAL |  | Review materials reconciliation tracking system and communicate to leadership: ▪ Flowlines ▪ Facilities
2021-03-04 | FODPA and NEFS Boatlanding Rehabilitation Works | Fresh | Approved. I. Confirm full budget availability for these activities. II. Carry out materials reconciliation with Hotdesk. III. Ensure security plan is properly reviewed and assurance provided for adequate cover at site | Approved | Uwaezuoke, D | F$: C.NG.PBW.DF.212.001 – FODPA F$: C.NG.PCW.DF.98.706.1230 - NEFS |  |  | Total: FODPA + NEFS = F$394,395.64 |  |  |  | Nil |  | Gramen Petroserve
| FULL REPLACEMENT OF OGUTA 12T FLOWLINE(4” X 4.3KM) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Confirm WBS for this activity. II. Carry out materials reconciliation with Hotdesk and discount available materials. III. Update Project Schedule to current plan. IV. Include Fabrication & Hook up in the scope summary. V. Confirm linepipes availability for this activity. VI. Align POB requirement with OABP Central Team | Conditional Approval | Akinbiyi, A | 102155 | $ 132,486.76 N 37,684,516.42 F$ 231,787.20 | [5 empty] | Nil |  | WILKRISS
| FULL REPLACEMENT OF OGUTA 16S FLOWLINE(4” X 2.9KM) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Confirm WBS for this activity. II. Carry out materials reconciliation with Hotdesk and discount available materials. III. Update Project Schedule to current plan. IV. Include Fabrication & Hook up in the scope summary. V. Confirm linepipes availability for this activity. VI. Align POB requirement with OABP Central Team | Conditional Approval | Akinbiyi, A | 102155 | $ 91,808.64 N 26,740,513.71 F$ 179,482.45 | [5 empty] | Nil |  | MORRAY SERVICES
| FULL REPLACEMENT OF OGUTA 25T FLOWLINE(4” X 5.6KM) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Confirm WBS for this activity. II. Carry out materials reconciliation with Hotdesk and discount available materials. III. Update Project Schedule to current plan. IV. Include Fabrication & Hook up in the scope summary. V. Confirm linepipes availability for this activity. VI. Align POB requirement with OABP Central Team | Conditional Approval | Akinbiyi, A | 102155 | $ 165,827.86 N 46,524,990.84 F$ 288,423.35 | [5 empty] | Nil |  | GUIZ AND COMPANY
| LEAK REPAIR OF FORCADOS 127T FLOWLINE | Fresh | Approved. I. Engage WRFM to confirm WBS for this activity. II. Update Project title to include “Optimization of Line size” III. Update Project Schedule to current plan. | Approved | Obiakor, O | 102155 |  |  | $ 47,933.39 N 1,545,750.79 F$ 52,006.51 |  |  |  | F$39,515.51 | Mob and De-mob, Houseboat | TONYMA INVESTMENT
| SECTIONAL REPLACEMENT OF OTUMARA 42LS, 16T FLOWLINES AND FABRICATION OF HOOK-UP ARM OF OTUMARA 4L. | Fresh | Approved. I. Carry out materials reconciliation with hotdesk and discount available materials. | Approved | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  |  | $ 160,601.21 N 61,143,932.41 F$ 321,718.29 |  |  |  | F$82,000 & F$77,000 | F$82,000 (Shared marine logistics) + F$77,000 (Single mob/demob) | ANASAMI
| Diebu Creek 8T Flowline Replacement – 4” x 3.07km | Fresh | Stepped down by the team | Stepped down | Ehizoyanyan, O | WRFM 102155 |  | $228,572.93 N 83,941,422.41 F$449,762.45 |  |  |  |  | Nil |  | SEVOIL LTD
| BONN 12S Flowline Replacement – 4” x 1.7km | Fresh | Stepped down by the team | Stepped down | Ehizoyanyan, O
| BONNY W30T Flowline Replacement (4" Sch 80 x 1km) -Resubmission & Reviewed offline | Resubmission & Reviewed Offline | Approved. WORP steer from previous sitting 25/02/21 have been incorporated. | Approved | Azaka, G | NIL |  | $ 101,126.24 N 37,144,159.42 F$199,002.81 |  |  |  |  | Nil |  | VANDRESSER NIG
| GENERAL |  | Ensure timely checks on materials availability prior to WORP submission. • Only funded activities should be brought into plan and ensure alignment of execution with IAP central team. • Proper security plan review / HSE documentation for each project before mobilization. • Early engagement on marine request to avoid delayed mobilization to sites.
2021-03-11 | UZU MANIFOLD LOCATION PREPARATION | Fresh | Approved. I. Limit PO value to the contractor to available ACV balance in SAP. II. Engage C&P to update remaining ACV III. Ensure combination of controls is in place for managing community workers. IV. Liase with the planning team to align schedule & demand requirements for IAP | Approved | Oludare, S | P.NG.PAE.DG.17.001 |  |  |  | F$: 2,037,279.64 (N: 473,610,898.60, $: 789,293.09) |  |  | F$:107,225.24 | 5 % LOP Discount | RAFFOUL NIG. LIMITED
| FORC 111T Flowline Replacement (6" sch 40 x 2.7 km bulkline) & (4" sch 40 x 0.25 km flowline) | Fresh | Approved. I. Ensure combination of controls is in place for managing community workers. II. Decomit previously issued PO for Forcados 126S before issuing the new PO for 111T to the Vendor. III. Update Project Schedule to current plan. | Approved | Orji, C | C.NG.PAE.DL.21.001.1230 |  |  | $ 251,239.91 N 92,278,553.00 F$ 494,398.16 |  |  |  | 33891.12 | From Materials to be taken from Hot Desk | HENSTEEL ENGINEERING
| FULL REPLACEMENT OF IMOR 36L (4-INCH x 1.0 KM) | Fresh | Approved. I. Carry out proper material reconciliation with hotdesk. | Approved | Aderiye, A | C.NG.PAE.DL.21.001 | $ 47,000.69 N 11,269,553.88 F$ 76,696.49 | [5 empty] | F$: 12,500 | MATERIALS FROM THE SPDC WAREHOUSE. | ROMEK AND COMPANY
| SECTIONAL REPLACEMENT OF (a) IMOR 4-inch TEST LINE (48M) (b) IMOR RIVER 26S (48M) © IMO RIVER 44S (48M) (d) IMO RIVER 55S (48M) (e) IMO RIVER 43T (48M) (f) IMOR 60T (48M) | Fresh | Approved. I. Prompt engagement with Asset PUM’s to provide enhanced security surveillance for these lines. II. Update Project Schedule to current plan. | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 35,160.13 N 10,617,977.01 F$ 63,138.99 | [5 empty] | FS11,525.18 | MOB & DEMOB. ALL MATERIALS FOR THESE SECTIONAL REPLACEMENT SHALL BE SOURCED FROM SPDC WAREHOUSE | GAMSTEC
| SECTIONAL REPLACEMENT OF (a) IMOR RIVER 6-INCH BULKLINE (IMO 2 -1) X 1500 M (Additional leak points) | Fresh | Approved. | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 17,777.50 N 5,370,063.42 F$ 31,927.86 | [5 empty] | 8,280.04 USD | MOB & DEMOB IF USING A NEW CONTRACTOR | GAMSTEC
| Diebu Creek 8T Flowline Replacement – 4” x 3.07km | Fresh | Conditional Approval. Subject to NAPIMS engagement on contract expiration date extension. | Conditional Approval | Ehizonyan, O | O.NG.PBE.DBC.09T.713FL |  | $238,624..58 N 87,632,760.32 F$469,540.94 |  |  |  |  | Nil |  | SEVOIL LTD
| FULL REPLACEMENT OF ETELEBOU 3S FLOWLINE (4” X 1.2KM) | Fresh | Approved: Premised on early mobilization. I. Update contract end date and engage NAPIMS. II. Forward cost savings to I&A for documentation. | Approved | Otavie, G | O.NG.PAE.ETL.03S.713FL |  | $ 57,925.84 N 13,410,314.07 F$ 85,626.42 |  |  |  |  | Nil |  | PECKON NIGERIA
| BONNY W18S Flowline Replacement (4" Sch 40 x 1.2km) | Fresh | Conditional Approval. I. Carry out work distribution alignment across team. II. Confirm Contractors capacity to execute | Conditional Approval | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  | $ 133,308.68 N 48,964,351.92 F$262,332.00 |  |  |  |  | Nil |  | IKONIBO
| Provision of lay barge for installation of CCUs at Kanbo W5L/S -Reviewed Offline | Fresh | Approved. | Approved | Ehizonyan, O | C.NG.AFS.DF.18.025.1202 |  |  | $ 22,320.8 N 602,305.87 F$ 23,907.9 |  |  |  | F$: 10,062.00 | Shared marine logistics and security deployment | HENZOL GLOBAL
2021-03-18 | Replacement of 1,75KM of 2” water equalization of Soku cluster D | Resubmission | Conditional Approval. WORP steers from previous sitting 18/02/21 have been incorporated. Further steers: I. Attach signed MoM of review meeting held with EST & Geomatics. II. Update WBS for this activity. III. Engage vendor & secure commitment to execute work accordingly. IV. Liase with C&P to load contract in SAP. | Conditional Approval | Obiakor, O | Nil |  | $ 107,282.92 N 39,409,715.49 F$211,129.34 |  |  |  |  | Nil |  | VANDREZZER NIG. LTD
| BOGT SHORE PROTECTION – PHASE1 | Fresh | Approved. I. Focused attention on vendor HSE risk management before and during site works. II. Review & accelerate project schedule. III. Proceed with interim plan to safeguard shoreline before actual work execution. IV. Kick off meeting to include Vendor top management in view of the nature of work. | Approved | Ogunkunle, M | C.NG.PBE.IC.07.001 |  |  |  | F$ 875,727.01 N69,244,408.04 + $693,264.80 |  |  | Nil |  | PILE FOUNDATION LIMITED
| Seibou 3 and 4 bulkline JIV and clamping. -Reviewed offline | Fresh | Approved. I. Update project schedule to current plan | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $ 27,976.94 N 511,967.62 F$ 29,326.00 |  |  |  | 9050.71 | cost saving on inter-area move instead of mobilizing a new contractor. | HENZOL GLOBAL
| GENERAL |  | Engage the relevant authorities with proposal to include equalization lines in FIMS for ease of line tracking and integrity monitoring.
2021-03-25 | Bonny W14 Maintenance Dredging works | Fresh | Approved. I. Reiterate the responsibility of the main contractor despite invoice partnering option. II. Ensure safe work completion before contract expiration date. III. Update project schedule to align with current plan IV. 5no top risk to include “Interface management risk” V. Align cost breakdown descriptions with cost summary sheet. VI. Ensure proper HSE & Security plan review. VII. Kick off meeting to emphasize Covid’19 protocols at site. | Approved | Onyejekwe, C | 110744 |  |  |  | $: 428,558.82 N: 192,570,123.89 F$: 935,989.97 |  |  | F$: 56,227.33 | Cost saving is from Low Oil Price LoP discounts (i.e. 7.5%). | SHORELINE DREDGING
| Bonny W13 Maintenance Dredging works | Fresh | Approved. I. Reiterate the responsibility of the main contractor despite invoice partnering option. II. Ensure safe work completion before contract expiration date. III. Update project schedule to align with current plan IV. 5no top risk to include “Interface management risk” V. Align cost breakdown descriptions with cost summary sheet. VI. Ensure proper HSE & Security plan review. VII. Kick off meeting to emphasize Covid’19 protocols at site. | Approved | Onyejekwe, C | 110744 |  |  |  | $: 412,055.67 N: 188,667,970.36 F$: 909,204.47 |  |  | F$: 54,055.53 | Cost saving is from Low Oil Price LoP discounts (i.e. 7.5%). | SHORELINE DREDGING
| Enwhe East Flare Test Pit and Bundwall Construction Work | Fresh | Approved. I. Capture cost savings and forward to I&A for reporting. II. Update project schedule to align with current plan III. Update appropriately the remaining ACV for this submission. | Approved | Otavie, G | C.NG.LNG.DG.19.004.1230 |  | $ 54,465.13 N 113,596,678.73 F$ 353,797.61 |  |  |  |  | Nil |  | Gramen Petroserve
| Enwhe West Flare Test Pit and Bundwall Construction Work | Fresh | Approved. I. Update project schedule to align with current plan. II. Update appropriately the remaining ACV for this submission III. Ensure vendor has adequate resources to deliver according to schedule. | Approved | Uwaezuoke, D | C.NG.LNG.DG.19.004.1230 |  | $ 49,888.81 N 95,735,716.20 F$ 302,156.84 |  |  |  |  | Nil |  | Gramen Petroserve
| Estuary Cluster 51 Ring A Replacement Work ahead of FORC73 Workover | Fresh | Approved. I. Ensure safe work completion before contract expiration date. II. Update project schedule to align with current plan. III. Harmonize project title with other relevant documentation. | Approved | Uwaezuoke, D | O.NG.STG.PBE.FOR.072FL |  |  | $ 102,377.04 N 26,433,707.21 F$ 172,031.08 |  |  |  | Nil |  | Miden Systems Ltd
| Kanbo 5LS TRP Outage surveillance cover. | Fresh | Approved. I. Vendor to deploy adequate resources for security surveillance. | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $ 31,947.75 N 372,012.45 F$ 32,928.02 |  |  |  | Nil |  | HENZOL GLOBA
| Kanbo W7S (6’’ x 0.1Km) & W6T (6’’ x 0.1Km) Flowline Sectional Replacement | Fresh | Deferred. I. Liase with C&P to update remaining ACV for this activity. II. Update summary description of cost saving initiative. | Deferred | Otavie, G | O.NG.STG.PBE.KAN.007FL O.NG.STG.PBE.KAN.006FL |  |  | $ 122,276.73 N 3,736,362.47 F$ 132,122.22 |  |  |  | F$: $20,000 | Elimination of Mob and De-mob of Houseboat, by latching onto existing houseboat already in Tunu | FEIMA
| FORC 110T & FORC 112T Integrity Checks | Fresh | Deferred. I. Liase with C&P to update remaining ACV for this activity | Deferred | Orji, C | C.NG.PCW.DL.21.001 |  |  | $ 64,269.17 N 1,986,542.12 F$ 69,503.80 |  |  |  | Nil |  | TUSOJA MARINE
| Tunu BQRT-3 Flowline Replacement (6" SCH 80 x 6.1km) | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Carry out material reconciliation with hotdesk. II. Update 5no top risk to include “Interface management risk” III. Update summary | Conditional Approval | Otavie, G | C.NG.AFS.DL.19.006.1230 |  |  | $ 306,292.32 N 117,178,807.88 F$ 615,063.88 |  |  |  | F$: 20,000 | Campaign mobilization will enable the sharing of Marine logistic resources like houseboat which are already in the field | SEVOIL & OSAKS INTEQ
| GENERAL |  | Escalate security challenges in Kanbo and Seibou axis to Security LT.
2021-04-01 | FORC 110T & FORC 112T INTEGRITY CHECKS | Resubmission | Approved. I. Update Contractor’s name with the correct spelling in the submission. II. Include value proposition (bopd) for both lines. III. Indicate all the WBS provided for this project and charge each flowline cost to specific WBS provided IV. Review and update risk No3 in the top risks. | Approved | Orji, C | O.NG.STG.PBE.FOR.110FL |  |  | $ 64,269.17 N 1,986,542.12 F$ 69,503.80 |  |  |  | Nil |  | ELKON INTEGRATED
| TUNU BQRT-3 Flowline Replacement (6" Sch 80 x 6.1km) -Resubmission & Reviewed offline | Resubmission | Approved. WORP steers from previous sitting 25/03/21 have been incorporated. | Approved | Otavie, G | C.NG.AFS.DL.19.006.1230 |  |  | $ 304,115.16 N 116,379,232 F$ 610,779.8 |  |  |  | F$: 20,000 F$: 4,284.08 | House boat sharing and materials discounted | SEVOIL & OSAKS INTEQ
| BONNY W18S Flowline Replacement (4" Sch 40 x 1.2km) -Resubmission & Reviewed offline | Resubmission | Approved. WORP steers from previous sitting 11/03/21 have been incorporated. | Approved | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  | $ 132,180.84 N 48,550,109.36 F$260,112.61 |  |  |  |  | Nil |  | IKONIBO NIG
| GENERAL |  | Always ensure equitable work allocation.
2021-04-08 | SECTIONAL REPLACEMENT OF (a) IMOR RIVER 6-INCH BULKLINE (IMO 2 -1) X 800 M (Additional leak points) (b) IMOR RIVER 26S (300 M) © IMO RIVER 60T (2200M) | Fresh | Deferred. I. Evaluate all additional work scope for each conduit, hold an alignment meeting with the Vendor and attach MoM to the resubmission. | Deferred | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 36,849.85 N 11,959,792.85 F$ 68,364.45 | [5 empty] | 8,280.04 USD | MOB & DEMOB USING A NEW CONTRACTOR. | GAMSTEC INTEGRATED
| GENERAL |  | Engage Asset team to provide enhanced security surveillance for these lines.
2021-04-15 | AFAM VI VENT GATHERING PROJECT | Fresh | Conditional Approval. I. Update value of work order in split currency. II. Include security risk in the 5nos top risks. III. Attach email confirmation of materials reconciliation carried out with Hotdesk. IV. Confirm and document contractor’s readiness and capability to mobilize according to schedule. V. Engage C&P to provide steers on the provision of accommodation by the contractor at site. | Conditional Approval | Dienagha, I | C.NG.PCE.NO.21.004 | USD 88,709.22 NGN 8,425,414.35 F$: 111,835.53 | [5 empty] | F$: 7,824.72 | (Nonstock materials) | ADVANCED COATING TECH
| SCAFFOLDING OKGP DRYER PROJECT | Fresh | Conditional Approval. I. Update value of work order in split currency. II. Liaise with C&P to seek support on the proposed mode of payment to the contractor. III. Engage BSU to confirm budget availability for this activity. | Conditional Approval | Ewenike, M | C.NG.PCE.NO.21.004 | NGN 3,111,284.44 USD 4,372.58 F$: 14,582.31 | [5 empty] | NIL |  | GRAMEN PETRO-SERV
| CRACK REPAIR OF SOKU GP AG2 TURBINE EXHAUST COLLECTOR | Fresh | Approved. I. Engage Contract Holder to confirm adequate ACV ceiling for this activity. II. Update Project title to properly describe activity. | Approved | Obiakor, O | O.NG.PBE.SKG.FAC.72FC |  | $ 8,346.46 N 6,773171.82 F$26,194.08 |  |  |  |  | NIL |  | GRAMEN PETRO-SERV
| GENERAL |  | Engage NAPIMS to discuss Mechanical modification contracts. • Expedite action on ceiling increase and time extension for GRAMEN PETRO-SERVE contract. • Liase with C&P to resolve contract ACV split value issues and revert to Manager.
2021-04-22 | AFAM VI VENT GATHERING PROJECT - Resubmission | Resubmission | Approved. WORP steers from previous sitting 15/04/21 have been incorporated. I. Proceed to execution and follow through on steers from C&P. | Approved | Dienagha, I | C.NG.PCE.NO.21.004 | USD 88,709.22 NGN 8,425,414.35 F$: 111,835.53 | [5 empty] | 7824.72 | (Nonstock materials) | ADVANCED COATING TECH
| DELETED SEs FOR OPUKUSHI 2T FLOWLINE REPLACEMENT - Resubmission | Resubmission | Approved. I. This payment is for provision of services rendered in 2019. Invoice could not be provided by the Vendor due to their internal constraints. II. This P.O is to enable creation of S.E for invoice payment. | Approved | Ehizoyanyan, O | C.NG.PCW.DL.21.001.1230 |  |  | $ 10,983.23 N 4,041,941.25 F$ 21,633.93 |  |  |  | NIL |  | VANDREZZER ENERGY SERVICES
| SECTIONAL REPLACEMENT OF (a) IMOR RIVER 6-INCH BULKLINE (IMO 2 -1) X 800 M (Additional leak points) (b) IMOR RIVER 26S (300 M) © IMO RIVER 60T (1850M) (d) IMO RIVER 32L/GLL (e) IMO RIVER 4-INCH BULKLINE (f) IMO RIVER 57GLL (g) IMO RIVER 36S (h) IMO RIVER 63T (i) IMO RIVER 4-INCH TEST LINE - Resubmission | Resubmission | Approved. WORP steers from previous sitting 15/04/21 have not been fully incorporated. I. Ensure C&P and PS participation in the alignment meeting with the contractor and document MoM to WORP secretariat. | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 38,413.62 N 12,943,786.38 F$ 72,521.09 | [5 empty] | NIL |  | GAMSTEC INTEGRATED
| SECTIONAL REPLACEMENT OF AFAM 27T FLOWLINE (8” x 12m) | Fresh | Approved | Approved | Akinbiyi, A | O.NG.PAE.I1F.FAC.724FC | $ 30,177.06 + 98,171.47 N 51,406,830.37 + 2,393,303.75 F$ 165,636.43 + 104,477.93 | [5 empty] | F$: 11,596.18 | Mob and De-mob from the two Contractors | GAMSTEC INTEGRATED
| ESTUARY CLUSTER 9 RING AND 2 Nos. BULKLINE RISER REPLACEMENT WORK. | Fresh | Approved | Approved | Uwaezuoke, D | C.NG.PBW.DF.212.001 |  |  | $ 119,090.63 N 31,814,175.20 F$ 202,922.45 |  |  |  | NIL |  | Miden Systems Limited
| SECTIONAL REPLACEMENT OF NKALI 10S – (4” Sch.80 X 120M) NKALI 13L – (4” Sch.80 X 120M) NKALI 13S – (4” Sch.80 X 120M) | Fresh | Approved. I. Reference percentage of commitment to date as part of the reasons for choice of contractor. | Approved | Aderiye, A | O.NG.PAE.NKF.FAC.724FC | $ 41,624.94 N 4,030,118.50 F$ 52,244.49 | [5 empty] | FS 22,162.92 | MOB & DEMOB BY USING ONE CONTRACTOR TO EXECUTE THE REPAIRS OF THE THREE (3) FLOWLINE REPAIRS. | WILKRISS NIGERIA
| NUN RIVER WELL 13T MAINTENANCE DREDGING WORKS. | Fresh | Approved | Approved | Onjejekwe, C | 110744 |  |  |  | $: 391,403.14 N: 225,529,048.35 F$: 985,682.59 |  |  | F$: 111,908.44 | Cost saving is from Low Oil Price LoP discounts (i.e. 15%). | FW DREDGING LTD
| GENERAL |  | Ensure C&P participation in all alignment meetings with contractors. • Always reference percentage of commitment to date as part of the reasons for choice of contractor. • Document contractor’s performance at site for referencing.
2021-04-29 | LOCATION DREDGING WORKS AT BENISEDE EAUA-2 – ADDITIONAL RIG PAD AREA SAND FILLING WORKS | Fresh | Conditional Approval. Update and revert upon completion of the following: I. Engage PS to finalize review on the estimated volume/cost of additional sandfill works. | Conditional Approval | Onjejekwe, C | C.NG.AFS.DD.19.009.9401 |  |  |  | $: 18,696.66 N: 59,495,875.75 F$: 175,471.03 |  |  | F$: 44,242.44 | Cost saving is from Low Oil Price LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| NUN RIVER DIEBU CREEK BULKLINE TO GBARAN - Civil Structural Scope. | Fresh | Conditional Approval. Update and revert upon completion of the followings: I. Update Project title to appropriately describe activity. II. Forward project MTO to PS for review. III. Engage C&P to review and update omitted contract line items in ARIBA / SAP | Conditional Approval | Ehizoyanyan, O | C.NG.PAE.DL.21.002.1230 |  | $ - 267,723..54 N – 146,066,686.79 F$ - 652,616,00 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| GBARAN 5T FLOWLINE INTEGRITY CHECK | Fresh | Approved. I. In the event of line failure, revert to EST to review the pipe schedule for replacement works | Approved | Okeke, N | C.NG.PAE.DL.21.002.1230 |  | $ 12,158.02 N 3,511,033.32 F$ 21,409.68 |  |  |  |  | NIL |  | THOMPSON AND GRACE LTD
2021-05-06 | CONSTRUCTION OF AIR COMPRESSOR FOUNDATION BAY & SHED AT ESCRAVOS FS FOR THE IG - IA PROJECT – Additional work | Fresh | Approved. I. Update the remaining ACV for this submission II. CH to liaise with C&P and resolve contract ACV split value issues. | Approved | Ehizoyanyan, O | C.NG.PAE.DL.21.002.1230 |  |  | $ - 7,171.22 N – 18,981,937.62 F$ - 57,187.92 |  |  |  | NIL |  | GRAMEN PETROSERVE
| SEIBOU BULKLINE 3 AND 4 JIV - 2ND JIV AND SEIBOU BULKLINE 3 AND 4 JIV - Proposed 3rd JIV. | Fresh | Deferred. I. Engage C&P to support execution strategy and revert. | Deferred | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300 |  |  | $ 75,346.14 N 1,168,966.47 F$ 78,426.42 |  |  |  | NIL |  | TONYMAR INVESTMENT
| BONNY WELL 12S JIV SUPPORT TO THE ASSET TEAM. | Fresh | Approved. I. Update WBS for this activity to Asset account. II. Update the remaining ACV for this submission. | Approved | Ehizoyanyan, O | C.NG.PAE.DL.20.001.1230 |  | $ 14,073.00 N 718,429.33 F$ 15,966.89 |  |  |  |  | NIL |  | SURVEILLANCE 2000 LTD
| APARA 10 BORROW PIT RECLAMATION PROJECT- ADDITIONAL WORK | Fresh | Deferred. I. Secure approval from Divestment finance team to carry out this activity and revert. | Deferred | Agbonsalo, O | O.NG.PAE.OBP.MFC.71300 |  |  |  | $ 89,508.25 N 53,704,949.76 F$ 231,023.27 |  |  | F$: 31,503.17 | Lop,re-negotiated rates | EA TEMILE
| SECTIONAL REPLACEMENT OF IMOR (a) 63T (3-INCH x 80M) – IMO 1 AREA (b) 21S (4-INCH X 24M) – IMO 2 AREA | Fresh | Approved | Approved | Aderiye, A | O.NG.PAE.UCF.FAC724FC | $ 13,612.36 N 3,308,636.05 F$ 23,169.24 | [5 empty] | FS8,282.04 | MOB & DEMOB SINCE THE SAME CONTRACTOR IS ALREADY ON THE SITE | ROMEK AND COMPANY
| LOCATION DREDGING WORKS AT BENISEDE EAUA-2 – ADDITIONAL RIG PAD AREA SAND FILLING WORKS. -Resubmission & reviewed offline | Resubmission & Reviewed offline | Approved. WORP steer from previous sitting 29/04/21 have been incorporated | Approved | Onyejekwe, C | C.NG.AFS.DD.19.009.9401 |  |  |  | $: 18,696.66 N: 59,495,875.75 F$: 175,471.03 |  |  | F$: 44,242.44 | Cost saving is from Low Oil Price LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| GENERAL |  | Forward to ALL the procedure on managing emergency/urgent works. • Harmonize template for standard list of materials for hook up/flowline works and circulate to team.
2021-05-14 | Provision of Engineering support for JIV to SEIBOU bulklines 3 and 4 (Repeat JIV and access new leak points) - Resubmission | Resubmission | Approved. WORP steer from previous sitting 06/05/21 have been incorporated. I. Engage Asset team for an enhanced surveillance cover. | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $ 75,518.29 N 1,188,378.37 F$ 78,649.72 |  |  |  | NIL |  | TONYMAR INVESTMENT
| Deleted SEs for Soku Relocation of Emergency Spill Reponses Caravan, Construction of Chemical Shed and procurement and Installation of Jib Crane | Resubmission | Approved. | Approved | Ehizoyanyan, O | O.NG.PBE.SKF.FAC.724FP |  | $ 136,725.22 N 29,734,583.43 F$ 215,077.218 |  |  |  |  | NIL |  | VANDREZZER ENERGY SERVICES
| Bonny 12S Flowline Replacement – (4” x 1.75km). | Fresh | Approved. I. Engage BSU to provide adequate budget for this activity. II. Ensure linepipe cost is transferred from previous activity to Bonny 12S. III. Provide assurance of Vendors ability to carry out work in this community. IV. Capture cost savings secured from discounting houseboat to the use of hotel accommodation and forward to I&A for documentation. | Approved | Ehizoyanyan, O | C.NG.PAE.DL.21.001.1230 |  | $ 246,444.75 N 6,442,651.14 F$ 263,421.44 |  |  |  |  | NIL |  | JOSBANI CONSTRUCTION
| Repair of cracked 2” sampling line to Atmospheric flare of Soku GP GRU train 3. | Fresh | Conditional Approval. I. Update ACV for this activity. II. Review interim mobilization to “Distance below 100km” and revert with updated cost. | Conditional Approval | Obiakor, O | O.NG.PBE.SKG.FAC.72FC |  | $ 5,043.65 N 3,689,043.98 F$14,764.45 |  |  |  |  | 25456.77 | Cost saving initiative -savings for not doing full mobilization and no demobilization | GRAMEN PETRO-SERV
| GENERAL |  | Proper materials tracking & reconciliation procedure.
2021-05-20 | OTUMARA FLOW STATION GANTRY WORKS -Resubmission | Resubmission | Deferred. WORP steers from previous sitting 25/02/21 have been incorporated. Further steers: I. Engage C&P to review vendor rates and benchmark with PS to ensure process is in line with approved contracting procedures. II. Update risk register to include “Scaffolding” and review procedure with SME in EST prior mobilization. III. Ensure active participation of the Quality team to avoid equipment & materials failure. | Deferred | Azaka, G | C.NG.PBW.IM.17.005.1230 |  |  | $ 224,535.15 N 15,882,943.33 F$266,387.44 |  |  |  | NIL |  | NAPEBI CONSTRUCTION
| TUNU CDRY-3 FLOWLINE CONSTRUCTION -2 days standby | Fresh |  | Deferred | Azaka, G | C.NG.AFS.DF.19.003.1200 |  |  | $3,847.34 N 2,103,075.15 F$ 9,389.04 |  |  |  | NIL |  | IKONIBO NIG LTD
| REPLACEMENT OF CORRODED RISER FORCADOS 127T FLOWLINE. | Fresh | Approved. I. Update contract expiration date. II. Update business case and specify that this activity is different from previously completed work. III. Full adherence to CSSS requirements at site. IV. Always attach QAQC reports to justify additional work submissions. | Approved | Obiakor, O | 102155 |  |  | $ 75,911.23 N 1,393,860.79 F$ 78,425.57 |  |  |  | F$29,515.51 | Mob and De-mob, Houseboat | TONYMA INVESTMENT
| ABRICATION/INSTALLATION OF OBELLE 3L HOOK-UP ARM (a) 3T (3-INCH x 12 M) | Fresh | Approved. I. Update ACV for this activity. II. Always ensure risk assessment is carried out for all submissions prior to WORP submission. III. Update Project Schedule to current plan. | Approved | Aderiye, A | O.NG.PAE.OLF.FAC.724FC | $ 6,007.13 N 1,414,531.68 F$ 9,734.48 | [5 empty] | FS8.801.96 | MOB & DEMOB SINCE THE SAME CONTRACTOR IS ALREADY ON THE SITE | ROMEK
| GENERAL |  | Proper reporting of all non-compliance at sites by HSE inspectors. • Full adherence to CSSS requirements at all OABP sites. • Free-issue materials to be included as savings and differentiated in the remarks.
2021-05-27 | Repair of Cracked 2” sampling line to atmospheric flare of Soku GP GRU Train 3 -Resubmission | Resubmission | Approved. WORP steers from previous sitting 14/05/21 have been implemented. | Approved | Obiakor, O | O.NG.PBE.SKG.FAC.72FC |  | $ 3,669.00 N 2,710,751.95 F$10,811.96 |  |  |  |  | 25456.77 | savings for not doing full mobilization and no demobilization | GRAMEN PETRO-SERV
| Unblocking of Etelebou Test line to Gbaran (6” X 8km Bulk line) - Resubmission | Resubmission | Deferred. WORP steers from previous sitting 25/06/20 have not been fully implemented. Further steers: I. Engage PS to further review cost optimization on Inter area spread and As-built survey. II. Confirm Vendors CAP assessment status. III. Engage hotdesk for materials reconciliation. IV. Prioritize Inventory spill / environmental impact in the 5no top risks. | Deferred | Obiakor, O | C.NG.PCE.NO.21.002.1230 |  | $ 70,330.40 N 20,070,011.95 F$ 126,105.43 |  |  |  |  | NIL |  | ROMEK & COMPANY
| Sectional Replacement of Afam 25T flowline (Additional Work) | Fresh | Approved. I. Always include line length in the project title. | Approved | Akinbiyi, A | O.NG.PAE.I1F.FAC.724FC | $ 40,336.43 N 11,879,588.32 F$ 71,639.69 | [5 empty] | NIL |  | GAMSTEC INTEGRATED
| Gbaran Produced Water Flowline Construction – 6” sch. 40 x 1.72km | Fresh | Deferred. I. Carry out proper corrosion management study to determine required linepipe schedule for this activity. II. Engage hotdesk for materials reconciliation. | Deferred | Arowosafe, T | C.NG.PBE.IM.21.001.1230 |  | $ 76,928.46 N 19,082,949.85 F$ 127,212.92 |  |  |  |  | NIL |  | GUIZ AND COMPANY
| Fabrication and Installation of Ubie 8T Hook Up Arm | Fresh | Approved | Approved | Azaka, G | C.NG.AFS.DF.19.003.1200 |  | $ 643.30 N 225,164 F$ 1,381.55 |  |  |  |  | NIL |  | MORRAY SERVICES
| Enwhe East Miscellaneous Civil Works. | Fresh | Approved. I. Include resource sharing as cost savings and forward to I&A. II. Ensure proper HSE supervision and adequate security cover at site. | Approved | Ebirim, M | C.NG.LNG.17.003.1230 |  |  |  | F$: 219,812.14 |  |  | F$: 15,281.06 | 6.5 % LOP Discount | BENCOV NIG.LIMITED
| GENERAL |  | Shrink Sleeves now available for collection at the warehouse.
2021-06-03 | Sectional Replacement of ImoR 36L (3” x 80m) from Gathering manifold to Inlet manifold. | Fresh | Conditional Approval. Subject to pending resolution of contract time extension by NAPIMS. | Conditional Approval | Aderiye, A | O.NG.PAE.UCF.FAC724FC | $ 10,654.64 N 2,021,999.35 F$ 15,982.70 | [5 empty] | FS6,617.11 | Free Issue materials | ROMEK
| Re-routing of NUNR 3S, 13T, 16T Flowline (4” sch 80 x 1.1km) | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Capture cost savings from shared resources. II. Engage C&P to reconcile ACV figures. | Conditional Approval | Uwaezuoke, D | P.NG.PAE.OP.19.005.9401 |  | $ 248,215.97 N 7,477,220.95 F$ 267,918.80 |  |  |  |  | NIL |  | Tonymar Investment
| Re-routing of NUNR 12LS Flowline (4” sch. 80 x 700m) | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Capture cost savings from shared resources. II. Engage C&P to reconcile ACV figures. | Conditional Approval | Uwaezuoke, D | P.NG.PAE.OP.19.005.9401 |  | $ 183,798.51 N 5,919,883.68 F$ 203,207.96 |  |  |  |  | NIL |  | Surveillance 2000 Limited
| Unblocking of Etelebou Test line to Gbaran (6” X 8km Bulk line) -Resubmission | Resubmission | Approved. WORP steers from previous sitting 27/05/21 have been incorporated. I. Ensure top-level risk of potential spill to the environment and mitigation are well adhered to at site. | Approved | Obiakor, O | C.NG.PCE.NO.21.002.1230 |  | $ 76,114.92 N 20,641,979.95 F$ 133,453.75 |  |  |  |  | NIL |  | ROMEK & COMPANY
| FORC 111T Flowline Replacement (4" sch 40 x 0.411km Additional scope) -Reviewed offline | Fresh | Approved. | Approved | Orji, C | C.NG.PCW.DL.21.001.1230 |  |  | $ 38,383.78 N 14,097,183.85 F$ 75,530.51 |  |  |  | NIL |  | HENSTEEL ENGINEERING
| Otumara flow station Gantry work. -Reviewed offline. | Resubmission | Approved. WORP steers from previous sitting 20/05/21 have been incorporated. | Approved | Azaka, G | C.NG.PBW.IM.17.005.1230 |  |  | $ 82,470.03 N 2,409,002.58 F$88,817.86 |  |  |  | NIL |  | NAPEBI & PECOM
| GENERAL |  | Project Leads to ensure all submissions are reviewed prior WORP sitting.
2021-06-10 | Gbaran Produced Water Flowline Construction – 6” sch. 80 x 1.72km -Resubmission | Resubmission | Approved. WORP steers from previous sitting 27/05/21 have been incorporated. I. Engage NAPIMS for approval to raise P.O. II. Confirm linepipes availability & location. | Approved | Arowosafe, T | C.NG.PBE.IM.21.001.1230 |  | $ 72,928.93 N 17,434,041.54 F$ 115,450.98 |  |  |  |  | NIL |  | GUIZ AND COMPANY
| Re-routing of NUNR 12LS Flowline (4” sch. 80 x 700m) -Resubmission | Resubmission | WORP steers from previous sitting 03/06/21 have been incorporated | Approved | Uwaezuoke, D | P.NG.PAE. OP.19.005.9401 |  | $ 179,829.74 N 5,297,237.66 F$ 192,749.83 |  |  |  |  | F$: 87,447.78 | Shared Resources – houseboat | Surveillance 2000 Limited
| Re-routing of NUNR 3S, 13T, 16T Flowline (4” sch 80 x 1.1km) -Resubmission | Resubmission | WORP steers from previous sitting 03/06/21 have been incorporated. | Approved | Uwaezuoke, D | P.NG.PAE.OP.19.005.9401 |  | $ 241,645.94 N 6,316,713.09 F$ 257,052.56 |  |  |  |  | NIL |  | Tonymar Investment
| Estuary Cluster 51: Installation of Forcados. 73LS Hook-up Arm | Fresh | Progress manual deletion of previous PO for Opukushi 32T flowline. | Approved | Uwaezuoke, D | C.NG.AFS.DL.18.004.1218 |  |  | $ 67,038.61 N 2,973,825.23 F$ 74,874.78 |  |  |  | NIL |  | Gawason Integrated
| Bonny W12S JIV Support Services to the Asset Team – Additional work. | Fresh | Approved. I. Attach e-mail confirmation of additional work at site & forward to the Secretariat. | Approved | Ehizoyanyan, O | O.NG.PCE.BNF.FAC.71300 |  | $ 9,171.00 N 286,524.00 F$ 9,926.00 |  |  |  |  | NIL |  | SURVEILLANCE 2000 LTD
| Otumara flowstation Replacement of corroded drip pan. | Fresh | Approved. I. Progress manual deletion of previous PO for Otumara W20, 25 & 27 WHP rehabilitation. II. Ensure proper kick-off meeting | Approved | Obiakor, O | C.NG.PBW.IM.17.005.1230 |  |  | $ 108,500.00 N 3,350,000 F$116,670.73 |  |  |  | NIL |  | ROESON NIG
2021-06-17 | K2S Simultaneous Flow Project - Materials for Workshop Fabrication | Fresh | Deferred. I. Carry out further engagement with Procurement team to expedite materials delivery and revert with outcome. II. Document delays encountered from Procurement team and involve Asset team in the engagement. III. Liase with C&P to reconcile ACV figures. | Deferred | Akoma, I | C.NG.PBE.DF.21.005 |  | $11,908.95 N F$11,908.95 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Gbaran Produce Water Re-injection Project – Preliminary Works (Phase 1) | Fresh | Approved. I. Liase with C&P to reconcile ACV figures. II. Start early documentation of project pictures & forward to SE Lead. | Approved | Akoma, I | C.NG.PBE.IM.21.001.1230 |  | $ 13,865.02 N 10,453,136.83 F$ 39,360.48 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Kanbo 3L Flow line Sectional Replacement – (6’’ SCH 40 x 0.2km) | Fresh | Stepped Down. Project Lead to reconcile contracting issue and revert. | Stepped Down | Ehizoyanyan, O
| Replacement of Otumara 4L GLL (4" Sch 40 x 1.0km) | Fresh | Stepped Down. Project Lead to reconcile contracting issue and revert. | Stepped Down | Obiakor, O
| GENERAL |  | Always ensure strict adherence to SPDC procedures.
2021-06-24 | Diebu Creek FS Shutdown activities. | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Update WBS for this activity. II. Attach an approved OABP-WR. III. Carry out materials reconciliation with Hotdesk. IV. Update Project title to appropriately describe work scope. V. Engage CH for contract ceiling increase. VI. Liase with EST to ascertain Asset Integrity scope. | Conditional Approval | Uwaezuoke, D | TBA |  | $ 38,880.07 N 16,955.578.78 F$ 80,235.14 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Gbaran Produce Water Re-injection Project. -Reviewed offline | Fresh | Approved | Approved | Akoma, I | C.NG.PBE.IM.21.001.1230 |  | 800661.49 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
2021-07-01 | Kanbo 3L Flow line Sectional Replacement – (6’’ sch 40 x 0.2km) | Fresh | Approved. I. Set up an interface management meeting with the vendors and document MoM. II. Update CTS cost in the cost breakdown summary. | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $35,265.98 - N 2,357,063.1 F$41,014.91 - ELKON $31,746.32 N 1,024,554.20 F$34,245.23 - PALTOJEN |  |  |  | NIL |  | PALTOJEN NIG ELKON INTEGRATED
| Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km – Additional work | Fresh | Deferred. I. Engage C&P and other relevant project teams (NLNG) to ascertain company decision on vendors hotel accommodation payment during Covid’19 at site. | Deferred | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 1,115.74 N 198,497.00 F$ 1,638.79 |  |  |  |  | NIL |  | ABBEYCOURT ENERGY
2021-07-08 | Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km – Additional work -Resubmission | Resubmission | Deferred. WORP steers from previous sitting 01/07/21 have not been closed out. I. Engage C&P with outcome of discussions held with NLNG team to ascertain company decision on vendors hotel accommodation payment during covid’19 at site and revert. | Deferred | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 1,115.74 N 198,497.00 F$ 1,638.79 |  |  |  |  | NIL |  | ABBEYCOURT ENERGY
| Re-routing of NUNR 3S & 13T Flowline (4” Sch 80 x 700m) - SLOT Re-routing of NUNR 16T Flowline (4” sch 80 x 350m) – TONYMAR -Resubmission | Resubmission | Deferred. I. Advised to propose a single Vendor to reduce cost implication. | Deferred | Uwaezuoke, D | P.NG.PAE.OP.19.005.9401 |  | Slot $ 173,807.54 N 4,600,382.20 F$ 185,027.98 Tonymar $ 119,438.25 N 4,047,964.33 F$ 129,311.34 |  |  |  |  | NIL |  | Slot Engineering Tonymar Investment
| Provision of TRP scale inhibition injection points in Tunu, Opukushi & Benisede flow stations. | Fresh | Deferred. I. Engage CH to update ACV. II. Attach an approved e-WR | Deferred | Obiakor, O | C.NG.PBW.DF.21.003 |  |  | $ - 65,451.78 N – 22,088,4444.87 F$ - 119,326.04 |  |  |  | F$: 42,345.22 | Inter area mobilization instead of full mob to two facilities and domobilization | GRAMEN PETROSERVE
| Nun River Diebu Creek Bulkline to Gbaran - Civil Structural Scope. (missed out scope) | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Engage CH to update ACV. II. Update submission to clearly explain “Inter area move” as specified in the contract. III. Attach an updated Project schedule IV. Ensure provision for proper crew change to avoid personnel overstay at site | Conditional Approval | Obiakor, O / Ehizoyanyan, O | C.NG.PAE.DL.21.002.1230 |  | $ - 48,263.45 N – 48,639,602.94 F$ - 166,896.63 |  |  |  |  | F$: 21,151.12 | inter area move to Nun river manifold instead of full mob plus demob charge. | GRAMEN PETROSERVE
| Location Dredging works at Ogbotobo ANTM-1 & Ogbotobo AOTM-1. | Fresh | Conditional Approval I. Project Lead to reconcile contracting issue and revert. II. Update 5no top risk | Conditional Approval | Onyejekwe, C | TBA |  |  |  | $: 982,895.93 N: 585,168,641.77 F$: 2,410,136.52 |  |  | F$: 538,142.04 | Low Oil Price LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| GENERAL |  | Ensure proper review of submissions prior WORP
2021-07-15 | Re-routing of NUNR 3S, 13T, 16T Flowline (4” sch 80 x 1.1km) -Resubmission | Resubmission | Conditional Approval. WORP steer from previous sitting 08/07/21 have been incorporated. Further steer: I. Carry out contract alignment with NAPIMS and attach evidence of engagement to the resubmission. | Conditional Approval | Uwaezuoke, D | P.NG.PAE. OP.19.005.9401 |  | $ 241,645.94 N 6,316,713.09 F$ 257,052.56 |  |  |  |  | NIL |  | Slot Engineering
| Kanbo 3S JIV Asset Support. | Fresh | Approved | Approved | Ehizoyanya, O | O.NG.PCW.OKF.FAC.71300. |  |  | $23,535.13 N 787,950.12 F$27,456.96 |  |  |  | NIL |  | ELKON INTEGRATED
| Gbaran Produce Water Re-injection Project: Provision of Filtering Unit | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Build-up a detailed scope/cost to justify ceiling increase & secure TA2 assurance before engaging MTB. II. Carry out contract alignment with NAPIMS and attach evidence of engagement. III. Update 5no top risk to include “Possible procurement delay” and provide mitigations. IV. Update “Payment on behalf of SPDC” in the cost breakdown to “Reimbursable” | Conditional Approval | Akoma, I / Jimba, O | C.NG.PBE.IM.21.001.1230 |  | $ 560,099.71 N 33,501,980.40 F$ 646,948.56 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Otumara 55T Flowline Replacement (4” Sch 40 x 3.3km). -Reviewed offline | Fresh | Approved | Approved | Uwaezuoke, D | C.NG.PCW.DL.21.001.1230 |  |  | $ 459,067.57 N 8,974,812.70 F$ 480,957.36 | [5 empty] | Tomba Resources
| Otumara 30L Flowline Replacement (4” x 2.8km). -Reviewed offline | Fresh | Approved | Approved | Azaka, G | C.NG.PCW.DL.21.001.1230 |  |  | $404,380.20 N6,341,841.27 F$419,848.11 |  |  |  | 20056.18 | Houseboat sharing with another vendor working on OTUM55T | WILANDSON INTERNATIONAL
2021-07-22 | No Submission
2021-07-29 | Gbaran Produced Water Flowline Construction – 6” sch. 80 x 1.72km | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Attach mail confirmation of contract alignment meeting held with NAPIMS. II. Review the Contract ceiling availability and ensure is sufficient to accommodate this work. III. Capture cost savings from resource sharing. IV. Engage PS to review surveillance cost. V. Update Project schedule. | Conditional Approval | Arowosafe, T | C.NG.PBE.IM.21.001.1230 |  | $141,857.81 N 2,510,439.45 F$ 148,472.93 |  |  |  |  | NIL |  | JOSBANI
| Gbaran Produce Water Re-injection Project – Balance of Plant Works | Fresh | Approved. I. Ensure proper materials inspection by QAQC team. | Approved | Akoma, I | C.NG.PBE.IM.21.001.1230 |  | $ 909,985.52 N 298,402,543.02 F$ 1,637,796.60 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| KANBO 3S Flow line Sectional Replacement – (6’’ SCH 40 x 0.2km) | Fresh | Approved. I. Carry out interface management meeting with other vendors working on same RoW and ensure HSE & Security presence in the meeting. II. Engage HSE | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $.97,898.40 N 2,050,545.09 F$102,899.73 |  |  |  | NIL |  | EPOXY SERVICES
| Replacement of Otumara 4L GLL (4" Sch 40 x 1.0km). | Fresh | Approved. I. Carry out interface management meeting with the vendors and ensure HSE & Security presence in the meeting. | Approved | Obiakor, O | O.NG.STG.PBE.OTM.004FL |  |  | GAWASON $ 99,128.67 N 2,770.114.70 F$105,885.05 KEMUD $101,979.55 N 2,749,753.93 F$108,686.27 |  |  |  | NIL |  | GAWASON INTEGRATED. KEMUD INTERNATIONAL
| Afam VI Vent Gathering Project | Fresh | Approved | Approved | Dienagha, I | C.NG.PCE.NO.21.004 | USD 3,328.15 NGN 32,970 F$: 4,125.64 | [5 empty] | NIL |  | ADVANCED COATING TECH
| Resubmission: Re-routing of NUNR 3S, 13T, 16T Flowline (4” sch 80 x 1.1km) - Resubmission & Reviewed offline | Resubmission | Approved. WORP steer from previous sitting 15/07/21 have been incorporated. | Approved | Uwaezuoke, D | P.NG.PAE. OP.19.005.9401 |  | $ 241,645.94 N 6,316,713.09 F$ 257,052.56 |  |  |  |  | NIL |  | Slot Engineering
2021-08-05 | AJATITON W01L HOOK UP ARM REPLACEMENT. | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Attach an approved e-WR to the resubmission. II. Capture cost savings from resource sharing. III. Confirm vendors capability to execute work according to schedule. | Conditional Approval | Azaka, G | O.NG.STG.PBE.AJA.001FL |  |  | $67,692.69 N3,179,278.93 F$75,447.03 | [5 empty] | ELEKING W.W. SERVICES
| GENERAL |  | • Always document Contractors work performance. • Carry out a post-execution materials reconciliation review and report out with recommendations for improvement. • General HSE stand down in all OABP teams.
2021-08-12 | Ajatiton W01L Hook up Arm Replacement. -Resubmission | Resubmission | Approved. WORP steers from previous sitting 05/08/21 have been incorporated. I. Carry out a proper kick-off meeting and ensure HSE & Security presence, document MoM. | Approved | Azaka, G | O.NG.STG.PBE.AJA.001FL |  |  | $67,692.69 N3,179,278.93 F$75,447.03 |  |  |  | F$48,272.37 | (No cost for houseboat) | ELEKING W.W. SERVICES
| Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km – Additional work -Resubmission | Resubmission | Approved | Approved | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 1,819.93 N 160,592.00 F$ 2,211.62 |  |  |  |  | NIL |  | ABBEYCOURT ENERGY
| Provision of TRP Scale Inhibition Injection Points in Tunu, Opukushi & Benisede flowstation. -Resubmission | Resubmission | Conditional Approval WORP steers from previous sitting 08/07/21 have not been fully incorporated. I. Further engagement with the CH to secure additional eLDL to accommodate works on the Gramen Contract. | Conditional Approval | Obiakor, O | C.NG.PBW.DF.21.003 |  |  | $ 65,451.78 N 22,088,4444.87 F$ - 119,326.04 |  |  |  | F$: 42,345.22 | For doing inter area mobilization instead of full mob to two facilities and demobilization | GRAMEN PETROSERVE
| Installation of Flare tip & RIS at Agbada & Ahia FS. | Fresh | Deferred. I. Engage Asset team to decide funding procedure for divested OML17 activity. II. Update WBS for this activity. | Deferred | Ewenike, M | NIL | F$: 894.87 | [7 empty] | KEMUD INTERNATIONAL
| Kanbo 5S flowline JIV Asset Support. |  | Stepped Down by PMT
| Leak Repair of approach line of Nun River W13T Flowline. | Fresh | Deferred. I. Update WBS for this activity II. Engage CH to secure additional eLDL to accommodate works on the Gramen Contract | Deferred | Obiakor, O | C.NG.PAE.DL.21.001 |  | $ 14,338.89 N 9,489,577.88 F$ 37,484.20 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Nun River Diebu Creek Bulkline to Gbaran – Mechanical, Electrical & Instrumentation scopes. | Fresh | Deferred. I. Engage CH to secure additional eLDL to accommodate works on the Gramen Contract | Deferred | Ehizoyanyan, O | C.NG.PAE.DL.21.002.1230 |  | MECHANICAL PACO ELECTRICAL TOTAL COST $ 599,603.70 $ 268,558.89 $ 5,480.82 $ 873,643.34 N 252,401,417.93 N 13,288,610.75 N 10,392,665.63 N276,082,694.31 F$ 1,215,216.91 F$ 300,970.14 F$ 30,828.78 F$ 1,547,015.83 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Enwhe West 3.5km Location Access Road Additional Scope / Local content. | Fresh | Approved. I. Engage ER and ensure proper processes are deployed in the payment. | Approved | Ezenduka, D | C.NG.LNG.19.004.1230 |  |  |  | N38,871,180 +$ 3,660.94, F$:98,468.70 |  |  | NIL |  | MIFE CONSTRUCTION
| Gbaran Produced Water Flowline Construction – 6” sch. 80 x 1.72km -Resubmission & Reviewed offline | Fresh | Approved | Approved | Arowosafe, T | C.NG.PBE.IM.21.001.1230 |  | $ 143,031.76 N 2,550,416.89 F$ 149,252.29 |  |  |  |  | F$: 96,713.65 | Cost saving for not mobilizing tie-in barge and lay barge, also savings from cost of surveillance. (reduced from 43days to 15days) | JOSBANI
| Replacement of Otumara 4L GLL (4" Sch 40 x 1.0km) -Resubmission & Reviewed offline | Resubmission | Approved | Approved | Obiakor, O | O.NG.STG.PBE.OTM.004FL |  |  | $ 166,934.26 N 3,924,654.46 F$176,506.59 |  |  |  | NIL |  | TONYMAR
| Estuary Cluster 51: Forc. 73LS Hook-up Arm Modification – Reviewed offline | Fresh | Approved | Approved | Uwaezuoke, D | C.NG.AFS.DL.18.004.1218 |  |  | $58,153.30 N 2,432,214.52 F$ 64,085.53 |  |  |  | F$: 25,726.45 | Shared Resources, Scaffold | Gawason
2021-08-19 | Installation of flare tip & RIS at Agbada and Ahia flowstation Resubmission | Resubmission | Approved. WORP steers from previous sitting 12/08/21 have been incorporated. I. Erase Agbada from the Project title. II. Document payment agreement with the vendor to forestall future claims. | Approved | Ewenike, M | C.NG.PCE.N0.20.001.1230 | F$: 885.54 | [5 empty] | NIL |  | KEMUD INTERNATIONAL
| Construction of Enwhe West Location, By-pass, and Concrete Bridge. Additional Scope. | Fresh | Approved | Approved | Ezenduka, D | C.NG.LNG.19.004.1230 |  |  |  | N56,723,927.76 +$ 34,431.58, F$:172,782.62 |  |  |  |  | ENERCO NIG
| Geotechnical Investigation for Oloibiri Oil and Gas Museum and Research Center (OMRC) | Fresh | Approved. I. Update Risk item 2 title appropriately. | Approved | Edoh, C | 110866 |  |  |  | N 6,005,140.00 |  |  | N 316, 060 | 5% Discount on the Contract Rates | Eadro Geotechnics
| Gbaran 26 Location Rehabilitation Project (Gbaran 14 Replacement Well) | Fresh | Approved. I. Engage the contractor on the criticality of the schedule with regards to working during December period. II. Engage Wells team on the need for Well test location and revert to WORP for approval of the extra work scope if needed. | Approved | Chioke, K | C.NG.LNG.DG.19.006.1231 |  |  |  | $ 161,394.54 N 96,834,975.99 F$ 397,577.41 |  |  | F$: 20,925.13 | (LoP) | RAFFOUL NIG
| Disconnection of Afremo 6T Hook-up Arm (Afremo B) | Fresh | Approved. I. Align OABP security plan with CWI team. II. Hold a proper kick off meeting and ensure Security, HSE & Marine presence. | Approved | Uwaezuoke, D | P.NG.PAE. OP.19.004.1230 |  |  | $59,166.78 N 1,507,497.96 F$ 62,843.60 |  |  |  | F$: 123,952.48 | Shared Resources (Logistics and Security etc) | Kemud International
| Kanbo 5S flowline JIV Asset Support / Flowline Sectional Replacement (6’’ x 0.2Km) | Fresh | Approved | Approved | Otavie, G | O.NG.STG.PBE.KAN.005FL |  |  | $ 103,554.77 N 2,100,446.5 F$ 108,677.81 |  |  |  | NIL |  | WIRELINK SERVICES
| Repair of Cracked 3” Weldolet of Soku GP spiking pump discharge header. | Fresh | Approved. I. Engage CH to update ACV split values in the submission. | Approved | Obiakor, O | O.NG.PBE.SKG.FAC.724FC |  | $ 13,634.14 N 10,119,593.96 F$ 38,316.08 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Leak Detection System Project (Installation of Coriolis Meter at Kolo Creek and Rumuekpe Manifolds) – Provision of Shortfall Materials | Fresh | Approved. I. Engage CH to update ACV split values in the submission. | Approved | Odey, E | O.NG.PPE.MAN.MAN.71300 | $ 275,665.28 N 25,091,470.98 F$ 336,863.99 | [5 empty] | NIL |  | GRAMEN PETROSERVE
| Forcados 73LS Hook-up Arm Replacement. -Reviewed offline | Resubmission | Approved | Approved | Uwaezuoke, D | C.NG.AFS.DL.18.004.1218 |  |  | $ 31,605.99 N 1,103,594.09 F$ 34,297.68 |  |  |  | F$: 117,417.71 | Shared Resources, Logistics, Security and Scaffold etc) | Gawason
| GENERAL |  | Always ensure vendor supplied materials are inspected by the QAQC team.
2021-08-26 | Nun River Diebu Creek Bulkline to Gbaran – Mechanical, Electrical & Instrumentation scope. -Resubmission | Resubmission | Approved. WORP steers from previous sitting 12/08/21 have been incorporated. | Approved | Ehizoyanyan, O | C.NG.PAE.DL.21.002.1230 |  | MECHANICAL PACO ELECTRICAL TOTAL COST $ 599,603.70 $ 268,558.89 $ 5,480.82 $ 873,643.34 N 252,401,417.93 N 13,288,610.75 N 10,392,665.63 N276,082,694.31 F$ 1,215,216.91 F$ 300,970.14 F$ 30,828.78 F$ 1,547,015.83 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Provision of TRP Scale Inhibition Injection points in Tunu, Opukushi & Benisede flow stations. -Resubmission. | Resubmission | Approved. WORP steers from previous sitting 12/08/21 have been incorporated. | Approved | Obiakor, O | C.NG.PBW.DF.21.003 |  |  | $ 65,451.78 N 22,088,4444.87 F$ - 119,326.04 |  |  |  | F$: 42,345.22 | For doing inter area mobilization instead of full mob to two facilities and demobilization. | GRAMEN PETROSERVE
| Geotechnical Investigation for Gbaran NLNG Project/EPU Phase 2 Gas Dev. | Fresh | Approved. I. Update Project schedule to current plan. II. Engage C&P on clarification of rates application on this contract. | Approved | Edoh, C | P.NG.PAE.DG.20.001.1238 |  |  |  | N 10,489,484.49 |  |  | N 552,078.13 | Low Oil Price {LOP} | EADRO GEOTECHNICS
2021-09-02 | GBARAN PRODUCE WATER RE-INJECTION PROJECT – Materials | Fresh | Approved. I. Attach e-mail evidence of materials search carried out with Hotdesk. | Approved | Akoma, I | C.NG.PBE.IM.21.001.1230 |  | F$ 213,689.52 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| TUNU CPF INLET LINE TO TWISTER TUBE LEAK REPAIR | Fresh | Approved. I. Update WBS for this activity to AF. | Approved | Obiakor, O | C.NG.PBW.DF.21.003 |  |  | $ 19,031.56 N 9,402,872.46 F$41,965.40 |  |  |  | NIL |  | GRAMEN PETROSERVE
| TUNU HP GAS RE-ROUTING PROJECT | Fresh | Approved. I. Confirm WBS is from SSAGS team. | Approved | Obiakor, O | C.NG.PBW.DF.21.004.1230 |  |  | $ 170,906.29 N 70,497,828.59 F$342,852.21 |  |  |  | NIL |  | GRAMEN PETROSERVE
| GENERAL |  | • Strict adherence to SPDC policy of “NO PO = NO WORK” • Imbibe an aggressive cost saving initiative in all OABP activities.
2021-09-09 | Gbaran Produced Water Flowline Construction – 6” sch. 80 x 1.72km additional scope | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Update Project Schedule to current plan. II. Engage Security to mitigate exposure during river crossing. III. Confirm water depth to ascertain equipment requirement. IV. Review work method statement & certifications required. V. Update Project title to indicate the 50m additional scope VI. Review risks and update 5nos top risks. | Conditional Approval | Arowosafe, T | C.NG.PBE.IM.21.001.1230 |  | $ 35,653.72 N 3,444,186.22 F$ 44,054.17 |  |  |  |  | NIL |  | JOSBANI CONST
2021-09-16 | K2S Simultaneous Flow Project - Materials for Workshop Fabrication -Resubmission | Resubmission | Conditional Approval. WORP steers from previous sitting 17/06/21 have been incorporated. Further steer: I. Reconfirm materials availability from the Hotdesk and revert offline | Conditional Approval | Jimba, O | C.NG.PBE.DF.21.005 |  | $ 3,526.61 N F$ 3,526.61 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Gbaran Produce Water Re-injection Project: Provision of Safety Shutdown Valve | Fresh | Stepped down by PMT | Stepped down by PMT | Jimba, O
| Leak Detection System Project (Installation of Coriolis Meter at Kolo Creek and Rumuekpe Manifolds) – Provision of Shortfall Materials | Fresh | Conditional Approval I. Engage CH to reconcile ACV figures. II. Attach evidence of materials bench mark / moving average pricing from SAP. | Conditional Approval | Odey, E | C.NG.PPE.DP.21.012 |  | N 17,741,953.14 $ 3,507.71 F$46,780.77 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| Enwhe East Drilling/Cellar Slot Retaining Walls and Underground Flare line Section (20m) | Fresh | Conditional Approval I. Engage CH to reconcile ACV figures. II. Update Project Schedule to current plan. | Conditional Approval | Uwaezuoke, D | C.NG.LNG.DG.19.004.1230 |  | $ 1,268.00 N 6,739,191.07 F$ 17,705.05 |  |  |  |  | NIL |  | GRAMEN PETROSERVE
| GENERAL |  | • Always ensure test results are attached to every material supplied by vendors.
23-Sep=21 | SECTIONAL REPLACEMENT OF AFAM 25T FLOWLINE- HYDROTEST (EXTRA WORK) AND AFAM 27T VOWD | Fresh | Approved. I. Attach the approved e-WR and previously secured WORP for Afam 25T and forward to the secretariat. | Approved | Akinbiyi, A | O.NG.PAE.I1F.FAC.724FC | $ 8,691.50 + 904.79 N 13,926,116.91 + 1,103,839.58 F$ 42,657.64 + 3,597.08 | [5 empty] | NIL |  | BG TECHNICAL LIMITED
| GENERAL |  | Always secure Leadership support/approval in writing for any emerging (additional) scope of work at site before execution.