## Civil Milestone
Project Sub Item | Milestone Description | Milestone Category | Team | Action Party/ Team Lead | Activity Start Status | Remaining Days to Start | Milestone Start | Milestone Finish | New Start Date | New Finish Date | Current Week Update
Sectional Rehabilitation Of Obigbo F/S Road | Complete Road Rehabilitation | Inhouse | Corporate Civil | Dan Ezenduka/Tayo Tella | Started | N/A | 2021-03-15 | 2021-08-30 | 2021-03-15 | 2021-08-30 | Completed
Apara 10 Restoration | Complete 100% Apara 10 BP Restoration | Inhouse | Corporate Civil | Salo Ogbebor / Tayo Tella | Started | N/A | 2021-01-16 | 2021-03-28 | 2021-01-16 | 2021-03-28 | Completed
Imo River Bridge Rehabilitation | Complete 100% Rehabilitation | Inhouse | Corporate Civil | Victor Agweda / Tayo Tella | Started | N/A | 2021-06-01 | 2021-09-30 | 2021-06-01 | 2021-09-30 | Ongoing
Bonny 13 Maintenance Dredging | Secure WORP | Inhouse | Corporate Civil | Emeka Onyejekwe / Mike Adigwe | Started | N/A | 2021-03-15 | 2021-03-31 | 2021-03-15 | 2021-03-31 | Completed
Bonny 14 Maintenance Dredging | Secure WORP | Inhouse | Corporate Civil | Emeka Onyejekwe / Mike Adigwe | Started | N/A | 2021-03-15 | 2021-03-31 | 2021-03-15 | 2021-03-31 | Completed
Ogbotobo AMTS 1 dredging | Secure WORP | Inhouse | Corporate Civil | Emeka Onyejekwe / Mike Adigwe | Started | N/A | 2021-08-31 | 2021-09-30 | 2021-08-31 | 2021-09-30 | Ongoing
Escravos FLB | PO Placement for 100% of materials for Staff Accommodation Block | Inhouse | Corporate Civil | Maxwell Ebirim / Mike Adigwe | Started | N/A | 2021-02-02 | 2021-12-30 | 2021-02-02 | 2021-12-30 | Ongoing
Escravos FLB | 50% Completion of Existing Staff Accommodation Block | Inhouse | Corporate Civil | Maxwell Ebirim / Mike Adigwe | Started | N/A | 2021-02-02 | 2021-12-30 | 2021-02-02 | 2021-12-30 | Ongoing
Escravos FLB | Complete installation of temp site facilities | Inhouse | Corporate Civil | Maxwell Ebirim / Mike Adigwe | Started | N/A | 2021-02-02 | 2021-11-30 | 2021-02-02 | 2021-12-30 | Ongoing
Ogbotobo AMTT 1 dredging | Secure WORP | Inhouse | Corporate Civil | Maxwell Ebirim / Mike Adigwe | Started | N/A | 2021-08-31 | 2021-09-30 | 2021-08-31 | 2021-09-30 | Ongoing
BOGT Shore Protection | Secure WORP | Inhouse | Corporate Civil | Moses Ogukunle Mike Adigwe | Started | Started | 2021-02-15 | 2021-03-15 | 2021-03-01 | 2021-03-30 | Completed
BOGT Shore line Reclamation | Complete 30% reclamation - BOGT | Inhouse | Corporate Civil | Moses Ogukunle / Mike Adigwe | Not Started | 69 | 2021-11-01 | 2021-12-30 | 2021-11-01 | 2021-12-30
Okoloma Well Location Preparation | Complete 70% Construction of Access Road | Inhouse | Corporate Civil | Osakwe Remigus Tayo Tella | Not Started | -54 | 2021-07-01 | 2021-12-30 | 2021-07-01 | 2021-12-30 | Ongoing
Okoloma Well Location Preparation | Complete 20% Construction of Well Location | Inhouse | Corporate Civil | Osakwe Remigus Tayo Tella | Not Started | 22 | 2021-09-15 | 2021-12-30 | 2021-09-15 | 2021-12-30 | Ongoing
Benesede Eaua -2 Dredging (Ssags Step 2) | Complete Site works | Corporate | Corporate Civil | Emeka Onyejekwe / Mike Adigwe | Started | N/A | 2021-04-15 | 2021-07-31 | 2021-06-01 | 2021-07-01 | Completed
Ogbotobo AOTM 1 and ANTM 1 dredging | Secure WORP Approval | Inhouse | Corporate Civil | Sunny Oludare Mike Adigwe | Started | N/A | 2021-03-31 | 2021-04-15 | 2021-02-01 | 2021-04-30 | Completed
Ogbotobo AOTM 1 and ANTM 1 dredging | Complete Site works | Inhouse | Corporate Civil | Sunny Oludare Mike Adigwe | Started | N/A | 2021-05-30 | 2021-10-30 | 2021-04-01 | 2022-01-31
Complete FYIP CPF/FLB Internal Roads Paving | Complete FYIP CPF/FLB Internal Roads Paving | Inhouse | Corporate Civil | Emeka Onyejekwe /Tayo Tella | Started | N/A | 2021-02-02 | 2021-09-30 | 2021-02-15 | 2021-11-15 | Ongoing
Construction Of Enwhe West Location, By-Pass,Bridge And Manifold Sand Filling | Completion of Location and Manifold sand filling | Inhouse | Corporate Civil | Dan Ezenduka / Tayo Tella | Started | N/A | 2021-01-16 | 2021-04-10 | 2021-01-16 | 2021-08-30 | Ongoing
Construction Of Enwhe West Location, By-Pass,Bridge And Manifold Sand Filling | Complete piling works | Inhouse | Corporate Civil | Dan Ezenduka / Tayo Tella | Started | N/A | 2021-06-24 | 2021-09-30 | 2021-06-24 | 2021-12-15 | Ongoing
Construction Of Enwhe West Location, By-Pass,Bridge And Manifold Sand Filling | Complete location concrete works | Inhouse | Corporate Civil | Dan Ezenduka / Tayo Tella | Not Started | 144 | 2021-06-25 | 2021-12-20 | 2022-01-15 | 2022-04-15
Construction Of Enwhe West Location, By-Pass,Bridge And Manifold Sand Filling | Complete location platform stabilization | Inhouse | Corporate Civil | Dan Ezenduka / Tayo Tella | Not Started | 203 | 2021-11-21 | 2021-11-30 | 2022-03-15 | 2022-04-15
Construction Of Enwhe West Location, By-Pass,Bridge And Manifold Sand Filling | Complete location asphalting | Inhouse | Corporate Civil | Dan Ezenduka / Tayo Tella | Not Started | 235 | 2021-12-21 | 2021-12-31 | 2022-04-16 | 2022-04-30
Construction Of Enwhe West Location, By-Pass,Bridge And Manifold Sand Filling | Complete Bridge Works | Inhouse | Corporate Civil | Dan Ezenduka / Tayo Tella | Started | N/A | 2021-03-15 | 2021-11-30 | 2021-03-15 | 2022-02-28
Construction Of Enwhe West 3.5Km Access Road | Completion of Earthworks | Inhouse | Corporate Civil | Dan Ezenduka / Tayo Tella | Started | N/A | 2021-01-16 | 2021-09-10 | 2021-03-02 | 2021-12-30 | Ongoing
Construction Of Enwhe West 3.5Km Access Road | Complete concrete culverts | Inhouse | Corporate Civil | Dan Ezenduka / Tayo Tella | Not Started | 38 | 2021-03-25 | 2021-09-30 | 2021-10-01 | 2022-03-28
Construction Of Enwhe West 3.5Km Access Road | Complete 50% road stabilization | Inhouse | Corporate Civil | Dan Ezenduka / Tayo Tella | Not Started | Started | 2021-07-10 | 2021-09-30 | 2021-07-10 | 2021-12-30 | Ongoing
Construction Of Enwhe West 3.5Km Access Road | Complete 100% road stabilization | Inhouse | Corporate Civil | Dan Ezenduka / Tayo Tella | Not Started | 145 | 2021-10-01 | 2021-11-15 | 2022-01-16 | 2021-02-28
Construction Of Enwhe West 3.5Km Access Road | Complete aphalting road works | Inhouse | Corporate Civil | Dan Ezenduka / Tayo Tella | Not Started | 145 | 2021-11-16 | 2021-12-30 | 2022-01-16 | 2022-04-28
Rehabilitation Of Aminigboko-Emesu-Jetty Road. | Complete mobilization | Inhouse | Corporate Civil | Dan Ezenduka / Tayo Tella | Started | N/A | 2021-01-21 | 2021-02-15 | 2021-01-15 | 2021-02-15 | Completed
Rehabilitation Of Aminigboko-Emesu-Jetty Road. | Complete Road Rehabilitation | Inhouse | Corporate Civil | Dan Ezenduka | Started | N/A | 2021-02-16 | 2021-08-15 | 2021-03-15 | 2021-08-15 | Completed
Enwhe East Location | Complete location stabilization | Inhouse | Corporate Civil | Maxwell Ebirim | Started | N/A | 2021-01-15 | 2021-02-28 | 2021-03-15 | 2021-06-30 | Completed
Enwhe East Location | Complete location concrete works | Inhouse | Corporate Civil | Maxwell Ebirim | Started | N/A | 2021-01-20 | 2021-03-25 | 2021-08-27 | 2021-12-30 | Completed
Enwhe East Location | Complete location asphalting | Inhouse | Corporate Civil | Maxwell Ebirim | Started | N/A | 2021-03-15 | 2021-03-30 | 2021-05-01 | 2021-12-30 | Completed
Enwhe East Location | Complete 100% of 1.5km Access Road | Inhouse | Corporate Civil | Maxwell Ebirim | Started | N/A | 2021-01-15 | 2021-01-30 | 2021-06-01 | 2021-12-31 | Completed
Enwhe East 5.4Km Community Road | Complete road stabilisation | Inhouse | Corporate Civil | Maxwell Ebirim | Started | N/A | 2021-01-21 | 2021-02-15 | 2021-07-15 | 2021-12-31 | Completed
Enwhe East 5.4Km Community Road | Concrete Works | Inhouse | Corporate Civil | Maxwell Ebirim | Started | N/A | 2021-02-01 | 2021-03-15 | 2021-01-16 | 2021-03-28 | Completed
Enwhe East 5.4Km Community Road | Complete asphalting | Inhouse | Corporate Civil | Maxwell Ebirim | Started | N/A | 2021-02-21 | 2021-03-28 | 2021-03-15 | 2021-03-31 | Completed
Enwhe Location Campsite | Complete Campsite platform stabilization | Inhouse | Corporate Civil | Remijus Osakwe | Started | N/A | 2021-01-21 | 2021-03-20 | 2021-05-15 | 2021-08-31 | Completed
Enwhe Location Campsite | Complete Campsite concrete works | Inhouse | Corporate Civil | Remijus Osakwe | Started | N/A | 2021-02-10 | 2021-03-14 | 2021-03-15 | 2021-03-31 | Completed
Enwhe Location Campsite | Complete Campsite asphalting | Inhouse | Corporate Civil | Remijus Osakwe | Started | N/A | 2021-03-15 | 2021-03-28 | 2021-05-15 | 2021-08-31 | Completed
Assa North Wellbay 3 | Complete Location concrete works | Inhouse | Corporate Civil | Dan Ezenduka | Started | N/A | 2021-01-15 | 2021-03-20 | 2021-02-02 | 2021-08-31 | Completed
Assa North Wellbay 3 | Complete location platform stabilization | Inhouse | Corporate Civil | Dan Ezenduka | Started | N/A | 2021-01-21 | 2021-02-15 | 2021-02-02 | 2021-08-31 | Completed
Assa North Wellbay 3 | Complete location asphalting | Inhouse | Corporate Civil | Dan Ezenduka | Started | N/A | 2021-03-15 | 2021-03-28 | 2021-02-02 | 2021-06-30 | Completed
Opolo Drainage Construction | Mobilization 100% | Inhouse | Corporate Civil | Umoru Sule | Started | N/A | 2021-01-05 | 2021-01-15 | 2021-02-02 | 2021-10-31 | Completed
Opolo Drainage Construction | Complete Bini-Uba concrete drain works | Inhouse | Corporate Civil | Umoru Sule | Started | N/A | 2021-01-31 | 2021-02-28 | 2021-02-02 | 2021-08-30 | Completed
Opolo canals disilting works | Secure WORP | Inhouse | Corporate Civil | Umoru Sule | Started | N/A | 2021-03-01 | 2021-03-31 | 2021-08-02 | 2021-08-30 | Ongoing
Opolo canals disilting works | Complete site work | Inhouse | Corporate Civil | Umoru Sule | Not Started | 69 | 2021-03-01 | 2021-03-31 | 2021-11-01 | 2022-12-30 | Ongoing
Total | 57