## OABP Q1 2021 Savings
DATE | PROJECT | PE / SPONSOR | WBS | COST SAVINGS Q1 | [5 empty] | Remarks
|  |  |  | LAND | CENTRAL | SWAMP WEST | CIVIL | OABP ASSET, 100% Savings | FCF Savings
2021-01-01 | No Submission(s)
| Opukushi 34T Flowline Replacement | Otavie, G | 102155 |  |  | 65000 |  |  |  | Renegotiated excavation rates, use of only one vendor reduced double mobilization and associated catering costs
| Opukushi W26T Flowline Replacement (4" x 2km | Otavie, G | 102155 |  |  | 35000 |  |  |  | Campaign mobilization will enable the sharing of Marine logistic resources like hosueboat
| Rehabilitation of 800m failed sections of Obigbo flow station road. | Ezenduka, D | C.NG.PAE.IC.21.001 |  |  |  | 29844.89 |  |  | 6.5 % LOP Discount
| Addendum to Construction of 1 No. Well bay location Assa-North | Ezenduka, D | C.NG.ANO.DG.17.004.1231 |  |  |  | 7589.49 |  |  | 5 % LOP Discount
| Sectional Replacement of (a) ImoR 59T (6-inch) (b) ImoR 25L (4-inch) | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | 8280.04 | [5 empty] | THERE IS A SAVINGS OF 8,280.04 USD WHICH SHOULD HAVE COVERED MOB & DEMOB USING A NEW CONTRACTOR
| Full Replacement of ImoR 58T (4- inch x 3.4km) | Aderiye, A | C.NG.PAE.DL.21.001 | [6 empty] | THERE IS A SAVINGS OF 12,508.36 FROM THE MATERIALS THAT WILL BE COLLECTED FROM THE SPDC WAREHOUSE
2021-02-01 | LOCATION DREDGING WORKS AT BENISEDE EAUA-2. | Onyejekwe, C | C.NG.AFS.DD.19.009.9401 |  |  |  | 115543.79 |  |  | Low Oil Price LoP discounts (i.e. 22%).
| FULL REPLACEMENT OF IMOR 58T (4-INCH x 3.4KM) | Aderiye, A | C.NG.PAE.DL.21.001 | 14800 | [5 empty] | Warehouse Materials
| K2S Simultaneous Flow Project | Akoma, I | C.NG.PBE.DF.21.005 |  | 22416.83 |  |  |  |  | Savings on Mob and De-mob by using same contractor for Mechanical/ Instrumentation works, etc
| Replacement of LP header of Yokri flow station. | Obiakor, O | O.NG.PCW.YKF.FAC.71300 |  |  | 23907.23 |  |  |  | saved for combining mobilization of Forcados Yokri 127T flowline sectional replacement and replacement of Yokri LP header
| LEAK REPAIR OF FORCADOS 127T FLOWLINE | Obiakor, O | 102155 |  |  | 39515.51 |  |  |  | Mob and De-mob, Houseboat
| SECTIONAL REPLACEMENT OF OTUMARA 42LS, 16T FLOWLINES AND FABRICATION OF HOOK-UP ARM OF OTUMARA 4L. | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  |  | 159000 |  |  |  | F$82,000 (Shared marine logistics) + F$77,000 (Single mob/demob)
2021-03-01 | UZU MANIFOLD LOCATION PREPARATION | Oludare, S | P.NG.PAE.DG.17.001 |  |  |  | 107225.24 |  |  | 5 % LOP Discount
| FORC 111T Flowline Replacement (6" sch 40 x 2.7 km bulkline) & (4" sch 40 x 0.25 km flowline) | Orji, C | C.NG.PAE.DL.21.001.1230 |  |  | 33891.12 |  |  |  | From Materials to be taken from Hot Desk
| FULL REPLACEMENT OF IMOR 36L (4-INCH x 1.0 KM) | Aderiye, A | C.NG.PAE.DL.21.001 | 12500 | [5 empty] | MATERIALS FROM THE SPDC WAREHOUSE.
| SECTIONAL REPLACEMENT OF (a) IMOR 4-inch TEST LINE (48M) (b) IMOR RIVER 26S (48M) © IMO RIVER 44S (48M) (d) IMO RIVER 55S (48M) (e) IMO RIVER 43T (48M) (f) IMOR 60T (48M) | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | 11525.18 | [5 empty] | MOB & DEMOB. ALL MATERIALS FOR THESE SECTIONAL REPLACEMENT SHALL BE SOURCED FROM SPDC WAREHOUSE
| SECTIONAL REPLACEMENT OF (a) IMOR RIVER 6-INCH BULKLINE (IMO 2 -1) X 1500 M (Additional leak points) | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | 8280.04 | [5 empty] | MOB & DEMOB IF USING A NEW CONTRACTOR
| Provision of lay barge for installation of CCUs at Kanbo W5L/S | Ehizonyan, O | C.NG.AFS.DF.18.025.1202 |  |  | 10062 |  |  |  | Shared marine logistics and security deployment
| Seibou 3 and 4 bulkline JIV and clamping. -Reviewed offline | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | 9050.71 |  |  |  | cost saving on inter-area move instead of mobilizing a new contractor.
| Bonny W14 Maintenance Dredging works | Onyejekwe, C | 110744 |  |  |  | 56227.33 |  |  | Cost saving is from Low Oil Price LoP discounts (i.e. 7.5%).
| Bonny W13 Maintenance Dredging works | Onyejekwe, C | 110744 |  |  |  | 54055.53 |  |  | Cost saving is from Low Oil Price LoP discounts (i.e. 7.5%).
| Kanbo W7S (6’’ x 0.1Km) & W6T (6’’ x 0.1Km) Flowline Sectional Replacement | Otavie, G | O.NG.STG.PBE.KAN.007FL O.NG.STG.PBE.KAN.006FL |  |  | 20000 |  |  |  | Elimination of Mob and De-mob of Houseboat, by latching onto existing houseboat already in Tunu
| TUNU BQRT-3 Flowline Replacement (6" Sch 80 x 6.1km) | Otavie, G | C.NG.AFS.DL.19.006.1230 |  |  | 24284.08 |  |  |  | House boat sharing and materials discounted
| Total |  |  | 55385.26 | 22416.83 | 419710.65 | 370486.27 | 867999.01 | 252587.7119
|  |  |  | 67893.62 | 22416.83 | 375426.57 | 370486.27 | 836223.29 | 243340.9774

## Summary Sheet
OABP Team Q1-2021 SAVINGS
S/No | Description | Initiative Number | Amount $ | 100% Savings $ | FCF Savings $
1 | Land Asset | I-0152635 | 55385.26 |  | 16117.1107
2 | Central Asset | I-0152488 | 22416.83 |  | 6523.2975
3 | Swamp West | I-0152627 | 419710.65 |  | 122135.7992
4 | Civil | I-0152636 | 370486.27 |  | 107811.5046
5 | Matrix-ROCi | I-0151647 |  |  | 0
| Total |  |  | 867999.01 | 252587.7119
252587.7119

## Sheet1 (2)
DATE | PROJECT | WORP DECISION | PE / SPONSOR | WBS | TOTAL VALUE/COST | [5 empty] | COST SAVINGS | Remarks | CONTRACT
[5 empty] | LAND | CENTRAL | SWAMP WEST | CIVIL | OABP ASSET | AF
2021-01-07 | No Submission(s)
| Opukushi 34T Flowline Replacement | Approved - Update the narrative in the submission to indicate initial PO will be deleted - Update in the submission G&H to CTS | Otavie, G | 102155 |  |  | FUSD:390,382.95 NGN:6,387,108.86 USD: 373,574.27 |  |  |  | FUSD: 65,000 | Renegotiated excavation rates, use of only one vendor reduced double mobilization and associated catering costs | WILANDSON
| Opukushi W26T Flowline Replacement (4" x 2km | Conditional Approval: Complete the actions below and revert offline - Contract extension to be updated in SAP - Engage PST to reconcile cost - Update submission to reflect risk, work schedule etc | Otavie, G | 102155 |  |  | $ 182,085.5 N 66,885,002.36 F$ 401,380.6 |  |  |  | F$: 35,000 | Campaign mobilization will enable the sharing of Marine logistic resources like hosueboat | SEVOIL
2021-01-21 | Opukushi W26T Flowline Replacement (4" x 2km) - Resubmission & Reviewed offline | Approved | Otavie, G | 102155 |  |  | $ 177,590.51 N 65,234,247.10 F$ 349,485.76 |  |  |  | F$: 35,000 | Campaign mobilization will enable the sharing of Marine logistic resources like hosueboat | SEVOIL
| Rehabilitation of 800m failed sections of Obigbo flow station road. | Deferred: Complete item below and revert offline - Engage the Asset team to get confirmation from divestment BOM on the execution of this project | Ezenduka, D | C.NG.PAE.IC.21.001 |  |  |  | F$: 429,307.22 |  |  | F$: 29,844.89 | 6.5 % LOP Discount | BENCOV NIG
| Rehabilitation of 800m failed sections of Obigbo flow station road. -Resubmission | Approved. WORP steers from previous sitting 21-01-21 have been incorporated. | Ezenduka, D | 110854 |  |  |  | F$: 429,307.22 |  |  | F$: 29,844.89 | 6.5 % LOP Discount | BENCOV NIG
| Addendum to Construction of 1 No. Well bay location Assa-North | Approved. I. Resolve ACV balance in SAP II. Update 5 top risks to include Covid19 | Ezenduka, D | C.NG.ANO.DG.17.004.1231 |  |  |  | F$: 144,200.22 |  |  | F$: 7,589.49 | 5 % LOP Discount | RAFFOULNIG.LIMITED
| Sectional Replacement of (a) ImoR 59T (6-inch) (b) ImoR 25L (4-inch) | Approved. I. Include line length in the Project Title | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 12,297.25 N 3,357,092.47 F$ 21,143.34 | [5 empty] | 8280.04 | THERE IS A SAVINGS OF 8,280.04 USD WHICH SHOULD HAVE COVERED MOB & DEMOB USING A NEW CONTRACTOR | GAMSTEC INTEGRATED
| Full Replacement of ImoR 58T (4- inch x 3.4km) | Approved. | Aderiye, A | C.NG.PAE.DL.21.001 | $ 110,900.38 N 26,084,203.78 F$ 179,633.46 | [5 empty] | 12508.36 | THERE IS A SAVINGS OF 12,508.36 FROM THE MATERIALS THAT WILL BE COLLECTED FROM THE SPDC WAREHOUSE | THOMPSON AND GRACE
2021-02-18 | : LOCATION DREDGING WORKS AT BENISEDE EAUA-2. | Approved. I. Liase with OABP focal persons to confirm ETC/OTC availability. | Onyejekwe, C | C.NG.AFS.DD.19.009.9401 |  |  |  | $: 103,003.11 N: 267,683,624.79 F$: 808,361.80 |  |  | F$: 115,543.79 | Low Oil Price LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| FULL REPLACEMENT OF IMOR 58T (4-INCH x 3.4KM) | Approved. I. Proceed to execution with the proposed new vendor (WILKRISS NIG. LTD) II. Ensure the MoM and offer decline letter from Thompson & Grace Investment Ltd is duly signed for documentation | Aderiye, A | C.NG.PAE.DL.21.001 | $ 137,763.36 N 12,884,978.45 F$ 179,633.46 | [5 empty] | 14800 | Warehouse Materials | WILKRISS
| K2S Simultaneous Flow Project | Approved. I. Engage CH to update ACV split currency values. II. Carry out materials check with Hotdesk. III. Emphasize criticality of this activity with the Vendor. | Akoma, I | C.NG.PBE.DF.21.005 |  | $ - 104,725.16 N - 36,794,719.22 F$ - 201,680.94 |  |  |  |  | F$: 22,416.83 | Savings on Mob and De-mob by using same contractor for Mechanical/ Instrumentation works, etc | GRAMEN PETROSERVE
| Replacement of LP header of Yokri flow station. -Reviewed offline | Approved | Obiakor, O | O.NG.PCW.YKF.FAC.71300 |  |  | $ 31,865.72 N 375,865.72 F$ 32,854.55 |  |  |  | 23907.23 | saved for combining mobilization of Forcados Yokri 127T flowline sectional replacement and replacement of Yokri LP header | TONYMAR INVESTMENT
| LEAK REPAIR OF FORCADOS 127T FLOWLINE | Approved. I. Engage WRFM to confirm WBS for this activity. II. Update Project title to include “Optimization of Line size” III. Update Project Schedule to current plan. | Obiakor, O | 102155 |  |  | $ 47,933.39 N 1,545,750.79 F$ 52,006.51 |  |  |  | F$39,515.51 | Mob and De-mob, Houseboat | TONYMA INVESTMENT
| SECTIONAL REPLACEMENT OF OTUMARA 42LS, 16T FLOWLINES AND FABRICATION OF HOOK-UP ARM OF OTUMARA 4L. | Approved. I. Carry out materials reconciliation with hotdesk and discount available materials. | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  |  | $ 160,601.21 N 61,143,932.41 F$ 321,718.29 |  |  |  | F$82,000 & F$77,000 | F$82,000 (Shared marine logistics) + F$77,000 (Single mob/demob) | ANASAMI
2021-03-11 | UZU MANIFOLD LOCATION PREPARATION | Approved. I. Limit PO value to the contractor to available ACV balance in SAP. II. Engage C&P to update remaining ACV III. Ensure combination of controls is in place for managing community workers. IV. Liase with the planning team to align schedule & demand requirements for IAP | Oludare, S | P.NG.PAE.DG.17.001 |  |  |  | F$: 2,037,279.64 (N: 473,610,898.60, $: 789,293.09) |  |  | F$:107,225.24 | 5 % LOP Discount | RAFFOUL NIG. LIMITED
| FORC 111T Flowline Replacement (6" sch 40 x 2.7 km bulkline) & (4" sch 40 x 0.25 km flowline) | Approved. I. Ensure combination of controls is in place for managing community workers. II. Decomit previously issued PO for Forcados 126S before issuing the new PO for 111T to the Vendor. III. Update Project Schedule to current plan. | Orji, C | C.NG.PAE.DL.21.001.1230 |  |  | $ 251,239.91 N 92,278,553.00 F$ 494,398.16 |  |  |  | 33891.12 | From Materials to be taken from Hot Desk | HENSTEEL ENGINEERING
| FULL REPLACEMENT OF IMOR 36L (4-INCH x 1.0 KM) | Approved. I. Carry out proper material reconciliation with hotdesk. | Aderiye, A | C.NG.PAE.DL.21.001 | $ 47,000.69 N 11,269,553.88 F$ 76,696.49 | [5 empty] | F$: 12,500 | MATERIALS FROM THE SPDC WAREHOUSE. | ROMEK AND COMPANY
| SECTIONAL REPLACEMENT OF (a) IMOR 4-inch TEST LINE (48M) (b) IMOR RIVER 26S (48M) © IMO RIVER 44S (48M) (d) IMO RIVER 55S (48M) (e) IMO RIVER 43T (48M) (f) IMOR 60T (48M) | Approved. I. Prompt engagement with Asset PUM’s to provide enhanced security surveillance for these lines. II. Update Project Schedule to current plan. | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 35,160.13 N 10,617,977.01 F$ 63,138.99 | [5 empty] | FS11,525.18 | MOB & DEMOB. ALL MATERIALS FOR THESE SECTIONAL REPLACEMENT SHALL BE SOURCED FROM SPDC WAREHOUSE | GAMSTEC
| SECTIONAL REPLACEMENT OF (a) IMOR RIVER 6-INCH BULKLINE (IMO 2 -1) X 1500 M (Additional leak points) | Approved. | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 17,777.50 N 5,370,063.42 F$ 31,927.86 | [5 empty] | 8,280.04 USD | MOB & DEMOB IF USING A NEW CONTRACTOR | GAMSTEC
| Provision of lay barge for installation of CCUs at Kanbo W5L/S -Reviewed Offline | Approved. | Ehizonyan, O | C.NG.AFS.DF.18.025.1202 |  |  | $ 22,320.8 N 602,305.87 F$ 23,907.9 |  |  |  | F$: 10,062.00 | Shared marine logistics and security deployment | HENZOL GLOBAL
| Seibou 3 and 4 bulkline JIV and clamping. -Reviewed offline | Approved. I. Update project schedule to current plan | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $ 27,976.94 N 511,967.62 F$ 29,326.00 |  |  |  | 9050.71 | cost saving on inter-area move instead of mobilizing a new contractor. | HENZOL GLOBAL
2021-03-25 | Bonny W14 Maintenance Dredging works | Approved. I. Reiterate the responsibility of the main contractor despite invoice partnering option. II. Ensure safe work completion before contract expiration date. III. Update project schedule to align with current plan IV. 5no top risk to include “Interface management risk” V. Align cost breakdown descriptions with cost summary sheet. VI. Ensure proper HSE & Security plan review. VII. Kick off meeting to emphasize Covid’19 protocols at site. | Onyejekwe, C | 110744 |  |  |  | $: 428,558.82 N: 192,570,123.89 F$: 935,989.97 |  |  | F$: 56,227.33 | Cost saving is from Low Oil Price LoP discounts (i.e. 7.5%). | SHORELINE DREDGING
| Bonny W13 Maintenance Dredging works | Approved. I. Reiterate the responsibility of the main contractor despite invoice partnering option. II. Ensure safe work completion before contract expiration date. III. Update project schedule to align with current plan IV. 5no top risk to include “Interface management risk” V. Align cost breakdown descriptions with cost summary sheet. VI. Ensure proper HSE & Security plan review. VII. Kick off meeting to emphasize Covid’19 protocols at site. | Onyejekwe, C | 110744 |  |  |  | $: 412,055.67 N: 188,667,970.36 F$: 909,204.47 |  |  | F$: 54,055.53 | Cost saving is from Low Oil Price LoP discounts (i.e. 7.5%). | SHORELINE DREDGING
| Kanbo W7S (6’’ x 0.1Km) & W6T (6’’ x 0.1Km) Flowline Sectional Replacement | Deferred. I. Liase with C&P to update remaining ACV for this activity. II. Update summary description of cost saving initiative. | Otavie, G | O.NG.STG.PBE.KAN.007FL O.NG.STG.PBE.KAN.006FL |  |  | $ 122,276.73 N 3,736,362.47 F$ 132,122.22 |  |  |  | F$: $20,000 | Elimination of Mob and De-mob of Houseboat, by latching onto existing houseboat already in Tunu | FEIMA
| Tunu BQRT-3 Flowline Replacement (6" SCH 80 x 6.1km) | Conditional Approval. Update and revert upon completion of these conditions: I. Carry out material reconciliation with hotdesk. II. Update 5no top risk to include “Interface management risk” III. Update summary | Otavie, G | C.NG.AFS.DL.19.006.1230 |  |  | $ 306,292.32 N 117,178,807.88 F$ 615,063.88 |  |  |  | F$: 20,000 | Campaign mobilization will enable the sharing of Marine logistic resources like houseboat which are already in the field | SEVOIL & OSAKS INTEQ
| TUNU BQRT-3 Flowline Replacement (6" Sch 80 x 6.1km) -Resubmission & Reviewed offline | Approved. WORP steers from previous sitting 25/03/21 have been incorporated. | Otavie, G | C.NG.AFS.DL.19.006.1230 |  |  | $ 304,115.16 N 116,379,232 F$ 610,779.8 |  |  |  | F$: 20,000 F$: 4,284.08 | House boat sharing and materials discounted | SEVOIL & OSAKS INTEQ

## WORP Submission Q1
DATE | PROJECT | TYPE | WORP DECISION | STATUS | PE / SPONSOR | WBS | TOTAL VALUE/COST | [5 empty] | COST SAVINGS | Remarks | CONTRACT
[7 empty] | LAND | CENTRAL | SWAMP WEST | CIVIL | OABP ASSET | AF
2021-01-07 | No Submission(s)
2021-01-14 | Replacement of 2” water equalization of Soku cluster B | Fresh | Conditional Approval: Complete the actions below and revert offline - Confirmation availability of signed work request - Finalise the procurement process - MCIA: Baseline integrity request to be carried out. - Engage C&P to negotiate the swamp buggy cost. - Engage C&P on procurement of 2” line pipes - Update all documents as related to contractor change | Conditional Approval | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  | $ 155,435.95 N 7,195,661.10 F$ 174,396.85 |  |  |  |  | Nil |  | KEMUD INT’L
| FORCADOS 127T Flowline Sectional Replacement – (6’’ x 0.05km) | Fresh | Approved. - Update total cost column to reflect realities - Ensure an elaborate kick off meeting with contractor due to change in work environment. | Approved | Obiakor, O | 102155 |  |  | $ 58,352.89 N 1,953,504.45 F$ 63,500.46 |  |  |  | Nil |  | TONYMA INVESTMENT
| Provision of Security/surveillance and Downtime for Tunu BQRT-4 Flowline | Fresh | Approved | Approved | Otavie, G | C.NG.AFS.DL.19.004.1230 |  |  | $49,124.21 N 25,544,732.98 F$116,435.76 |  |  |  | Nil |  | IKONIBO NIG
| Provision of support to CWI for open-up of Tunu BQRT-4(W5ST) | Fresh | Approved. - Reconfirm that there is not/wouldn’t be a double charge on equipment due to resource sharing. - Confirm that all necessary plans, HSE, Security etc are in place and signed off | Approved | Otavie, G | C.NG.AFS.DD.19.005.9411 |  |  | $11,713.68 N10,860,399.09 F$40,331.33 |  |  |  | Nil |  | IKONIBO NIG
| Opukushi 34T Flowline Replacement | Fresh | Approved - Update the narrative in the submission to indicate initial PO will be deleted - Update in the submission G&H to CTS | Approved | Otavie, G | 102155 |  |  | FUSD:390,382.95 NGN:6,387,108.86 USD: 373,574.27 |  |  |  | FUSD: 65,000 | Renegotiated excavation rates, use of only one vendor reduced double mobilization and associated catering costs | WILANDSON
| Opukushi W26T Flowline Replacement (4" x 2km | Fresh | Conditional Approval: Complete the actions below and revert offline - Contract extension to be updated in SAP - Engage PST to reconcile cost - Update submission to reflect risk, work schedule etc | Conditional Approval | Otavie, G | 102155 |  |  | $ 182,085.5 N 66,885,002.36 F$ 401,380.6 |  |  |  | F$: 35,000 | Campaign mobilization will enable the sharing of Marine logistic resources like hosueboat | SEVOIL
| GENERAL |  | Change all submission from OP19 to OP20 Activity owners to confirm support of activities in OP20 before commencing activities. Work allocation spreadsheet to be updated and current at all times.
2021-01-21 | Opukushi W26T Flowline Replacement (4" x 2km) - Resubmission & Reviewed offline | Resubmission | Approved | Approved | Otavie, G | 102155 |  |  | $ 177,590.51 N 65,234,247.10 F$ 349,485.76 |  |  |  | F$: 35,000 | Campaign mobilization will enable the sharing of Marine logistic resources like hosueboat | SEVOIL
| Diebu Creek 9T Flowline Replacement – 4” x 4.2km | Resubmission | Deferred: Complete item below and revert offline - Reconcile materials list with materials HotDesk and EST | Deferred | Uwaezuoke, D | 102155 |  | $337,905.66 N124,092,863.66 F$664,896.08 |  |  |  |  | Nil |  | ANASAMI CONSTRUCTION
| Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km | Fresh | Deferred: Complete items below and revert offline - Reconcile materials list with materials HotDesk and EST - Review work distribution to vendors equitably. | Deferred | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 69,057.09 N 19,127,794.00 F$ 119,459.71 |  |  |  |  | Nil |  | PECKON NIGERIA
| Sectional Replacement Of IMOR Well 32L & GLL Flowlines | Fresh |  |  | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 8,876.10 N 2,214,970.80 F$ 14,712.65 | [5 empty] | Nil |  | ADLAND PROJECTS
| Sectional Replacement Of IMOR4- Inch Delivery Line/57GLL/36S/22S | Fresh |  |  | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 48,732.29 N 14,993,395.11 F$ 88,240.58 | [5 empty] | Nil |  | GAMSTEC INTEGRATED
| DBCU W12T Flowline Replacement (4" Sch 80 x 5km) | Fresh | Deferred: Complete items below and revert offline - Reconcile materials list with materials HotDesk and EST - Review work distribution to vendors equitably. | Deferred | Azaka, G | NIL |  | $ 337,588.93 N 127,747,467.01 F$674,209.40 |  |  |  |  | Nil |  | MIDEN SERVICES
| FORC 126S Flowline Replacement (6” sch 80 x 1.2 km) | Fresh | Deferred: Complete items below and revert offline - Reconcile materials list with materials HotDesk and EST - Review work distribution to vendors equitably. | Deferred | Orji, C | C.NG.PAE.DL.21.001 |  |  | $ 132,054.33 N 48,500,624.65 F$ 259,687.56 |  |  |  | Nil |  | STEVE INEGRATED
| Rehabilitation of 800m failed sections of Obigbo flow station road. | Fresh | Deferred: Complete item below and revert offline - Engage the Asset team to get confirmation from divestment BOM on the execution of this project | Deferred | Ezenduka, D | C.NG.PAE.IC.21.001 |  |  |  | F$: 429,307.22 |  |  | F$: 29,844.89 | 6.5 % LOP Discount | BENCOV NIG
| GENERAL |  | All submissions are be subject to DRB approval EST to share a standard hook up arm materials list template to all
2021-01-28 | Sectional Replacement of Afam 25T Flowline (8” x 12m) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Engage Asset team, EST, HSE, Technical Safety and Security teams to review and sign off method statement. II. Include clamping as a mitigation against spill in the 5 top risks | Conditional Approval | Akinbiyi, A | O.NG.PAE.I1F.FAC.724FC | $ 27,733.14 + 35,712.58 N 46,114,670.79 + 11,048,655.19 F$ 149,247.42 + 64,826.30 | [5 empty] | Nil |  | BG TECHNICAL NIG LTD
| Rehabilitation of 800m failed sections of Obigbo flow station road. -Resubmission | Resubmission | Approved. WORP steers from previous sitting 21-01-21 have been incorporated. | Approved | Ezenduka, D | 110854 |  |  |  | F$: 429,307.22 |  |  | F$: 29,844.89 | 6.5 % LOP Discount | BENCOV NIG
| Addendum to Construction of 1 No. Well bay location Assa-North | Fresh | Approved. I. Resolve ACV balance in SAP II. Update 5 top risks to include Covid19 | Approved | Ezenduka, D | C.NG.ANO.DG.17.004.1231 |  |  |  | F$: 144,200.22 |  |  | F$: 7,589.49 | 5 % LOP Discount | RAFFOULNIG.LIMITED
| FORC 126S Flowline Replacement (6” sch 80 x 1.2 km) -Resubmission & Reviewed Offline | Resubmission | Approved. WORP steers from previous sitting 21-01-21 and 28-01-21 have been incorporated. | Approved | Orji, C | C.NG.PAE.DL.21.001 |  |  | $ 132,054.33 N 48,500,624.65 F$ 259,687.56 |  |  |  | Nil |  | HENSTEEL ENGINEERING
| Sectional Replacement of ImoR Well 32L & GLL | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Update cost saving column with proposed cost savings. II. Reconcile materials list with Hotdesk and expunge cost of available materials from cost estimate. | Conditional Approval | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 8,876.10 N 2,214,970.80 F$ 14,712.65 | [5 empty] | Nil |  | ADLAND PROJECTS
| Sectional Replacement of (a) ImoR 4-inch Delivery line (b) ImoR 57GLL (c) ImoR 36S (d) ImoR 23L (e) ImoR 14L (f) ImoR 6-inch Bulkline (g) ImoR 63T Manifold | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Update cost saving column with cost saved from inter-field move. II. Reconcile materials list with Hotdesk and expunge cost of available materials from cost estimate. | Conditional Approval | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 48,732.29 N 14,993,395.11 F$ 88,240.58 | [5 empty] | Nil |  | GAMSTEC INTEGRATED
| Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km -Resubmission & Reviewed Offline | Resubmission | Approved. WORP steers from previous sitting 21-01-21 have been incorporated. | Approved | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 72,553.73 N 5,439,173.57 F$ 86,886.20 |  |  |  |  | Nil |  | ABBEYCOURT ENERGY
| DBCU W12T Flowline Replacement (4" Sch 80 x 4.8km) -Resubmission & Reviewed Offline | Resubmission | Approved. WORP steers from previous sitting 21-01-21 have been incorporated. | Approved | Azaka, G | NIL |  | $ 324,004.09 N 121,078,352 F$727,442.65 |  |  |  |  | Nil |  | MIDEN SERVICES LTD
2021-02-04 | BONNY WELL 12S & OLOMA FS LIGAMENT VALVES CHANGE -OUT | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Update WBS for this activity. II. Attach an approved e-AEWR. III. Ensure all equipment have valid premob certificates. IV. Specify crew boat type in the cost estimate. V. Ensure detailed security plan review. VI. Update OP’19 to OP’20 in the submission | Conditional Approval | Ehizoyanyan, O | NIL |  | $ 17,399.52 N 2,002,876.74 F$ 22,677.19 |  |  |  |  | Nil |  | SURVEILLANCE 2000
2021-02-11 | Saghara 3S and 5L Flowline Replacement – 4” Sch. 40 x 850m Each (Total = 4” Sch. 40 x 1.7km) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Include fabrication of hook up arm in the work scope. II. Expunge CP survey and balancing from cost estimate. III. Expedite materials availability check with Hotdesk IV. Engage PS for a review of cost estimate. | Conditional Approval | Uwaezuoke, D | O.NG.PBW.SHF.03S.713FL/O.NG.PBW.SHF.05L713FL |  |  | $ 211,509.27 N 77,405,267.22 F$ 415,475.72 |  |  |  | Nil |  | ANASAMI
| Sectional Replacement of (a) ImoR 59T (6-inch) (b) ImoR 25L (4-inch) | Fresh | Approved. I. Include line length in the Project Title | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 12,297.25 N 3,357,092.47 F$ 21,143.34 | [5 empty] | 8280.04 | THERE IS A SAVINGS OF 8,280.04 USD WHICH SHOULD HAVE COVERED MOB & DEMOB USING A NEW CONTRACTOR | GAMSTEC INTEGRATED
| Full Replacement of ImoR 58T (4- inch x 3.4km) | Fresh | Approved. | Approved | Aderiye, A | C.NG.PAE.DL.21.001 | $ 110,900.38 N 26,084,203.78 F$ 179,633.46 | [5 empty] | 12508.36 | THERE IS A SAVINGS OF 12,508.36 FROM THE MATERIALS THAT WILL BE COLLECTED FROM THE SPDC WAREHOUSE | THOMPSON AND GRACE
| Sectional Replacement of Afam 25T flowline (8” x 12m) -Resubmission & reviewed offline | Resubmission | Approved. WORP steers from previous sitting 28/01/21 have been incorporated. | Approved | Dienagha, I | O.NG.PAE.I1F.FAC.724FC | $ 30,998.84 + 35,712.58 N 52,409,398.79 + 11,048,655.19 F$ 169,100.02 + 64,826.30 | [5 empty] | Nil |  | GAMSTEC INTEGRATED
| GENERAL |  | Ensure all cost are independently assured by PS. • Advise the team on when to commence movement of bare pipes to coating vendors (SOLEWANT & PCN). • Confirm availability of coated pipes from stockist. • Send sample of disused spool piece from Saghara 3S & 5L to MCI for analysis. • Expunge CP survey and balancing from cost estimate and where necessary, reports should be provided for documentation • Early request for Houseboat to the marine team • Ensure kickoff meetings are held prior mobilizations.
2021-02-18 | : LOCATION DREDGING WORKS AT BENISEDE EAUA-2. | Fresh | Approved. I. Liase with OABP focal persons to confirm ETC/OTC availability. | Approved | Onyejekwe, C | C.NG.AFS.DD.19.009.9401 |  |  |  | $: 103,003.11 N: 267,683,624.79 F$: 808,361.80 |  |  | F$: 115,543.79 | Low Oil Price LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| FULL REPLACEMENT OF OGUTA 16S FLOWLINE (4” X 2.9KM) | Fresh | NOT TREATED |  | Akinbiyi, A | 102155 | $ 91,808.64 N 26,740,513.71 F$ 179,482.45 | [5 empty] | Nil |  | MORRAY SERVICES
| FULL REPLACEMENT OF OGUTA 25T FLOWLINE (4” X 5.6KM) | Fresh | NOT TREATED |  | Akinbiyi, A | 102155 | $ 227,072.62 N 51,829,929.49 F$ 363,646.87 | [5 empty] | Nil |  | GESON INVESTMENT
| FULL REPLACEMENT OF OGUTA 12T FLOWLINE (4” X 4.3KM) | Fresh | NOT TREATED |  | Akinbiyi, A | 102155 | $ 140,649.15 N 17,728,986.10 F$ 187,365.85 | [5 empty] | Nil |  | ABBEYCOURT
| INTEGRITY CHECK OF AGBADA 67T GAS LINE | Fresh | Conditional Approval Update and resubmit upon completion of these conditions: I. Update WBS for this activity. II. Formal engagement with the Pipeline Contract Holder and review contract line items. III. Review work method statement with the vendor IV. Recourse option of engaging a flowline vendor to manage the overall activity. | Conditional Approval | Dienagha, I | NIL | $ 47,136.48 N 76,378,129.79 F$ 248,131.56 | [5 empty] | Nil |  | BG TECHNICAL
| BONNY W30T Flowline Replacement (4" Sch 80 x 1km) | Fresh | Deferred. I. Stepped down for a proper internal review by Project Lead. | Stepped Down | Azaka, G | NIL |  | $ 104,781.24 N 38,486,464.52 F$206,194.85 |  |  |  |  | Nil |  | VANDRESSER NIG
| Tunu CDRY-3 Flowline Construction (6" x 2.1km) & Tunu CDRY-4 Wellhead Platform Installation and hookup | Fresh | Approved. I. Update cost saving column with the proposed cost savings. II. Liase with C&P to affirm benchmark rates | Approved | Azaka, G | C.NG.AFS.DF.19.003.1200 |  |  | $324,929.80 N 118,704,995.67 F$ 637,697.73 |  |  |  | Nil |  | IKONIBO NIG
| Replacement of 1,75KM of 2” water equalization of Soku cluster D | Fresh | Deferred. I. Provide and attach basis for the additional 1.75km scope. II. Engage EST & Geomatics for a proper review III. Review and simplify execution strategy. | Deferred | Obioakor, O | NIL |  | $ 225,297.74 N 13,915,985.80 F$ 261,967.01 |  |  |  |  | Nil |  | HENZOL, KEMUD, VISCA
| FULL REPLACEMENT OF IMOR 58T (4-INCH x 3.4KM) | Fresh | Approved. I. Proceed to execution with the proposed new vendor (WILKRISS NIG. LTD) II. Ensure the MoM and offer decline letter from Thompson & Grace Investment Ltd is duly signed for documentation | Approved | Aderiye, A | C.NG.PAE.DL.21.001 | $ 137,763.36 N 12,884,978.45 F$ 179,633.46 | [5 empty] | 14800 | Warehouse Materials | WILKRISS
| SAGHARA 3S & 5L FLOWLINE REPLACEMENT – 4” Sch. 40 x 850m each (Total = 4” Sch. 40 x 1.7km). Resubmission & Reviewed offline | Resubmission | Approved. WORP steers from previous sitting 11/02/21 have been incorporated | Approved | Uwaezuoke, D | O.NG.PBW.SHF.03S.713FL/O.NG.PBW.SHF.05L.713FL |  |  | $ 204,508.67 N 74,834,367.87 F$ 401,700.68 |  |  |  | Nil |  | ANASAMI CONSTRUCTION
2021-02-25 | BONNY W30T Flowline Replacement (4" Sch 80 x 1km) | Resubmission | Conditional Approval. WORP steers from previous sitting 18/02 have not been fully incorporated. I. Engage WRFM to provide WBS for this activity and resubmit offline | Conditional Approval | Azaka, G | NIL |  | $ 101,126.24 N 37,144,159.42 F$199,002.81 |  |  |  |  | Nil |  | VANDRESSER NIG
| OTUMARA FLOW STATION GANTRY WORKS | Fresh | Deferred. I. Update WBS for this activity. II. Engage EST to review existing structural frame and attach schematic drawing. III. Confirm Gantry maximum load. | Deferred | Azaka, G | NIL |  |  | $ 187,308.06 N 6,577,567.94 F$206,814.41 |  |  |  | Nil |  | NAPEBI CONSTRUCTION
| KOCR 22T Flowline Sectional Replacement – 4” sch. 40 x 0.06km and 8” Sch 160 x 0.012km | Fresh | Approved. I. Forward approved e-WR to the Secretariat and Manager. II. Plan for mitigation against Vendors under performance due to low project cost. | Approved | Arowosafe, T | O.NG.PAE.GBG.FAC.724FC |  | $ 55,973.34 N 4,979,690.78 F$ 69,,095.05 |  |  |  |  | Nil |  | ABBEYCOURT ENERGY
| K2S Simultaneous Flow Project | Fresh | Approved. I. Engage CH to update ACV split currency values. II. Carry out materials check with Hotdesk. III. Emphasize criticality of this activity with the Vendor. | Approved | Akoma, I | C.NG.PBE.DF.21.005 |  | $ - 104,725.16 N - 36,794,719.22 F$ - 201,680.94 |  |  |  |  | F$: 22,416.83 | Savings on Mob and De-mob by using same contractor for Mechanical/ Instrumentation works, etc | GRAMEN PETROSERVE
| Replacement of LP header of Yokri flow station. -Reviewed offline | Fresh | Approved | Approved | Obiakor, O | O.NG.PCW.YKF.FAC.71300 |  |  | $ 31,865.72 N 375,865.72 F$ 32,854.55 |  |  |  | 23907.23 | saved for combining mobilization of Forcados Yokri 127T flowline sectional replacement and replacement of Yokri LP header | TONYMAR INVESTMENT
| GENERAL |  | Review materials reconciliation tracking system and communicate to leadership: ▪ Flowlines ▪ Facilities
2021-03-04 | FODPA and NEFS Boatlanding Rehabilitation Works | Fresh | Approved. I. Confirm full budget availability for these activities. II. Carry out materials reconciliation with Hotdesk. III. Ensure security plan is properly reviewed and assurance provided for adequate cover at site | Approved | Uwaezuoke, D | F$: C.NG.PBW.DF.212.001 – FODPA F$: C.NG.PCW.DF.98.706.1230 - NEFS |  |  | Total: FODPA + NEFS = F$394,395.64 |  |  |  | Nil |  | Gramen Petroserve
| FULL REPLACEMENT OF OGUTA 12T FLOWLINE(4” X 4.3KM) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Confirm WBS for this activity. II. Carry out materials reconciliation with Hotdesk and discount available materials. III. Update Project Schedule to current plan. IV. Include Fabrication & Hook up in the scope summary. V. Confirm linepipes availability for this activity. VI. Align POB requirement with OABP Central Team | Conditional Approval | Akinbiyi, A | 102155 | $ 132,486.76 N 37,684,516.42 F$ 231,787.20 | [5 empty] | Nil |  | WILKRISS
| FULL REPLACEMENT OF OGUTA 16S FLOWLINE(4” X 2.9KM) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Confirm WBS for this activity. II. Carry out materials reconciliation with Hotdesk and discount available materials. III. Update Project Schedule to current plan. IV. Include Fabrication & Hook up in the scope summary. V. Confirm linepipes availability for this activity. VI. Align POB requirement with OABP Central Team | Conditional Approval | Akinbiyi, A | 102155 | $ 91,808.64 N 26,740,513.71 F$ 179,482.45 | [5 empty] | Nil |  | MORRAY SERVICES
| FULL REPLACEMENT OF OGUTA 25T FLOWLINE(4” X 5.6KM) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Confirm WBS for this activity. II. Carry out materials reconciliation with Hotdesk and discount available materials. III. Update Project Schedule to current plan. IV. Include Fabrication & Hook up in the scope summary. V. Confirm linepipes availability for this activity. VI. Align POB requirement with OABP Central Team | Conditional Approval | Akinbiyi, A | 102155 | $ 165,827.86 N 46,524,990.84 F$ 288,423.35 | [5 empty] | Nil |  | GUIZ AND COMPANY
| LEAK REPAIR OF FORCADOS 127T FLOWLINE | Fresh | Approved. I. Engage WRFM to confirm WBS for this activity. II. Update Project title to include “Optimization of Line size” III. Update Project Schedule to current plan. | Approved | Obiakor, O | 102155 |  |  | $ 47,933.39 N 1,545,750.79 F$ 52,006.51 |  |  |  | F$39,515.51 | Mob and De-mob, Houseboat | TONYMA INVESTMENT
| SECTIONAL REPLACEMENT OF OTUMARA 42LS, 16T FLOWLINES AND FABRICATION OF HOOK-UP ARM OF OTUMARA 4L. | Fresh | Approved. I. Carry out materials reconciliation with hotdesk and discount available materials. | Approved | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  |  | $ 160,601.21 N 61,143,932.41 F$ 321,718.29 |  |  |  | F$82,000 & F$77,000 | F$82,000 (Shared marine logistics) + F$77,000 (Single mob/demob) | ANASAMI
| Diebu Creek 8T Flowline Replacement – 4” x 3.07km | Fresh | Stepped down by the team | Stepped down | Ehizoyanyan, O | WRFM 102155 |  | $228,572.93 N 83,941,422.41 F$449,762.45 |  |  |  |  | Nil |  | SEVOIL LTD
| BONN 12S Flowline Replacement – 4” x 1.7km | Fresh | Stepped down by the team | Stepped down | Ehizoyanyan, O
| BONNY W30T Flowline Replacement (4" Sch 80 x 1km) -Resubmission & Reviewed offline | Resubmission & Reviewed Offline | Approved. WORP steer from previous sitting 25/02/21 have been incorporated. | Approved | Azaka, G | NIL |  | $ 101,126.24 N 37,144,159.42 F$199,002.81 |  |  |  |  | Nil |  | VANDRESSER NIG
| GENERAL |  | Ensure timely checks on materials availability prior to WORP submission. • Only funded activities should be brought into plan and ensure alignment of execution with IAP central team. • Proper security plan review / HSE documentation for each project before mobilization. • Early engagement on marine request to avoid delayed mobilization to sites.
2021-03-11 | UZU MANIFOLD LOCATION PREPARATION | Fresh | Approved. I. Limit PO value to the contractor to available ACV balance in SAP. II. Engage C&P to update remaining ACV III. Ensure combination of controls is in place for managing community workers. IV. Liase with the planning team to align schedule & demand requirements for IAP | Approved | Oludare, S | P.NG.PAE.DG.17.001 |  |  |  | F$: 2,037,279.64 (N: 473,610,898.60, $: 789,293.09) |  |  | F$:107,225.24 | 5 % LOP Discount | RAFFOUL NIG. LIMITED
| FORC 111T Flowline Replacement (6" sch 40 x 2.7 km bulkline) & (4" sch 40 x 0.25 km flowline) | Fresh | Approved. I. Ensure combination of controls is in place for managing community workers. II. Decomit previously issued PO for Forcados 126S before issuing the new PO for 111T to the Vendor. III. Update Project Schedule to current plan. | Approved | Orji, C | C.NG.PAE.DL.21.001.1230 |  |  | $ 251,239.91 N 92,278,553.00 F$ 494,398.16 |  |  |  | 33891.12 | From Materials to be taken from Hot Desk | HENSTEEL ENGINEERING
| FULL REPLACEMENT OF IMOR 36L (4-INCH x 1.0 KM) | Fresh | Approved. I. Carry out proper material reconciliation with hotdesk. | Approved | Aderiye, A | C.NG.PAE.DL.21.001 | $ 47,000.69 N 11,269,553.88 F$ 76,696.49 | [5 empty] | F$: 12,500 | MATERIALS FROM THE SPDC WAREHOUSE. | ROMEK AND COMPANY
| SECTIONAL REPLACEMENT OF (a) IMOR 4-inch TEST LINE (48M) (b) IMOR RIVER 26S (48M) © IMO RIVER 44S (48M) (d) IMO RIVER 55S (48M) (e) IMO RIVER 43T (48M) (f) IMOR 60T (48M) | Fresh | Approved. I. Prompt engagement with Asset PUM’s to provide enhanced security surveillance for these lines. II. Update Project Schedule to current plan. | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 35,160.13 N 10,617,977.01 F$ 63,138.99 | [5 empty] | FS11,525.18 | MOB & DEMOB. ALL MATERIALS FOR THESE SECTIONAL REPLACEMENT SHALL BE SOURCED FROM SPDC WAREHOUSE | GAMSTEC
| SECTIONAL REPLACEMENT OF (a) IMOR RIVER 6-INCH BULKLINE (IMO 2 -1) X 1500 M (Additional leak points) | Fresh | Approved. | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 17,777.50 N 5,370,063.42 F$ 31,927.86 | [5 empty] | 8,280.04 USD | MOB & DEMOB IF USING A NEW CONTRACTOR | GAMSTEC
| Diebu Creek 8T Flowline Replacement – 4” x 3.07km | Fresh | Conditional Approval. Subject to NAPIMS engagement on contract expiration date extension. | Conditional Approval | Ehizonyan, O | O.NG.PBE.DBC.09T.713FL |  | $238,624..58 N 87,632,760.32 F$469,540.94 |  |  |  |  | Nil |  | SEVOIL LTD
| FULL REPLACEMENT OF ETELEBOU 3S FLOWLINE (4” X 1.2KM) | Fresh | Approved: Premised on early mobilization. I. Update contract end date and engage NAPIMS. II. Forward cost savings to I&A for documentation. | Approved | Otavie, G | O.NG.PAE.ETL.03S.713FL |  | $ 57,925.84 N 13,410,314.07 F$ 85,626.42 |  |  |  |  | Nil |  | PECKON NIGERIA
| BONNY W18S Flowline Replacement (4" Sch 40 x 1.2km) | Fresh | Conditional Approval. I. Carry out work distribution alignment across team. II. Confirm Contractors capacity to execute | Conditional Approval | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  | $ 133,308.68 N 48,964,351.92 F$262,332.00 |  |  |  |  | Nil |  | IKONIBO
| Provision of lay barge for installation of CCUs at Kanbo W5L/S -Reviewed Offline | Fresh | Approved. | Approved | Ehizonyan, O | C.NG.AFS.DF.18.025.1202 |  |  | $ 22,320.8 N 602,305.87 F$ 23,907.9 |  |  |  | F$: 10,062.00 | Shared marine logistics and security deployment | HENZOL GLOBAL
2021-03-18 | Replacement of 1,75KM of 2” water equalization of Soku cluster D | Resubmission | Conditional Approval. WORP steers from previous sitting 18/02/21 have been incorporated. Further steers: I. Attach signed MoM of review meeting held with EST & Geomatics. II. Update WBS for this activity. III. Engage vendor & secure commitment to execute work accordingly. IV. Liase with C&P to load contract in SAP. | Conditional Approval | Obiakor, O | Nil |  | $ 107,282.92 N 39,409,715.49 F$211,129.34 |  |  |  |  | Nil |  | VANDREZZER NIG. LTD
| BOGT SHORE PROTECTION – PHASE1 | Fresh | Approved. I. Focused attention on vendor HSE risk management before and during site works. II. Review & accelerate project schedule. III. Proceed with interim plan to safeguard shoreline before actual work execution. IV. Kick off meeting to include Vendor top management in view of the nature of work. | Approved | Ogunkunle, M | C.NG.PBE.IC.07.001 |  |  |  | F$ 875,727.01 N69,244,408.04 + $693,264.80 |  |  | Nil |  | PILE FOUNDATION LIMITED
| Seibou 3 and 4 bulkline JIV and clamping. -Reviewed offline | Fresh | Approved. I. Update project schedule to current plan | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $ 27,976.94 N 511,967.62 F$ 29,326.00 |  |  |  | 9050.71 | cost saving on inter-area move instead of mobilizing a new contractor. | HENZOL GLOBAL
| GENERAL |  | Engage the relevant authorities with proposal to include equalization lines in FIMS for ease of line tracking and integrity monitoring.
2021-03-25 | Bonny W14 Maintenance Dredging works | Fresh | Approved. I. Reiterate the responsibility of the main contractor despite invoice partnering option. II. Ensure safe work completion before contract expiration date. III. Update project schedule to align with current plan IV. 5no top risk to include “Interface management risk” V. Align cost breakdown descriptions with cost summary sheet. VI. Ensure proper HSE & Security plan review. VII. Kick off meeting to emphasize Covid’19 protocols at site. | Approved | Onyejekwe, C | 110744 |  |  |  | $: 428,558.82 N: 192,570,123.89 F$: 935,989.97 |  |  | F$: 56,227.33 | Cost saving is from Low Oil Price LoP discounts (i.e. 7.5%). | SHORELINE DREDGING
| Bonny W13 Maintenance Dredging works | Fresh | Approved. I. Reiterate the responsibility of the main contractor despite invoice partnering option. II. Ensure safe work completion before contract expiration date. III. Update project schedule to align with current plan IV. 5no top risk to include “Interface management risk” V. Align cost breakdown descriptions with cost summary sheet. VI. Ensure proper HSE & Security plan review. VII. Kick off meeting to emphasize Covid’19 protocols at site. | Approved | Onyejekwe, C | 110744 |  |  |  | $: 412,055.67 N: 188,667,970.36 F$: 909,204.47 |  |  | F$: 54,055.53 | Cost saving is from Low Oil Price LoP discounts (i.e. 7.5%). | SHORELINE DREDGING
| Enwhe East Flare Test Pit and Bundwall Construction Work | Fresh | Approved. I. Capture cost savings and forward to I&A for reporting. II. Update project schedule to align with current plan III. Update appropriately the remaining ACV for this submission. | Approved | Otavie, G | C.NG.LNG.DG.19.004.1230 |  | $ 54,465.13 N 113,596,678.73 F$ 353,797.61 |  |  |  |  | Nil |  | Gramen Petroserve
| Enwhe West Flare Test Pit and Bundwall Construction Work | Fresh | Approved. I. Update project schedule to align with current plan. II. Update appropriately the remaining ACV for this submission III. Ensure vendor has adequate resources to deliver according to schedule. | Approved | Uwaezuoke, D | C.NG.LNG.DG.19.004.1230 |  | $ 49,888.81 N 95,735,716.20 F$ 302,156.84 |  |  |  |  | Nil |  | Gramen Petroserve
| Estuary Cluster 51 Ring A Replacement Work ahead of FORC73 Workover | Fresh | Approved. I. Ensure safe work completion before contract expiration date. II. Update project schedule to align with current plan. III. Harmonize project title with other relevant documentation. | Approved | Uwaezuoke, D | O.NG.STG.PBE.FOR.072FL |  |  | $ 102,377.04 N 26,433,707.21 F$ 172,031.08 |  |  |  | Nil |  | Miden Systems Ltd
| Kanbo 5LS TRP Outage surveillance cover. | Fresh | Approved. I. Vendor to deploy adequate resources for security surveillance. | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $ 31,947.75 N 372,012.45 F$ 32,928.02 |  |  |  | Nil |  | HENZOL GLOBA
| Kanbo W7S (6’’ x 0.1Km) & W6T (6’’ x 0.1Km) Flowline Sectional Replacement | Fresh | Deferred. I. Liase with C&P to update remaining ACV for this activity. II. Update summary description of cost saving initiative. | Deferred | Otavie, G | O.NG.STG.PBE.KAN.007FL O.NG.STG.PBE.KAN.006FL |  |  | $ 122,276.73 N 3,736,362.47 F$ 132,122.22 |  |  |  | F$: $20,000 | Elimination of Mob and De-mob of Houseboat, by latching onto existing houseboat already in Tunu | FEIMA
| FORC 110T & FORC 112T Integrity Checks | Fresh | Deferred. I. Liase with C&P to update remaining ACV for this activity | Deferred | Orji, C | C.NG.PCW.DL.21.001 |  |  | $ 64,269.17 N 1,986,542.12 F$ 69,503.80 |  |  |  | Nil |  | TUSOJA MARINE
| Tunu BQRT-3 Flowline Replacement (6" SCH 80 x 6.1km) | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Carry out material reconciliation with hotdesk. II. Update 5no top risk to include “Interface management risk” III. Update summary | Conditional Approval | Otavie, G | C.NG.AFS.DL.19.006.1230 |  |  | $ 306,292.32 N 117,178,807.88 F$ 615,063.88 |  |  |  | F$: 20,000 | Campaign mobilization will enable the sharing of Marine logistic resources like houseboat which are already in the field | SEVOIL & OSAKS INTEQ
| GENERAL |  | Escalate security challenges in Kanbo and Seibou axis to Security LT.
2021-04-01 | FORC 110T & FORC 112T INTEGRITY CHECKS | Resubmission | Approved. I. Update Contractor’s name with the correct spelling in the submission. II. Include value proposition (bopd) for both lines. III. Indicate all the WBS provided for this project and charge each flowline cost to specific WBS provided IV. Review and update risk No3 in the top risks. | Approved | Orji, C | O.NG.STG.PBE.FOR.110FL |  |  | $ 64,269.17 N 1,986,542.12 F$ 69,503.80 |  |  |  | Nil |  | ELKON INTEGRATED
| TUNU BQRT-3 Flowline Replacement (6" Sch 80 x 6.1km) -Resubmission & Reviewed offline | Resubmission | Approved. WORP steers from previous sitting 25/03/21 have been incorporated. | Approved | Otavie, G | C.NG.AFS.DL.19.006.1230 |  |  | $ 304,115.16 N 116,379,232 F$ 610,779.8 |  |  |  | F$: 20,000 F$: 4,284.08 | House boat sharing and materials discounted | SEVOIL & OSAKS INTEQ
| BONNY W18S Flowline Replacement (4" Sch 40 x 1.2km) -Resubmission & Reviewed offline | Resubmission | Approved. WORP steers from previous sitting 11/03/21 have been incorporated. | Approved | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  | $ 132,180.84 N 48,550,109.36 F$260,112.61 |  |  |  |  | Nil |  | IKONIBO NIG
| GENERAL |  | Always ensure equitable work allocation.

## Q1 Savings
DATE | PROJECT | TYPE | WORP DECISION | STATUS | PE / SPONSOR | WBS | TOTAL VALUE/COST | [5 empty] | COST SAVINGS (FUSD) | Remarks | CONTRACT
[7 empty] | LAND | CENTRAL | SWAMP WEST | CIVIL | OABP ASSET | AF
2021-01-07 | No Submission(s)
2021-01-14 | Replacement of 2” water equalization of Soku cluster B | Fresh | Conditional Approval: Complete the actions below and revert offline - Confirmation availability of signed work request - Finalise the procurement process - MCIA: Baseline integrity request to be carried out. - Engage C&P to negotiate the swamp buggy cost. - Engage C&P on procurement of 2” line pipes - Update all documents as related to contractor change | Conditional Approval | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  | $ 155,435.95 N 7,195,661.10 F$ 174,396.85 |  |  |  |  | Nil |  | KEMUD INT’L
| FORCADOS 127T Flowline Sectional Replacement – (6’’ x 0.05km) | Fresh | Approved. - Update total cost column to reflect realities - Ensure an elaborate kick off meeting with contractor due to change in work environment. | Approved | Obiakor, O | 102155 |  |  | $ 58,352.89 N 1,953,504.45 F$ 63,500.46 |  |  |  | Nil |  | TONYMA INVESTMENT
| Provision of Security/surveillance and Downtime for Tunu BQRT-4 Flowline | Fresh | Approved | Approved | Otavie, G | C.NG.AFS.DL.19.004.1230 |  |  | $49,124.21 N 25,544,732.98 F$116,435.76 |  |  |  | Nil |  | IKONIBO NIG
| Provision of support to CWI for open-up of Tunu BQRT-4(W5ST) | Fresh | Approved. - Reconfirm that there is not/wouldn’t be a double charge on equipment due to resource sharing. - Confirm that all necessary plans, HSE, Security etc are in place and signed off | Approved | Otavie, G | C.NG.AFS.DD.19.005.9411 |  |  | $11,713.68 N10,860,399.09 F$40,331.33 |  |  |  | Nil |  | IKONIBO NIG
| Opukushi 34T Flowline Replacement | Fresh | Approved - Update the narrative in the submission to indicate initial PO will be deleted - Update in the submission G&H to CTS | Approved | Otavie, G | 102155 |  |  | FUSD:390,382.95 NGN:6,387,108.86 USD: 373,574.27 |  |  |  | 65000 | Renegotiated excavation rates, use of only one vendor reduced double mobilization and associated catering costs | WILANDSON
| Opukushi W26T Flowline Replacement (4" x 2km | Fresh | Conditional Approval: Complete the actions below and revert offline - Contract extension to be updated in SAP - Engage PST to reconcile cost - Update submission to reflect risk, work schedule etc | Conditional Approval | Otavie, G | 102155 |  |  | $ 182,085.5 N 66,885,002.36 F$ 401,380.6 |  |  |  | F$: 35,000 | Campaign mobilization will enable the sharing of Marine logistic resources like hosueboat | SEVOIL
| GENERAL |  | Change all submission from OP19 to OP20 Activity owners to confirm support of activities in OP20 before commencing activities. Work allocation spreadsheet to be updated and current at all times.
2021-01-21 | Opukushi W26T Flowline Replacement (4" x 2km) - Resubmission & Reviewed offline | Resubmission | Approved | Approved | Otavie, G | 102155 |  |  | $ 177,590.51 N 65,234,247.10 F$ 349,485.76 |  |  |  | 35000 | Campaign mobilization will enable the sharing of Marine logistic resources like hosueboat | SEVOIL
| Diebu Creek 9T Flowline Replacement – 4” x 4.2km | Resubmission | Deferred: Complete item below and revert offline - Reconcile materials list with materials HotDesk and EST | Deferred | Uwaezuoke, D | 102155 |  | $337,905.66 N124,092,863.66 F$664,896.08 |  |  |  |  | Nil |  | ANASAMI CONSTRUCTION
| Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km | Fresh | Deferred: Complete items below and revert offline - Reconcile materials list with materials HotDesk and EST - Review work distribution to vendors equitably. | Deferred | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 69,057.09 N 19,127,794.00 F$ 119,459.71 |  |  |  |  | Nil |  | PECKON NIGERIA
| Sectional Replacement Of IMOR Well 32L & GLL Flowlines | Fresh |  |  | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 8,876.10 N 2,214,970.80 F$ 14,712.65 | [5 empty] | Nil |  | ADLAND PROJECTS
| Sectional Replacement Of IMOR4- Inch Delivery Line/57GLL/36S/22S | Fresh |  |  | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 48,732.29 N 14,993,395.11 F$ 88,240.58 | [5 empty] | Nil |  | GAMSTEC INTEGRATED
| DBCU W12T Flowline Replacement (4" Sch 80 x 5km) | Fresh | Deferred: Complete items below and revert offline - Reconcile materials list with materials HotDesk and EST - Review work distribution to vendors equitably. | Deferred | Azaka, G | NIL |  | $ 337,588.93 N 127,747,467.01 F$674,209.40 |  |  |  |  | Nil |  | MIDEN SERVICES
| FORC 126S Flowline Replacement (6” sch 80 x 1.2 km) | Fresh | Deferred: Complete items below and revert offline - Reconcile materials list with materials HotDesk and EST - Review work distribution to vendors equitably. | Deferred | Orji, C | C.NG.PAE.DL.21.001 |  |  | $ 132,054.33 N 48,500,624.65 F$ 259,687.56 |  |  |  | Nil |  | STEVE INEGRATED
| Rehabilitation of 800m failed sections of Obigbo flow station road. | Fresh | Deferred: Complete item below and revert offline - Engage the Asset team to get confirmation from divestment BOM on the execution of this project | Deferred | Ezenduka, D | C.NG.PAE.IC.21.001 |  |  |  | F$: 429,307.22 |  |  | F$: 29,844.89 | 6.5 % LOP Discount | BENCOV NIG
| GENERAL |  | All submissions are be subject to DRB approval EST to share a standard hook up arm materials list template to all
2021-01-28 | Sectional Replacement of Afam 25T Flowline (8” x 12m) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Engage Asset team, EST, HSE, Technical Safety and Security teams to review and sign off method statement. II. Include clamping as a mitigation against spill in the 5 top risks | Conditional Approval | Akinbiyi, A | O.NG.PAE.I1F.FAC.724FC | $ 27,733.14 + 35,712.58 N 46,114,670.79 + 11,048,655.19 F$ 149,247.42 + 64,826.30 | [5 empty] | Nil |  | BG TECHNICAL NIG LTD
| Rehabilitation of 800m failed sections of Obigbo flow station road. -Resubmission | Resubmission | Approved. WORP steers from previous sitting 21-01-21 have been incorporated. | Approved | Ezenduka, D | 110854 |  |  |  | F$: 429,307.22 |  |  | 29844.89 | 6.5 % LOP Discount | BENCOV NIG
| Addendum to Construction of 1 No. Well bay location Assa-North | Fresh | Approved. I. Resolve ACV balance in SAP II. Update 5 top risks to include Covid19 | Approved | Ezenduka, D | C.NG.ANO.DG.17.004.1231 |  |  |  | F$: 144,200.22 |  |  | 7589.49 | 5 % LOP Discount | RAFFOULNIG.LIMITED
| FORC 126S Flowline Replacement (6” sch 80 x 1.2 km) -Resubmission & Reviewed Offline | Resubmission | Approved. WORP steers from previous sitting 21-01-21 and 28-01-21 have been incorporated. | Approved | Orji, C | C.NG.PAE.DL.21.001 |  |  | $ 132,054.33 N 48,500,624.65 F$ 259,687.56 |  |  |  | Nil |  | HENSTEEL ENGINEERING
| Sectional Replacement of ImoR Well 32L & GLL | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Update cost saving column with proposed cost savings. II. Reconcile materials list with Hotdesk and expunge cost of available materials from cost estimate. | Conditional Approval | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 8,876.10 N 2,214,970.80 F$ 14,712.65 | [5 empty] | Nil |  | ADLAND PROJECTS
| Sectional Replacement of (a) ImoR 4-inch Delivery line (b) ImoR 57GLL (c) ImoR 36S (d) ImoR 23L (e) ImoR 14L (f) ImoR 6-inch Bulkline (g) ImoR 63T Manifold | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Update cost saving column with cost saved from inter-field move. II. Reconcile materials list with Hotdesk and expunge cost of available materials from cost estimate. | Conditional Approval | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 48,732.29 N 14,993,395.11 F$ 88,240.58 | [5 empty] | Nil |  | GAMSTEC INTEGRATED
| Adibawa 12T Flowline Replacement – 4” sch. 40 x 1.1km -Resubmission & Reviewed Offline | Resubmission | Approved. WORP steers from previous sitting 21-01-21 have been incorporated. | Approved | Arowosafe, T | C.NG.PAE.DL.21.001.1230 |  | $ 72,553.73 N 5,439,173.57 F$ 86,886.20 |  |  |  |  | Nil |  | ABBEYCOURT ENERGY
| DBCU W12T Flowline Replacement (4" Sch 80 x 4.8km) -Resubmission & Reviewed Offline | Resubmission | Approved. WORP steers from previous sitting 21-01-21 have been incorporated. | Approved | Azaka, G | NIL |  | $ 324,004.09 N 121,078,352 F$727,442.65 |  |  |  |  | Nil |  | MIDEN SERVICES LTD
2021-02-04 | BONNY WELL 12S & OLOMA FS LIGAMENT VALVES CHANGE -OUT | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Update WBS for this activity. II. Attach an approved e-AEWR. III. Ensure all equipment have valid premob certificates. IV. Specify crew boat type in the cost estimate. V. Ensure detailed security plan review. VI. Update OP’19 to OP’20 in the submission | Conditional Approval | Ehizoyanyan, O | NIL |  | $ 17,399.52 N 2,002,876.74 F$ 22,677.19 |  |  |  |  | Nil |  | SURVEILLANCE 2000
2021-02-11 | Saghara 3S and 5L Flowline Replacement – 4” Sch. 40 x 850m Each (Total = 4” Sch. 40 x 1.7km) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Include fabrication of hook up arm in the work scope. II. Expunge CP survey and balancing from cost estimate. III. Expedite materials availability check with Hotdesk IV. Engage PS for a review of cost estimate. | Conditional Approval | Uwaezuoke, D | O.NG.PBW.SHF.03S.713FL/O.NG.PBW.SHF.05L713FL |  |  | $ 211,509.27 N 77,405,267.22 F$ 415,475.72 |  |  |  | Nil |  | ANASAMI
| Sectional Replacement of (a) ImoR 59T (6-inch) (b) ImoR 25L (4-inch) | Fresh | Approved. I. Include line length in the Project Title | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 12,297.25 N 3,357,092.47 F$ 21,143.34 | [5 empty] | 8280.04 | THERE IS A SAVINGS OF 8,280.04 USD WHICH SHOULD HAVE COVERED MOB & DEMOB USING A NEW CONTRACTOR | GAMSTEC INTEGRATED
| Full Replacement of ImoR 58T (4- inch x 3.4km) | Fresh | Approved. | Approved | Aderiye, A | C.NG.PAE.DL.21.001 | $ 110,900.38 N 26,084,203.78 F$ 179,633.46 | [5 empty] | 12508.36 | THERE IS A SAVINGS OF 12,508.36 FROM THE MATERIALS THAT WILL BE COLLECTED FROM THE SPDC WAREHOUSE | THOMPSON AND GRACE
| Sectional Replacement of Afam 25T flowline (8” x 12m) -Resubmission & reviewed offline | Resubmission | Approved. WORP steers from previous sitting 28/01/21 have been incorporated. | Approved | Dienagha, I | O.NG.PAE.I1F.FAC.724FC | $ 30,998.84 + 35,712.58 N 52,409,398.79 + 11,048,655.19 F$ 169,100.02 + 64,826.30 | [5 empty] | Nil |  | GAMSTEC INTEGRATED
| GENERAL |  | Ensure all cost are independently assured by PS. • Advise the team on when to commence movement of bare pipes to coating vendors (SOLEWANT & PCN). • Confirm availability of coated pipes from stockist. • Send sample of disused spool piece from Saghara 3S & 5L to MCI for analysis. • Expunge CP survey and balancing from cost estimate and where necessary, reports should be provided for documentation • Early request for Houseboat to the marine team • Ensure kickoff meetings are held prior mobilizations.
2021-02-18 | : LOCATION DREDGING WORKS AT BENISEDE EAUA-2. | Fresh | Approved. I. Liase with OABP focal persons to confirm ETC/OTC availability. | Approved | Onyejekwe, C | C.NG.AFS.DD.19.009.9401 |  |  |  | $: 103,003.11 N: 267,683,624.79 F$: 808,361.80 |  |  | 115543.79 | Low Oil Price LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| FULL REPLACEMENT OF OGUTA 16S FLOWLINE (4” X 2.9KM) | Fresh | NOT TREATED |  | Akinbiyi, A | 102155 | $ 91,808.64 N 26,740,513.71 F$ 179,482.45 | [5 empty] | Nil |  | MORRAY SERVICES
| FULL REPLACEMENT OF OGUTA 25T FLOWLINE (4” X 5.6KM) | Fresh | NOT TREATED |  | Akinbiyi, A | 102155 | $ 227,072.62 N 51,829,929.49 F$ 363,646.87 | [5 empty] | Nil |  | GESON INVESTMENT
| FULL REPLACEMENT OF OGUTA 12T FLOWLINE (4” X 4.3KM) | Fresh | NOT TREATED |  | Akinbiyi, A | 102155 | $ 140,649.15 N 17,728,986.10 F$ 187,365.85 | [5 empty] | Nil |  | ABBEYCOURT
| INTEGRITY CHECK OF AGBADA 67T GAS LINE | Fresh | Conditional Approval Update and resubmit upon completion of these conditions: I. Update WBS for this activity. II. Formal engagement with the Pipeline Contract Holder and review contract line items. III. Review work method statement with the vendor IV. Recourse option of engaging a flowline vendor to manage the overall activity. | Conditional Approval | Dienagha, I | NIL | $ 47,136.48 N 76,378,129.79 F$ 248,131.56 | [5 empty] | Nil |  | BG TECHNICAL
| BONNY W30T Flowline Replacement (4" Sch 80 x 1km) | Fresh | Deferred. I. Stepped down for a proper internal review by Project Lead. | Stepped Down | Azaka, G | NIL |  | $ 104,781.24 N 38,486,464.52 F$206,194.85 |  |  |  |  | Nil |  | VANDRESSER NIG
| Tunu CDRY-3 Flowline Construction (6" x 2.1km) & Tunu CDRY-4 Wellhead Platform Installation and hookup | Fresh | Approved. I. Update cost saving column with the proposed cost savings. II. Liase with C&P to affirm benchmark rates | Approved | Azaka, G | C.NG.AFS.DF.19.003.1200 |  |  | $324,929.80 N 118,704,995.67 F$ 637,697.73 |  |  |  | Nil |  | IKONIBO NIG
| Replacement of 1,75KM of 2” water equalization of Soku cluster D | Fresh | Deferred. I. Provide and attach basis for the additional 1.75km scope. II. Engage EST & Geomatics for a proper review III. Review and simplify execution strategy. | Deferred | Obioakor, O | NIL |  | $ 225,297.74 N 13,915,985.80 F$ 261,967.01 |  |  |  |  | Nil |  | HENZOL, KEMUD, VISCA
| FULL REPLACEMENT OF IMOR 58T (4-INCH x 3.4KM) | Fresh | Approved. I. Proceed to execution with the proposed new vendor (WILKRISS NIG. LTD) II. Ensure the MoM and offer decline letter from Thompson & Grace Investment Ltd is duly signed for documentation | Approved | Aderiye, A | C.NG.PAE.DL.21.001 | $ 137,763.36 N 12,884,978.45 F$ 179,633.46 | [5 empty] | 14800 | Warehouse Materials | WILKRISS
| SAGHARA 3S & 5L FLOWLINE REPLACEMENT – 4” Sch. 40 x 850m each (Total = 4” Sch. 40 x 1.7km). Resubmission & Reviewed offline | Resubmission | Approved. WORP steers from previous sitting 11/02/21 have been incorporated | Approved | Uwaezuoke, D | O.NG.PBW.SHF.03S.713FL/O.NG.PBW.SHF.05L.713FL |  |  | $ 204,508.67 N 74,834,367.87 F$ 401,700.68 |  |  |  | Nil |  | ANASAMI CONSTRUCTION
2021-02-25 | BONNY W30T Flowline Replacement (4" Sch 80 x 1km) | Resubmission | Conditional Approval. WORP steers from previous sitting 18/02 have not been fully incorporated. I. Engage WRFM to provide WBS for this activity and resubmit offline | Conditional Approval | Azaka, G | NIL |  | $ 101,126.24 N 37,144,159.42 F$199,002.81 |  |  |  |  | Nil |  | VANDRESSER NIG
| OTUMARA FLOW STATION GANTRY WORKS | Fresh | Deferred. I. Update WBS for this activity. II. Engage EST to review existing structural frame and attach schematic drawing. III. Confirm Gantry maximum load. | Deferred | Azaka, G | NIL |  |  | $ 187,308.06 N 6,577,567.94 F$206,814.41 |  |  |  | Nil |  | NAPEBI CONSTRUCTION
| KOCR 22T Flowline Sectional Replacement – 4” sch. 40 x 0.06km and 8” Sch 160 x 0.012km | Fresh | Approved. I. Forward approved e-WR to the Secretariat and Manager. II. Plan for mitigation against Vendors under performance due to low project cost. | Approved | Arowosafe, T | O.NG.PAE.GBG.FAC.724FC |  | $ 55,973.34 N 4,979,690.78 F$ 69,,095.05 |  |  |  |  | Nil |  | ABBEYCOURT ENERGY
| K2S Simultaneous Flow Project | Fresh | Approved. I. Engage CH to update ACV split currency values. II. Carry out materials check with Hotdesk. III. Emphasize criticality of this activity with the Vendor. | Approved | Akoma, I | C.NG.PBE.DF.21.005 |  | $ - 104,725.16 N - 36,794,719.22 F$ - 201,680.94 |  |  |  |  | 22416.83 | Savings on Mob and De-mob by using same contractor for Mechanical/ Instrumentation works, etc | GRAMEN PETROSERVE
| Replacement of LP header of Yokri flow station. -Reviewed offline | Fresh | Approved | Approved | Obiakor, O | O.NG.PCW.YKF.FAC.71300 |  |  | $ 31,865.72 N 375,865.72 F$ 32,854.55 |  |  |  | 23907.23 | saved for combining mobilization of Forcados Yokri 127T flowline sectional replacement and replacement of Yokri LP header | TONYMAR INVESTMENT
| GENERAL |  | Review materials reconciliation tracking system and communicate to leadership: ▪ Flowlines ▪ Facilities
2021-03-04 | FODPA and NEFS Boatlanding Rehabilitation Works | Fresh | Approved. I. Confirm full budget availability for these activities. II. Carry out materials reconciliation with Hotdesk. III. Ensure security plan is properly reviewed and assurance provided for adequate cover at site | Approved | Uwaezuoke, D | F$: C.NG.PBW.DF.212.001 – FODPA F$: C.NG.PCW.DF.98.706.1230 - NEFS |  |  | Total: FODPA + NEFS = F$394,395.64 |  |  |  | Nil |  | Gramen Petroserve
| FULL REPLACEMENT OF OGUTA 12T FLOWLINE(4” X 4.3KM) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Confirm WBS for this activity. II. Carry out materials reconciliation with Hotdesk and discount available materials. III. Update Project Schedule to current plan. IV. Include Fabrication & Hook up in the scope summary. V. Confirm linepipes availability for this activity. VI. Align POB requirement with OABP Central Team | Conditional Approval | Akinbiyi, A | 102155 | $ 132,486.76 N 37,684,516.42 F$ 231,787.20 | [5 empty] | Nil |  | WILKRISS
| FULL REPLACEMENT OF OGUTA 16S FLOWLINE(4” X 2.9KM) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Confirm WBS for this activity. II. Carry out materials reconciliation with Hotdesk and discount available materials. III. Update Project Schedule to current plan. IV. Include Fabrication & Hook up in the scope summary. V. Confirm linepipes availability for this activity. VI. Align POB requirement with OABP Central Team | Conditional Approval | Akinbiyi, A | 102155 | $ 91,808.64 N 26,740,513.71 F$ 179,482.45 | [5 empty] | Nil |  | MORRAY SERVICES
| FULL REPLACEMENT OF OGUTA 25T FLOWLINE(4” X 5.6KM) | Fresh | Conditional Approval. Update and resubmit upon completion of these conditions: I. Confirm WBS for this activity. II. Carry out materials reconciliation with Hotdesk and discount available materials. III. Update Project Schedule to current plan. IV. Include Fabrication & Hook up in the scope summary. V. Confirm linepipes availability for this activity. VI. Align POB requirement with OABP Central Team | Conditional Approval | Akinbiyi, A | 102155 | $ 165,827.86 N 46,524,990.84 F$ 288,423.35 | [5 empty] | Nil |  | GUIZ AND COMPANY
| LEAK REPAIR OF FORCADOS 127T FLOWLINE | Fresh | Approved. I. Engage WRFM to confirm WBS for this activity. II. Update Project title to include “Optimization of Line size” III. Update Project Schedule to current plan. | Approved | Obiakor, O | 102155 |  |  | $ 47,933.39 N 1,545,750.79 F$ 52,006.51 |  |  |  | 39515.51 | Mob and De-mob, Houseboat | TONYMA INVESTMENT
| SECTIONAL REPLACEMENT OF OTUMARA 42LS, 16T FLOWLINES AND FABRICATION OF HOOK-UP ARM OF OTUMARA 4L. | Fresh | Approved. I. Carry out materials reconciliation with hotdesk and discount available materials. | Approved | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  |  | $ 160,601.21 N 61,143,932.41 F$ 321,718.29 |  |  |  | F$82,000 & F$77,000 | F$82,000 (Shared marine logistics) + F$77,000 (Single mob/demob) | ANASAMI
| Diebu Creek 8T Flowline Replacement – 4” x 3.07km | Fresh | Stepped down by the team | Stepped down | Ehizoyanyan, O | WRFM 102155 |  | $228,572.93 N 83,941,422.41 F$449,762.45 |  |  |  |  | Nil |  | SEVOIL LTD
| BONN 12S Flowline Replacement – 4” x 1.7km | Fresh | Stepped down by the team | Stepped down | Ehizoyanyan, O
| BONNY W30T Flowline Replacement (4" Sch 80 x 1km) -Resubmission & Reviewed offline | Resubmission & Reviewed Offline | Approved. WORP steer from previous sitting 25/02/21 have been incorporated. | Approved | Azaka, G | NIL |  | $ 101,126.24 N 37,144,159.42 F$199,002.81 |  |  |  |  | Nil |  | VANDRESSER NIG
| GENERAL |  | Ensure timely checks on materials availability prior to WORP submission. • Only funded activities should be brought into plan and ensure alignment of execution with IAP central team. • Proper security plan review / HSE documentation for each project before mobilization. • Early engagement on marine request to avoid delayed mobilization to sites.
2021-03-11 | UZU MANIFOLD LOCATION PREPARATION | Fresh | Approved. I. Limit PO value to the contractor to available ACV balance in SAP. II. Engage C&P to update remaining ACV III. Ensure combination of controls is in place for managing community workers. IV. Liase with the planning team to align schedule & demand requirements for IAP | Approved | Oludare, S | P.NG.PAE.DG.17.001 |  |  |  | F$: 2,037,279.64 (N: 473,610,898.60, $: 789,293.09) |  |  | 107225.24 | 5 % LOP Discount | RAFFOUL NIG. LIMITED
| FORC 111T Flowline Replacement (6" sch 40 x 2.7 km bulkline) & (4" sch 40 x 0.25 km flowline) | Fresh | Approved. I. Ensure combination of controls is in place for managing community workers. II. Decomit previously issued PO for Forcados 126S before issuing the new PO for 111T to the Vendor. III. Update Project Schedule to current plan. | Approved | Orji, C | C.NG.PAE.DL.21.001.1230 |  |  | $ 251,239.91 N 92,278,553.00 F$ 494,398.16 |  |  |  | 33891.12 | From Materials to be taken from Hot Desk | HENSTEEL ENGINEERING
| FULL REPLACEMENT OF IMOR 36L (4-INCH x 1.0 KM) | Fresh | Approved. I. Carry out proper material reconciliation with hotdesk. | Approved | Aderiye, A | C.NG.PAE.DL.21.001 | $ 47,000.69 N 11,269,553.88 F$ 76,696.49 | [5 empty] | 12500 | MATERIALS FROM THE SPDC WAREHOUSE. | ROMEK AND COMPANY
| SECTIONAL REPLACEMENT OF (a) IMOR 4-inch TEST LINE (48M) (b) IMOR RIVER 26S (48M) © IMO RIVER 44S (48M) (d) IMO RIVER 55S (48M) (e) IMO RIVER 43T (48M) (f) IMOR 60T (48M) | Fresh | Approved. I. Prompt engagement with Asset PUM’s to provide enhanced security surveillance for these lines. II. Update Project Schedule to current plan. | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 35,160.13 N 10,617,977.01 F$ 63,138.99 | [5 empty] | 11525.18 | MOB & DEMOB. ALL MATERIALS FOR THESE SECTIONAL REPLACEMENT SHALL BE SOURCED FROM SPDC WAREHOUSE | GAMSTEC
| SECTIONAL REPLACEMENT OF (a) IMOR RIVER 6-INCH BULKLINE (IMO 2 -1) X 1500 M (Additional leak points) | Fresh | Approved. | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 17,777.50 N 5,370,063.42 F$ 31,927.86 | [5 empty] | 8280.04 | MOB & DEMOB IF USING A NEW CONTRACTOR | GAMSTEC
| Diebu Creek 8T Flowline Replacement – 4” x 3.07km | Fresh | Conditional Approval. Subject to NAPIMS engagement on contract expiration date extension. | Conditional Approval | Ehizonyan, O | O.NG.PBE.DBC.09T.713FL |  | $238,624..58 N 87,632,760.32 F$469,540.94 |  |  |  |  | Nil |  | SEVOIL LTD
| FULL REPLACEMENT OF ETELEBOU 3S FLOWLINE (4” X 1.2KM) | Fresh | Approved: Premised on early mobilization. I. Update contract end date and engage NAPIMS. II. Forward cost savings to I&A for documentation. | Approved | Otavie, G | O.NG.PAE.ETL.03S.713FL |  | $ 57,925.84 N 13,410,314.07 F$ 85,626.42 |  |  |  |  | Nil |  | PECKON NIGERIA
| BONNY W18S Flowline Replacement (4" Sch 40 x 1.2km) | Fresh | Conditional Approval. I. Carry out work distribution alignment across team. II. Confirm Contractors capacity to execute | Conditional Approval | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  | $ 133,308.68 N 48,964,351.92 F$262,332.00 |  |  |  |  | Nil |  | IKONIBO
| Provision of lay barge for installation of CCUs at Kanbo W5L/S -Reviewed Offline | Fresh | Approved. | Approved | Ehizonyan, O | C.NG.AFS.DF.18.025.1202 |  |  | $ 22,320.8 N 602,305.87 F$ 23,907.9 |  |  |  | 10062 | Shared marine logistics and security deployment | HENZOL GLOBAL
2021-03-18 | Replacement of 1,75KM of 2” water equalization of Soku cluster D | Resubmission | Conditional Approval. WORP steers from previous sitting 18/02/21 have been incorporated. Further steers: I. Attach signed MoM of review meeting held with EST & Geomatics. II. Update WBS for this activity. III. Engage vendor & secure commitment to execute work accordingly. IV. Liase with C&P to load contract in SAP. | Conditional Approval | Obiakor, O | Nil |  | $ 107,282.92 N 39,409,715.49 F$211,129.34 |  |  |  |  | Nil |  | VANDREZZER NIG. LTD
| BOGT SHORE PROTECTION – PHASE1 | Fresh | Approved. I. Focused attention on vendor HSE risk management before and during site works. II. Review & accelerate project schedule. III. Proceed with interim plan to safeguard shoreline before actual work execution. IV. Kick off meeting to include Vendor top management in view of the nature of work. | Approved | Ogunkunle, M | C.NG.PBE.IC.07.001 |  |  |  | F$ 875,727.01 N69,244,408.04 + $693,264.80 |  |  | Nil |  | PILE FOUNDATION LIMITED
| Seibou 3 and 4 bulkline JIV and clamping. -Reviewed offline | Fresh | Approved. I. Update project schedule to current plan | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $ 27,976.94 N 511,967.62 F$ 29,326.00 |  |  |  | 9050.71 | cost saving on inter-area move instead of mobilizing a new contractor. | HENZOL GLOBAL
| GENERAL |  | Engage the relevant authorities with proposal to include equalization lines in FIMS for ease of line tracking and integrity monitoring.
2021-03-25 | Bonny W14 Maintenance Dredging works | Fresh | Approved. I. Reiterate the responsibility of the main contractor despite invoice partnering option. II. Ensure safe work completion before contract expiration date. III. Update project schedule to align with current plan IV. 5no top risk to include “Interface management risk” V. Align cost breakdown descriptions with cost summary sheet. VI. Ensure proper HSE & Security plan review. VII. Kick off meeting to emphasize Covid’19 protocols at site. | Approved | Onyejekwe, C | 110744 |  |  |  | $: 428,558.82 N: 192,570,123.89 F$: 935,989.97 |  |  | 56227.33 | Cost saving is from Low Oil Price LoP discounts (i.e. 7.5%). | SHORELINE DREDGING
| Bonny W13 Maintenance Dredging works | Fresh | Approved. I. Reiterate the responsibility of the main contractor despite invoice partnering option. II. Ensure safe work completion before contract expiration date. III. Update project schedule to align with current plan IV. 5no top risk to include “Interface management risk” V. Align cost breakdown descriptions with cost summary sheet. VI. Ensure proper HSE & Security plan review. VII. Kick off meeting to emphasize Covid’19 protocols at site. | Approved | Onyejekwe, C | 110744 |  |  |  | $: 412,055.67 N: 188,667,970.36 F$: 909,204.47 |  |  | 54055.53 | Cost saving is from Low Oil Price LoP discounts (i.e. 7.5%). | SHORELINE DREDGING
| Enwhe East Flare Test Pit and Bundwall Construction Work | Fresh | Approved. I. Capture cost savings and forward to I&A for reporting. II. Update project schedule to align with current plan III. Update appropriately the remaining ACV for this submission. | Approved | Otavie, G | C.NG.LNG.DG.19.004.1230 |  | $ 54,465.13 N 113,596,678.73 F$ 353,797.61 |  |  |  |  | Nil |  | Gramen Petroserve
| Enwhe West Flare Test Pit and Bundwall Construction Work | Fresh | Approved. I. Update project schedule to align with current plan. II. Update appropriately the remaining ACV for this submission III. Ensure vendor has adequate resources to deliver according to schedule. | Approved | Uwaezuoke, D | C.NG.LNG.DG.19.004.1230 |  | $ 49,888.81 N 95,735,716.20 F$ 302,156.84 |  |  |  |  | Nil |  | Gramen Petroserve
| Estuary Cluster 51 Ring A Replacement Work ahead of FORC73 Workover | Fresh | Approved. I. Ensure safe work completion before contract expiration date. II. Update project schedule to align with current plan. III. Harmonize project title with other relevant documentation. | Approved | Uwaezuoke, D | O.NG.STG.PBE.FOR.072FL |  |  | $ 102,377.04 N 26,433,707.21 F$ 172,031.08 |  |  |  | Nil |  | Miden Systems Ltd
| Kanbo 5LS TRP Outage surveillance cover. | Fresh | Approved. I. Vendor to deploy adequate resources for security surveillance. | Approved | Ehizoyanyan, O | O.NG.PCW.OKF.FAC.71300. |  |  | $ 31,947.75 N 372,012.45 F$ 32,928.02 |  |  |  | Nil |  | HENZOL GLOBA
| Kanbo W7S (6’’ x 0.1Km) & W6T (6’’ x 0.1Km) Flowline Sectional Replacement | Fresh | Deferred. I. Liase with C&P to update remaining ACV for this activity. II. Update summary description of cost saving initiative. | Deferred | Otavie, G | O.NG.STG.PBE.KAN.007FL O.NG.STG.PBE.KAN.006FL |  |  | $ 122,276.73 N 3,736,362.47 F$ 132,122.22 |  |  |  | 20000 | Elimination of Mob and De-mob of Houseboat, by latching onto existing houseboat already in Tunu | FEIMA
| FORC 110T & FORC 112T Integrity Checks | Fresh | Deferred. I. Liase with C&P to update remaining ACV for this activity | Deferred | Orji, C | C.NG.PCW.DL.21.001 |  |  | $ 64,269.17 N 1,986,542.12 F$ 69,503.80 |  |  |  | Nil |  | TUSOJA MARINE
| Tunu BQRT-3 Flowline Replacement (6" SCH 80 x 6.1km) | Fresh | Conditional Approval. Update and revert upon completion of these conditions: I. Carry out material reconciliation with hotdesk. II. Update 5no top risk to include “Interface management risk” III. Update summary | Conditional Approval | Otavie, G | C.NG.AFS.DL.19.006.1230 |  |  | $ 306,292.32 N 117,178,807.88 F$ 615,063.88 |  |  |  | F$: 20,000 | Campaign mobilization will enable the sharing of Marine logistic resources like houseboat which are already in the field | SEVOIL & OSAKS INTEQ
| GENERAL |  | Escalate security challenges in Kanbo and Seibou axis to Security LT.
2021-04-01 | FORC 110T & FORC 112T INTEGRITY CHECKS | Resubmission | Approved. I. Update Contractor’s name with the correct spelling in the submission. II. Include value proposition (bopd) for both lines. III. Indicate all the WBS provided for this project and charge each flowline cost to specific WBS provided IV. Review and update risk No3 in the top risks. | Approved | Orji, C | O.NG.STG.PBE.FOR.110FL |  |  | $ 64,269.17 N 1,986,542.12 F$ 69,503.80 |  |  |  | Nil |  | ELKON INTEGRATED
| TUNU BQRT-3 Flowline Replacement (6" Sch 80 x 6.1km) -Resubmission & Reviewed offline | Resubmission | Approved. WORP steers from previous sitting 25/03/21 have been incorporated. | Approved | Otavie, G | C.NG.AFS.DL.19.006.1230 |  |  | $ 304,115.16 N 116,379,232 F$ 610,779.8 |  |  |  | F$: 20,000 F$: 4,284.08 | House boat sharing and materials discounted | SEVOIL & OSAKS INTEQ
| BONNY W18S Flowline Replacement (4" Sch 40 x 1.2km) -Resubmission & Reviewed offline | Resubmission | Approved. WORP steers from previous sitting 11/03/21 have been incorporated. | Approved | Obiakor, O | C.NG.PAE.DL.21.001.1230 |  | $ 132,180.84 N 48,550,109.36 F$260,112.61 |  |  |  |  | Nil |  | IKONIBO NIG
| GENERAL |  | Always ensure equitable work allocation.
856223.29
[7 empty] | 67893.62 | 22416.83 | 375426.57 | 370486.27 |  |  | 836223.29

## Summary
| LAND | CENTRAL | SWAMP WEST | CIVIL | OABP ASSET | AF | 100% (F$ ‘000) | FCF (100% x 0.3 x 0.97) (F$ ‘000)
|  |  | 100000 | 37434.38 |  |  | 137.4344 | 39.9934 | January
| 35588.4 | 22416.83 | 23907.23 | 115543.79 |  |  | 197.4563 | 57.4598 | February
| 32305.22 |  | 251519.34 | 217508.1 |  |  | 501.3327 | 145.8878 | March
Total | 67893.62 | 22416.83 | 375426.57 | 370486.27 | 0 | 0 | 836.2233 | 243.341
Remark