## Swamp West COST SAVINGS
OABP WEST FLOWLINE COST SAVINGS ACTIVITY JUNE 2022
S/N | OABP | Conduit | KM | 2022 Scope | BOPD | VENDOR | CATEGORY | STATUS | Plan Start | COST SAVINGS | REMARKS
1 | SSAGS | OPUK GESI-1 | 3 | NEW FLOWLINE | 2000 | SUNUP / TECHSTONE | MAJOR | ONGOING | 2022-02-01 | 256053 | Shared HB for 3 months due to concurrent activity execution
2 | SSAGS | OPUK FRSN-2 | 3 | NEW FLOWLINE | 2000 | A & N | MAJOR | ONGOING | 2022-02-01
4 | FIIP | FORC126S | 1.2 | FLRR | 625 | MATIZ / ARIOSH | MAJOR | ONGOING | 2022-03-01 | 85000 | Use of hotel rather than HB
5 | JV | TUNU | 0 | TWISTER INLET HEADER |  | KEMUD | MAJOR | COMPLETED | 2022-06-01 | 17000 | Use of Asset FLB instead of HB
6 | FIIP | FORC114S | 0 | JIV | 90 | MATIZ | MAJOR | COMPLETED | 2022-06-01 | 22000 | Use of vendor already at site for JIV
7 | JV | OTUM54T | 0 | JIV | 346 | HOECHY | MAJOR | COMPLETED | 2022-06-01 | 8000 | Single mob/demob by using one vendor and combining the JIVs to happen concurrently
8 | JV | OTUM42S | 0 | JIV | 346 | HOECHY | MAJOR | COMPLETED | 2022-06-01
9 | FIIP | BENS10L | 1.7 | FLRR | 950 | ANASAMI | MAJOR | COMPLETED | 2022-03-01 | 123823 | Use of DFTP security
10 | FIIP | BENS11S | 2.7 | FLRR | 700 | DAIIK / ROADLAMP | MAJOR | COMPLETED | 2022-03-01 | 123823 | Use of DFTP security
13 | WRFM | BENS002T | 0.2 | HKUP ARM REPL. | 500 | KEMUD | MAJOR | COMPLETED | 2022-02-01 | 85000 | Offsite fab/use of Asset FLB rather than HB
16 | WRFM | TUNU13T | 0.2 | SECT. REPL. | 1000 | KEMUD | MAJOR | PO ISSUED | 2022-07-01 | 20000 | Use of Asset FLB instead of HB
|  |  | 12 |  | 8557 |  |  |  |  | 740699

## Security West Opuh
Start Date: 22nd March 2022 | 22nd March 2022
Stop Date: | 27th June 2022
Duration on Site 49 days | 98 days
Activity | Description | Qty /Day | Daily Rate (N) | Duration (Days) | Total (N)
Allowances | Officer | 1 | 3000 | 98 | 294000
| Rank & File | 14 | 2000 | 98 | 2744000
| MPVs | 2 | 125000 | 98 | 24500000
| Patrol Boats | 2 | 40000 | 98 | 7840000
Accommodation | 40-Man House Boat | 1 | 180000 | 98 | 17640000
| AGO (Old Rate) | 200 | 295.53 | 40 | 2364240
| AGO (New Rate)* | 200 | 614 | 58 | 7122400
| Sewage/Waste Disposal | 1 | 70000 | 3 | 210000
Transportation | Tug Boat | 1 | 100000 | 98 | 9800000
Mob/Dempb | House Boat | 1 | 500000 | 1 | 500000
Catering | Meals (Old Rate) | 22 | 4200 | 40 | 3696000
| Meals (New Rate)* | 22 | 5118 | 58 | 6530568
| Portable Water | 150000 | 10 | 3 | 4500000
Total: NGN |  |  |  |  | 87741208
Total: USD |  |  |  |  | 0
Overall Total USD |  |  |  |  | 211043.1942
Exchange rate is 415.07 USD/1 NGN
*New Rate effective 1st May 2022

## Security Civil Works
Mobilized 28th April 2022
Demobilized 15th | 7th June 2022
Duration on Site 49 days | 41 days
Optimazed Elements
House Boat
Tug Boat
Mob/Demob
Activity | Description | Qty /Day | Daily Rate (N) | Duration (Days) | Total (N)
Accommodation | 40-Man House Baot | 1 | 180000 | 41 | 7380000
Transportaion | Tug Boat | 1 | 100000 | 41 | 4100000
*Others | Mobilization/Demobilization | 1 | 500000 | 1 | 500000
Total: NGN |  |  |  |  | 11980000 | 28815.3939
Total: USD |  |  |  |  | 0
Overall Total USD |  |  |  |  | 28815.3939
Exchange rate is 415.07 USD/1 NGN
*Mob/Demob=one-off |  |  |  |  | 8385.2796 | 7347.9254
S/No | Description | 100% | FCF
1 | Swamp West Security | 141363 | 36047.565
2 | Civil Works Security Savings | 28815.3939 | 7347.9254
| Total |  | 43395.4904

## Security Swamp West
Mobilized 28th April 2022
Demobilized 15th | 15th June 2022
Duration on Site 49 days
Optimazed Elements
House Boat
Tug Boat
Mob/Demob
1. Benisede Well 10S Cost Savings Spreadsheet
Activity | Description | Qty /Day | Daily Rate (N) | Duration (Days) | Total (N)
Accommodation | 40-Man House Baot | 1 | 180000 | 49 | 8820000
Transportaion | Tug Boat | 1 | 100000 | 49 | 4900000
Others | Mobilization/Demobilization | 1 | 500000 | 1 | 500000
Total: NGN |  |  |  |  | 14220000
Total: USD |  |  |  |  | 0
Overall Total USD |  |  |  |  | 34203.2471
Exchange rate is 415.07 USD/1 NGN
Mobilized 28th April 2022 | 29th March 2022
Demobilized 15th | 17th May 2022
Duration on Site 49 days | 50 days
2. Benisede Well 11L Cost Avoaidnace Spreasheet.
Activity | Description | Qty /Day | Daily Rate (N) | Duration (Days) | Total (N)
Allowances | Officer | 1 | 3000 | 50 | 150000
| Rank & File | 14 | 2000 | 50 | 1400000
| MPVs | 2 | 125000 | 50 | 12500000
| Patrol Boats | 2 | 40000 | 50 | 4000000
Accommodation | 40-Man House Boat | 1 | 180000 | 50 | 9000000
| AGO (Old Rate) | 200 | 295.53 | 33 | 1950498
| AGO (New Rate)* | 200 | 614 | 17 | 2087600
| Sewage/Waste Disposal | 1 | 70 | 2 | 140
Transportation | Tug Boat | 1 | 100000 | 50 | 5000000
Mob/Dempb |  | 1 | 500000 | 1 | 500000
Catering | Meals (Old Rate) | 22 | 4200 | 33 | 3049200
| Meals (New Rate)* | 22 | 5118 | 17 | 1914132
| Portable Water | 150000 | 10 | 2 | 3000000
Total: NGN |  |  |  |  | 44551570
Total: USD |  |  |  |  | 0
Overall Total USD |  |  |  |  | 107159.5189
Exchange rate is 415.07 USD/1 NGN
Overall NGN Total
Benisede Well 10 Cost Savings Total: NGN |  |  |  |  | 14220000 | 34203.2471
Benisede Well 11 Cost Savings Total: NGN |  |  |  |  | 44551570 | 107159.5189
Benisede 10 and 11 Grand Total: NGN |  |  |  |  | 58771570 | 141362.7661
Overall USD Total
Benisede Well 10 Cost Savings Total: USD |  |  |  |  | 34203
Benisede Well 11 Cost Savings Total: USD |  |  |  |  | 107160
Benisede 10 and 11 Cost Savings Grand Total: USD |  |  |  |  | 141363
Exchange rate is 415.07 USD/1 NGN
|  |  |  | FCF | 36047.565 | 36047.565
*New Rtae for AGO and Meals effective 1st May 2022.

## Q2- 2022 Saving Summary
| LAND | CENTRAL | SWAMP WEST | CIVIL | OABP ASSET | AF | 100% (F$ ‘000) | FCF (100% x 0.3 x 0.85) (F$ ‘000) |  | Civil FCF | Swamp West FCF
|  |  |  | 115355.909 |  |  | 115355.909 | 29415.7568 | April | 29415.7568 | 0
|  |  | 46304.25 | 7247.204 |  |  | 53551.454 | 13655.6208 | May | 1848.037 | 11807.5837
|  |  | 24000 | 128061.18 |  |  | 152061.18 | 38775.6009 | June | 32655.6009 | 6120
Total | 0 | 0 | 70304.25 | 250664.293 | 0 | 0 | 320968.543 | 81846.9785 |  | 34503.6379 | 17927.5837
Remark

## OABP 2022 Actual Cost Savings
OABP TEAM 2022 - FCF PLANNED & ACTUAL SAVINGS | [7 empty] | 2022 PLANNED SAVINGS |  | 2022-CUMULATIVE ACTUAL SAVINGS |  | Q1-2022 SAVINGS |  | Q2-2022 SAVINGS |  | Q3-2022 SAVINGS |  | Q4-2022 SAVINGS
S/No | Id | Initiative: Initiative Name | Actual L-Gate | Planned Date | Approval status | Data filter 1 | Project CAPEX Budget | 100% savings applying 5% (F$ '000) | FCF Impact (F$'000') | 100% savings (F$ '000) | FCF Impact (F$'000') | 100% savings (F$ '000) | FCF Impact (F$'000') | 100% savings (F$ '000) | FCF Impact (F$'000') | 100% savings (F$ '000) | FCF Impact (F$'000') | 100% savings (F$ '000) | FCF Impact (F$'000')
1 | I-0151647 | 2022 OABP Matrix Projects Team Work Activities Optimization | L4 | 2022-01-26 | Bypassed | OABP/Portfolio | 890000 | 44500 | 11347.5 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | I-0211215 | 2022 OABP OGI Facilities Upgrade Works - Central East Asset Optimization | L4 | 2022-01-26 |  | OABP/Portfolio | 8420000 | 421000 | 107355 | 43425.65 | 11073.5407 | 43425.65 | 11073.5407 |  | 0 |  | 0 |  | 0
|  | 2023 OABP OGI Facilities Upgrade Works - Land Asset Optimization |  |  |  |  | 470000 | 23500 | 5992.5 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | I-0261802 | 2022 OABP OGI Facilities Upgrade Works - West Asset Area Optimization | L4 | 2022-01-26 |  | OABP/Portfolio | 3528000 | 176400 | 44982 | 608459 | 155157.045 |  | 0 | 141363 | 36047.565 | 467096 | 119109.48 |  | 0
4 | I-0261804 | 2022 OABP Civil Projects Team Work Activities Optimization | L4 | 2022-01-26 |  | OABP/Portfolio | 9009000 | 450450 | 114864.75 | 805777.9239 | 205473.3706 | 776962.53 | 198125.4451 | 28815.3939 | 7347.9254 |  | 0 |  | 0
5 | I-0261805 | 2022 OABP Fowlines | L4 | 2022-01-26 |  | OABP/Portfolio | 7620000 | 381000 | 97155 | 1770000 | 451350 | 1770000 | 451350 |  | 0 |  | 0 |  | 0
|  | 2022 D&R Projects Work Activities Optimization |  |  |  |  | 1500000 | 75000 | 19125 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Total |  |  |  |  | 31437000 | 1571850 | 400821.75 | 3227662.5739 | 823053.9563 | 2590388.18 | 660548.9859 | 170178.3939 | 43395.4904 | 467096 | 119109.48 | 0 | 0
| I-0158039 | Iseni Hook up Project | L0 |  |  | OABP/Portfolio | [7 empty] | Security
Security
1 | I-0158024 | Provision of Dredging Services in the Niger Delta | L3 | 2021-10-29 | Approved | OABP/Portfolio |  |  |  | 300000 | 76500 |  | July | security Opu
2 | I-0158034 | Provision of Roads and Location Preparation Works in the Niger Delta | L3 | 2021-10-29 | Approved | OABP/Portfolio |  |  |  | 300000 | 76500 |  | July | Asset West
3 | I-0158036 | Provision of Marine Foundation and Other Concrete Works in SPDC | L3 | 2021-10-29 | Approved | OABP/Portfolio |  |  |  | 300000 | 76500
[10 empty] | Facilities | 252594
[10 empty] | Flowlines | 451350

## Q1-2022 Savings Details
| LAND | CENTRAL | SWAMP WEST | CIVIL | OABP ASSET | AF | 100% (F$ ‘000) | FCF (100% x 0.3 x 0.97) (F$ ‘000)
|  | 43425.65 |  | 674508.59 |  |  | 717934.24 | 208918.8638 | Jan
|  |  |  | 42147.66 |  |  | 42147.66 | 12264.9691 | Feb
|  |  |  | 60306.28 |  |  | 60306.28 | 17549.1275 | March
Total | 0 | 43425.65 | 0 | 776962.53 | 0 | 0 | 820388.18 | 238732.9604
[7 empty] | 0.82039 | 0.23873
Q1 OABP Team's Savings
[7 empty] | 1770000 | 451350 |  | S/No | Savins Description | Amount $ (000)
[7 empty] | Flowline Replacement Contract |  |  | 1 | Facilities | 238.7 | OABP savings
[10 empty] | 2 | Materials |  | Collating Material Cost
[10 empty] | 3 | Flowline Replacement | 451.4 | CP Initiative
43425.65

## OABP 2022 Plan Cost Savings Ini
S/No | Id | Initiative: Initiative Name | Actual L-Gate | Planned Date | Approval status | Data filter 1 | Project CAPEX Budget | 100% savings applying 5% (F$ '000) | FCF Impact (F$'000')
1 | I-0151647 | 2022 OABP Matrix Projects Team Work Activities Optimization | L1 | 2022-01-26 | Bypassed | OABP/Portfolio | 890000 | 44500 | 11347.5
2 | I-0211215 | 2022 OABP OGI Facilities Upgrade Works - Central East Asset Optimization | L0 | 2022-01-26 |  | OABP/Portfolio | 8420000 | 421000 | 107355 | 8890000 | 444500 | 113347.5
3 |  | 2023 OABP OGI Facilities Upgrade Works - Land Asset Optimization |  |  |  |  | 470000 | 23500 | 5992.5
4 | I-0261802 | 2022 OABP OGI Facilities Upgrade Works - West Asset Area Optimization | L0 | 2022-01-26 |  | OABP/Portfolio | 3528000 | 176400 | 44982
5 | I-0261804 | 2022 OABP Civil Projects Team Work Activities Optimization | L0 | 2022-01-26 |  | OABP/Portfolio | 9009000 | 450450 | 114864.75
6 |  | 2022 OABP Fowlines |  |  |  |  | 7620000 | 381000 | 97155 | 9120000 | 456000 | 116280
7 | I-0261805 | 2022 D&R Projects Work Activities Optimization | L0 | 2022-01-26 |  | OABP/Portfolio | 1500000 | 75000 | 19125
|  | Total |  |  |  |  | 31437000 | 1571850 | 400821.75
| I-0158039 | Iseni Hook up Project | L0 |  |  | OABP/Portfolio
1 | I-0158024 | Provision of Dredging Services in the Niger Delta | L3 | 2021-10-29 | Approved | OABP/Portfolio |  | 300000 | 76500
2 | I-0158034 | Provision of Roads and Location Preparation Works in the Niger Delta | L3 | 2021-10-29 | Approved | OABP/Portfolio |  | 300000 | 76500
3 | I-0158036 | Provision of Marine Foundation and Other Concrete Works in SPDC | L3 | 2021-10-29 | Approved | OABP/Portfolio |  | 300000 | 76500

## OABP Team 2022 Saving Outline
S/No | Execution Team | DMD Approved Budget (2022 $m)
1 | OABP SWAMP WEST | 3.528
2 | OABP CENTRAL | 8.4178
3 | OABP LAND | 0.468
4 | OABP MATRIX | 0.89111
5 | CIVIL PROJECT | 9.0889
6 | OABP Decommissioning | 1.5001
7 | OABP Fowline Replacement | 7.62
| Total | 31.514

## Ideation
S/No | Category | Idea | Remarks
1 | Use Surplus Materials | Use of surplus materials on projects: Reduce inventory of surplus; Reduce costs; Use of excess spares | Batch Up
2 | Optimised Contracting Strategy | Use of one contractor to execute activities in the same facility to save multiple mobilization cost Use of community vendors to execute jobs in community agitation prone sites/location to avoid work stoppage and schedule slip | Batch Up
3 | Optimising Security Deployment | Security costs: share resources, MPV needed, low cost security, inhouse? Optimize security requirements when woring close to production facilities Elepa 1,2,3 dredging: Share security resources | Batch Up
4 | Maximising Resources & Equipment Usage | Shared equipment on site Marine Logistics sharing Cost saving by using shared houseboat and doing campaign mobilization in swamp locations The use of marine equipment for different reasons that are not put to use: The use of JUBs by different teams one after the other Equipment hired but not in use eg tug boats: Evauate requirement for such | Batch Up
5 | Effective Execution | Mobilize activities for same area and share security costs Execute on campaign mode: Share cost, manpower, resources Identify projects/activities with same proximity and mobilize on campaign mode basis Campaign mobilization | Batch Up
6 | External Interface | Iseni: Influence Bayelsa Govt to finish access road/bridge | ER Team
2 | External -Contracting | Lock in OABP Logistics demand on long term hire contract | Logistic Team
5 | Effective Execution | Carry out minor design modification by using in house resources to save time and cost | Batch Up
7 | Use of New Technology | flow lines deployment: how do we progress FCP option to save costs on current practice of using carbon steel Deploy composite pipes for flowlines Alternative materials: Composite pipe; eliminate welding | New Tech -Initiative card
2 | Optimising Contracting Strategy | Optimiza logistics costs: Rates; Facilities deployed; Need to benchmark logistics rates with rates from other teams and open market Rate contracts are more expensive when used for extensive scope: Minor contract to execute extensive scope in facilities Challenge logistics costs from the SPDC Logistics team (for JUBS, Cranes, etc) with current market rates Opportunity exists in challenging the existing contract rates | Batch up Logistics Team
6 | External | Build diesel tank in location as against using barges for storage | NA - Logistics Team
5 | Commercial & Effective Execution | Implement OKN optimization ideas on Iseni Iseni: Reduce commute time to site by using closer hotel | Opportunity-New Project
5 | Effective Execution | Dredging 24 hours work: why not? Alreadu being done on some cases 24-hour Operations | Batch up
8 | Value Creation/Addation | Value creation/addition via efficient work execution, Asset debottlenecking works, capacity increase & expansion works, Ahead of time-Onschedule project delivery for the Asset teams

## Gold Medal Target Cost & Schedu
S/N | Project Type | Execution Team | Activity | NAPIMS Approved Budget (2022 $m) | Cost Savings Target (5% of Budget) | Promised Schedule Target | Gold Medal Schedule Target
1 | Portfolio | OABP Swamp West | Otumara flare segregation | 1.98
2 |  |  | Cluster 2 (shutdown) and cluster 3 | 1.26
3 |  |  | Facility Mechanical Upgrade West (ESCRAVOS) -For IG to IA project | 0.27
4 |  |  | Repair of Tunu Jetty | 0.0108
5 |  |  | Repair of Benisede Jetty | 0.0072
|  |  | Sub Total | 3.528 | 0.1764 |  |  | 0.294 | 0.0147
6 | Portfolio | OABP Civil | Escravos Beach FLB project | 4.18
7 |  |  | Remediation Civil - Structural Works at Soku FS | 0.099
8 |  |  | Shoreline & Jetty Repairs East | 0.57933
20 |  |  | Repair of Escravos Beach main access road | 0.36
|  |  | Repair of Civil Assets (Underdeck support, handrails etc) | 0.045
18 |  |  | Repair of Oguta well access road | 1.4856
9 |  |  | Repair of Adibawa access road | 2.34 |  | 2022-12-01 | 2022-11-01
|  |  | Sub Total | 9.0889 | 0.45445 |  |  | 0.75741 | 0.03787
8 | Portfolio | OABP Central East | Gbaran Produced Water Re-injection project | 6.91 |  | 2022-05-01 | 2022-04-01
11 |  |  | Soku GP Condensate Storage Tank 5501 Internal Inspection and repairs | 0.657
16 |  |  | Remedial works on Pontoon and jetty platform at Soku Flowstation | 0.387
|  |  | Citadel Fencing in Soku GP | 0.46
13 |  |  | Completion of outstanding works on Ahia Instrumentation Gas to Instrumentation Air conversion | 0.243
15 |  |  | Gathering of Afam VI vents to flare header | 0.225 |  | 2022-08-01 | 2022-07-01
|  |  | Sub Total | 8.882 | 0.4441 |  |  | 0.74017 | 0.037008
12 | Portfolio | OABP Matrix | Onramp Bonny Projects | 0.36 |  | 2022-12-01 | 2022-11-01
14 | Portfolio |  | Design and installation of liquid outlet valve 11LCV901 | 0.01
22 | GM COG |  | OX-BOW | 0.52
23 | GM COG |  | Iseni | 0
|  |  | Sub Total | 0.89 | 0.0445
10 | Portfolio | OABP Flowline | Installation/replacement of insulation joints on flowlines | 0.72
21 |  |  | Flowlines procurement | 4.5
|  |  | Flowlines construction-Gbara 14 Replacement | 2.4
|  |  | Sub Total | 7.62 | 0.381 |  |  | 1.905
24 | D&R | OABP | 16.2Km decomm for Pilot Pipeline (Imo R - Komkom D/L) :: Restoration of 1No. Adibawa Borrow Pit :: Restoration of 1No. Ubie Borrow Pit :: Decommissioning of Burnt Rig in EA Field - Front-end Activities | 1.5001
|  |  | Sub Total | 1.5001 | 0.075007 |  |  | 0.37504
| OABP-Total |  |  | 31.5091 | 1.5755

## New OABP Budget 2022 Feb
Activities
Project Type | Execution Team | Activity | DMD Approved Budget (2022 $m) | Budget Loaded? | WBS | Comment
Portfolio | OABP SWAMP WEST | Otumara flare segregation | 1.98 | Yes | C.NG.PCW.NO.21.001 |  | 3.528
Portfolio |  | Cluster 2 (shutdown) and cluster 3 | 1.26 | Yes | C.NG.PBW.DF.21.001
Portfolio |  | Facility Mechanical Upgrade West (ESCRAVOS) -For IG to IA project | 0.27 | Yes | C.NG.PBW.IM.17.002
Portfolio |  | Repair of Tunu Jetty | 0.0108 | No | C.NG.PBW.IC.17.001 | Team has decided not to progress with this project for now on account of the budget amount
Portfolio |  | Repair of Benisede Jetty | 0.0072 | No | C.NG.PBW.IC.19.001 | Team has decided not to progress with this project for now on account of the budget amount
Portfolio | OABP CENTRAL | Gbaran Produced Water Re-injection project | 3.24 | Yes | C.NG.PBE.IM.21.001.1230 |  | 8.4178
Portfolio |  | Produced Water Disposal | 3.6748 | No | C.NG.PBE.IM.21.001 | Common cost budget of $1.3m loaded out of a total budget of $3.7m
|  | Soku GP Condensate Storage Tank 5501 Internal Inspection and repairs | 0.657 | Yes | C.NG.PBE.DF.21.002
|  | Remedial works on Pontoon and jetty platform at Soku Flowstation | 0.387 | Yes | C.NG.PBE.IC.17.001
Portfolio |  | Citadel Fencing in Soku GP | 0.459 | Yes | C.NG.PBE.DF.21.003
Portfolio | OABP LAND | Completion of outstanding works on Ahia Instrumentation Gas to Instrumentation Air conversion | 0.243 | Yes | C.NG.PAE.DF.19.032 |  | 0.468
Portfolio |  | Gathering of Afam VI vents to flare header | 0.225 | Yes | C.NG.PCE.NO.21.004
Portfolio | OABP MATRIX | Onramp Bonny Projects | 0.36 | Yes | C.NG.PAE.IM.20.002 |  | 0.89111
GM COG |  | OX-BOW | 0.52346 | Yes | C.NG.PAE.IM.20.003
|  | Design and installation of liquid outlet valve 11LCV901 | 0.007654 | No | C.NG.PBE.DF.20.001 | Budget amount very insignificant
GM COG |  | Iseni | 0
Portfolio | CIVIL PROJECT | Remediation Civil - Structural Works at Soku FS | 0.099 | Yes | C.NG.PAE.DF.20.001 |  | 9.0889
|  | Escravos Beach FLB project | 4.18 | Yes | C.NG.PBW.DF.18.101
Portfolio |  | Repair of Oguta well access road | 1.4856 | No | C.NG.PAE.IC.22.001 | Budget is outside the DRB approved portfolio budget for 2022. Team will need to get DRB approval, before budget can be loaded.
|  | Repair of Adibawa access road | 2.34 | Yes | C.NG.PAE.IC.18.001
Single Wells |  | Shoreline & Jetty Repairs East | 0.57933 | No | C.NG.PBE.IC.21.001
|  | Repair of Escravos Beach main access road | 0.36 | No | C.NG.PCW.IC.22.001
|  | Repair of Civil Assets (Underdeck support, handrails etc) | 0.045 | No
D&R | OABP | 16.2Km decomm for Pilot Pipeline (Imo R - Komkom D/L) :: Restoration of 1No. Adibawa Borrow Pit :: Restoration of 1No. Ubie Borrow Pit :: Decommissioning of Burnt Rig in EA Field - Front-end Activities | 1.5001 | Yes | P.NG.PPE.DP.18.006 |  | 1.5001
Portfolio | OABP | Flowlines procurement | 4.5 | Yes | C.NG.PCW.DL.21.001 |  | 7.62
Portfolio |  | Installation/replacement of insulation joints on flowlines | 0.72 | Yes | C.NG.PCE.DL.21.001
Portfolio |  | Gbaran 14 replacement | 2.4 | Yes | C.NG.PAE.DF.22.001
Overall Total | Overall Total |  | 31.514 |  |  |  | 31.514 | 31.5
31.514

## OABP NAPIMS Approved Budget (3)
S/N | Project Type | Execution Team | Activity | NAPIMS Approved Budget (2022 $m) | Apply 5% cost savings across | Remark
West
1 | Portfolio | OABP | Otumara flare segregation | 1.98
2 | Portfolio | OABP | Cluster 2 (shutdown) and cluster 3 | 1.26
3 | Portfolio | OABP | Facility Mechanical Upgrade West (ESCRAVOS) -For IG to IA project | 0.27
4 | Portfolio | OABP | Repair of Tunu Jetty | 0.0108
5 | Portfolio | OABP | Repair of Benisede Jetty | 0.0072
|  |  | Sub Total | 3.528 | 0.1764
Civil
6 | Portfolio | OABP | Escravos Beach FLB project | 4.18
7 | Portfolio | OABP | Remediation Civil - Structural Works at Soku FS | 0.099
8 | Portfolio | OABP | Shoreline & Jetty Repairs East | 0.57933 |  | Additional budget moved from OF-Maintenance
20 | Portfolio | OABP | Repair of Escravos Beach main access road | 0.36 |  | Moved from Refurbishment of Corroded Helipad above
18 | Portfolio | OABP | Repair of Oguta well access road | 1.4856 |  | Additional budget moved from OF-Maintenance
9 | Portfolio | OABP | Repair of Adibawa access road | 2.34
|  |  | Sub Total | 9.0439 | 0.4522
Central East & Land
8 | Portfolio | OABP | Gbaran Produced Water Re-injection project | 3.24
11 | Portfolio | OABP | Soku GP Condensate Storage Tank 5501 Internal Inspection and repairs | 0.657
16 | Portfolio | OABP | Remedial works on Pontoon and jetty platform at Soku Flowstation | 0.387
13 | Portfolio | OABP | Completion of outstanding works on Ahia Instrumentation Gas to Instrumentation Air conversion | 0.243
15 | Portfolio | OABP | Gathering of Afam VI vents to flare header
|  |  | Sub Total | 4.527 | 0.22635
Matrix
12 | Portfolio | OABP | Onramp Bonny Projects | 0.36
14 | Portfolio | OABP | Design and installation of liquid outlet valve 11LCV901 | 0.108
22 | GM COG | OABP | OX-BOW | 0.54
23 | GM COG | OABP | Iseni | 0.05
|  |  | Sub Total | 1.058 | 0.0529
Flowline
10 | Portfolio | OABP | Installation/replacement of insulation joints on flowlines | 0.72
21 | Portfolio | OABP | Flowlines procurement | 4.5
|  | OABP | Flowlines construction | 2.63
|  |  | Sub Total | 7.85 | 0.3925
24 | D&R | OABP | 16.2Km decomm for Pilot Pipeline (Imo R - Komkom D/L) :: Restoration of 1No. Adibawa Borrow Pit :: Restoration of 1No. Ubie Borrow Pit :: Decommissioning of Burnt Rig in EA Field - Front-end Activities | 1.5001
|  |  | Sub Total | 1.5001 | 0.075007
|  |  |  | 27.5071 | 1.3754

## OABP NAPIMS Approved Budget-Mai
S/N | Project Type | Execution Team | Activity | NAPIMS Approved Budget (2022 $m) | Apply 5% cost savings across | Remark
West
1 | Portfolio | OABP | Otumara flare segregation | 1.98
3 | Portfolio | OABP | Cluster 2 (shutdown) and cluster 3 | 1.26
4 | Portfolio | OABP | Facility Mechanical Upgrade West Ogbotobo: Refurbishment of Corroded Helipad | 0 |  | Moved to Repair of Escravos Beach main access road
5 | Portfolio | OABP | Facility Mechanical Upgrade West (ESCRAVOS) -For IG to IA project | 0.27
6 | Portfolio | OABP | Repair of Tunu Jetty | 0.0108
7 | Portfolio | OABP | Repair of Benisede Jetty | 0.0072
|  |  | Sub Total | 3.528 | 0.1764
Civil
2 | Portfolio | OABP | Escravos Beach FLB project | 4.18
17 | Portfolio | OABP | Remediation Civil - Structural Works at Soku FS | 0.099
19 | Portfolio | OABP | Shoreline & Jetty Repairs East | 0.57933 |  | Additional budget moved from OF-Maintenance
20 | Portfolio | OABP | Repair of Escravos Beach main access road | 0.36 |  | Moved from Refurbishment of Corroded Helipad above
18 | Portfolio | OABP | Repair of Oguta well access road | 1.4856 |  | Additional budget moved from OF-Maintenance
9 | Portfolio | OABP | Repair of Adibawa access road | 2.34
|  |  | Sub Total | 9.0439 | 0.4522
Central East & Land
8 | Portfolio | OABP | Gbaran Produced Water Re-injection project | 3.24
11 | Portfolio | OABP | Soku GP Condensate Storage Tank 5501 Internal Inspection and repairs | 0.657
16 | Portfolio | OABP | Remedial works on Pontoon and jetty platform at Soku Flowstation | 0.387
13 | Portfolio | OABP | Completion of outstanding works on Ahia Instrumentation Gas to Instrumentation Air conversion | 0.243
15 | Portfolio | OABP | Gathering of Afam VI vents to flare header | 0.225
|  |  | Sub Total | 4.752 | 0.2376
Matrix
12 | Portfolio | OABP | Onramp Bonny Projects | 0.36
14 | Portfolio | OABP | Design and installation of liquid outlet valve 11LCV901 | 0.108
22 | GM COG | OABP | OX-BOW | 0.54
23 | GM COG | OABP | Iseni | 0
|  |  | Sub Total | 1.008 | 0.0504
FL
10 | Portfolio | OABP | Installation/replacement of insulation joints on flowlines | 0.72
21 | Portfolio | OABP | Flowlines procurement | 4.5
|  | OABP | Flowlines construction | 2.63
|  |  | Sub Total | 7.85 | 0.3925
24 | D&R | OABP | 16.2Km decomm for Pilot Pipeline (Imo R - Komkom D/L) :: Restoration of 1No. Adibawa Borrow Pit :: Restoration of 1No. Ubie Borrow Pit :: Decommissioning of Burnt Rig in EA Field - Front-end Activities | 1.5001
|  |  | Sub Total | 1.5001 | 0.075007
|  |  |  | 27.6821 | 1.3841
ADDITIONAL WORKS - EXTERNAL BUDGET
S/N | Project Type | Execution Team | Activity | NAPIMS Approved Budget (2022 $m) | Apply 5% cost savings across | Remark
West
|  |  | Sub Total | 0 | 0
Civil
|  |  | Sub Total | 0 | 0
Central East & Land
|  |  | Sub Total | 0 | 0
Matrix
|  |  | Sub Total | 0 | 0
|  |  | Sub Total | 0 | 0
|  |  |  | 0 | 0

## OABP NAPIMS Approved Budget
S/N | Project Type | Execution Team | Activity | NAPIMS Approved Budget (2022 $m) | Remark
1 | Portfolio | OABP | Otumara flare segregation | 1.98
2 | Portfolio | OABP | Escravos Beach FLB project | 4.18
3 | Portfolio | OABP | Cluster 2 (shutdown) and cluster 3 | 1.26
4 | Portfolio | OABP | Facility Mechanical Upgrade West Ogbotobo: Refurbishment of Corroded Helipad | 0 | Moved to Repair of Escravos Beach main access road
5 | Portfolio | OABP | Facility Mechanical Upgrade West (ESCRAVOS) -For IG to IA project | 0.27
6 | Portfolio | OABP | Repair of Tunu Jetty | 0.0108
7 | Portfolio | OABP | Repair of Benisede Jetty | 0.0072
8 | Portfolio | OABP | Gbaran Produced Water Re-injection project | 3.24
9 | Portfolio | OABP | Repair of Adibawa access road | 2.34
10 | Portfolio | OABP | Installation/replacement of insulation joints on flowlines | 0.72
11 | Portfolio | OABP | Soku GP Condensate Storage Tank 5501 Internal Inspection and repairs | 0.657
12 | Portfolio | OABP | Onramp Bonny Projects | 0.36
13 | Portfolio | OABP | Completion of outstanding works on Ahia Instrumentation Gas to Instrumentation Air conversion | 0.243
14 | Portfolio | OABP | Design and installation of liquid outlet valve 11LCV901 | 0.108
15 | Portfolio | OABP | Gathering of Afam VI vents to flare header | 0.225
16 | Portfolio | OABP | Remedial works on Pontoon and jetty platform at Soku Flowstation | 0.387
17 | Portfolio | OABP | Remediation Civil - Structural Works at Soku FS | 0.099
18 | Portfolio | OABP | Repair of Oguta well access road | 1.4856 | Additional budget moved from OF-Maintenance
19 | Portfolio | OABP | Shoreline & Jetty Repairs East | 0.57933 | Additional budget moved from OF-Maintenance
20 | Portfolio | OABP | Repair of Escravos Beach main access road | 0.36 | Moved from Refurbishment of Corroded Helipad above
21 | Portfolio | OABP | Flowlines procurement | 4.5
| Subtotal Portfolio |  |  | 23.0119
22 | GM COG | OABP | OX-BOW | 0.54
23 | GM COG | OABP | Iseni | 0
| Subtotal GM COG |  |  | 0.54
24 | D&R | OABP | 16.2Km decomm for Pilot Pipeline (Imo R - Komkom D/L) :: Restoration of 1No. Adibawa Borrow Pit :: Restoration of 1No. Ubie Borrow Pit :: Decommissioning of Burnt Rig in EA Field - Front-end Activities | 1.5001
| Overall Total |  |  | 25.0521