## Swamp West COST SAVINGS
OABP WEST FLOWLINE COST SAVINGS ACTIVITY JUNE 2022
S/N | OABP | Conduit | KM | 2022 Scope | BOPD | VENDOR | CATEGORY | STATUS | Plan Start | COST SAVINGS | REMARKS
1 | SSAGS | OPUK GESI-1 | 3 | NEW FLOWLINE | 2000 | SUNUP / TECHSTONE | MAJOR | ONGOING | 2022-02-01 | 256053 | Shared HB for 3 months due to concurrent activity execution
2 | SSAGS | OPUK FRSN-2 | 3 | NEW FLOWLINE | 2000 | A & N | MAJOR | ONGOING | 2022-02-01
4 | FIIP | FORC126S | 1.2 | FLRR | 625 | MATIZ / ARIOSH | MAJOR | ONGOING | 2022-03-01 | 85000 | Use of hotel rather than HB
5 | JV | TUNU | 0 | TWISTER INLET HEADER |  | KEMUD | MAJOR | COMPLETED | 2022-06-01 | 17000 | Use of Asset FLB instead of HB
6 | FIIP | FORC114S | 0 | JIV | 90 | MATIZ | MAJOR | COMPLETED | 2022-06-01 | 22000 | Use of vendor already at site for JIV
7 | JV | OTUM54T | 0 | JIV | 346 | HOECHY | MAJOR | COMPLETED | 2022-06-01 | 8000 | Single mob/demob by using one vendor and combining the JIVs to happen concurrently
8 | JV | OTUM42S | 0 | JIV | 346 | HOECHY | MAJOR | COMPLETED | 2022-06-01
9 | FIIP | BENS10L | 1.7 | FLRR | 950 | ANASAMI | MAJOR | COMPLETED | 2022-03-01 | 123823 | Use of DFTP security
10 | FIIP | BENS11S | 2.7 | FLRR | 700 | DAIIK / ROADLAMP | MAJOR | COMPLETED | 2022-03-01 | 123823 | Use of DFTP security
13 | WRFM | BENS002T | 0.2 | HKUP ARM REPL. | 500 | KEMUD | MAJOR | COMPLETED | 2022-02-01 | 85000 | Offsite fab/use of Asset FLB rather than HB
16 | WRFM | TUNU13T | 0.2 | SECT. REPL. | 1000 | KEMUD | MAJOR | PO ISSUED | 2022-07-01 | 20000 | Use of Asset FLB instead of HB
|  |  | 12 |  | 8557 |  |  |  |  | 740699