## Q2- 2022 Saving Summary
| LAND | CENTRAL | SWAMP WEST | CIVIL | OABP ASSET | AF | 100% (F$ ‘000) | FCF (100% x 0.3 x 0.85) (F$ ‘000) |  | Civil FCF | Swamp West FCF
|  |  |  | 115355.909 |  |  | 115355.909 | 29415.7568 | April | 29415.7568 | 0
|  |  | 46304.25 | 7247.204 |  |  | 53551.454 | 13655.6208 | May | 1848.037 | 11807.5837
|  |  | 24000 | 128061.18 |  |  | 152061.18 | 38775.6009 | June | 32655.6009 | 6120
Total | 0 | 0 | 70304.25 | 250664.293 | 0 | 0 | 320968.543 | 81846.9785 |  |  | 17927.5837
Remark

## April to June 2022
DATE | PROJECT | TYPE | WORP DECISION | STATUS | PE / SPONSOR | WBS | TOTAL VALUE/COST | [6 empty] | COST SAVINGS | Remarks | CONTRACT
[7 empty] | LAND | CENTRAL | SWAMP WEST | MATRIX | CIVIL | OABP ASSET | AF
2022-01-20 | Repair of Failed Weldolet on Soku Condensate Spiking Pump Discharge Header. – Resubmission. | Resubmission | Approved. WORP steers from previous sitting 23/12/21 have been fully incorporated. Further steers: I. Capture free-issue of weldolet (material) as cost saving. | Approved | Ehizoyanyan, O | O.NG.PBE.SKG.FAC.724FC |  | $ 114,297.50 N 10,174,989.43 F$ 39,114.5 | [5 empty] | F$: 43,425.65 | Using Inter area move instead of full Mob and Demob etc) | GRAMEN PETROSERVE
| Soku Structural Integrity Rehabilitation – Resubmission. | Resubmission | Approved. WORP steers from previous sitting 23/12/21 have been fully incorporated. Further steers: I. Include “Flowstation (FS)” in project title to reflect full workscope II. Confirm WBS is still valid. | Approved | Ehizoyanyan, O | O.NG.PBE.SKG.FAC.724FC |  | $ 94,263.12 N 32,029,442.44 F$ 172,883.61 | [5 empty] | NIL |  | GRAMEN PETROSERVE
| Zarama 15 Location Preparation and Access Road Rehabilitation | New | Approved. | Approved. | Osakwe, R | C.NG.LNG.DG.21.001.AC04 |  |  |  |  | $ 957,087.82 N 603,988,005.37 F$ 2,430,229.30 |  |  | F$: 62,313.57 | LOP @2.5% (NAPIMS Discount) | ZEROCK NIG
| Location and Access Road Rehabilitation Works at Gbaran 14/15 Location | New | Approved. I. Review needed to confirm schedule and quality assurance of work. | Approved. | Ezenduka, D | C.NG.PAE.DN.21.001.9410 |  |  |  |  | $ 159,007.05 N 98,628,691.97 F$ 399,564.84 |  |  | F$: 12,357.68 | LOP @3% (NAPIMS Discount) | RAYCON NIG
| Locations Dredging Works: Ogbotobo ANTM-1 & Ogbotobo AOTM-1. | New | Approved | Approved. | Onyejekwe, C | C.NG.AFS.DD.21.003.9401 C.NG.AFS.DD.21.002.9401 |  |  |  |  | $: 982,895.93 N: 585,168,641.77 F$: 2,410,136.52 |  |  | F$: 538,142.04 | LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| GENERAL |  | • Engage Warri materials support team and resolve issues with materials request/search in Warri area.
2022-01-27 | Tunu BQRT-3(W17) Hook Up -CWI Support and replacement of defective flowline valve | New | Approved. I. Ensure ownership of the work is clearly defined and understood by all parties via work permit. II. Review and reconcile VAT, HCD and NCD cost values for the work. | Approved | Otavie, G | C.NG.AFS.DD.19.009.9411 |  |  | $ 16,836.38 N 5,995,104.5 F$ 31,458.59 |  |  |  |  | NIL |  | Hoechy Limited
| Nun River FLB Jetty & Ramp Slots and Approach Areas Maintenance Dredging Works | New | Approved. | Approved | Onyejekwe, C | 110744 |  |  |  |  | $: 220,584.57 N: 181,236,514.25 F$: 662,624.85 |  |  | F$: 61,695.30 | LoP discounts (i.e. 15%). | BRIDGSITE NIG LTD
| GENERAL |  | • Teams should always notify leaders by email of emerging additional works while construction work at site is in progress. • Teams should endeavour to use pictures, drawings, diagrams in submissions presentation as this helps to explain the case better. • Civil team should carry out a CI on Civil Projects mobilization. • Strategy to manage identified CTS gaps in the replacement Civil contracts to be further discussed.
2022-02-10 | Estuary cluster 2 bulkline risers replacement and boatlanding Rehabilitation Works | New | Approved. I. Update Risk on Covid 19 II. Update Security Plan & SSP III. Fine tune the QA/QC scope | Approved | Uwaezuoke, D | C.NG.PBW.DF.21.001.1230 |  |  | $ 125,311.27 N 58,881,500.64 F$ 268,924.69 |  |  |  |  | Nil |  | Gramen Petroserve
| Installation of Pre-deployment Infrastructure for the Beyond Visual Line of Sight (BVLoS) Drone Project | New | Approved | Approved | Chioke, K | 113169 |  |  |  |  | $ 8,131.48 N 5,204,145.60 F$ 20,824.52 |  |  | Nil |  | RAYCON NIG
| Reconstruction of Nun River 07 Location, Access Road and Camp site. (Reviewed offline 30-12-21) |  | Approved | Approved | Agweda, V | P.NG.PAE.OP.19.005.9401 |  |  |  |  | $1,834,568.10 N1,175,162,339.14 F$ 4,700,817.70 |  |  | F$: 42,147.66 | Reduced the specification of houseboat from 60man to 40man capacity | MADONNA LIMITED
| GENERAL |  | All submissions to highlight Cost Savings
2022-02-24 | OPUK GESI-1 FLOWLINE CONSTRUCTION WORK 4” SCH 80 x 1km (SUNUP) | New | Conditional Approval | Conditional Approval | Uwaezuoke, D | C.NG.AFS.DL.21.001.1230 |  |  | $ 109,194.85 N 25,639,363.63 F$ 171,729.89 |  |  |  |  | NIL |  | SUNUP LOGISTICS
2022-03-03 | Kanbo W5L Flowline Sectional Replacement (4’’ x 1Km) | New | Conditional Approval. I. Engage CP to expedite loading of approved eLDL into SAP. II. Accelerate contract time extension with CP. III. Further review with PS to expunge houseboat and security escort rates and update rates as cost savings in the submission. IV. Harmonize security/surveillance with the already existing structure for W5S at site. V. Update project schedule to current plan. | Conditional Approval | Otavie, G | C.NG.AFS.DL.18.009.1202 |  |  | $ 90,167.35 N 22,812,340.57 F$ 147,346.37 |  |  |  |  | F$: 65,773.29 | Cost savings for using same houseboat / AGO / security. | ROMEK AND COMPANY LTD
| Flushing of 10’’Gbaran Produce Water from the Gbaran Oil & NAG Manifold to Gbaran CPF. | New | Deferred. I. Engage CP to finalize contract & rate extraction for this activity. | Deferred | Ehizoyanyan, O | C.NG.PBE.IM.21.001.1230 |  | $ 24,344.51 N6,159,174.43 F$39,203.80 | [5 empty] | NIL |  | Matiz Energy Limited
| ESCRAVOS ROAD AND SHORE PROTECTION REHAB (Reviewed Offline) | New | Approved | Approved | Agweda, V | C.NG.PAE.IC.21.001 |  |  |  |  | $ 128,792.54 N 77,269,896.49 F$ 317,255.70 |  |  | F$: 43,262.14 | LOP @12% (NAPIMS Discount) | TEMILE NIG
| GENERAL |  | Continuous Improvement Drive – collate and review FL activities timeline with a view to identifying and eliminating delay points.
2022-03-10 | OPUK FRSN-2 FLOW LINE WELL HEAD PLATFORM FABRICATION & INSTALLATION JOB. | New | Approved. I. Update contract ACV values in the submission. II. Accelerate contract time extension with CP. III. Ensure adequate security deployment at site. IV. Update cost savings from resource sharing (Houseboat) and forward to I&A. | Approved | Ehizoyanyan, O | C.NG.AFS.DL.21.002.1230 |  |  | $ 43,230.59 N 10,578,899.73 F$ 69,791.63 |  |  |  |  | NIL |  | AandN ENGINEERING
2022-03-17 | Replacement of 200M section of Soku 48S flowline. | New | Approved only for JIV. I. Ensure full stakeholders’ participation at the JIV. II. Engage Asset to confirm JIV cost ownership and execution. III. Revert with JIV report and updated work scope for WORP review. | Approved only for JIV | Obiakor, O | C.NG.PCW.DL.21.001. |  | $ 52,047.20 N 13,170,954.91 F$ 84,171.48 | [5 empty] | NIL |  | ANASAMI
| OPUK GESI-1 Flowline Construction Work 4” sch 80 x 1km (SUNUP) -Resubmission & reviewed offline | Resubmission | Approved. | Approved. | Uwaezuoke, D | C.NG.AFS.DL.21.001.1230 |  |  | $ 109,194.85 N 25,639,363.63 F$ 171,729.89 |  |  |  |  | NIL |  | SUNUP LOGISTICS
2022-03-24 | SECTIONAL REPLACEMENT OF OGUTA 17L FLOWLINE (4” x 48m) | New | Stepped Down | Stepped Down | Akinbiyi, A
| SECTIONAL REPLACEMENT OF MININTA 2T FLOWLINE (4” x 48m) | New | Stepped Down | Stepped Down | Akinbiyi, A
| LOCATION DREDGING WORKS AT BENISEDE ECTW-2. | New | Approved. I. Engage SE Lead & Corporate Environment to manage & ensure compliance with Net Zero Deforestation (NZD) commitment. II. Carry out a proper kick-off meeting and ensure adequate stakeholders’ participation. III. Update the cost savings value in the submission. IV. Revert to WORP if Sand replacement works would not be required after Geotechnical Investigation. | Approved | Onyejekwe, C | C.NG.AFS.DD.19.016.9401 |  |  |  |  | $: 1,052,957.60 N: 488,494,843.48 F$: 2,244,408.44 |  |  | F$: 17,044.14 | LoP discounts (i.e., 1%). | STRIDES ENERGY
2022-03-31 | Provision of 72hrs Security/surveillance for Kanbo W5S Flowline. | New | Approved. I. EST & Execution team to identify standard flowline handover requirement as prescribed in the SOP. | Approved | Otavie, G | C.NG.AFS.DL.19.004.1230 |  |  | $ 10,118.52 N 3,382,623.32 F$ 18,368.82 |  |  |  |  | NIL |  | ROMEK AND COMPANY
| Provision of Piping Materials for Leak Detection System (Installation of Coriolis Meter at Kolo Creek and Rumuekpe Manifolds | New | Deferred. I. Liase with CH to include submission in the summary of engagement scheduled with NAPIMS for support. | Deferred | Martyns, I | C.NG.PPE.DP.21.012 |  |  |  | N 26,297,103.15 $ 57,665.79 F$ 121,805.07 |  |  |  | NIL |  | GRAMEN PETROSERVE
| CR Support for LDS Project (Installation of Coriolis Meter at Kolo Creek and Rumuekpe Manifolds) | New | Conditional Approval Update and revert offline upon completion of the following: I. Attach evidence of NAPIMS support aligning the use of this vendor (Gramen Petroserve) | Conditional Approval | Martyns, I | C.NG.PPE.DP.21.012 |  |  |  | N 20,973,568.00 F$ 51,011.63 |  |  |  | NIL |  | GRAMEN PETROSERVE
| Geotechnical Investigation for design and construction of Odieke Bridge | New | Conditional Approval Update and revert offline upon completion of the followings: I. Update summary description of cost saving initiative to specify cost from negotiation outcome II. Carry out NAPIMS engagement and attach MoM to the resubmission. | Conditional Approval | Edoh, C | C.NG.LNG.DG.19.004.1230 |  |  |  |  | N 7,000,000 |  |  | ₦1,116,966.37.00 | (Original Scope Cost – N8,116,966.37; final scope cost – N7,000,000.00) | Geocadinal Integrated
| Geotechnical Investigation for Remediation of Collapsed Slope along Adibawa Main Access Road | New | Conditional Approval Update and revert offline upon completion of the following: I. Carry out NAPIMS engagement and attach MoM to the resubmission | Conditional Approval | Edoh, C | C.NG.PAE.IC.18.001 |  |  |  |  | N 7,400,000 |  |  | N 509,510.00 | (Original Scope Cost – N7,909,510; final scope cost – N7,400,000.00) | Kyje Geodrills
| Tunu W13T Leak Search/ Flowline Sectional Replacement (6’’ x 0.2Km) -Reviewed offline | Resubmission | Approved. | Approved | Otavie, G | O.NG.STG.PBE.TUN.013FL. |  |  | $ 47,195.58 N 11,960,471.22 F$ 77,369.19 |  |  |  |  | NIL |  | KEMUD INTERNATIONAL
| GENERAL |  | • EST & Execution team to identify standard flowline handover requirement as prescribed in the SOP. • Absence of Finance & CP for Flowlines & Facilities
2022-04-07 | BENISEDE WELL 2T MAINTENANACE DREDGING WORKS | New | Approved. I. Explore option of further cost savings from efficient execution at site. II. Update Project Schedule to current plan. | Approved | Oludare, S | 110744 |  |  |  |  | $: 200,002.45 N: 190,044,268.62 F$: 663,525.06 |  |  | F$ 111,446.11 | Low Oil Price LoP discounts (i.e. 22%). | LOENSE INTERNATIONAL
| PROVIDE ESCORT SWAMP VEST FOR OPUK GESI-1/FRSN 2 FLOWLINE CONSTRUCTION WORK | New | Approved. I. Update 5no top risks in line with the dynamic risk assessment carried out. | Approved | Uwaezuoke, D | C.NG.AFS.DL.21.001.1230 |  |  | $ 218.19 N 809,179.84 F$ 2,191.80 |  |  |  |  | NIL |  | SUNUP LOGISTICS
| GENERAL |  | • Update LOP 22% discount to 2015 (LOP 22% agreed discount) in the cost saving initiative. • PMT cost to be distinctive with Salaries
2022-04-14 | Geotechnical Investigation for Remediation of Collapsed Slope along Adibawa Main Access Road - Resubmission | Resubmission | Approved. WORP steers from previous sitting 31/03/22 have been incorporated. I. Include list of nominated Contracts in the MoM with NAPIMS. II. Ensure MoM is signed and forwarded to the secretariat. | Approved | Edoh, C | C.NG.PAE.IC.18.001 |  |  |  |  | N 7,400,000 |  |  | N 509,510.00 | (Original Scope Cost – N7,909,510; final scope cost – N7,400,000.00) | Kyje Geodrills
| Geotechnical Investigation for design and construction of Odieke bridge | Resubmission | Approved. WORP steers from previous sitting 31/03/22 have been incorporated. I. Include list of nominated Contracts in the MoM with NAPIMS. II. Ensure MoM is signed and forwarded to the secretariat. | Approved | Edoh, C | C.NG.LNG.DG.19.004.1230 |  |  |  |  | N 7,000,000 |  |  | ₦1,116,966.37.00 | (Original Scope Cost – N8,116,966.37; final scope cost – N7,000,000.00) | Geocadinal Integrated
| Replacement of 1.0kM section of SEIBU 1T flowline | New | Deferred. I. Engage CR & Asset team to resolve any underlying issues with the community to avoid reoccurrence of line vandalization. II. Liase with the Marine team to optimize houseboat to a 100-man capacity and adopt campaign mode mobilization. III. Include soft drinks and biscuits in the catering estimates to mitigate risk of fatigue from long walking hours. IV. Engage C&P to update Surveillance unit rate to “day” as against “hourly” provision in SAP. V. Hold a strategy meeting to align the need for either an OH Doctor at site or as would be advised by stakeholders and document. | Deferred | Obiakor, O | C.NG.AFS.DL.22.003. |  |  | $ 94,012.15 N 23,539,762.92 F$ 152,054.73 |  |  |  |  | NIL |  | ROMEK AND COMPANY
| Replacement of 1.0kM section of SEIBU 2S flowline | New | Deferred. I. Engage CR & Asset team to resolve any underlying issues with the community to avoid reoccurrence of line vandalization. II. Liaise with the Marine team to optimize houseboat to a 100-man capacity and adopt campaign mode mobilization. III. Include soft drinks and biscuits in the catering estimates to mitigate risk of fatigue from long walking hours. IV. Engage C&P to update Surveillance unit rate to “day” as against “hourly” provision in SAP. V. Hold a strategy meeting to align the need for either an OH Doctor at site or as would be advised by stakeholders and document. | Deferred | Obiakor, O | C.NG.AFS.DL.22.003. |  |  | $ 99,904.47 N 25,458,699.77 F$ 161,998.86 |  |  |  |  | NIL |  | ROADLAMP LTD
| Replacement of 1.0kM section of SEIBU 3L/S flowline | New | Deferred. I. Engage CR & Asset team to resolve any underlying issues with the community to avoid reoccurrence of line vandalization. II. Liaise with the Marine team to optimize houseboat to a 100-man capacity and adopt campaign mode mobilization. III. Include soft drinks and biscuits in the catering estimates to mitigate risk of fatigue from long walking hours. IV. Engage C&P to update Surveillance unit rate to “day” as against “hourly” provision in SAP. V. Hold a strategy meeting to align the need for either an OH Doctor at site or as would be advised by stakeholders and document. | Deferred | Obiakor, O | C.NG.AFS.DL.22.002 |  |  | $ 192,745.32 N 5,748,466.14 F$ 206,765.97 |  |  |  |  | NIL |  | TUESBEN GLOBAL
| Gbaran 14 Replacement Work. | New | Conditional Approval. I. Update Contract ACV in the submission. II. Carry out formal engagement with NAPIMS on the choice of vendor. | Conditional Approval | Omon, E | TBA |  | $ 50,510.65 N 37,798,432.95 F$ 142,701.95 | [5 empty] | NIL |  | Gramen Petroserve
| Gbaran 14 Flare Test Pit and Bund wall Construction Work | New | Conditional Approval. I. Carry out formal engagement with NAPIMS on the choice of vendor. II. Include procurement of materials in the scope summary. III. Carry out materials reconciliation with hotdesk and discount available materials. | Conditional Approval | Omon, E | TBA |  | $ 59,957.13 N 115,662,488.25 F$ 342,660.71 | [5 empty] | NIL |  | Gramen Petroserve
| Gbaran Produce Water Re-injection Project – Balance of Plant Works 2 | New | Deferred. I. Engage C&P to review adopted rates in the detailed cost estimates and revert. | Deferred | Akoma, I | C.NG.PBE.IM.21.001.1230 |  | $ 201,589.17 N 66,315,046.86 F$ 363,333.19 | [5 empty] | NIL |  | GRAMEN PETROSERVE
| GENERAL |  | • Continuous advocacy for Covid19 vaccination across OABP sites.
2022-04-21 | No Submission
2022-04-28 | SOKU FLOWSTATION PONTOON RECONSTRUCTION AND WOODEN FENDERS CHANGEOUT WORKS. | New | Conditional Approval. I. Update contract ACV. II. Engage EST & MCI to ascertain types of materials to be deployed for this activity. III. Carry out materials reconciliation with hotdesk. IV. Update WBS for the Pontoon work. V. Carry out desktop review of the 6no top risks. VI. Confirm accommodation type requirement between FLB or Houseboat deployment and update cost accordingly. VII. Attach a signed e-WR. | Conditional Approval | Ehizoyanyan, O | O.NG.PBE.SKF.FAC.724FC – FENDERS INSTALLATION. O.NG.PBE.SKF.FAC.724FC - PONTOON WORKS |  | $ 154,612.29 N 33,725,027.82 F$ 236,863.45 | [5 empty] | NIL |  | GRAMEN PETROSERVE
| SECTIONAL REPLACEMENT OF OPUKUSHI 24T (4" x 500m) | New | Approved. I. Update contract ACV. II. Hold a proper kick off meeting and ensure adequate stakeholder participation. III. Ensure proper Goal Zero documentation. | Approved | Orji, C | C.NG.AFS.DL.22.004 |  |  | $ 54,473.62 N 13,781,827.32 F$ 88,087.83 |  |  |  |  | NIL |  | MATIZ ENERGY
| SECTIONAL REPLACEMENT OF OPUKUSHI 12L/S | New | Deferred. I. Update flowline length in the submission. II. Attach a signed copy of the JIV report and revalidate scope length. III. Engage PS for a proper cost review of houseboat duration. IV. Carry out materials reconciliation with hotdesk and discount accordingly. V. Confirm vendor’s capability to deliver on schedule. | Deferred. | Orji, C | C.NG.AFS.DL.22.004 |  |  | $ 55,430.64 N 14,023,952.78 F$ 89,635.40 |  |  |  |  | NIL |  | Ariosh Limited
| GENERAL |  | • Ensure equitable work distribution among contractors. • Hold a proper kick off meeting for all our new vendors and ensure adequate stakeholder participation. • Always ensure early houseboat request to the marine team
2022-05-05 | Sectional Replacement of Opukushi 12L/S (4” x 200m) each -Resubmission. | Resubmission | Approved. WORP steers from previous sitting 28/04/22 have been incorporated. Further steers: I. Finalize materials reconciliation with hotdesk and discount available stock during Service Entry. II. Hold a proper kick off meeting with adequate stakeholder participation III. Ensure contractor understands the importance of good surveillance and intelligence gathering during work execution | Approved | Orji, C | C.NG.AFS.DL.22.006.1230 |  |  | $ 55,430.64 N 14,023,952.78 F$ 89,635.40 |  |  |  |  | F$ 46,304.25 | Cost saving from houseboat. To share houseboat with workers of Opuk 24T | Ariosh Limited
| Forcados 126S Flow line Replacement – Additional scope (4’’ sch 60 x 200m) | New | Approved. I. Escalate to Asset Leadership to forestall further community encroachment into SPDC’s RoW. | Approved | Orji, C | C.NG.PCW.DL.21.001.1230 |  |  | $ 24,706.83 N 6,250,826.14 F$ 39,952.74 |  |  |  |  | NIL |  | MATIZ ENERGY
| Epu 2 Development Geotechnical Investigation- {Location + Hand Auger} | New | Approved. I. Update project schedule to current plan | Approved | Edoh, C | P.NG.PAE.DG.20.001.1238 |  |  |  |  | N 7,999,999.76 |  |  | ₦1,199,688.49 | Cost savings from contract negotiation outcome | Transcore Geoscience
| Epu 2 Development Geotechnical Investigation- Right of Way | New | Approved. I. Update project schedule to current plan | Approved | Edoh, C | P.NG.PAE.DG.20.001.1238 |  |  |  |  | N 8,000,000 |  |  | ₦1,815,148.37 | Cost savings from contract negotiation outcome. | Groundscan Services
| Tunu CPF Twister Inlet Fabrication Header & Installation. | New | Approved. I. Engage Asset team to provide FLB accommodation and discount Houseboat / Tugboats cost from the estimate. II. Forward final submission to the secretariat for documentation. | Approved | Azaka, G | TBA |  |  | $20,415.70 N5,165,170.95 F$ 33,013.67 |  |  |  |  | NIL |  | KEMUD INTERNATIONAL
| Fabrication of 6-INCH Spool for IMOR 37L (6” x 12m) | New | Conditional Approval. I. Project Team to call Engr. Simple (NAPIMS Representative) and notify him of the IMOR 37L fabricated spool” II. Engage Integration team for a proper cost savings categorization. | Conditional Approval | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 2,697.19 N 682,391.37 F$ 4,361.56 | [6 empty] | NIL |  | ROMEK
| GENERAL |  | • Ensure equitable work distribution amongst contractors. • Forward summary of cost savings for Q1/2022 to the Manager • Always document contractors site performance for referencing.
2022-05-12 | Forcados 114 Flowline JIV Asset Support. | New | Approved. I. Ensure proper HSE engagement prior mobilization. II. Update 5no top risks. | Approved | Orji, C | O.NG.PCW.OKF.FAC.71300. |  |  | $ 6,328.81 N 1,601,187.59 F$ 10,234.14 |  |  |  |  | NIL |  | MATIZ ENERGY
| Flushing of 10’’ Gbaran Produce Water from the Gbaran Oil & NAG Manifold to Gbaran CPF.) -Resubmission | Resubmission | Approved. WORP steer from previous sitting 03/03/22 have been incorporated. | Approved | Ehizoyanyan, O | C.NG.PBE.IM.21.001.1230 |  | $ 20,110.20 N5,080,092.01 F$32,520.18 | [5 empty] | NIL |  | Matiz Energy
| Gbaran 14 Replacement Work | Resubmission | Conditional Approval. I. Engage NAPIMS on the choice of vendor for this activity. II. Finalize contract release in SAP. | Conditional Approval | Ehizoyanyan, O | C.NG.PAE.DF.22.001 |  | $ 45,055.98 N 31,846,961.53 F$ 122,731.49 | [5 empty] | NIL |  | SCANTEX AGENCIES
| Gbaran 14 Flare Test Pit and Bund wall Construction Work | Resubmission | Deferred. I. Carry out formal engagement with NAPIMS on the choice of vendor. | Deferred | Ehizoyanyan, O | C.NG.PAE.DF.22.001. |  | $ 102,983.40 N 77,815,012.87 F$ 292,776.11 | [5 empty] | NIL |  | SCANTEX AGENCIES
| Fabrication of 6-Inch spool for ImoR 37L (6” x 12m) – Resubmission | Resubmission | Approved. WORP steers from previous sitting 05/05/22 have been incorporated. | Approved | Aderiye, A | O.NG.PAE.I1F.FAC.724FC | $ 2,697.19 N 682,391.37 F$ 4,361.56 | [6 empty] | NIL |  | ROMEK
| Gbaran Produce Water Re-injection Project – Balance of Plant Works 2 | New | Conditional Approval. Update and revert upon completion of the following: I. Engage Finance Advisor to resolve budget provision for this activity. | Conditional Approval | Akoma, I | C.NG.PBE.IM.21.001.1230 |  | $ 277,168.33 N 204,994,138.50 F$ 777,154.04 | [5 empty] | NIL |  | GRAMEN PETROSERVE
| Diebu W12T Hook-up arm fabrication / installation and platform repairs. | New | Conditional Approval. Update and revert upon completion of the followings: I. Carry out material reconciliation with Hotdesk and discount available stock. II. Update Project Schedule to current plan. III. Explore opportunity for cost savings from resource (houseboat) sharing. IV. Proper CR engagement to forestall community work delays at site. | Conditional Approval | Azaka, G | O.NG.PBE.DBC.12T.713FL |  | $ 31,257.95 N7,908,260.45 F$50,546.39 | [5 empty] | NIL |  | TECHSTONE NIGERIA
2022-05-19 | DIEBU W12T HOOK UP ARM FABRICATION / INSTALLATION AND PLATFORM REPAIRS. - Resubmission. | Resubmission | Approved. WORP steers from previous sitting 12/05/22 have been incorporated. I. Finalize accommodation plan prior mobilization | Approved | Azaka, G | O.NG.PBE.DBC.12T.713FL |  | $ 50,546.39 N9,175.29 F$ 59,721.68 | [5 empty] | NIL |  | TECHSTONE
| INTERGRITY TESTS ON ETELEBOU 9T FLOWLINE & HOOKUP ARM. | New | Approved. I. Hold a proper kick-off meeting with adequate stakeholder participation. | Approved | Aderiye, A | O.NG.PAE.ETL.03S.713 |  | $ 6,513.98 N 1,647,557.71 F$ 10,532.41 | [5 empty] | NIL |  | QUICK TOOLS
| OPUKUSHI W7 JIV | New | Deferred / Stepped down I. Engage EST to confirm SPDC’s current position on line clamping and revert. | Deferred | Uwaezuoke, D
2022-05-26 | REPLACEMENT OF 1.0km SECTION OF SEIBU 1T FLOWLINE - Resubmission | Resubmission | Conditional Approval. WORP steers from previous sitting 14/04/22 have not been fully incorporated. Further steers: I. Develop a strategy note on securing the line post construction. II. Engage NAPIMS on securing the line post construction and attach outcome of the engagement to the resubmission. | Conditional Approval | Obiakor, O | C.NG.AFS.DL.22.003. |  |  | $ 94,012.15 N 23,539,762.92 F$ 152,054.73 |  |  |  |  | NIL |  | ROMEK AND COMPANY
| REPLACEMENT OF 1.0km SECTION OF SEIBU 2L/S BULKLINE - Resubmission | Resubmission | Conditional Approval. WORP steers from previous sitting 14/04/22 have not been fully incorporated. Further steers: I. Develop a strategy note on securing the line post construction. II. Engage NAPIMS on securing the line post construction and attach outcome of the engagement to the resubmission. | Conditional Approval | Obiakor, O | C.NG.AFS.DL.22.003. |  |  | $ 99,904.47 N 25,458,699.77 F$ 161,998.86 |  |  |  |  | NIL |  | ROADLAMP LTD
| REPLACEMENT OF 1.0km SECTION OF SEIBU 3L/S BULKLINE - Resubmission | Resubmission | Conditional Approval. WORP steers from previous sitting 14/04/22 have not been fully incorporated. Further steers: I. Develop a strategy note on securing the line post construction. II. Engage NAPIMS on securing the line post construction and attach outcome of the engagement to the resubmission. | Conditional Approval | Obiakor, O | C.NG.AFS.DL.22.002 |  |  | $ 192,745.32 N 5,748,466.14 F$ 206,765.97 |  |  |  |  | NIL |  | TUESBEN GLOBAL
| JIV INSPECTION OF OTUMARA WELL 42L & 54T FLOWLINES |  | Stepped down by team.
| CONSTRUCTION OF ENWHE WEST LOCATION, BY-PASS, AND CONCRETE BRIDGE EMERGENCY REMEDIAL ACCESS TO LOCATION THROUGH BRIDGE. | New | Deferred. I. Attach current site location pictures & evidence of NLNG support to the resubmission. II. Carry out NAPIMS alignment and document evidence for this activity. | Deferred | Ezenduka, D | C.NG.LNG.19.004.1230 |  |  |  |  | N176,178,864.60 +$ 293,847.62, F$:723,552.17 |  |  | F$: 128,061.18 | Avoidance of mobilization | ENERCO NIG LIMITED
| GENERAL |  | Update contractors work distribution template
2022-06-02 | FORC 114 FLOWLINE JUNE 2022 JIV ASSET SUPPORT. | New | Approved. I. Update Business case to specify this activity is a “Repeat JIV” II. Attach e-mail evidence of initial JIV suspension after mobilization by the Asset. III. Ensure adequate stakeholders’ participation to avoid repeat cancellation. | Approved | Orji, C | O.NG.PCW.OKF.FAC.71300. |  |  | $ 6,328.81 N 1,601,187.59 F$ 10,234.14 |  |  |  |  | NIL |  | MATIZ ENERGY
| GBAR016 well re-injection project: Flowline temporary de-commissioning & re-instatement | New | Deferred. I. Carry out PS review II. Update Business case to specify actual work scope for this submission. III. Attach MoM of NAPIMS engagement. IV. Engage Project Lead to explore option of using the newly approved Mechanical Modification contracts for this activity. | Deferred | Uwaezuoke, D | C.NG.PAE. DN.22.001.9413 |  | $ 28,003.18 N 27,044,805.00 F$ 93,966.12 | [5 empty] | NIL |  | Gramen Petroserve
| GENERAL |  | Update contractors’ work distribution template
2022-06-09 | CONSTRUCTION OF ENWHE WEST LOCATION, BY-PASS, AND CONCRETE BRIDGE EMERGENCY REMEDIAL ACCESS TO LOCATION THROUGH BRIDGE - Resubmission | Resubmissiojn | Approved. WORP steers from previous sitting 26/05/22 have been fully incorporated. | Approved | Ezenduka, D | C.NG.LNG.19.004.1230 |  |  |  |  | N134,526,452.71 +$224,399.24, F$:552,512.54 |  |  | F$: 128,061.18 | Avoidance of mobilization | ENERCO NIG LIMITED
| Gbaran 14 Flare Test Pit and Bund wall Construction Work. | Resubmissiojn | Approved. WORP steers from previous sitting 26/05/22 have been incorporated. Further steers: I. Update WBS for this activity. II. Attach evidence of NAPIMS engagement held. III. Further engagement with Hotdesk to discount all available materials and send updated resubmission to the secretariat | Approved | Ehizoyanyan, O | TBA |  | $ 88,366.94 N 120,415,928.79 F$ 382,064.32 | [5 empty] | NIL |  | Gramen
| AHIA INSTRUMENT GAS TO INSTRUMENT AIR INSTALLATION | New | Mechanical Scope: I. Approved. Proceed upon completion of material reconciliation with hotdesk and forward updated submission to the secretariat. PACO (Instrument Scope): I. Not Approved. Engage C&P on contract extension and revert. | Approved | Dienagha, I | C.NG.PAE.DF.19.032 | CW593866 – $ 53,419.33 CW263542 – $3,102.55 CW593866 – N 33,741,324.68 CW263542 – N7,898,612.00 CW593866 – F$ 135,715.24 CW263542 – $22,367.46 | [6 empty] | NIL |  | CLE-PARINNA INT'L LTD
| BONNY WELL 31 MAINTENANCE DREDGING WORKS. | New | Approved. I. Update project schedule to current plan and align CTS duration in the schedule | Approved | Oludare, S | O.NG.PTE.NAG.FAC.71300 |  |  |  |  | $: 313,246.78 N: 168,131,635.47 F$: 723,323.94 |  |  | NIL |  | SHORELINE DREDGING
| PROVISION OF SURVEILLANCE FOR COMPLETED OPUK 39 FLOWLINE | New | Approved. I. Ensure full compliance to SPDC HSE standards and the use of PFDs at site. | Approved | Uwaezuoke, D | C.NG.AFS.DD.19.012.9411 |  |  | $ 34,735.25 N 8,788,018.16 F$ 56,169.44 |  |  |  |  | NIL |  | A & N ENGINEERING
| FLUSHING & BLIND FLANGING OF BENISEDE W10L FLOWLINE (4" SCH 60 x 1.7km) | New | Approved. I. Strict adherence to procedures to avoid spill into the environment. | Approved | Otavie, G | C.NG.PCW.DL.21.001.1230 |  |  | $ 6,763.24 N 1,711,177.69 F$ 10,936.84 |  |  |  |  | NIL |  | ANASAMI
| JIV INSPECTION OF OTUMARA WELL 42L & 54T FLOWLINES | New | Approved. I. Ensure full stakeholders’ participation to forestall repeat visit | Approved | Obiakor, O | O.NG.PBW.OTF.FAC.71300. |  |  | $ 23,615,62 N 5,974,743.98 F$ 38,188.17 |  |  |  |  | NIL |  | HOECHEY
| INTERGRITY TESTS ON AHIA 14S FLOWLINE & HOOKUP ARM. | New | Conditional Approval. I. Engage Project Lead to confirm contractors’ capacity to deliver this activity simultaneously with previously assigned works. | Conditional Approval | Aderiye, A | O.NG.STG.PAE.AHA.014SFL | $ 6,513.98 N 1,647,557.71 F$ 10,532.41 | [6 empty] | NIL |  | CLE-PARINNA INT'L LTD
| ADDITIONAL LOCATION DREDGING WORKS AT OGBOTOBO AMTT-1. | New | Deferred. I. Confirm additional works are within the approved work Order by NAPIMS. II. Update Project Schedule to current plan | Deferred | Onyejekwe, C | C.NG.AFS.DD.21.004.9401 |  |  |  |  | $: 397,970.62 N: 117,328,501.77 F$: 684,137.70 |  |  | NIL |  | SERVITECO LTD)
| ADDITIONAL LOCATION DREDGING WORKS AT OGBOTOBO AMTS-1. | New | Deferred. I. Confirm additional works are within the approved work Order by NAPIMS. II. Update Project Schedule to current plan | Deferred | Onyejekwe, C | C.NG.AFS.DD.21.005.9401 |  |  |  |  | $: 357,057.86 N: 124,087,236.27 F$: 659,709.66 |  |  | NIL |  | FW DREDGING
| GBAR016 WELL FLOWLINE APPROACH DECOMMISSIONING -Resubmission & reviewed offline | Resubmission | Approved. WORP steers from previous sitting 02/06/22 have been incorporated. | Approved | Uwaezuoke, D | C.NG.PAE. DN.22.001.9413 |  | $ 9,428.22 N 6,653,643.08 F$ 25,656.62 | [5 empty] | NIL |  | SCANTEX AGENCY
| GENERAL |  | • Progress contract time extension for all contracts expiring in September 2022 • Confirm HCD allocation status
2022-06-16 | ADDITIONAL LOCATION DREDGING WORKS AT OGBOTOBO AMTT-1. | Resubmission | Conditional Approval. Carry out the following WORP steers and revert offline I. Forward secured NAPIMS approval on budget, emails, notes etc to NAPIMS (Ohallem, S) II. Kindly communicate SPDC requested support to NAPIMS | Conditional Approval | Onyejekwe, C | C.NG.AFS.DD.21.004.9401 |  |  |  |  | $: 397,970.62 N: 117,328,501.77 F$: 684,137.70 |  |  | NIL |  | SERVITECO
| ADDITIONAL LOCATION DREDGING WORKS AT OGBOTOBO AMTS-1. | Resubmission | Conditional Approval. Carry out the following WORP steers and revert offline I. Forward secured NAPIMS approval on budget, emails, notes etc to NAPIMS (Ohallem, S) II. Kindly communicate SPDC requested support to NAPIMS | Conditional Approval | Onyejekwe, C | C.NG.AFS.DD.21.005.9401 |  |  |  |  | $: 357,057.86 N: 124,087,236.27 F$: 659,709.66 |  |  | NIL |  | FW DREDGING LTD
| Seibou 1T – Sectional Replacement of Flowline Re-submission | Resubmission | Deferred Carry out the following WORP steer and revert offline I. Align with NAPIMS on strategy for work execution | Deferred | Obiakor, O | C.NG.AFS.DL.22.003. |  |  | $ 94,012.15 N 23,539,762.92 F$ 152,054.73 |  |  |  |  | NIL |  | ROMEK AND COMPANY
| Seibou 2S – Sectional Replacement of Flowline Re-submission | Resubmission | Deferred Carry out the following WORP steer and revert offline I. Align with NAPIMS on strategy for work execution | Deferred | Obiakor, O | C.NG.AFS.DL.22.003. |  |  | $ 99,904.47 N 25,458,699.77 F$ 161,998.86 |  |  |  |  | NIL |  | ROADLAMP LTD
| Seibou 3L/S – Sectional Replacement of Flowline Re-submission | Resubmission | Deferred Carry out the following WORP steer and revert offline I. Align with NAPIMS on strategy for work execution | Deferred | Obiakor, O | C.NG.AFS.DL.22.002 |  |  | $ 192,745.32 N 5,748,466.14 F$ 206,765.97 |  |  |  |  | NIL |  | TUESBEN GLOBAL
| Repair of Soku GP Condensate Storage Tank (T5501). | New | Deferred Carry out the following WORP steers and revert offline I. Demonstrate and show how cost compares with the use of other contracts to execute the work II. Engage and Align with NAPIMS on strategy for work execution | Deferred | Obiakor, O | C.NG.PBE.DF.19.091.1230 |  | $ 105,402.09 N 138,643,188.41 F$ 439,885.05 | [5 empty] | NIL |  | GRAMEN
| Gbaran 14 - Replacement Work- Materials Integrity Check | New | Approved. I. Ensure there is contingency in place to secure the required number of instruments II. Correct the name of the vendor in the cost estimate document & forward to the secretariat. | Approved | Arowosafe, T | C.NG.PAE.DF.22.001. |  | $ 3,143.78 N 2,218,589.36 F$ 8,554.97 | [5 empty] | NIL |  | SCANTEX AGENCIES
| Kanbo 5L – Sectional Replacement of Flowline | New | Carry out the following WORP steer and revert offline I. Align with NAPIMS on strategy for work execution | Deferred | Otavie, G | C.NG.AFS.DL.22.009.1230 |  |  | $ 124,129.46 N 31,285,699.29 F$ 200,436.04 |  |  |  |  | NIL |  | DAIIK ENGINEERING
| AJAT001L - Insulating Joint/Flowline Approach Replacement | New | Deferred Carry out the following WORP steer and revert offline I. Align with NAPIMS on strategy for work execution | Deferred | Otavie, G | C.NG.AFS.DL.22.009.1230 |  |  | $ 43,551.84 N 10,363,939.66 F$ 68,829.74 |  |  |  |  | F$: 24,000 | using Houseboat in the field without mobilizing an additional one | ROMEK
| Integrity Test on Ahia 14S flowline & hookup arm. Resubmission & reviewed offline | Resubmission | Approved. | Approved | Aderiye, A | O.NG.STG.PAE.AHA.014SFL | $ 6,513.98 N 1,647,557.71 F$ 10,532.41 | [6 empty] | NIL |  | GUIZ AND COMPANY
2022-06-23 | Replacement of Otumara 35L GLL (4” x 2.0km line) | New | Conditional Approval. Carry out the following WORP steers and revert offline I. Recategorize piracy and boat hijack to security risk. II. Engage PS & Security Lead to review houseboat provision and security accommodation at site. III. Include personnel OSP value in the cost estimate. | Conditional Approval | Obiakor, O | C.NG.AFS.DL.22.003. |  |  | $ 265,227.78 N 7,314,141.89 F$ 282,852.22 |  |  |  |  | NIL |  | JOLANDY’S INT LTD
| Replacement of Otumara 39L GLL (4” x 1.8km line) | New | Conditional Approval. Carry out the following WORP steers and revert offline I. Recategorize piracy and boat hijack to security risk. II. Engage PS & Security Lead to review houseboat provision and security accommodation at site. III. Include personnel OSP value in the cost estimate. | Conditional Approval | Olusola, O | C.NG.AFS.DL.22.003. |  |  | $ 250,987.24 N 6,992,549.81 F$ 267,836.76 |  |  |  |  | NIL |  | HABOUR OIL & GAS
| Soku Alternative Condensate Evacuation Project (ACE) – In Plot Scope - Gramen | New | Conditional Approval. Carry out the following WORP steers and revert offline I. Engage CH and secure alignment to use Gramen contract for this scope. II. Ensure a Technical Integrity Verification (TIV) is in plan for the project | Conditional Approval | Ogbobe, O | C.NG.PAE.DF.22.003.1230 |  |  |  | $: 186,218.97 N: 76,947,848.51 F$:373,896.65 |  |  |  | NIL |  | Gramen Petro serve
| Alternative Condensate Evacuation Project - Soku Gas Plant Out plot scope - Anasami | New | Approved. I. Ensure a Technical Integrity Verification (TIV) is in plan for the project | Approved | Odey, E | C.NG.PAE.DF.22.003.1230 |  |  |  | $: 89,758.22 N: 22,708,019.10 F$: 145,143.63 |  |  |  | NIL |  | Anasami Construction
| AJAT001L Insulating Joint/Flowline Approach Replacement - Resubmission & reviewed offline | Resubmission | Approved. WORP steers from previous sitting 16/06/22 have been incorporated. | Approved | Otavie, G | C.NG.AFS.DL.22.009.1230 |  |  | $ 43,551.84 N 10,363,939.66 F$ 68,829.74 |  |  |  |  | F$: 24,000 | using Houseboat in the field without mobilizing an additional one | ROMEK
| Replacement of 1.0km section of SEIBU 1T flowline - Resubmission & reviewed offline | Resubmission | Approved. WORP steers from previous sitting 16/06/22 have been incorporated. | Approved | Obiakor, O | C.NG.AFS.DL.22.003. |  |  | $ 94,012.15 N 23,539,762.92 F$ 152,054.73 |  |  |  |  | NIL |  | ROMEK
| Replacement of 1.0km section of SEIBU 2L/S Bulkline - Resubmission & reviewed offline | Resubmission | Approved. WORP steers from previous sitting 16/06/22 have been incorporated. | Approved | Obiakor, O | C.NG.AFS.DL.22.003. |  |  | $ 99,904.47 N 25,458,699.77 F$ 161,998.86 |  |  |  |  | NIL |  | ROADLAMP
| Replacement of 1.0km section of SEIBU 3L/S Bulkline - Resubmission & reviewed offline | Resubmission | Approved. WORP steers from previous sitting 16/06/22 have been incorporated. | Approved | Obiakor, O | C.NG.AFS.DL.22.002 |  |  | $ 192,745.32 N 5,748,466.14 F$ 206,765.97 |  |  |  |  | NIL |  | TUESBEN GLOBAL
| Kanbo W 5L Flowline Sectional Replacement (4’’ x 1.7Km) -Resubmission & reviewed offline | Resubmission | Approved. WORP steers from previous sitting 16/06/22 have been incorporated. | Approved | Otavie, G | C.NG.AFS.DL.22.009.1230 |  |  | $ 124,129.46 N 31,285,699.29 F$ 200,436.04 |  |  |  |  | NIL |  | DAIIK ENGINEERING
| Sectional Replacement & Hook up arm replacement of Opukushi N021T -Reviewed offline | New | Approved | Approved | Orji, C | C.NG.AFS.DL.22.004.1230 |  |  | $ 74217.53 N 11,611,739.48 F$ 90,126.26 |  |  |  |  | NIL |  | TECHSTONE
| GENERAL |  | • Follow up on e-LDL allocation for Mechanical Modification contracts. • Include personnel OSP value in the cost estimate for swamp submissions.
2022-06-30 | Soku flow station Pontoon Reconstruction and Wooden fenders Changeout works. -Resubmission | Resubmission | Conditional Approval. WORP steers from previous sitting 28/04 has not been fully implemented. Further steer: I. Attach an approved e-WR to the resubmission. | Conditional Approval | Ehizoyanyan, O | C.NG.PAE.DF.20.001 – FENDERS INSTALLATION. C.NG.PBE.IC.17.001 - PONTOON WORKS |  | $ 154,612.29 N 33,725,027.82 F$ 236,863.45 | [5 empty] | NIL |  | GRAMEN PETROSERVE
| NUNR W11S Complete Flowline Replacement. | New | Deferred. Update and revert upon completion of the followings: I. Engage CH to update ACV and Budget provision for this activity. II. Explore opportunity for cost savings from resource sharing. | Deferred | Azaka, G | O.NG.PBE.DBC.127.713FL |  | $67,973.16 N17,197,209.82 F$ 109,917.58 | [5 empty] | NIL |  | KEMUD
| NUNR W11L Complete Flowline Replacement | New | Deferred. Update and revert upon completion of the followings: I. Engage CH to update ACV and Budget provision for this activity. II. Explore opportunity for cost savings from resource sharing. | Deferred | Azaka, G | O.NG.PBE.DBC.127.713FL |  | $67,973.16 N17,197,209.82 F$ 109,917.58 | [5 empty] | NIL |  | ROMEK
| Diebu W12T Flowline Replacement -Additional Works. | New | Deferred. I. Engage C&P to advise and support strategy II. Align agreed strategy with NAPIMS and attach evidence to the resubmission. | Deferred | Azaka, G | O.NG.PBE.DBC.127.713FL |  | $ 49,232.78 N41,396,482.21 F$150,199.81 | [5 empty] | NIL |  | SCANTEX
| Yokri Cluster 51 Bulkline-2 JIV | New | Conditional Approval. Update and revert upon completion of the followings: I. Attach an approved e-WR or an email confirmation from Asset. II. Proper HSE & Marine team engagement and attach assurances provided to the resubmission. | Conditional Approval | Uwaezuoke, D | 113316 |  |  | $ 6,611.06 N 1,672,599.79 F$ 10,690.58 |  |  |  |  | NIL |  | HOECHY
| Tunu BQRT-3 Flowline Replacement (6" SCH 80 x 3.5km) -Downtime payment to Sevoil due to non-technical risks | New | Approved. Further supporting documentation was provided during WORP. Including notes on: I. PS team review of the additional downtime days II. AF team budget support / NAPIMS alignment discussions III. CP review / support. | Approved | Gilbert, O | C.NG.AFS.DL.22.013.1230 |  |  | $ 44,258.90 N 22,466,084.37 F$ 99,054.22 |  |  |  |  | NIL |  | A&N ENGINEERING
| Construction of EPU-2 Location Manifold. | New | Approved. I. Update QAQC value in the submission. II. Accelerate Project Schedule. | Approved | Ebirim, M | P.NG.PAE.DG.20.001.1230. |  |  |  |  | N331,579,033.1 + $621,626.98 (FUSD 1,430,356.33) |  |  | NIL |  | NUGI NIG
| Ogbotobo ANTM-1 Flowline Construction (4" SCH 60 x 2km)/Fabrication & Installation of Wellhead Platform | New | Approved. I. Update cost savings initiative with the value derived from houseboat resource sharing. II. Ensure proper kick-off meeting with adequate stakeholders’ participation. III. Upfront community engagement prior mobilization | Approved | Gilbert, O | C.NG.AFS.DL.22.012.1230 |  |  | $ 414,808.98 N 9,363,693.89 F$ 424,644.38 |  |  |  |  | NIL |  | Wilandson
| Ogbotobo AOTM-1 Flowline Construction (4" SCH 60 x 2km)/Fabrication & Installation of Wellhead Platform | New | Approved. I. Update cost savings initiative with the value derived from houseboat resource sharing II. Align total work scope with cost break down total and forward to the secretariat. III. Ensure proper kick-off meeting with adequate stakeholders’ participation. IV. Upfront community engagement prior mobilization | Approved | Azaka, G | C.NG.AFS.DL.22.010.1230 |  |  | $ 401,656.67 N 9,539,895.65 F$ 424,644.37 |  |  |  |  | NIL |  | B2 OIL AND GAS
| GENERAL |  | • Mandatory attendance of Project Leads or Team designate to support PE’s during team presentations at WORP • Always ensure proper resource alignment prior mobilization to site. • Update contractors work distribution tracker. • Hold a proper kick-off meeting with adequate stakeholders’ participation for all new mobilizations. • Activity owners to ensure proper alignment with all the appropriate support teams before WORP presentation. • Always attach an approved e-WR to submissions as applicable
2022-07-07 | Repair of Soku GP Condensate storage Tank (T5501) -Resubmission | Resubmission | Approved. WORP steers from previous sitting 16/06 have been fully implemented. I. Align total work scope with cost break down total and forward to the secretariat | Approved | Obiakor. O | C.NG.PBE.DF.19.091.1230 |  | $ 105,402.09 N 138,643,188.41 F$ 439,885.05 | [5 empty] | NIL |  | GRAMEN PETRO-SERV
| Kanbo W4 & W9 Flowline RoW JIV Asset Support | New | Conditional Approval. Update and revert upon completion of the followings: I. Carry out NAPIMS alignment and attach evidence of engagement. II. Ensure the use of EMR boat due to remoteness of location. | Conditional Approval | Gilbert, O | O.NG.PCW.TNF.FAC.71300. |  |  | $ 18,981.04 N 5,310,950.57 F$ 31,778.51 |  |  |  |  | NIL |  | HOECHY DEVELOPMENT
| Opukushi W7 Sectional Replacement – 4” Sch. 80 x 0.2km/Opukushi W38 Hook-up Arm Replacement Work | New | Conditional Approval. Update and revert upon completion of the followings: I. Update WBS for this activity. II. Carry out materials reconciliation with hotdesk and discount available stock. III. Update cost savings from mobilizing a single vendor. IV. Include painting in the project work scope. V. Carry out NAPIMS alignment and attach evidence of engagement. | Conditional Approval | Uwaezuoke, D | C.NG.PCW.DL.21.001.230 |  |  | $ 83,069.62 N 1,263,307.31 F$ 86,113.74 OPUKUSHI W38 $ 83,133.22 N 3,017,673.45 F$ 90,404.72 |  |  |  |  | NIL |  | EBITATOM GLOBAL
| Yokri Cluster 51 Bulkline-2 JIV -Resubmission & reviewed offline | Resubmission | Approved. WORP steers from previous sitting 30/06 have been fully implemented. | Approved | Uwaezuoke, D | 113316 |  |  | $ 6,611.06 N 1,672,599.79 F$ 10,690.58 |  |  |  |  | NIL |  | HOECHY DEVELOPMENT
| GENERAL |  | Forward list of community flowline contractors for upload into the contractor’s work distribution template.
2022-07-14 | DIEBU 9T HOOK-UP ARM MODIFICATION/ALIGNMENT | New | Conditional Approval. I. Carry out NAPIMS alignment and attach evidence of engagement. II. Update project schedule to current plan. III. Engage CH for an internal alignment | Conditional Approval | Uwaezuoke, D | O.NG.PBE.DBC.09T.713FL |  | $ 35,600.74 N 9,006,836.77 F$ 57,303.96 | [5 empty] | NIL |  | HOECHY
| ESCRAVOS IG TO IA + NGC IG TO IA PROJECT. | New | Deferred. I. Engage CH for an internal alignment on the execution strategy and seek NAPIMS support on agreed modality. | Deferred | Ehizoyanyam, O | C.NG.PBW.IM.17.002 |  |  | $: 295,852.40 N:103,928,649.66 F$ 546,354.93 |  |  |  |  | NIL |  | STEVE INTEGRATED
| REHABILITATION OF ZARAMA-OKORDIA-JK4 ACCESS ROAD | New | Stepped down by the team. | Stepped Down | Umoru, S
2022-07-21 | DIEBU 9T HOOK-UP ARM MODIFICATION / ALIGNMENT. | Resubmission | Approved. WORP steers from previous sitting 14/07 have been fully implemented. | Approved | Uwaezuoke, D | O.NG.PBE.DBC.09T.713FL |  | $ 35,600.74 N 9,006,836.77 F$ 57,303.96 | [5 empty] | NIL |  | HOECHY
| REPLACEMENT OTUMARA 39L GLL (4” X 1.8KM LINE | Resubmission | Approved. WORP steers from previous sitting 23/06 have been fully implemented. | Approved | Olusola, O | C.NG.AFS.DL.22.003.1230 |  |  | $ 274,187.24 N 6,992,549.81 F$ 291,036.76 |  |  |  |  | NIL |  | HABOUR OIL& GAS
| REPLACEMENT OTUMARA 35L GLL (4” X 2.0KM LINE) | Resubmission | Approved. WORP steers from previous sitting 23/06 have been fully implemented. | Approved | Obiakor, O | C.NG.AFS.DL.22.003.1230 |  |  | $ 288,427.78 N 7,314,141.89 F$ 306,052.22 | [6 empty] | JOLANDY’S
| DIEBU W12T FLOW LINE REPLACEMENT-ADDITIONAL WORKS | Resubmission | Approved. WORP steers from previous sitting 30/06 have been fully implemented. | Approved | Azaka, G | O.NG.PBE.DBC.12T.713FL |  | $ 68,304.78 N33,593,421.98 F$150,440.29 | [5 empty] | NIL |  | Gramen
| SOKU: REPAIR OF FAILED PIPE SUPPORTS AND LEAKING CONDENSATE LINE AT THE GAS PLANT. | New | Conditional Approval. I. Engage EST / QAQC to confirm that recommended actions for the failed pipe supports and leaking condensate line are adequate to forestall reoccurrence. | Conditional Approval | Obiakor, O | O.NG.PBE.SKG.FAC.724FC |  | $ 20,572.59 N 24,449.097.72 F$ 79,486.08 | [5 empty] | NIL |  | Gramen
| REHABILITATION OF ZARAMA-OKORDIA-JK4 ACCESS ROAD.- Resubmission & reviewed offline | Resubmission | Approved | Approved | Umoru, S | C.NG.PAE.IC.18.001. |  |  |  |  | N993,000,563.94 + $595,550.95 F$: 2,988,323.39 (N415/$) |  |  | NIL |  | CAINERGY
| KANBO W4 & W9 FLOWLINE ROW JIV ASSET SUPPORT. - Resubmission & reviewed offline | Resubmission | Approved. WORP steers from previous sitting 07/07 have been fully implemented. | Approved | Otavie, G | O.NG.PCW.TNF.FAC.71300. |  |  | $ 17,511.88 N 4,939,253.13 F$ 29,413.70 |  |  |  |  | NIL |  | KEMUD
| GENERAL |  | • Forward updated contractors work distribution template to the LT. • Engage CP to clarify rates for personnel carrier in stop-gap (community) contracts