## Slide 1
  Business Unit: Onshore Asset Brownfield Project (OABP)
  Project Sponsor: Olagunju, Toyin (GM COG Project & Engineering)
  Project Champion: Karunwi Adebayo (OABP Manager)
  Project Manager: Biakpara Allen
  Project Team: Ugbelase John, Anozie Okey, Uche Oraka ,Nwajei Mike
  Lean Coach: Lanre Ogunsakin Lanre & Ogofia Lasbery
PROJECT OWNERSHIP
There is an opportunity to reduce the current cycle time for the construction and handover of flowline works. This will ensure a reduction in the associated deferment and cost from the delayed flowline works, enable effective project delivery.
OPPORTUNITY STATEMENT
IN:
Improve Work efficiency
Effective project delivery
Focus delivery
Streamline work processes
Material & equipment availability
SCOPE
One of the key functions of the Onshore Asset Brownfield project team is to carry out construction, repairs and replacement (sectional replacement & leak repairs) of flowlines, and well hook-up works for the different Production Asset teams (Land east, Central East & Swamp West).
Presently it takes an average time of 14/21 days (Land and Swamp respectively) for the flowline contractors to complete one (1km) kilometre of flowline construction/repair and handover work activities after being mobilised to site.
BUSINESS CASE
The plan is to look at different means of reducing both land and swamp flowline construction & handover works to 11/17 days per km respectively for flowlines of length less than 3km. And for lines that are 3km and above, the plan is to use different execution strategy of deployment of 2 or more spreads.
GOAL
  Production Outage
  Poor quality delivery
  Poor project management principle
  Materials & equipment availability
POTENTIAL ROADBLOCKS/ ISSUES
OUT:
Personnel In-efficiency
Unreliability
Bad work ethics
Contractor incompetence
PROJECT CHARTER: FLOWLINE CONSTRUCTION & REPAIRS WORK EXECUTION PROCESS - REDUCTION IN THE CYCLE TIME
  Reduced project cycle time by 20% (3/4) days
  On schedule (time) delivery: avoid cost escalation).
  Improved Productivity (Early production delivery)
  Quality delivery (Zero failure after handover)
BENEFITS
PROJECT STATUS
G
Y
R
On Track
Delayed
Stopped
0%
0%
100%
Health
% Compl
Completion Date
Start Date
11/11/19 29/04/20
07/10/19 11/11/19
30/04/20 31/05/20
Overall % Compl
0%
IDENTIFY
IMPROVE
SUSTAIN
0%
01/06/20 30/06/20
CLOSE
  Contractor corporation
  Fire incident
  Security incidents
  Community