## Slide 1: Riskpoynt deployment to Gbaran/Soku
SCOPE
In-Scope: Deploy Riskpoynt for Gbaran/Soku Technical Activities on a separate instance for SPDC on a locally hosted Cloud Provide training and reference materials to end-users Fulfil all compliance requirements (IRM and Supportability) User Acceptance Tests and sign-off Transition to operate phase Out of scope Non-Technical risks are not in scope for the deployment Other SPDC Assets
DELIVERABLES
Approved business requirements & acceptance criteria Functional and stable implementation of Riskpoynt for Gbaran/Soku Operations Train identified Gbaran/Soku Business users to be competent in usage of solution Mandatory PDF deliverables
PROJECT COSTS
BACKGROUND
Cumulative Risk Visualisation (CRV) is a methodology that permits visualisation of all major safety risks to enable decision making for better asset management. This provides detailed visualisation of HSE risk areas which is achieved through real-time visualization of asset health for effective management of operational risks. CRV removes manual efforts by providing an integrated platform to interface with other applications such as Facility Status Reporting (FSR) and SAP for SAP PM, CM and Notifications. Riskpoynt is an approved group solution for Cumulative Risk Management for Production / Distribution Assets and a compliance tool for AMS MEC standard requirement. It has been in use in Nigeria since 2020 when it was first deployed to Bonga. The Gbaran/Soku is the 4th deployment of Riskpoynt in Nigeria
OBJECTIVES
Provide an automated solution which provides real-time cumulative risk visualization
HIGH LEVEL RISKS & ASSUMPTIONS
The following are identified risks: Delays resulting from infrastructure availability Unavailability of Business resources throughout project delivery and and delays from conflicting resource priorities The following are assumptions made: Existing Riskpoynt FSR and SAP interfaces will be integrated seamlessly No additional integrations are in scope
KEY ACTIVITIES/TIMELINE
Signoff Charter & Project Kickoff Dec-2022 Resource Plan & Assignments Dec-2022 Complete Initiation & Business Requirement Jan-2022 Complete Planning/FID Feb-2023 Setup & Configure Riskpoynt Mar-2023 Training & UAT Apr-2023 Complete Go Live/AtD Apr-2023 Complete Hypercare/AtO May-2023 Closeout May-2023
TEAM/STAKEHOLDERS
Steering Committee: Trost Amos (Business Sponsor); Kebin Ofori & IDT Portfolio Mgr, SEAD Project Team: Ogbodu Oghenerume – Product owner Muktar Sani- Business SME Durodola Oba – Business SME Hanson Eno– Business SME (HSSE) Taylor-Harry Tamunoemi - Business SME Anban Sunderson – Global BA Toyin Ariyo – Nigeria Support Analyst Lapo Faturoti, Lokesh Venkata, Nnamdi Egeolu – SAP SMEs Ajay Karna – FSR SME Opeyemi Ladeji – Project Manager Ogbole Oghedegbe – Program Mgr
DEPENDENCIES
Availability of Human resources (Business) to deliver on project requirements (provide data and participate in testing) Budget is available as per issued CTR
SN | Activity Detail | Cost ($)
1 | Subscription | 30,000
2 | Deployment of existing integrations | 7,200
3 | Additional Instance hosting cost | 5,000
4 | Software hosting services | 2,000
5 | Project Resources | 25,800
 | TOTAL | 70,000
Demand: DMND0028003
Project: PRJ2735524
BENEFITS
L3: Improve visibility for the Gbaran/Soku Asset leadership near to Real-Time Cumulative Risk representation across its assets
L3: Facilitate management decision to deviate or extend the target due date for any of the process safety action item after taking the cumulative risk into consideration.
L1: Potential cost avoidance of USD 1M resulting from facility trips L3: Allows effective and better-informed decision making for:
  Deviation and deferral management
  Maintenance work prioritization
  Override implementation
  Mitigation measures
L2: Efficiency gains of USD237k resulting from the reduction in time to generate cumulative risks reports.
L3: Improved process safety performance
**Costs will be reconfirmed before end of SG2
Notes: MTO – Manage Threats and Opportunities
FSR - Facility Status Reporting (Production Portfolio)
WRFM – Wells, Reservoirs and Facility Management
MRTA – Maintenance, Reliability, and Turnarounds
FCF – Free Cash Flow
IVD – Integrated Value Delivery
EC – Energy Components
PU – Production Unit
MEC – Manage Equipment Care
KPI – Key Performance Indicators