## Slide 1
Project Title: OPERATIONALIZING ONLINE VESSEL DE-SANDING IN SOUTH BANK FACILITIES
Business Case/objectives:
  As facilities produce oil & gas, sand builds up in the vessels resulting in erosion, wall thickness loss and wear leading to pump and equipment damage. This results in facilities’ ullage reduction, lower availability and unscheduled deferments.
  To mitigate this, scheduled vessel de-sanding PMs are done, Requiring 2 days (conservative estimate) facility Shutdown/TA in 2021. This results in a conservative production deferment of circa 20,100 bbls for Southbank facility (using 2days)
  This document outlines the merits, scope and plan for implementing a new online de-sanding technology in Southbank that has huge cost saving potential and positive impact on goal zero.
Objective:
Project Scope/Actions (With start and end dates and action party) :
Action Party: Abiye Opubo
Develop project plan
  Draft Logistics Plan 10/04/21
  Draft detailed work plan 10/04/21
  Finalize work preparation 12/04/21
  Vendor Site mobilization 17/04/21
  Execute Online de-sanding 19/04/21
  Demobilize from site 29/04/21
  Project Sponsor:
  Van den Hemel, Paul
  Maichibi, Meshach C
  Implementation Lead: Afode, Aford
  Project Team:
  Akaka, Alphonsus; Opubo, Tamunobarabiye; Uduanochie, Adanma; Olasubulumi, Akintunde; Busari, Abiodun; Chiroma, Barka; Wya, Daniel, Otumara Asset Team.
Input High-level Timeline:
L2: Impacts fully identified and FCF calculated
Critical Success Factors
  Secure Contract
  Logistic Plan
  Goal Zero
Potential Benefits & Measurement:
Compliance with regulatory requirement of no vessel entry
Save circa 20,100 bbl. across Southbank facility.
Potential savings of circa $703,500/year. (@$35/bbl)
Cost for Online de-sanding is circa $ 180, 000 for
Free cash flow is circa $523,500
Charter Template