## PSO East Asset_2023_Oil Well
S/N | Activity Type | CATEGORY: OPTZ or DEF or LIP | Subsurface Node | Choke (Well ID/Manifold/ Equipment/ facility) | Description | Estimated Gains | Current Rate (Bopd) | New Test Rate | WRFM Actual Gains (Bopd) | Remarks/ Update | Objective | Action Parties | Target Date | Date Achieved | Status | 2023-10-16
1 | PSO | OPTZ | GBAR/KC | GBAR Node 27 IPSC Oil Wells | Test to determine flash production gains from 27 Conduits, Current TAR to Last test rates variance is ~2.700 bopd | 2700 | 20890 |  |  | KCTL/ TNP Availability has been erratic for reliable Test results. Focused plan available to commence testing upon PL availability | 1. To determine flash production from wells due to prolonged well closure 2. Upside to be collated for TAR upward review 3. Stabilized Test rates to be used for Bean up opportunity reviews | PT/Programmer/Prod Ops | 2023-05-31 |  | Pending
2 | PSO | OPTZ | GBAR/KC | ETEL012T | Bean up well from 28/64” to 32/64“. | 379 | 1125.3706 |  |  | Test well on bean 32/64". Take wellhead samples for watercut and sandcut analysis. | Increase net Oil Rates | PT/Programmer/Prod Ops | 2023-05-31 |  | Pending
3 | PSO | OPTZ | GBAR/KC | GBAR009T | Bean-up Opportunities. (Constrained by TAR) | TBA | 402.8778 |  |  | Carry-out MER test. Request for upward review of NUPRC TAR. Implement bean-up opportunity, as advised by PT. | Increase net Oil Rates | PT/Programmer/Prod Ops | 2023-05-31 |  | Pending
4 | PSO | OPTZ | GBAR/KC | GBAR023T | Bean-up Opportunities. (Constrained by TAR) | TBA | 738.0599 |  |  | Carry-out MER test. Request for upward review of NUPRC TAR. Implement bean-up opportunity, as advised by PT. | Increase net Oil Rates | PT/Programmer/Prod Ops | 2023-05-31 |  | Pending
5 | PSO | OPTZ | GBAR/KC | GBAR008T | Well was beaned-up to 26/64“, | 86 | 140.9248 |  |  | Test well on routine bean 26/64". Take wellhead samples for watercut and sandcut analysis. | Increase net Oil Rates | PT/Programmer/Prod Ops | 2023-05-31 |  | Pending
6 | PSO | OPTZ | GBAR/KC | GBAR019T | Bean up well from 24/64” to 28/64“. | 127 | 810.0153 |  |  | Test well on bean 28/64". Take wellhead samples for watercut and sandcut analysis. | Increase net Oil Rates | PT/Programmer/Prod Ops | 2023-05-31 |  | Pending
7 | PSO | OPTZ | GBAR/KC | KOCR020T | Bean-up Opportunities. (Constrained by TAR) | TBA | 682.966 |  |  | Carry-out MER test. Request for upward review of NUPRC TAR. Implement bean-up opportunity, as advised by PT. | Increase net Oil Rates | PT/Programmer/Prod Ops | 2023-05-31 |  | Pending
8 | PSO | OPTZ | GBAR/KC | KOCR025T | Bean up well from 24/64” to 28/64“. | 172 | 292.5698 |  |  | Test well on bean 28/64". Take wellhead samples for watercut and sandcut analysis. | Increase net Oil Rates | PT/Programmer/Prod Ops | 2023-05-31 |  | Pending
9 | PSO | OPTZ | GBAR/KC | ZARA012S | Bean up well from 44/64” to 48/64“. Test well on bean 32/64". Take wellhead samples for watercut and sandcut analysis. | 285 | 1071.7158 |  |  | Bean up well from 44/64” to 48/64“. Test well on bean 32/64". Take wellhead samples for watercut and sandcut analysis. | Increase net Oil Rates | PT/Programmer/Prod Ops | 2023-07-31 |  | Pending
10 | WELL REST | Deferment | GBAR/KC | ETEL 1S, 7L/S | Fix Etel FS Flare Line | 517 | 517 |  |  | Restore IPSC | Restore IPSC Oil rates | PUM/OTL | 2023-07-31 |  | Pending
11 | WELL REST | Deferment | GBAR/KC | ETEL011T | Review Well Annulus A Issues Causing ELC | 828 | 828 |  |  | Restore IPSC, CM carried out on well. Awaiting Bulk line repairs | Restore IPSC Oil rates | PT/Programmer/Prod Ops | 2023-07-31 | 2023-09-01 | Closed
12 | WELL REST | Deferment | GBAR/KC | ETEL012T | Restore ETEL 12T Well Head control unit. CCU stolen. Consider use of Modified Com Unit less attractive to Vandals | 1125 | 1125 |  |  | Restore IPSC. CCU vaialable. To be instaled Post Bulk line Repairs | Restore IPSC Oil rates | Prod Ops/ programmer | 2023-07-31 |  | Pending
13 | PSO | Deferment | GBAR/KC | ETEL013T | Well not producing. Carry out Joint RCA and troubleshoot to flow well | 598 | 598 |  |  | Restore IPSC. On hold till after bulk line repairs | Restore IPSC Oil rates | PT/Programmer/Prod Ops | 2023-07-31 |  | Pending
14 | WELL REST | Deferment | GBAR/KC | GBAR 4T and 9T | Clear refuse dump and flow well upon KCTL availability. Requires ER support | 984 | 984 |  |  | Q2 2023 PSO | Restore IPSC Oil rates | PUM/OTL | 2023-07-31 |  | Pending
15 | WELL REST | Deferment | GBAR/KC | GBAR008T | Repair Vandalised flow line | 141 | 141 |  |  | Q2 2023 PSO | Restore IPSC Oil rates | Prod Ops/OABP | 2023-07-31 |  | Pending
16 | PSO | OPTZ | GBAR/KC | KOCR003T | Assess opportunity to flow well on Test header to avoid bulking effect preventing well from flowing | 301 | 301 |  |  | Q2 2023 PSO | Restore IPSC Oil rates | PT/Programmer/Prod Ops | 2023-07-31 |  | Pending
17 | WELL REST | LiP | SOKU/NUNR | ADIB001L | Revisit Well upon Diesel Soak and restore production post Previously failed STOG on WAX cutting. | 290 | 0 |  |  | Well opened Up and flowing. Awaitng Well Test/ MRT and Sampling for Validation | Restore IPSC Oil rates | Prod Ops/ Programmer/PT |  |  | Pending
18 | WELL REST | LiP | SOKU/NUNR | ADNE001L | Well and Flowline Restoration | 1683 | 0 |  |  | Well opened Up and flowing. Awaitng Well Test/ MRT and Sampling for Validation | Restore IPSC Oil rates | Prod Ops/OABP/CWI |  |  | Pending
19 | WELL REST | LiP | SOKU/NUNR | ADNE004L | Well and Flowline Restoration | 1350 | 0 |  |  | Well opened Up and flowing. Awaitng Well Test/ MRT and Sampling for Validation | Restore IPSC Oil rates | Prod Ops/OABP/CWI |  |  | Pending
20 | WELL REST | Deferment | GBAR/KC | ETEL HP Bulked Wells | Flowline/Bulk line Restoration | 4800 | 0 |  |  | OABP Bulk line repairs Schedule Awaited | Restore IPSC Oil rates | Prod Ops/OABP | 2023-10-01 |  | Pending
21
Total | [5 empty] | 16366 | 30648.5001 | 0 | 30648.5001 | [5 empty] | 20

## PSO East Asset_2023_Gas Well
S/N | Activity Type | CATEGORY: OPTZ or DEF or LIP | Subsurface Node | Choke (Well ID/Manifold/ Equipment/ facility) | Description | Estimated Gains (mmscfd) | Current Rate (mmscfd) | New Test Rate | WRFM Actual Gains (MMscfd) | Remarks | Objective | Action Parties | Target Date | Date Achieved | Status
1 | PSO | Deferment | GBAR/KC | GBAR013T | Attempt to “rock” well back to production, pending TNP availability. Carry-out nitrogen lift, if required. | 17 | 22 |  |  | Attempted to rock but action placed on hold due to TNP unavailability | Restore IPSC | Prod Ops/ PT/CWI | 2023-07-31 |  | Pending
2 | PSO | Deferment | GBAR/KC | GBAR025T | Attempt to “rock” well back to production, pending TNP availability. Carry-out nitrogen lift, if required. | 25 | 25 |  |  | Attempted to rock but action placed on hold due to TNP unavailability | Restore IPSC | Prod Ops/ PT/CWI | 2023-07-31 |  | Pending
3 | WELL REST | LiP | GBAR/KC | KOMA002T | Attempt to “rock” well back to production, pending TNP availability. Carry-out nitrogen lift, if required. | 25 |  |  |  | Rocking attempted between Q3 2022 and Q2 2023 without success. Wells moved to LIP awaiting GNC project | Grow IPSC | Prod Ops/ PT/CWI | 2023-07-31 |  | Pending
4 | WELL REST | LiP | GBAR/KC | KOMA005T | Attempt to “rock” well back to production, pending TNP availability. Carry-out nitrogen lift, if required. | 22 |  |  |  | Rocking attempted between Q3 2022 and Q2 2023 without success. Wells moved to LIP awaiting GNC project | Grow IPSC | Prod Ops/ PT/CWI | 2023-07-31 |  | Pending
5 | WELL REST | LiP | GBAR/KC | KOMA008T | Attempt to “rock” well back to production, pending TNP availability. Carry-out nitrogen lift, if required. | 30 |  |  |  | Rocking attempted between Q3 2022 and Q2 2023 without success. Wells moved to LIP awaiting GNC project | Grow IPSC | Prod Ops/ PT/CWI | 2023-07-31 |  | Pending
6 | WELL REST | LiP | GBAR/KC | KOMA011T | Attempt to “rock” well back to production, pending TNP availability. Carry-out nitrogen lift, if required. | 52 |  |  |  | Rocking attempted between Q3 2022 and Q2 2023 without success. Wells moved to LIP awaiting GNC project | Grow IPSC | Prod Ops/ PT/CWI | 2023-07-31 |  | Pending
7 | WELL REST | Deferment | GBAR/KC | GBAR028T | Choke Upgrade and open well to production | 20 | 50 | 60 | 10 | Programmer to provide the volumes pre/post execution. Choke upgrade completed, well opened up to production but no gain recorded. Expected to achieve additional 20MMscf, but no gains. | Achieve Drilling premise of 70 mmscfd by debottlenecking contrained HIC choke installed and installing a larger Cv choke | Prod Ops/ Asset Engineering | 2023-04-30 | 2023-04-01 | Pending
8 | WELL REST | LiP | SOKU/NUNR | SOKU046T | To Rock well to production | 50 | 40 | 40 | 40 | Activity completed. Programmer Validated | Restore IPSC | Prod Ops/PT/Programmer | 2023-04-30 |  | Closed
9 | WELL REST | Deferment | GBAR/KC | EPU 3T and 4T | Fix vandalized Bulk Flow line | 110 | 110 | 110 | 110 | Vandalized bulk line on 6 June requiring sectional repairs to restore def production | Restore IPSC | Asset Engr/Prod Ops | 2023-07-31 |  | Pending
10 | WELL REST | Deferment | GBAR/KC | GBAR015T | Retrieve NRV and restore well back to production. Carry-out “poor-boy” MRT. | 12 | 22 |  |  | NRV retrieved, Well head accessories installed and well opened up. | Grow IPSC | Prod Ops/ PT/CWI | 2023-07-31 |  | Pending
11 | WELL REST | Deferment | SOKU/NUNR | SOKU038T | Opportunistic surveillance to rock in well which will avoid the STGG planned wireline intervention | 50 | 38 | 38 | 38 | Activity completed. Programmer to validate volumes | Grow IPSC | Prod Ops/PT/Programmer | 2023-04-30 |  | Closed
12 | PSO | LiP | SOKU/NUNR | SOKU039T and Degradation Charges | Manage NLNG Condensate degradation claims to avoid $18.5M Charge Payment in 2023 and flow Soku 39T | 23 | 0 |  |  | Review and progress options from 2018 EPST study. Chemical and or Process equipment solutions. | Manage NLNG Condensate degradation claims to avoid $18.5M Charge Payment in 2023 and flow Soku 39T | Process/ Prod Chemistry | 2023-08-31 |  | Pending
13 | PSO | OPTZ | SOKU/NUNR | SOKU045T | Sidetrack to D5000X reservoir | [5 empty] | Prod.Tech/Sub-surface team. Opportunity to use existing well for a sidetrack targeting attic volume in D5000X reservoir. | Prod Ops/ PT/CWI | 2023-08-31 |  | Pending
14 | PSO | OPTZ | SOKU/NUNR | SOKU053T | Cyclic production evaluation |  |  |  |  | PBU Surveillance ongoing | Operations to monitor CITHP and open well to the minimum static pressure | Prod Ops/PT/Programmer | 2023-08-31 |  | Pending
15 | PSO | OPTZ | SOKU/NUNR | Soku Wells Creaming post Soku 17 Stimulation | With NCTL unavailable, Optimise gas production with a water disposal constraint of 5kbwpd | 120 | 120 | 100 | 100 | PT & Operations Team. Opportunity is to use the IPSM to determine optimized dry gas contributors and rates with max of 5kbwpd disposal into SOKU017T and condensate spiking into EGGS | Soku Wells Creaming Post Water disposal Well Soku 17 Stimulation | Prod Ops/ PT/CWI | 2023-08-31 |  | Closed
16 | PSO | OPTZ | SOKU/NUNR | SOKU042T | Resolve well integrity issues and Flow well to minimum static pressure | 50 |  |  |  |  | CWI to restore well integrity and Operations to monitor CITHP and open well to the minimum static pressure. Operations to test the well to determine the liquid flow parameters and condensate quality. | Prod Ops/ PT/CWI | 2023-08-31 |  | Pending
17 | FACILITY OPTZ | OPTZ | GBAR/KC | K2S: KOCR43, 44, 45, 47, 48, 49 | Debottleneck K2S Export from 400 to 500 mmscfd | 100 | 400 | 500 | 100 | Safely Achieved KOCR to SOKU flow to 500mmscfd | Grow IPSC | Process/ Prod Ops/ Prog/PT | 2023-09-01 | 2023-09-30 | Closed
18 | FACILITY OPTZ | OPTZ | GBAR/KC | K2G: KOCR43, 44, 45, 47, 48, 48 + 39,40 | K2G Optimization: Optimize K2S split flow between SOKU and GBARAN to achieve net gain Performance above only KOCR39+40 to GBAR | 90 | 50 |  |  | Manual Force flow with MoC to achieve Split flow and additional net flow from K2S to GBAR ongoing. Successfully commisioned the Split flow with the PCV on auto, however, Alarm settings change required to operate before high pressure alarms | Split flow commisioned in Oct 2022 but did not achieve more than Net gain of 10 mmmscfd due to insufficient K2S flow and press because of Soku Couldn't demand for more K2S on Liq Evac constraints. Solution was implemented to use a manual valve to force flow to GBAR and achieve net gain of ~70mmscfd of K2S and KOCR39/41 | Process/ Prod Ops/ Prog/PT | TBA | TBA | Pending
19 | PSO | OPTZ | GBAR/KC | K2S & Soku NAG Available Wells | Restore Moisture Content of Condensate Spiked to NLNG from Soku GP Tank to within Specification due to increased withdrawal rate and reduced residence time post S2SB ramp up. |  |  |  |  | 3 Prong Approach applied: 1. Chemical Demulsifier Optimization (Type and class) 2. Well Combination and Creaming 3. Stagger Tank offtake Schedule between Spiking and S2SB. Spike at Night and S2SB day time. (Achieved positive results) | Restore Moisture Content of Condensate Spiked. Maintain IPSC | Prod Ops/ Prod Chem/ Prog/PMC | 2023-09-01 | 2023-10-01 | Closed
20 | WELL REST | Deferment | GBAR/KC | ENWHE 7.8.9 | Restoration of Vandalised Bulk line | 170 | 0 | 166 | 166 | Repaired and restored bulk line | Restore IPSC | OABP/ Prod OPs/ NLNG Proj | 2023-02-01 | 2023-03-01 | Closed
21 | WELL REST | Deferment | GBAR/KC | EPU 3,4 | Restoration of Vandalised Bulk line | 110 | 0 | 110 | 110 | Repaired and restored bulk line | Restore IPSC | OABP/ Prod OPs/ NLNG Proj | 2023-05-01 | 2023-07-01 | Closed
22 | WELL OPTZ | OPTZ | GBAR/KC | Zar010T | Well Performance Declined despite Low EGGS back press. Carry out RCA. Acquire FBHP data and troubleshoot cause of decline and restore well performance | 23 | 8 |  |  | Ops completed surface surveillance without findings, Smartfield to download FBHP data and share with PT to Model Performance | Restore IPSC | PT/Prod Ops/ prog/ Smartfield | 2023-10-01 |  | Pending
Total | [5 empty] | 1099 | 885 | 1124 | 674 | [5 empty] | 22

## Drop Downs
Activity Type | Category | Subsurface Node | Deferment | Deferment | GBAR/KC
FACILITY OPTZ | Deferment | EA/OTUM | LiP | Deferment | GBAR/KC
PSO | LiP | FORC | 0 | Deferment | GBAR/KC
WELL OPTZ | OPTZ | GBAR/KC |  | Deferment | GBAR/KC
WELL REST |  | SOKU/NUNR |  | Deferment | GBAR/KC
|  | SSW |  | Deferment | GBAR/KC
|  |  |  | Deferment | GBAR/KC
|  |  |  | Deferment | GBAR/KC
|  |  |  | LiP | GBAR/KC
|  |  |  | LiP | SOKU/NUNR
|  |  |  | LiP | SOKU/NUNR
|  |  |  | LiP | EA/OTUM
|  |  |  | LiP | EA/OTUM
|  |  |  | Deferment | EA/OTUM
|  |  |  | Deferment | EA/OTUM
|  |  |  | LiP | EA/OTUM
|  |  |  | LiP | EA/OTUM
|  |  |  | LiP | EA/OTUM
|  |  |  | LiP | EA/OTUM
|  |  |  | LiP | EA/OTUM
|  |  |  | LiP | EA/OTUM
|  |  |  | LiP | EA/OTUM
|  |  |  | Deferment | EA/OTUM
|  |  |  | LiP | EA/OTUM
|  |  |  | LiP | FORC
|  |  |  | Deferment | FORC
|  |  |  | Deferment | FORC
|  |  |  | LiP | FORC
|  |  |  | LiP | FORC
|  |  |  | LiP | FORC
|  |  |  | LiP | SSW
|  |  |  | LiP | SSW
|  |  |  | Deferment | SSW
|  |  |  | Deferment | SSW
|  |  |  | LiP | SSW
|  |  |  | LiP | SSW
|  |  |  | LiP | SSW
|  |  |  | LiP | SSW
|  |  |  | LiP | SSW
|  |  |  | LiP | SSW
|  |  |  | Deferment | SSW
|  |  |  | Deferment | SSW
|  |  |  | Deferment | SSW
|  |  |  | Deferment | SSW
|  |  |  | Deferment | SSW
|  |  |  | Deferment | SSW