## Summary
| F $ | %
Total Capex Budget | 40217219 | 100% | After discounting the 2019 POs
Loaded Budget | 38036007 | 94.58%
- Dropped activities | 10810640 | 26.88% | 7543501 | 18.76%
- Ongoing activities | 17379815 | 43.21% | 17379815 | 43.21%
- Planned activities | 15113224 | 37.58% | 15113224 | 37.58%
Total |  | 107.7% |  | 99.55%
Emergent activities | 1647945
AGG | 1047945
Execution - Central | 600000
From 2019 Pos | 3267139

## MRTA CAPEX 2020 BUDGET
MRTA 2020 CAPEX BUDGET TRACKER
HUB | PROJECT DESCRIPTION | SAP COST OBJECT | SAP COST OBJECT DESCRIPTION | APPROVED OP19 F$ | OP19 F$ Loaded in SAP | Actual F$ | SAP Commit. F$ | RemOrdplan F$ | Balance | COMMENTS | STATUS | Estimated Cost | CONTRACT DETAILS | Approved in OP19? | Volume at risk | Criticality | Priority
EXECUTION (WEST) | 1) Procurement of spares for Crude evacuation/export pump (driver) major overhaul for 4 pumps @ $220k each. | C.NG.PBW.DF.20.052 | WS1 Crude Oil evacuation Pumps major ov | 880000 | 880000 | 112741.14 | 46891 | 467534 | 252833.86 | 1) Procurement of spares for Crude evacuation/export pump (driver) major overhaul for 3 pumps @ $660k Overhaul of spares of Pump Opukushi pump (after further optimisation) = $150k | 1. (4510430854; 4510434557; 4510435153; 4710142583; 4710142584; 4710143116; 4710143117) created for major overhaul spares of 2nos crude export - (4710143878; 4710143878;)- Sulzer pump set rebuild for Tunu pump 2 & 4510431745 - Spares for OH Opukushi pump 9 - $524k 2. 4510398182; 4710136651, 4510404868 &4510401602 - $112k OH spares delivered 3. Plan for Bal spares awaits backload of pumps to Workshop | 150000 | To place order for overhaul spares through SPDC Procurement Team; The Overhaul to be carried out by SPDC workshop | Yes | 250kbopd | Production Critical | P1 | Issue PO to vendor asap by 31st July $70K to be returned
| 1) Procurement of 1Nos Instrument Air Compressor F$198k 2) Installation and commissioning F$50k 3) Transportation of 1Nos Instrument Air Compressor | C.NG.PCW.DG.20.061 | UPGRADE OF INSTRUMENT AIR COMPRESSOR (IAC) PACKAGE AT FOT | 248000 | 248000 | 84076.96 | 0 | 0 | 163923.04 | PR 10688170 MoC number 71530 220k 1) Procurement and installation of 1Nos Instrument Air Compressor | PO awaits completion of enquiry | 220000 | To place order for overhaul spares through SPDC Procurement Team; The Overhaul to be carried out by SPDC workshop | Yes | 250kbopd | Production Critical | P1 | Issue PO asap before 31st July
| This is a phased approach to Revamp 20nos CPI & 5nos IGF units for produced water treatment in FOT. 1) Purchase of spares and rehabilitation of 1nos induced gas floatation (IGF) @ F$124K 2) Purchase of spares and rehabilitation of 2nos CPI units @ F$276K | C.NG.PTW.DF.20.007 | REVAMP OF CPI AND IGF UNITS | 400000 | 400000 | 1501 | 0 |  | 398499 | 4510404096 (3nos propak internal X731 worth 306k in total). About 76k is required for propak installation. 1) Purchase of spares and rehabilitation of 1nos induced gas floatation (IGF) @ F$76K | PO awaits completion of enquiry | 400000 | Place order for Rurbishment materials through procurement process. Refurbishment to be executed with service contract | Yes | 100kbopd | Production Critical | P2 | Materials ordered and ariving soon. $76K is for installation and additional $72K needed for corrective works on the IGF. Issue PO before 31st July.
| 1) Replacement of WDP House 8ton Gantry Crane 1 @ F$87.17K 2) Replacement Power House 10ton Gantry Crane 1 @ F$109.6K 3) CLP 12ton Gantry Crane 1 @ F$124.04K 4) Procurement of1No. 15Ton x 60ft Manlift = F$92.83k 5) Procurement of 5Nos. Sanitary Lift Pumps = F$18.95k 6) Procurement of 2Nos. Arc Welding Machines = F$4.75k | C.NG.PTW.DF.20.012 | PROCUREMENT AND REVAMP OF WORKSHOP MACHINERY | 240000 | 240000 | 445774 | 165268 | 13224 | -384266 | 4510435625 for 7nos Sanitary lift pumps worth $32k. Budget realignment is required from WBS O.NG.PTW.IFU.FAC.724FP. Awaiting release of PR 10685119 (Procurement of 2Nos Arc Welding Machine at $3.4k) 1) Replacement of WDP House 8ton Gantry Crane 1 @ F$116K 2) Replacement Power House 10ton Gantry Crane 1 @ F$109.6K 3) CLP 12ton Gantry Crane 1 @ F$124.04K 4) Procurement of1No. 15Ton x 60ft Manlift = F$92.83k 5) Procurement of 5Nos. Sanitary Lift Pumps = F$18.95k 6) Procurement of 2Nos. Arc Welding Machines = F$4.75k Completed the delivery of Ordered workshop equipment in 2019 (PO 4510422529 TANK-TOTE-SPEDFLO-SS-316-TT-1000 l & PO 4510419145 BEARINGKIT_PUMP_INJECTION - $218K. Resulting in Budget overrun of S384k | PO awaits the completion of enquiry (PR 10684101 ) LEC May Regret; Power House Crane - 109k Manlift - 92k Sanitary Lift Pump - 18k | 240000 | To place order for the items through SPDC procurement process. Installation to be carried out DIY | Yes |  | Safety Critical | P2 | 1) Replacement of WDP House 8ton Gantry Crane 1 @ F$116K - Dropped 3) CLP 12ton Gantry Crane 1 @ F$124.04K - Dropped 6) Procurement of 2Nos. Arc Welding Machines = F$4.75k - Issue PO before 31st July.
| Procurement and installation of 2 Nos Fire Jockey Pumps = F$289.78K | C.NG.PTW.DF.20.011 | FOT CRUDE OIL PUMPS OVERHAUL | 289800 | 289800 | 0 | 0 | 0 | 289800 | Awaiting CC approval from last week's West CLP session. Procurement and installation of 2 Nos Fire Jockey Pumps = F$289.78K | Procurement deferred till 2021 | 289780 | Place order for the pumps through SPDC procurement team | Yes |  | Safety Critical | P1 | Dropped but issue PO with notional budget
| Procurement of 3nos. portable fire pumps @ F$21,394.80 each | C.NG.PTW.DF.20.002 | PROCUREMENT OF 3 PROTABLE FIRE PUMPS FOR FOT | 21000 | 21000 | 0 | 0 | 0 | 21000 | 2 nos portable fire pump ordered on previous line. Will be reallocated Procurement of 3nos. portable fire pumps @ F$7,131.60 Procurement of 2 nos. portable fire pumps @ F$14,263.2 each | PO awaits the completion of enquiry LEC May Procurement of 2 nos. portable fire pumps deferred till 2021 | 21000 | Place order for the pumps through SPDC procurement team | Yes |  | Safety Critical | P1 | PO issued for 2 portable fire pumps, confirm EDD
| Phase II of Upgrade of currently installed aqua-cell system and Sewage Treatment Plant. 1) Propagation and bombardment of the macropytes -220K 2) Inoculation of bioagents - 71.5K 3) Rapid sand filter - 242K 4) Equipment for site laboratory - 170.5K 5) Phase III of Upgrade of currently installed aqua-cell system and Sewage Treatment Plant. 6) Anti-Corrosion and Bitumen coating - 71.5K 7) Civil Construction - $2.22m | C.NG.PTW.DF.18.013 | UPGRADE OF SEWAGE TREATMENT FACILITIES AT FOT | 1200000 | 1200000 | 0 |  |  | 1200000 | Phase II of Upgrade of currently installed aqua-cell system and Sewage Treatment Plant. 1) Propagation and bombardment of the macropytes -220K 2) Inoculation of bioagents - 71.5K 3) Rapid sand filter - 242K 4) Equipment for site laboratory - 170.5K 5) Phase III of Upgrade of currently installed aqua-cell system and Sewage Treatment Plant. - 125k 6) Anti-Corrosion and Bitumen coating - 71.5K 7) Civil Construction - $2.22m but only 0.3m was approved in OP19. Civil construction partial scope of $0.3m to be deferement to 2021 | * Upon review of these activities in the Forcados Terminal, cost deferment of $0.3 Million can be achieved by partial scope deferment. | 0 | Scope to be executed via CW200124 - PHASE 1 UPGRADE OF THE FORCADOS TERMINAL | Yes |  | Safety Critical | P2 | Deffered to next year. Move to Eng
| 1) Installation of 1nos fume hood for the Organic Chloride equipment - $20k. 2) Procurement and installation of Agilent gas Chromatograph for fluid fingerprint analysis - F$120k 3) Procurement of Spectro Xepos, Pamas S40 and accessories for lube oil and fuel oil analysis equipment- $193k. 4) Procurement of Jiskoot Lab Mixer, Orbital Shaker, Hot bath and other accessories for sample preparation - F$31.4k 5) Purchase Filter Blocking Tendency tester, Coulometer, Water distiller, Colorimeter, flashpoint tester and OptiDist -$105.8k | C.NG.PTW.DF.20.015 | UPGRADE OF FOT LABORATORY | 448000 | 448000 | 0 |  | 0 | 448000 | Awaiting BFM approval 1) Procurement and installation of Agilent gas Chromatograph for fluid fingerprint analysis - F$120k 2) Purchase Filter Blocking Tendency tester, Coulometer, Water distiller, Colorimeter, flashpoint tester and OptiDist -$105.8k 3) Procurement of Spectro Xepos, Pamas S40 and accessories for lube oil and fuel oil analysis equipment- $193k. 4) Procurement of Jiskoot Lab Mixer, Orbital Shaker, Hot bath and other accessories for sample preparation - F$31.4k 5) Installation of 1nos fume hood for the Organic Chloride equipment - $20k. | * Upon review of these activities in the Forcados Terminal, cost deferment of $0.248Million can be achieved by partial scope deferment. PO awaits the completion of enquiry LEC May | 205000 | Place order for the equipment through procurement team and Installation to be carried out by DIY | Yes |  | Production Critical | P2 | Put this in the notional budget. Move to Chemistry team
| Procurement/Replacement of 6nos Export Pump Lube Oil Coolers @ F$70.02K | C.NG.PTW.DF.20.061 | PROCUREMENT/REPLACEMENT OF NOS EXPORT PUMP LUBE OIL COOLERS | 70000 | 70000 | 0 | 60633 | 4851 | 4516 | PR 10685967 for 5nos lube oil coolers at $60k. Awaiting PO creation since March Procurement/Replacement of 6nos Export Pump Lube Oil Coolers @ F$70.02K | PO awaits the completion of enquiry LEC May (10685967) | 70000 | Place order for the equipment through procurement team | Yes | 100kbopd | Production Critical | P1 | Issue PO before 31st of July
| 1) Upgrade of Protection Relays for Switch Gear 201, 301, and 401. F$592K 2) Procurement of 2nos 500KVA Distribution Transformers 6.6kV/.415kV @ $30K each = F$60k 3) Rehabilitation of High voltage switch room floor rehab. F$163K | C.NG.PTW.IE.20.001 | MAJOR MID-LIFE AND END OF LIFE ELECTRICAL EQUIPMENT MAINTENANCE | 383000 | 383000 | 0 | 1228 | 98 | 381674 | Rehabilitation of High voltage switch room floor rehab. F$163K 1) Procurement of 2nos 500KVA Distribution Transformers 6.6kV/.415kV @ $30K 2) Upgrade of Protection Relays for Switch Gear 201, 301, and 401. F$592K 3) Procurement of 2nos 500KVA Distribution Transformers 6.6kV/.415kV @ $30K each = F$60k | PO awaits the completion of enquiry LEC May (10685967) Deferred till 2021: 1) Upgrade of Protection Relays for Switch Gear 201, 301, and 401. F$592K 2) Procurement of 2nos 500KVA Distribution Transformers 6.6kV/.415kV @ $30K each = F$60k 3) Rehabilitation of High voltage switch room floor rehab. F$163K | 163000 | To be executed via CW285588 (33 KV Trans Lines Supt(Tunu/Otumara S2) | Yes | 250kbopd | Safety Critical | P1 | Issue PO for the execution before 31st July
| Phase 1 FOT to South Bank Transmission line upgrade: Overhead Cables and Wooden poles replacement, Inspection of 33 KV (HV) Power Transmission Lines from FOT to Southbank, Substation integrity checks (transformer, XLPE cables & feeder pillar, Earthing system) = F$480K Phase 2 1. 240k in 2020 - Study and design 2. 550k in 2021 - Execution (material & construction) | C.NG.PTW.IE.20.001 | MAJOR MID-LIFE AND END OF LIFE ELECTRICAL EQUIPMENT MAINTENANCE | 240000 | 240000 | 0 | 0 | 0 | 240000 | Site survey completed. Handed over to Project Team Phase 1 FOT to South Bank Transmission line upgrade: Overhead Cables and Wooden poles replacement, Inspection of 33 KV (HV) Power Transmission Lines from FOT to Southbank, Substation integrity checks (transformer, XLPE cables & feeder pillar, Earthing system) = F$480K Phase 2 1. 240k in 2020 - Study and design 2. 550k in 2021 - Execution (material & construction) | PO 4510433935 issued for site survey. Site survey completed and report issued. Activity handed over to Project Team for execution. Balance $238k to partly fund Sea Eagle Rundown Cooler. | 1200 | To be executed via CW285588 (33 KV Trans Lines Supt(Tunu/Otumara S2) | Yes | 40kbopd | Improvement | P1 | Funds to be used in EA rundown cooler
| Change out of UPS 201, 202, 501, 611, 622, 623 Battery cabinet & bypass cabinet for UPS 20kVA UPS622 battery Charger & Rectifier - $69k UPS 623 battery Charger & Rectifier - $69k UPS 611 Battery cabinet & bypass cabinet - $65k UPS 501 Battery cabinet & bypass cabinet - $65k UPS 301 302 battery charger and rectifiers - $64k | C.NG.PTW.IE.19.051 | REPLACEMENT OF FORCADOS TERMINAL UPS BATTERIES | 830000 | 830000 | 444185 | 61599 | 6405 | 317811 | PO 1- 4510438559 (KNIGHTSEDGE NIGERIA LTD ) ROD - 29/08/2020 & PO 2 - 4510437225 (IKOSH NIGERIA LIMITED ) R0D - 29/07/2020 Change out of UPS 201, 202, 501, 611, 622, 623 Battery cabinet & bypass cabinet for UPS 20kVA UPS622 battery Charger & Rectifier - $69k UPS 623 battery Charger & Rectifier - $69k UPS 611 Battery cabinet & bypass cabinet - $65k UPS 501 Battery cabinet & bypass cabinet - $65k UPS 301 302 battery charger and rectifiers - $64k | PR 1068013 - PO Awaits completion of enquiry Deferred till 2021: UPS 501 Battery cabinet & bypass cabinet - $65k UPS 301 302 battery charger and rectifiers - $64k | 203000 | Place order for Materials through SPDC procurement process and execute installation scope through minor contract NG01023859 - MAJ UPGRADE OF UPS SYS IN FORCADOS TERM | Yes |  | Safety Critical | P1 | PO issued - EDD is August
| Procurement and installation of fiscal meters for Produced Water, Condensate & AGO measurements @ F$250k in yr 1 for the The scope to phase across 3yrs Detail Design - 250K in Yrs 1 Procurement of materials in Yr2 Execution in Yr 3 | C.NG.PTW.II.20.002 | FORCADOS TERMINAL METERING IMPROVEMENT | 250000 | 184142 |  |  |  | 250000 | Procurement and installation of fiscal meters for Produced Water, Condensate & AGO measurements @ F$250k in yr 1 for the to be realigned for other critical meters** | PO awaits the completion of enquiry LEC May (10685967) Deferred till 2021: Procurement and installation of fiscal meters for Produced Water, Condensate & AGO measurements @ F$250k in yr 1 for the | 0 |  | Yes |  | Statutory / Regulatory | P1
| a. Procurement and installation 15nos IQT Actuators and 15nos Pakboxes - F$350k b. Procurement and installation of Pakscan control system i) Pakscan IIE 120 Channel Master Station display Module PS100 @ $18K each ii) Power Supply Module PS210 @ $ 2K each Total =F$372k | C.NG.PTW.OR.20.001 | FORCADOS TERMINAL ROTORK MOV/GEARBOX AND PAKSCAN REPLACEMENT | 372000 | 372000 | 113456 | 112255 | 32659 | 113630 | a. Procurement and installation 2nos IQT Actuators and 15nos Pakboxes - F$350k (Procurement of Rotork JB & ENRAF Gauges $32K a. Procurement and installation 6nos IQT Actuators and 15nos Pakboxes - F$350k (Procurement of Rotork JB & ENRAF Gauges $79K- PR 10679315 & 10686278 - Procurement of Rotork JB & ENRAF Gauges ($79k) yet to matured to PO b. Procurement and installation of Pakscan control system i) Pakscan IIE 120 Channel Master Station display Module PS100 @ $18K each ii) Power Supply Module PS210 @ $ 2K each Scope deferement of 3nos pakboxes to 2021 = $72k | PO 4510434139 - Procurement of Rotork JB & ENRAF Gauges PR 10679315 & 10686278 - Procurement of Rotork JB & ENRAF Gauges ($79k) yet to matured to PO | 99000 | To place order for the items through SPDC procurement process. Installation to be carried out DIY | Yes | 250kbopd | Production Critical | P1 | PR for Enraf guages to be converted to PO before 31st July
| Procure LCV for IGF Inlet 1 Nos 18" x 150 - F$19.23k Procure and install 3 Nos 16" x 150 Butterfly Valves - $20.5k Procure and install 3 Nos 8" x 150 Butterfly Valves - $15k Procure and install 3 Nos 6" x 150 Butterfly Valves - $20k Procure and install 1Nos. Solar Gas Turbine Gas Inlet Shut Down Valve = F$81k | C.NG.PTW.OR.20.055 | REPLACEMENT OF VALVES AND ACTUATORS FOR FORCADOS TERM | 267300 | 267300 | 9674.93 | 64256 | 29153 | 164216.07 | PO 4510433260; 4510432902 & 4510433257 = $64K Procure LCV for IGF Inlet 1 Nos 18" x 150 - F$19.23k Procure and install 3 Nos 16" x 150 Butterfly Valves - $20.5k Procure and install 3 Nos 8" x 150 Butterfly Valves - $15k Procure and install 3 Nos 6" x 150 Butterfly Valves - $20k Procure and install 1Nos. Solar Gas Turbine Gas Inlet Shut Down Valve = F$81k Scope deferement of procurement of valves to 2021 = $67k | PO 4510433260; 4510432902 & 4510433257 = $64K | 96000 | Place order for valves through procrement process and carryu out the installation via DIY | Yes |  | Safety Critical | P2 | Procure LCV for IGF Inlet 1 Nos 18" x 150 - F$19.23k - defered to 2021 All butterfly valves have been ordered Solar GT ISV ordered on OPEX
| Sea Eagle Rundown Cooler (Heat Exchanger) Refurbishment Materials - Procurement of materials (Channel plates, bolts & tube, accessor | C.NG.PAO.NO.20.001 | Sea Eagle Rundown Cooler (Heat Exchanger) Refurbishment | 893000 | 1109000 | 0 |  |  | 893000 | Awaiting commitment Control Approval Sea Eagle Rundown Cooler (Heat Exchanger) Refurbishment Materials - Procurement of materials (Channel plates, bolts & tube, accessor | Under-going commitment control review and awaiting approval | 1109000 | Place order for Rurbishment materials through procurement process. Refurbishment to be executed with contract NG01023553 PROV OF BROWNFIELD MAINTENANCE AND ENGINEERING | Yes | 20kbopd | Production Critical | P1 | Load the amount in the wbs. Get confirmation from the vendors on delivery timeline. Tobe reviewed by 31st july.
| Sea Eagle Power Management System (PMS) Upgrade. 2020 Scope: Design and material procurement (by OEM) F$499,550 Sea Eagle LV Switchgears Air Circuit Breaker (8nos) upgrade 2020 Scope: Material Procurement (execution to be done inhouse)- 8 nos ABB Air Circuit breakers (4 nos of E4H 4000 PR122/P-LSIG In=4000A, 1nos of E3H 3200 PR122/P-LSIG In=3200A, and 3nos of E4H 3200 PR122/P-LSIG In=3200A) TOTAL=F$145,030 | C.NG.PAO.NO.20.003 | Sea Eagle Power Management System (PMS) Upgrade | 500000 | 500000 | 0 |  |  | 500000 | Awaiting NAPIMS work order authorisation Sea Eagle Power Management System (PMS) Upgrade. 2020 Scope: Design and material procurement (by OEM) F$499,550 | Awaiting NAPIMS Work order authrisation | 500000 | Scope to be executed with contract NG01022088 - PROV OF MAINT. SERV FOR SOLAR GAS TURBIN | Yes | 45kbopd | Improvement | P1 | Proceed with the work and PO issuence before 31st July
| Sea Eagle Inert Gas Generator Control System Upgrade: 2020 Scope: Design and Spares Procurement:$400k | C.NG.PAO.NO.20.004 | Sea Eagle Inert Gas Generator Control System Upgrade: | 400000 | 400000 | 0 |  |  | 400000 | Activity deferred till 2021. Funds to be released for rundown cooler refurbishment. Sea Eagle Inert Gas Generator Control System Upgrade: 2020 Scope: Design and Spares Procurement:$400k | Awaiting ELDL Approval for Corporate ECS contract to issue PO | 0 | Scope to be executed with contract NG01023867 - (PROVISION OF SPECIALIST MAINTENANCE SUPP) | Yes | 45kbopd | Safety Critical | P1 | Deffered to next year.
| Procurement of spares for 2 nos pump overhaul @ $92,422.55 * 2pumps = $184,845.10 FSR rate @ $3836.40 * 42Days = $161,128.8 Mob/Demob (x1) = $16,000 | C.NG.PAO.NO.20.005 | EA - CRUDE OIL PUMP OVERHAUL | 362000 | 362000 | 0 | 98618 | 2818 | 260564 | PO 4510421445 - to be picked up from OEM (FCA) PO 4510430795 - to be picked up from OEM (FCA) PO 4510424176 - delivered PO 4510424356 - delivered PO 4510428862 - delivered OEM Overhaul service deferred till next year Procurement of spares for 2 nos pump overhaul @ $92,422.55 * 2pumps = $184,845.10 FSR rate @ $3836.40 * 42Days = $161,128.8 Mob/Demob (x1) = $16,000 | 4510428862 & 4510421445 - OH spares = $185k OEM FSR to mobilsed after material delivery | 184845 | Scope to be executed via NG01023553 | Yes | 20kbopd | Production Critical | P2 | Focus on material delivery and work on contracting and price negotiation. Services should be done next year.
| Sea Eagle SYMP Crane 5Y recertification Materials required for 5yrly crane overhaul & recertification - $118,900.00 OEM FSR rate for @$3300 for 12Days - $39,600 | C.NG.PAO.NO.20.007 | Sea Eagle SYMP Crane 5Y recertification | 158000 | 147761 | 0 |  |  | 158000 | *Activity deferred till 2021 |  | 0 | Scope to be executed with contract NG01023553 - PROV OF BROWNFIELD MAINTENANCE AND ENGINEERING | Yes |  | Safety Critical | P3
| Refurbishment of severely corroded Sea Eagle Flash Gas Compressor Aftercooler cowlings 2 banks of cowling(4pcs each) @ F$157.87k | C.NG.PAO.NO.20.002 | EA - FLASH GAS COMPRESSOR BUNDLE | 316000 | 316000 | 0 |  |  | 316000 | Completed construction drawings and verification; CTR to be progressed to PO Refurbishment of severely corroded Sea Eagle Flash Gas Compressor Aftercooler cowlings - Bank 1- $158k Refurbishment of severely corroded Sea Eagle Flash Gas Compressor Aftercooler cowlings - Bank 2 - $158k | Completed construction drawings and verification; CTR to be progressed to PO | 158000 | To execute scope through contract NG01023553 - PROV OF BROWNFIELD MAINTENANCE AND ENGINEERING | Yes | 25MMscf/d | Production Critical | P2 | Deffered to 2021
|  |  |  | 8768100 | 8908003 | 1211409.03 | 610748 | 556742 | 6389200.97 |  |  | 4109825
|  |  |  | % Actual |  | 13.82% | 6.966% | 6.35% | 72.87%
|  |  |  | % Plan |  | #REF!
* Captured in OP19 CAPEX budget

## Dropped items
MRTA 2020 CAPEX BUDGET TRACKER
HUB | PROJECT DESCRIPTION | APPROVED OP19 F$ | OP19 F$ Loaded in SAP | COMMENTS | STATUS | Estimated Cost | Approved in OP19? | Volume at risk | Criticality | Priority
EXECUTION (CENTRAL) | 1) Upgrade of Clink II software on 18 units of Low voltage switchboards; Upgrade of obsolete LV Switch board including the breakers; Replacement of Obsolete 1 pc 160A Hole switchboard at Adibawa Flow Station; Replacement of RMU and associated transformers for Slot; Replacement of Obsolete 1 pc 100A Holec switchboard at Mbiama Microwave 2) Replacement of non-serviceable halyester panels for FGP, Abuja, Shore power and Oloma - $0.831M 3) Replace Soku EGGS1 HVAC system; GTG cooler fan replacement at BOGT; Replacement Seal water Cooler fan EF1104 (1unit) at BOGT; 2pcs Reconditioning of Gbaran Heat Exchanger; Provision of 1 unit GRU Heater bundles at Soku GP; Provision of Lube Oil Cooler Fan Motors for Solar G-8121 at Soku GP - $0.925M | 1756000 | 1376000 | 1. Upgrade of Clink II software on 18 units of Low voltage switchboards 2.Upgrade of obsolete LV Switch board including the breakers for Soku 3.Replacement of Obsolete 1 pc 100A Holec switchboard at Mbiama Microwave. 4.Replacement of non-serviceable halyester panels for FGP, Abuja, Shore power and Oloma - $0.831M 5.Provision of Lube Oil Cooler Fan Motors for Solar G-8121 at Soku GP 6.Procurement of 1unit fan GTG Cooler fan at BOGT Total = $992,157 | F$1,376K was loaded in SAP Balance budget to be loaded F$380,000 | 992157 | Yes |  | Production Critical | P1
| 1) 1 RO Main pump; 1 RO transfer Pump; 1 TEG booster pumps; 1 water transfer pumps - F$2.2M 2) Overhaul 3 Air Compressors across Oloma FS, Gbaran-K/Creek and NunR, Revamp 1 number Instrument Air Dryer at Bonny - F$0.5M 3) Purchase of new Gen for Adibawa IDG (community generator), Oloma facility Gas Gen Overhauling, Installation of additional gas generator (G3512) at NunR - F$0.78M | 3517000 | 3517000 | (1)1 RO Main pump; 1 RO transfer Pump; 1 TEG booster pumps; 1 water transfer pumps- (2)Revamp 1 number Instrument Air Dryer at Bonny - Installation of additional gas generator (G3512) at NunR . Bonny 2 nos Sulzer pumps -$986,252 (PR 10676182) Total= F$1,294,266 |  | 1294266 | Yes |  | Production Critical | P1
| 1) Passing and faulty Valves replacement (Control valve, ON/OFF valve, MOV) (8 qty) - F$400k 2) Replacement defective of 6" and 8" Goodwin check valve and manual valves in F$100k 3) MOVs and Critical Class One Check Valves Spares @USD 50K 4) Lighting Improvement Project at the Soku GP (CEAG Lights 100 pieces) 5) Upgrade of NPA Highbay lighting bulbs to LED; Earthing Protection Improvement for Soku Gas Plant; Installation of additional lighting fixtures and fittings on Titan/LNG gate road - $370K | 920000 | 920000 | 1.Replacement defective of 6" and 8" Goodwin check valve and manual valves in F$100k |  | 100000 | Yes |  | Production Critical | P1
Execution West | 1) Procurement of 1Nos Instrument Air Compressor F$198k 2) Installation and commissioning F$50k 3) Transportation of 1Nos Instrument Air Compressor | 248000 | 248000 | 2) Installation and commissioning F$50k 3) Transportation of 1Nos Instrument Air Compressor | PO awaits completion of enquiry Iinstallation and commissioning F$50k to be deferred till 2021 | 50000 | Yes | 250kbopd | Production Critical | P1
| Procurement and installation of 2 Nos Fire Jockey Pumps = F$289.78K | 289800 | 289800 | Procurement and installation of 2 Nos Fire Jockey Pumps = F$289.78K | Procurement deferred till 2021 | 289800 | Yes |  | Safety Critical | P1
| Procurement of 3nos. portable fire pumps @ F$21,394.80 each | 21000 | 21000 | Procurement of 2 nos. portable fire pumps @ F$14,263.2 each | PO awaits the completion of enquiry LEC May Procurement of 2 nos. portable fire pumps deferred till 2021 | 14263.2 | Yes |  | Safety Critical | P1
| Phase II of Upgrade of currently installed aqua-cell system and Sewage Treatment Plant. 1) Propagation and bombardment of the macropytes -220K 2) Inoculation of bioagents - 71.5K 3) Rapid sand filter - 242K 4) Equipment for site laboratory - 170.5K 5) Phase III of Upgrade of currently installed aqua-cell system and Sewage Treatment Plant. 6) Anti-Corrosion and Bitumen coating - 71.5K 7) Civil Construction - $2.22m | 1200000 | 1200000 | 7) Civil Construction - $2.22m but only 0.3m was approved in OP19. Civil construction partial scope of $0.3m to be deferement to 2021 | * Upon review of these activities in the Forcados Terminal, cost deferment of $0.3 Million can be achieved by partial scope deferment. | 300000 | Yes |  | Safety Critical | P2
| 1) Installation of 1nos fume hood for the Organic Chloride equipment - $20k. 2) Procurement and installation of Agilent gas Chromatograph for fluid fingerprint analysis - F$120k 3) Procurement of Spectro Xepos, Pamas S40 and accessories for lube oil and fuel oil analysis equipment- $193k. 4) Procurement of Jiskoot Lab Mixer, Orbital Shaker, Hot bath and other accessories for sample preparation - F$31.4k 5) Purchase Filter Blocking Tendency tester, Coulometer, Water distiller, Colorimeter, flashpoint tester and OptiDist -$105.8k | 448000 | 448000 | 3) Procurement of Spectro Xepos, Pamas S40 and accessories for lube oil and fuel oil analysis equipment- $193k. 4) Procurement of Jiskoot Lab Mixer, Orbital Shaker, Hot bath and other accessories for sample preparation - F$31.4k 5) Installation of 1nos fume hood for the Organic Chloride equipment - $20k. | * Upon review of these activities in the Forcados Terminal, cost deferment of $0.248Million can be achieved by partial scope deferment. PO awaits the completion of enquiry LEC May | 244400 | Yes |  | Production Critical | P2
| 1) Upgrade of Protection Relays for Switch Gear 201, 301, and 401. F$592K 2) Procurement of 2nos 500KVA Distribution Transformers 6.6kV/.415kV @ $30K each = F$60k 3) Rehabilitation of High voltage switch room floor rehab. F$163K | 383000 | 383000 | 2) Upgrade of Protection Relays for Switch Gear 201, 301, and 401. F$592K 3) Procurement of 2nos 500KVA Distribution Transformers 6.6kV/.415kV @ $30K each = F$60k 4) Rehabilitation of High voltage switch room floor rehab. F$163K | PO awaits the completion of enquiry LEC May (10685967) Deferred till 2021: 1) Upgrade of Protection Relays for Switch Gear 201, 301, and 401. F$592K 2) Procurement of 2nos 500KVA Distribution Transformers 6.6kV/.415kV @ $30K each = F$60k 3) Rehabilitation of High voltage switch room floor rehab. F$163K | 353000 | Yes | 250kbopd | Safety Critical | P1
| Change out of UPS 201, 202, 501, 611, 622, 623 Battery cabinet & bypass cabinet for UPS 20kVA UPS622 battery Charger & Rectifier - $69k UPS 623 battery Charger & Rectifier - $69k UPS 611 Battery cabinet & bypass cabinet - $65k UPS 501 Battery cabinet & bypass cabinet - $65k UPS 301 302 battery charger and rectifiers - $64k | 830000 | 830000 | UPS 501 Battery cabinet & bypass cabinet - $65k UPS 301 302 battery charger and rectifiers - $64k | PR 1068013 - PO Awaits completion of enquiry Deferred till 2021: UPS 501 Battery cabinet & bypass cabinet - $65k UPS 301 302 battery charger and rectifiers - $64k | 130000 | Yes |  | Safety Critical | P1
| Procurement and installation of fiscal meters for Produced Water, Condensate & AGO measurements @ F$250k in yr 1 for the The scope to phase across 3yrs Detail Design - 250K in Yrs 1 Procurement of materials in Yr2 Execution in Yr 3 | 250000 | 184142 | Procurement and installation of fiscal meters for Produced Water, Condensate & AGO measurements @ F$250k in yr 1 for the to be realigned for other critical meters** | PO awaits the completion of enquiry LEC May (10685967) Deferred till 2021: Procurement and installation of fiscal meters for Produced Water, Condensate & AGO measurements @ F$250k in yr 1 for the | 250000 | Yes |  | Statutory / Regulatory | P1
| a. Procurement and installation 15nos IQT Actuators and 15nos Pakboxes - F$350k b. Procurement and installation of Pakscan control system i) Pakscan IIE 120 Channel Master Station display Module PS100 @ $18K each ii) Power Supply Module PS210 @ $ 2K each Total =F$372k | 372000 | 372000 | Scope deferement of 3nos pakboxes to 2021 = $72k | PO 4510434139 - Procurement of Rotork JB & ENRAF Gauges PR 10679315 & 10686278 - Procurement of Rotork JB & ENRAF Gauges ($79k) yet to matured to PO | 72000 | Yes | 250kbopd | Production Critical | P1
| Procure LCV for IGF Inlet 1 Nos 18" x 150 - F$19.23k Procure and install 3 Nos 16" x 150 Butterfly Valves - $20.5k Procure and install 3 Nos 8" x 150 Butterfly Valves - $15k Procure and install 3 Nos 6" x 150 Butterfly Valves - $20k Procure and install 1Nos. Solar Gas Turbine Gas Inlet Shut Down Valve = F$81k | 267300 | 267300 | Scope deferement of procurement of valves to 2021 = $67k | PO 4510433260; 4510432902 & 4510433257 = $64K | 67000 | Yes |  | Safety Critical | P2
| Sea Eagle SYMP Crane 5Y recertification Materials required for 5yrly crane overhaul & recertification - $118,900.00 OEM FSR rate for @$3300 for 12Days - $39,600 | 158000 | 147761 | *Activity has been identified for deferment, with deferred cost of $0.2Million *Regret: Inability to meet statutory obligations. |  | 158000 | Yes |  | Safety Critical | P3
| Refurbishment of severely corroded Sea Eagle Flash Gas Compressor Aftercooler cowlings 2 banks of cowling(4pcs each) @ F$157.87k | 316000 | 316000 | Refurbishment of severely corroded Sea Eagle Flash Gas Compressor Aftercooler cowlings - Bank 2 - $158k | Completed construction drawings and verification; CTR to be progressed to PO | 158000 | Yes | 25MMscf/d | Production Critical | P2
EXECUTION (LAND EAST) | 1) Procure and install OKGP FGC Motorised Crane - $0.08M 2) Replacement of existing perimeter lighting poles with collapsible poles across Agbada facilities. - Ahia FS - 15 poles, Oguta FS - 15 poles Obigbo FS - 20 poles ,Agbada 1 - 20 poles, Agbada 2 - 20 poles, Umuechem - 20 poles, Obele FS - 20 poles. - $0.165M 3) Procurement and replacement of one of the existing Gas generator for Agbda AGG, Obigbo AGG and additional one - $1.4M 4) Gas Scrubber upgrade for Agbada FS 1, Agbada FS 2, Obele FS, Umuchem FS; AGG Scrubber revamp for Agbada AGG. The workscope involves revamp of the internal elements of all the scrubbers; Gas Scrubber upgrade for Imo 1, Nkali FS, Isimiri FS; AGG Scrubber revamp for Imo AGG. The workscope involves revamp of the internal elements of all the scrubbers. - $0.24M 5) Procure 1nos moisture analyzer for Agbada AGG Plant @ $0.110M 6) Upgrade of Switchboards and Switchgears - $0.4M 7) OBIGBO AGG DELTA V DCS UPGRADE - $0.25M 8) UPS systems Revamp at Gbaran and Crude Loading Platform at Bonny - $0.965M | 3610000 | 3106000 | 1) Procure and install OKGP FGC Motorised Crane - $0.08M - OABP to Execute 4) Gas Scrubber upgrade for Agbada FS 1, Agbada FS 2, Obele FS, Umuchem FS; AGG Scrubber revamp for Agbada AGG. The workscope involves revamp of the internal elements of all the scrubbers; Gas Scrubber upgrade for Imo 1, Nkali FS, Isimiri FS; AGG Scrubber revamp for Imo AGG. The workscope involves revamp of the internal elements of all the scrubbers. - $0.24M - Regret 5) Procure 1nos moisture analyzer for Agbada AGG Plant @ $0.110M - Regret 6) Upgrade of Switchboards and Switchgears - $0.4M - Regret 8) UPS systems Revamp at Gbaran and Crude Loading Platform at Bonny - $0.965M - Moved from Land WBS C.NG.PAE.DF.20.067 to Central |  | 1795000 | Yes | 30kbopd | Production Critical | P1
| 1.) Provision of Major overhaul of CAT 3408 engine and EMSCO pump for 3 nos Driver / D225 pumpsets. 3 Units in Imo 1 FS 2.) Provision of Major overhaul of CAT 342 engine and NATIONAL pump for 2 nos Driver/ D225 pumpset. 1 Unit at Nkali FS and1 Unit at Isimiri FS 3.) Major Overhaul of G342/D225 Pump sets 2 Units in Agbada 2 Flow and1 Unit in Agbada 1 Flow Station. 4.) Major Overhaul of 1no Obigbo Flow station EP2 G3408 DRIVER engine for Crude oil export pump 5.) Deployment of shielded ignition system on 12nos generators at Agbada AGG, Obigbo AGG, ImoR AGG 6.) Revamp of Obsolete Pump control system (Murphy TTD-T Crude oil pumpset controls on G342) at 6nos Pumps at Agbada 2 Flow Station | 1560000 | 1560000 | 2.) Provision of Major overhaul of CAT 342 engine and NATIONAL pump for 2 nos Driver/ D225 pumpset. 1 Unit at Nkali FS and1 Unit at Isimiri FS 3.) Major Overhaul of G342/D225 Pump sets 2 Units in Agbada 2 Flow and1 Unit in Agbada 1 Flow Station. 4.) Major Overhaul of 1no Obigbo Flow station EP2 G3408 DRIVER engine for Crude oil export pump 5.) Deployment of shielded ignition system on 12nos generators at Agbada AGG, Obigbo AGG, ImoR AGG 6.) Revamp of Obsolete Pump control system (Murphy TTD-T Crude oil pumpset controls on G342) at 6nos Pumps at Agbada 2 Flow Station |  | 514000 | Yes | 10kbopd | Production Critical | P2
| 1) Procurement and replacement of passing valves Land Asset 2) Replacement of 3nos 6"X600 Isolation valve passing in closed position on the metering skid prover loop at Obigbo FS 3) Change out 3 pcs passing valves,27UZ131,27UZ232,27UZ352 passing in closed position 4) Change out of SDV 120 (W44T) passing in closed position 5) Replacement of 16" Flow Station LP to AGG control valve 6) Replacement of 4pcs 10" Gate valve downstream of Coriolis meters 1 and 3 7) Replacement of 2 nos 8"X600 utility Gas PCV on Aba Gas line 8) Replacement of 1 nos 6"X600 Aba Gas PCV 9) Replacement of 3pcs 6"x600# MSDV for Agbada 1&2 FS 10) Replacement of 2pcs 4"X600# MSDV for Obele FS 11) Replacement of 1pc 8"x6x600# MSDV for Agbada 2 FS 12) Replacement of 2 nos 6"X600 Isolation valve passing in closed position on the metering skid prover loop at @ Ahia FS and Oguta FS | 473000 | 473000 | 1) Procurement and replacement of passing valves Land Asset 3) Change out 3 pcs passing valves,27UZ131,27UZ232,27UZ352 passing in closed position 6) Replacement of 4pcs 10" Gate valve downstream of Coriolis meters 1 and 3 7) Replacement of 2 nos 8"X600 utility Gas PCV on Aba Gas line 8) Replacement of 1 nos 6"X600 Aba Gas PCV 12) Replacement of 2 nos 6"X600 Isolation valve passing in closed position on the metering skid prover loop at @ Ahia FS and Oguta FS |  | 236500 | Yes | N/A | Safety Critical | P2
AGG | Bonny Terminal Hitachi 32k Inspection F$3.2M | 3200000 | 3200000 | 1) No vehicle for execution, discussion with HHI on having in country Rep ongoing. 2) Plan is to utilise fund for other emerging scope within AGG pofolio | Bonny Terminal Hitachi 32k Inspection F$3.2M | 3200000 | Yes | BOGT exporting capability at risk | Production Critical | P3
META(UNDERWATER) | 1. 3 pcs Mooring Grommets @$197,417.77 each, Total $592,253.31 ; ( 2 Yearly change out in SPM 1, 2 & 3); 2. 64 pcs of 20" MAINLINE HOSES @ $35,415.53 TOTAL $2,266,593.92 (7.5 yearly Change out of Floating hose string of SPM 3, Sectional changeout of 4 lacerated hose units in BSPM1) 3. 12 PCS OF 16" MAINLINE HOSES @ $34,851.89 TOTAL $418,222.68( 7.5 Yearly Change out of Floating hose string of SPM 3) 4. 3 PCS OF SUBSEA REINFORCED HOSE @ $31,843.57 TOTAL $95,530.71 (7.5 yearly change out in SPM2- 1 UNIT AND SPM3-2 UNITS) 5. 2 PCS SUBSEA LINE HOSE 20" X 35' - SEAFLEX SC STD 3091U @ $24,692.70 TOTAL $49,385.40 (SPM 3) 6. 25 PCS of SUBSEA BODY BEADS @ $4,986.90 TOTAL $124,672.50 7. 4 PCS of SUBSEA END BEADS @ $4,914.17 TOTAL $19,656.68 8. 1020 PCS 1 1/8” X 7” TEFLON COATED BOLT/NUT @ $10.12 TOTAL $10,322.40 (SPM 3) 9. 6 PCS GASKET METAL FOR 20"ANSI 150 SUS316 INNER AND OUTER RING GRAPHITE FILLER @$311.66 TOTAL $1,869.96 (SPM 3) | 3579000 | 3579000 | 1. 3 pcs Mooring Grommets @$197,417.77 each, Total $592,253.31 ; ( 2 Yearly change out in SPM 1, 2 & 3); |  | 592253.31 | YES |  | Safety Critical | P1
|  | 23398100 | 22438003 |  |  | 10810639.51
% Actual
% Plan
* Captured in OP19 CAPEX budget

## Sheet1 (hidden)
Safety Critical
Production Critical
Statutory / Regulatory
Improvement
others
P1
P2
P3
P4
P5
Yes
No

## 2020 EMERGING SCOPE
2020 EMERGING SCOPE
HUB | PROJECT DESCRIPTION | COMMENTS | Estimated Cost | CONTRACT DETAILS | Volume at risk | Criticality
Execution - Central | Load Bank 11KV/11MW | Required to complete the Calms control and the Power improvement program | 600000
AGG-CENTRAL | GBU Calms Control implementation - Outstanding scope | 1) Complementary Contract being put in-place. | 340000 | Nil | 1.25 Bcfd + 60Kbopd at risk. | Production Critical
| CDI payment for Soku LM1600 contract | 1) Inadvertly omitted NCDMB statutory payment associated with the delivered Soku AG3 PT last year [2019]. | 180000 | Nil | 65mmscf/d | Production Critical
AGG-LAND | IMOR 40k Outstanding Materials = 180,411.81 Exhaust duct bellow = 197,533.21 | Overhaul spares to be ordered in readiness for datum compressor 40k MOH planned for Q1,2021 | 377945.02 | Procuremnt Contract (Materials) | 20MMscf/d + 2kbopd | Production Critical
| Okoloma FGC 16k inspection for FSR charges F$150 | FSR service charge for Okoloma FGC 16K inspection planned for Q4 | 150000 | CW346032 | 120MMscf/d | Production Critical
1647945.02
* Scope not Captured in OP19 CAPEX budget

## 2020 DEFERRED SCOPE
DEFERRED SCOPE TO 2021
HUB | PROJECT DESCRIPTION | SAP COST OBJECT | COMMENTS | Estimated Cost | CONTRACT DETAILS | Volume at risk | Criticality
AGG-Central | Gbaran AGC1 & AGC2 PT Changeout (F$3M) and Gearbox inspection (F$600K) = F$3.6M |  | Gbaran AGC1 and 2 Contributes circa 170MMscf/d to the JV bussiness bottomline. Non implementation of the this scope which is will be due within the next 4months carries a potential risk of unit catastrophic failure which will keep the units down for a long haul and result to following. 1) High flare volume of circa 30mmscf/d and associated deferment of HGOR wells of circa 50kbbls/d 2) Potential shutdown of facility and high penalty payment to goverment due to flaring above target. 3) Potential company reputational issues with respect to SPDC and NLNG gas SLAs and flare impact to surrounding environment/Communities. | 3654913 | NG01011279 | 180MMscf/d | Production Critical
| Soku AG3 restoration F$3M |  | Restoration of SOKU AG3 will contribute additional 65MMscf/d to JV bussiness bottom line and Sustain SPDC and NLNG SLA with respect to gas supplies. | 3087635 | CW330165 | 65MMscf/d | Production Critical
| Soku AG2 PT (F$1.6M) Core Exchange (F$2.6M) = F$4.2M |  | SOKU AG2 Contributes circa 65MMscf/d to the JV bussiness bottomline. Non implementation of the this scope which is already overdue carries a potential risk of unit catastrophic failure which will keep the unit down for a long haul and result to following. 1) High flare volume of circa 12mmscf/d and associated deferment of HGOR wells of circa 7kbbls/d 2) Potential shutdown of facility and high penalty payment to goverment due to flaring above target. 3) Potential company reputational issues with respect to SPDC and NLNG gas SLAs, inability to receive third party companies(Eronton,Newcross etc)Associated gas and flare impact to surrounding environment/Communities and | 4213231 |  | 65MMscf/d | Production Critical
AGG-West | FoT (GT 820) Turbine 30K Inspection + FSR F$2.6M |  | Power capacity for Forcados Terminal (FOT) remain a huge concern given that FOT is the power node for South, North Banks CPFs and Escravos facilities and any failure will have a wider impact on overall western production. FOT GT 820 has exceed OEM recommended run hours for engine exchange (30K Inspection). Currently, the unit has covered > 34,700 run hours as against recommended standard of 30,000 runhours. Two(2) deviations had been raised on this particular unit since it exceeded inspection due date leaving unit with high potential for catastrophic failure and injury to operation personnel | 2553402 | NG01022088 | FOT exporting capability at risk | Production Critical
| FOT Control Retrofit and package system upgrade for 1 unit (1.7M) | C.NG.PCW.DG.20.060 | 3) Issued PO to Solar for FOT Control retrofit- PO (4510430832) - F$1,496,616 Note: 2019 spent has depleted WBS by $355k | 1700000 | NG01022088 | FOT exporting capability at risk | Production Critical
Workshop | Procurement of High-pressure hydraulic Torque Wrench Tools and accessories | C.NG.PSE.OR.18.051 | Procurement of High-pressure hydraulic Torque Wrench Tools and accessories | 308000 |  |  | Production Critical
| Procurement and installation of 2nos CXTM Manual pillar jib c/w electric wire rope hoist - 1-13YXQLFO Rev 1 3t, 5.50 m reach, 4.50 m lift & Cabling | C.NG.PSE.OR.18.051 | Procurement and installation of 2nos CXTM Manual pillar jib c/w electric wire rope hoist - 1-13YXQLFO Rev 1 3t, 5.50 m reach, 4.50 m lift & Cabling | 75508 |  |  | Production Critical
Execution - Central | Gbaran Fuel Gas Annual Certification-$0.1M Corroded Nuts and Bolts in Gbaran $0.3M |  |  | 400000 |  |  | Safety Critical
15992689
* Scope not Captured in OP19 CAPEX budget