## Slide 1: Reshape Initiatives
Nested Roadmap towards Aug 1 Go Live

## Slide 2: Reshape Initiatives – Nested Roadmap (Latest View)
Initiative | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  | 
HCM Process Scaling |  |  |  |  |  |  |  |  |  |  |  | RESHAPE MOR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
X-PMF  PMF Integration (Global) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pause/Exit Criteria |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Standardization of Design Archetypes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Clustering Campaign for contracts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Finalize Strawman
Scaled HCM
DG1 to DG3
Scaled HCM
Governance
Endorsement
Go Live
DG3 to OSD
Scaled HCM
Governance
Endorsement
Go Live
Kick off
Global Connect
X-PMF  PMF
End Design Phase
X-PMF  PMF
integration
Prospect to DG1
Draft Scaled HCM
Ideate Design
Archetypes
Create Design
Archetypes & SoP
Update Design
Archetypes
& SoP
Community
Survey
Distill
Survey
Outcomes
Get examples
(SCiN & Global)
Crystalize
Insights
Establish
Trigger Points
Define
Framework
Finalize
Framework
Governance
Endorsement
CP Strategy W/S
External
Requirements
Table
CP Tactics
W/S Internal
ITT SOW
Packages
CP Tactics W/S
External
Governance
Endorsement
Develop
Technical
ITT Package
Endorsement of
Technical Bid List
Nominees
Completed | On Track | Under Threat | Yet to Start
Global
Connect
Finalize Strawman for
Feed by difference
Go Live
Q3 – Q4
Go Live
Q1’22
Reshape
Go Live
TA1 Endorsement
Design Archetypes
& SoP
MCB
Approval
Contract
Execution
Framework
Test Design
Archetypes &
SoP
(KCFS)
Develop Commercial ITT Package
Advertise
In NIPEX
Publish approved
Technical ITT to
approved Technical
Bid List

## Slide 4: Reshape Initiatives – Nested Roadmap (Baseline)
Initiative | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  | 
HCM Process Scaling |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Standardization of Design Archetypes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Clustering Campaign for contracts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pause/Exit Criteria |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
X-PMF  PMF Integration (Global) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  | 
Create & Test Design Archetypes
Governance Endorsements
Ideate Design Archetypes
Community Roll Out
  Prepare Strawman for HCM Process
  Develop Scaled HCM process (Prospect to OSD)
  Governance Endorsements
  Community Roll Out
Kick off Feed by Difference
  Community Roll Out
Stakeholder Alignment (Internal & External)
CP Tactics - Internal
Prepare and Issue SoW for ITT (SCiN DO)
MCB
Approval
CP Strategy Endorsement
CP Tactics - External
Issue
Technical
ITT
Endorsement of
Technical Bid List
Nominees
Issue Commercial ITT
Community Survey
Distill Survey Outcomes, Project examples (SCiN, RDS)
Crystalize Insights
Define framework for Pause/Exit Criteria
Governance Endorsements
Finalize Documents
Governance Endorsements
Roll Out