## Slide 1
Enabler charter | Rollout of PT2020 Themes to STOGG activities
Enabler name: Rollout of PT2020 Themes to STOGG activities
Deliverables:
  Strawman for PT2020application to STOGG activities
  Developed pilot program for proof of concept
Teams/groups/assets/SOVs impacted/interdependencies
Teams impacted: OneSS (particularly Asset SS teams), central WRFM, CWI
Applies to SPDC opportunities only
Implementation high level timeline (phases and milestones)
Enabler description and key benefits:
PT2020 transformational themes (Competitive Scoping, Supply Chain Transformation, Efficient Execution and Technology & Innovation) have delivered significant savings in Capital projects (>40%)
2021 Short Term Oil & Gas Generation (STOGG) activtity budget is $102mln for 52 activities. This is the expected spend level for the next few years.
Key benefits include:
Based on the >40% savings in PT2020 application in Capital projects, 20% savings is assumed for STOGG activities translating to the following savings at a budget level of ~$100mln per annum
  2021: 5 M$ (opportunities already in flight, 25% assumed)
  2022: 20 M$
  2023: 20 M$
  2024: 20 M$
  2025: 20 M$
Sponsor: GM Development
Implementation owner, governance, and team members:
Implementation owner: ASM
Governance: GM Development, CWI Mgr, WRFM/Technology Manager
Team members: ASLs (1), Peter, Nodal Lead (3), CWI (1), Central WRFM (1), Asset BOM (1). Local PT2020 PMO (1)
Enabler level: SPDC
Key issues/risks/decisions:
CONFIDENTIAL
Implementation Deadline: End July 2021
Mindset change by practitioners being an NWW
Alignment of internal stakeholder – ASM, CWI, Central WRFM, Asset BOM
High UTC associated with inefficient planning and execution
  2020
  2021
  Dec
  Jan
  Feb
  Mar
  Apr
  May
  Jun
  Jul
  Aug
  Sep
  Oct
  Nov
  Dec
  Develop strawman for PT2020
  Application to STOGG
  Get endorsement by Governance
  Roll out PT2020 application to
  STOGG guide/pilot program
  Activity
Commitments
- Confirm ownership – W3
- Reconfirm impact ($$) – W3
  - Commence strawman for PT2020 Application to STOGG - Feb