## Slide 1: Rumuekpe phase 1 (AMOR 1b), Week #5
Activity | Last week Promise and Actual Status | Look Ahead (next One week) | Issues/Help Required | Overall Target
ITR3 action close out | Completed Schedule TA review and implemented action. Completed alternate concept options (gas destination) cost estimate. Submitted Economics assessment sheet with Wells & Facilities capex and production forecast Held Revised NTR-Q for new & emerging risk on mis-alignment with NAPIMS. | Complete all subsurface DEP input to Well Design. Awaiting TA review for Geohazard. Complete Brownfield Healthcheck update post Site visit. Issue IPA waiver request | JV partners (NAPIMS misalignment of AMOR 1B gas molecules swab with Tunu/Suku via ROH | 30th Mar 21
CSW | Commenced preparation – collating presentation slides. | Request meeting date with JV partners (8th Apr.) |  | Mar 21 LE - 8th Apr.
CP wkshop | NTR | NTR. Delayed due to CSW |  | Mar. 21 LE – 28th Apr.
PCN | NTR – Updating PCN post Economics review | Complete Economics update |  | Mar. 21
CR, SAR3 | Commenced CR preparation – weekly cadence | Progress preparation |  | May 21
DG3 |  |  |  | Jun 21 LE – Jul 21
FDP |  | Sign FDP and submit to DPR |  | Jul 21

## Slide 2: AMOR 1B Project
NEXT MILESTONE |  | OP20 DG3 |  |  | ISSUES/COMMENTS
 |  | P50 | P10 | LE | 
AMOR 1B | DG3 | Jun-21 | Jun-21 | Jul-21 | PCN on the critical path and may impact DG3 date.
  Updates / Issues / Mitigation:
    Scalable ORS combining DG2/3 being pursued
    PCN economics evaluation in final stages in preparation for internal endorsement.
    ITR3 held – ITR3 action close out in progress
    Assumes IPA waiver / derogation
Activity | Ambition | LE | OP20 | Status | Owner
ITR3 | Dec’20 |  | Dec’ 20 |  | George
PCN | Mar’19 |  | Dec’20 |  | Ralph
Complete Econs Evaluation | Apr’21 |  | Apr’20 |  | Mina
Competitiveness Review | May’21 |  | May’21 |  | George
Hold SAR3 | May’ 21 |  | May’ 21 |  | Mina
DG 3 | Jun’21 |  | Jun’21 |  | Mina / George
Dec-20
Mar-19
May-21
Jun-21
Jun-21
Completed
On Track
Delayed
Jul-21