## Slide 1: SSAGS Step 3A, Week #15
Activity | Last week Promise and Actual Status | Look Ahead (next One week) | Issues/Help Required | Overall Target
Bank ability | Continued preparing functional slides for Funding meeting with JV Partners | Continue preparing functional slides for Funding meeting with JV Partners Obtain agreement on timing for Funding alignment meeting with NAPIMS and JV Partners | External alignment on bankability Delay in securing firm date with NAPIMS over insistence on waiting till after Technical alignment meeting. | Funding Alignment with JV Partners LV: Apr 26th
ITR3/ SAR3 | Continued close out of high-urgency actions (80%) Concluded update to the Subsurface Fact Sheet (SSFS). Undergoing Portfolio BOM review & endorsement Concluded update to the Estimate and Schedule Fact Sheet (ESFS). Held TA2 review session. Undergoing functional review. | Continue close out of high-urgency actions from ITR/SAR3 (90%) Conclude functional review of ESFS and hold GM presentation & sign-off Sign-offs of the SSFS Obtain agreement on timing for C&P Strategy Workshop with NAPIMS and JV Partners | C&P Strategy contingent on successful alignment with JV Partners Delay in securing firm date with NAPIMS over insistence on waiting till after Technical alignment meeting. | Close-out of High-Urgency actions: LV: April 23rd C&P Strategy Workshop with JV Partners LV: Apr 27th
FDP | Sent Seibou and Kanbo FDPs to FEDM TA2 for review and endorsement FEDM TA2 concluded review of Seibou & Kanbo FDPs | Implement steers from FEDM TA2 to the Seibou & Kanbo FDPs Obtain FEDM TA2 endorsement of FDPs Conclude internal endorsement of FDPs and send to JV Partners via BGR | Prompt internal endorsement of FDPs | Internal FDP signoff: LV: Apr 21st FDPs to JV Partners: LV: Apr 23rd
Compet. Review | Continued functional inputs to CR slidepacks (90%) CR pack review with Line Managers April 15th Follow-up CR pack touchdown with COG PMO April 16th | Conclude functional inputs to CR slidepacks (100%) Competitiveness Review with in-country GMs April 21st |  | CR with in-country GMs: Apr 15th LV: Apr 21st
Others | Concluded inputs to the PCP-lite documentation. Undergoing Portfolio BOM review Held successful EIA Scoping Workshop April 13th-14th in Bayelsa State | Obtain BOM endorsement of PCP-Lite documentation Initiate signoffs of PCP-Lite |  | PCP-Lite signoffs: LV: 29th April
 |  |  |  | DG3: end-April 2021

## Slide 2: SSAGS Step 3A, Week #14
Activity | Last week Promise and Actual Status | Look Ahead (next One week) | Issues/Help Required | Overall Target
Bank ability | Prepared and sent out Funding alignment meeting agenda to JV Partners ahead of proposed April 13th meeting Continued preparing functional slides for Funding meeting with JV Partners | Funding alignment meeting with JV Partners scheduled for April 13th | External alignment on bankability | Funding Alignment with JV Partners LV: Apr 13th
ITR3/ SAR3 | Continued close out of high-urgency actions (60%) Held technical alignment meeting with NAPIMS 8-9 April Achieved internal alignment with C&P TA1 on Contracting Strategy | Continue close out of high-urgency actions from ITR/SAR3 (80%) C&P Strategy workshop with NAPIMS and JV Partners scheduled for 12th April | C&P Strategy contingent on successful alignment with JV Partners Delay in securing firm date with NAPIMS over insistence on waiting till after Technical alignment meeting. | Close-out of High-Urgency actions: Apr 12th LV: April 20th
FDP | Concluded implementing of steers from TA2s to the Seibou and Kanbo FDPs | Send Seibou and Kanbo FDPs to the FEDM TA2 for review and endorsement Conclude internal endorsement of FDPs and send to JV Partners via BGR | Prompt internal endorsement of FDPs | Internal FDP signoff: Mar 12th LV: Apr 16th FDPs to JV Partners: Mar 19th LV: Apr 19th
IPA Bench marking | Held alignment review meeting with IPA team on areas requiring clarification Received final IPA report – project assessed as optimal in Select phase with identified gaps for closure in subsequent phases | Implement IPA output for final SSAGS 3A Select phase reviews |  | Submission of final IPA report: 31st March LV: Apr 2nd
Compet. Review | Continued functional inputs to CR slidepacks (60%) Held initial touchdown with COG PMO April 9th to review CR pack | Continue functional input to CR slidepacks (90%) Follow-up touchdown with COG PMO April 14th CR pack review with Portfolio BOM April 15th CR pack review with Line Managers April 16th | Early and effective functional inputs | CR with in-country GMs: April 15th LV: Apr 21st
Others | Continued inputs to the PCP-lite documentation (95%) | Conclude inputs to the PCP-Lite documentation Hold EIA Scoping Workshop April 13th-14th | Early functional inputs to PCP-Lite | PCP-Lite preparation: Mar 26th LV: 16th April EIA Scoping Workshop: Mar 30-31 LV: 12-13 April
 |  |  |  | DG3: end-April 2021

## Slide 3: SSAGS Step 3A, Week #13
Activity | Last week Promise and Actual Status | Look Ahead (next One week) | Issues/Help Required | Overall Target
Bank ability | Sent out letter of invitation to NAPIMS and JV Partners for April 13th Funding alignment meeting. Agreed format of Funding alignment meeting with Finance team. | Prepare agenda and slidepack for JV Partners Funding alignment meeting. | External alignment on bankability | Funding Alignment with JV Partners LV: Mar 13th
ITR3/ SAR3 | Continued close out of high-urgency actions (30%) Preparing logistics for follow-up alignment meeting with NAPIMS scheduled for April 7-9 | Continue close out of high-urgency actions from ITR/SAR3 (60%) C&P Strategy workshop with NAPIMS and JV Partners now planned for 12th April | C&P Strategy contingent on successful alignment with JV Partners Delay in securing firm date with NAPIMS over insistence on waiting till after Technical alignment meeting. | Close-out of High-Urgency actions: Apr 12th
FDP | Implementing steers from TA2s to the Seibou and Kanbo FDPs | Conclude implementation of steers from TA2s to the Seibou and Kanbo FDPs Send the Seibou and Kanbo FDPs to the FEDM TA2 for review and endorsement | Prompt TA2 review of FDPs | Internal FDP signoff: Mar 12th LV: Apr 12th FDPs to JV Partners: Mar 19th LV: Apr 19th
IPA Bench marking | Received draft final IPA report IPA report undergoing functional reviews | Hold alignment meeting with IPA team April 6th on the draft IPA report | Conclusion of IPA report ahead of Competitiveness Review | Submission of final IPA report: 31st March LV: Apr 2nd
Compet. Review | Continued functional inputs to CR slidepacks (45%) | Continue functional input to CR slidepacks (70%) Touchdown with COG PMO April 9th | Early and effective functional inputs | CR with in-country GMs: April 15th LV: Apr 21st
Others | Continued inputs to the PCP-lite documentation (85%) Send PCP-Lite documentation to Finance team for review EIA Scoping Workshop postponed till 12-13 April due to delay in concluding logistics arrangements | Continue inputs to the PCP-Lite documentation (95%) Conclude logistics for EIA Scoping Workshop | Early functional inputs to PCP-Lite | PCP-Lite preparation: Mar 26th LV: 7th April EIA Scoping Workshop: Mar 30-31 LV: 12-13 April
 |  |  |  | DG3: end-April 2021

## Slide 4: SSAGS Step 3A, Week #12
Activity | Last week Promise and Actual Status | Look Ahead (next One week) | Issues/Help Required | Overall Target
Bank ability | Presented outcome of bankability assessment at the Mar 26th DRB. Received DRB approval to proceed with Funding Strategy discussions. | Initiate JV Partner engagement pack with Finance team Send out letters of invitations to JV Partners for Funding discussions Plan to hold combined C&P/Funding engagement | External alignment on bankability | Conclude internal bankability assessment: Feb 19th LV: Mar 19th
ITR3/ SAR3 | Continued close out of high-urgency actions Follow-up alignment meeting with NAPIMS postponed till April 7-9 to enable close-out of all COVID protocols | Continue close out of high-urgency actions from ITR/SAR3 C&P Strategy workshop with NAPIMS and JV Partners now planned for 7th April | C&P Strategy contingent on successful alignment with JV Partners Delay in securing firm date with NAPIMS over insistence on waiting till after Technical alignment meeting. | Close-out of High-Urgency actions: Apr 12th
FDP | Implementing steers from TA2s to the Seibou and Kanbo FDPs | Conclude implementation of steers from TA2s to the Seibou and Kanbo FDPs Send the Seibou and Kanbo FDPs to the FEDM TA2 for review and endorsement | Prompt TA2 review of FDPs | Internal FDP signoff: Mar 12th LV: Apr 5th FDPs to JV Partners: Mar 19th LV: Apr 9th
IPA Bench marking | Held verbal feedback session with the IPA team 25th March | Awaiting final report from IPA team (April 1st) | Conclusion of IPA report ahead of Competitiveness Review | Submission of final IPA report: 31st March LV: Apr 2nd
Compet. Review | Continued functional inputs to CR slidepacks (30%) | Continue functional input to CR slidepacks (40%) | Early and effective functional inputs | CR with in-country GMs: April 15th
Others | Continued inputs to the PCP-lite documentation (75%) EIA Scoping Workshop postponed till 12-13 April due to delay in concluding logistics arrangements | Continue inputs to the PCP-Lite documentation (90%) Send PCP-Lite documentation to Finance team for review Conclude logistics for EIA Scoping Workshop | Early functional inputs to PCP-Lite | PCP-Lite preparation: Mar 26th LV: 7th April EIA Scoping Workshop: Mar 30-31 LV: 12-13 April
 |  |  |  | DG3: end-April 2021

## Slide 5: SSAGS Step 3A, Week #11
Activity | Last week Promise and Actual Status | Look Ahead (next One week) | Issues/Help Required | Overall Target
Bank ability | Concluded composite cost profiling to carry out final assessments Carried out final bankability assessments for the various scenarios Preparing assessment summary to Portfolio BOM for 26-Mar DRB | Present bankability assessment update at the Mar-26 DRB Initiate JV Partner engagement pack with Finance team Send out letters of invitations to JV Partners for Funding discussions in week of 5th April | Alignment on bankability | Conclude internal bankability assessment: Feb 19th LV: Mar 19th
ITR3/ SAR3 | Continued close out of high-urgency actions (3 of 14) Validating COVID protocols for March 24-26 follow-up alignment meeting with NAPIMS | Continue close out of high-urgency actions from ITR/SAR3 (5 of 14) Fix C&P Strategy workshop with NAPIMS and JV Partners | C&P Strategy contingent on successful alignment with JV Partners | ITR3/SAR3: Feb 24-26 LV: Mar 3-5 Close-out of High-Urgency actions: Apr 12th
FDP | Sent the Seibou and Kanbo FDPs to the appropriate Discipline TA2s for review Implementing edits/steers from TA2s | Conclude implementation of steers from TA2s to the Seibou and Kanbo FDPs Send the Seibou and Kanbo FDPs to the FEDM TA2 for review and endorsement | TA2 reviews after ITR3/SAR3 to capture any steers | Internal FDP signoff: Mar 12th LV: Mar 26th FDPs to JV Partners: Mar 19th LV: Apr 2nd
IPA Bench marking | Responded to additional requests for information from IPA team | Awaiting draft report from IPA team | Conclusion of IPA report ahead of Competitiveness Review | Submission of final IPA report: 31st March LV: Apr 2nd
Compet. Review | Received approval to carry out Competitiveness Review at in-country GM level Continued functional inputs to CR slidepacks (20%) | Continue functional input to CR slidepacks (35%) | Early and effective functional inputs | CR with in-country GMs: April 15th
Others | Continued inputs to the PCP-lite documentation (70%) EIA Scoping Workshop fixed for 30-31 March | Continue inputs to the PCP-Lite documentation (90%) Prepare logistics for EIA Scoping Workshop, including weekly cadence | Early functional inputs to PCP-Lite | PCP-Lite preparation: Mar 26th EIA Scoping Workshop: Mar 30-31
 |  |  |  | DG3: end-April 2021

## Slide 6: SSAGS Step 3A, Week #10
Activity | Last week Promise and Actual Status | Look Ahead (next One week) | Issues/Help Required | Overall Target
Bank ability | Concluded updates to the project schedule as per cost sensitivities Awaiting composite cost profiling to carry out final assessments. | Receive composite cost profiles for cost sensitivities Final bankability assessment Prepare and send one-pager assessment to Portfolio BOM for DRB | Availability of cost engineer to conclude composite cost profiling Alignment on bankability | Conclude internal bankability assessment: Feb 19th LV: Mar 19th
ITR3/ SAR3 | Concluded further optimizations on cost and schedule. Held ITR3/SAR3 report out with 14 high-urgency actions identified. Initiated close out of high-urgency actions Follow-up alignment meeting with NAPIMS fixed for 23-25 March | Continue close out of high-urgency actions from ITR/SAR3 Fix C&P Strategy workshop with NAPIMS and JV Partners | C&P Strategy contingent on successful alignment with JV Partners | ITR3/SAR3: Feb 24-26 LV: Mar 3-5 Close-out of High-Urgency actions: Apr 12th
FDP | Concluded functional inputs to the Seibou (100%) and Kanbo (100%) FDPs Collated and submitted economic inputs for the Ogbotobo FDP as per request from DPR | Send the Seibou and Kanbo FDPs to the appropriate Discipline TA2s for review | Effective functional inputs TA2 reviews after ITR3/SAR3 to capture any steers | Internal FDP signoff: Mar 12th LV: Mar 26th FDPs to JV Partners: Mar 19th LV: Apr 2nd
IPA Bench marking | Concluded transmission of responses to requests from IPA team Held follow-up IPA sessions on Digitization & Carbonization | Respond to additional request for information from IPA team | Conclusion of IPA report ahead of Competitiveness Review | Submission of final IPA report: 31st March LV: Apr 2nd
Compet. Review | Continued functional inputs to CR slidepacks (15%) | Continue functional input to CR slidepacks (25%) | Early and effective functional inputs | CR with VPs: April 15th
Others | Continued inputs to the PCP-lite documentation (60%) EIA Scoping Workshop fixed for 30-31 March | Continue inputs to the PCP-Lite documentation (80%) Prepare logistics for EIA Scoping Workshop, including weekly cadence | Early functional inputs to PCP-Lite | PCP-Lite preparation: Mar 26th EIA Scoping Workshop: Mar 30-31
 |  |  |  | DG3: end-April 2021

## Slide 7: SSAGS Step 3A, Week #9
Activity | Last week Promise and Actual Status | Look Ahead (next One week) | Issues/Help Required | Overall Target
Bank ability | Awaiting composite cost profiling to carry out final assessments. | Preparation of composite cost profiles. Final bankability assessment | Availability of cost engineer to conclude composite cost profiling Alignment on bankability | Conclude internal bankability assessment: Feb 19th LV: Mar 12th
ITR3/ SAR3 | Concluded project base case cost estimation. Carrying out further optimizations on cost and schedule. Carried out project economics. Held ITR3/SAR3 with JV Partners in attendance. | ITR3/SAR3 report-out. Start to close out actions from ITR/SAR3 Fix C&P Strategy workshop with NAPIMS and JV Partners Fix follow-up technical alignment meeting with NAPIMS | C&P Strategy contingent on successful alignment with JV Partners | ITR3/SAR3: Feb 24-26 LV: Mar 3-5
FDP | Continued input to the Seibou (~95%) and Kanbo (~85%) FDPs | Progress input to the Seibou (~100%) and Kanbo (~100%) FDPs | Effective functional inputs TA2 reviews after ITR3/SAR3 to capture any steers | Internal FDP signoff: Mar 12th FDPs to DPR: Mar 19th
IPA Bench marking | Held IPA interviews and follow-up sessions Mar 1-2 Responded to further requests from IPA team | Conclude transmission of responses to requests from IPA team Hold follow-up IPA sessions | Conclusion of IPA report ahead of Competitiveness Review | Submission of final IPA report: 31st March
Compet. Review | Continued functional inputs to CR slidepacks (10%) | Continue functional input to CR slidepacks (20%) | Early and effective functional inputs | CR with VPs April 15th
 |  |  |  | DG3: end-April 2021

## Slide 8: SSAGS Step 3A, Week #8
Activity | Last week Promise and Actual Status | Look Ahead (next One week) | Issues/Help Required | Overall Target
Bank ability | Received assured STOG volumes and cost from the Asset Team. Volumes preliminarily assessed as insufficient to improve project bankability. Composite project volumes (SSAGS 3A+STOG) prepared for updated economics and bankability assessments. Continued cost estimation and composite cost profiling. | Preparation of composite cost profiles. Final bankability assessment | Availability of cost engineer to conclude cost estimation Alignment on bankability | Conclude internal bankability assessment: Feb 19th LV: Mar 2nd
ITR3/ SAR3 | Schedule Risk Assessment (SRA) endorsed. Preparing functional slidepacks for ITR3/SAR3. Held C&P Strategy Workshop with NCDMB 26-Feb. Collated and sent ITR3/SAR3 pre-reads to JV Partners and DPR. | Conclude Level 2 Cost Estimates Prepare Shell-view and Open-Book Economics Hold ITR3/SAR3 Mar 3-5 | C&P Strategy contingent on successful alignment with JV Partners Successful conclusion of Type 2 Cost Estimate | ITR3/SAR3: Feb 24-26 LV: Mar 3-5
FDP | Continued input to the Seibou (~90%) and Kanbo (~80%) FDPs | Progress input to the Seibou (~95%) and Kanbo (~90%) FDPs | Effective functional inputs TA2 reviews after ITR3/SAR3 to capture any steers | Internal FDP signoff: Mar 12th FDPs to DPR: Mar 19th
IPA Bench marking | Sent out 80% of IPA documentation (awaiting Cost & Schedule workbooks) IPA issued additional workbooks. Inputs ongoing. Prepared logistics for Mar 1-2 interview sessions | Conclude inputs and collation to IPA workbooks (100%) Send additional documentation to IPA team IPA interviews Mar 1-2 | Conclusion of workbook submission to IPA hinged on completion of Type 2 cost estimates | Submission of final IPA report: 31st March
Compet. Review | Held kickoff meeting with Local PMO Feb 24th. Scheduled weekly cadence to track progress. Initiated functional inputs to CR slidepacks (5%) | Continue functional input to CR slidepacks (10%) | Early and effective functional inputs | CR with VPs April 15th
 |  |  |  | DG3: end-April 2021

## Slide 9: SSAGS Step 3A, Week #7
Activity | Last week Promise and Actual Status | Look Ahead (next One week) | Issues/Help Required | Overall Target
Bank ability | Held alignment meeting Feb 16th with the Asset, Opportunity and Finance teams to review results of the reverse bankability assessment. Asset team concluded volumes assessment for STOG opportunities. Undergoing endorsement. Also awaiting cost profile from WRFM. | TA2 volumes and cost endorsement. Preparation of composite cost and production profiles. Final bankability assessment | Swamp Asset Team support for cost and volume ranges for STOG opportunities Alignment on bankability | Conclude internal bankability assessment: Feb 19th LV: Feb 26th
ITR3/ SAR3 | Held Stakeholder Mapping update meeting Feb 15th Concluded the Schedule Assurance Review. Undergoing endorsement from Head, Project Controls Held ITR3/SAR3 Dry Run Feb 17th Concluded SME review of Subsurface Fact Sheet (SSFS). Steers being implemented ahead of follow-up meeting with SME. Preparing functional pre-reads for ITR3/SAR3. Issued draft Project Execution Strategy Issued draft Production Promise | C&P Strategy Workshop with NCDMB only planned for week of 26-Feb. Conclude Level 2 schedule Conclude Type 2 Cost Estimates Collate and send off pre-reads to JV Partners | C&P Strategy Workshop contingent on successful alignment with JV Partners on Clustering initiative (Clear C&P plan for actualization desired) Successful conclusion of Type 2 Cost Estimate | ITR3/SAR3: Feb 24-26 LV: Mar 3-5
FDP | Continue input to the Seibou (~85%) and Kanbo (~75%) | Progress input to the Seibou (~90%) and Kanbo (~85%) FDPs | Effective functional inputs | Internal FDP signoff: Mar 5th FDPs to DPR: Mar 19th
IPA Bench marking | IPA workbook collation meeting Feb 15th. | Continue input and collation to IPA workbooks (100%) (Expected delivery date to IPA team Feb 23rd) IPA interviews tentatively fixed for Mar 1-2 | Workbook submission to IPA hinged on early completion of Type 2 cost estimates | Submission of final IPA report: 31st March
Compet. Review | Fixed kickoff meeting with PMO for Feb 23rd | Start functional input to CR slidepacks | Early and effective functional inputs | CR with VPs April 15th
 |  |  |  | DG3: end-April 2021

## Slide 10: SSAGS Step 3A, Week #6
Activity | Last week Promise and Actual Status | Look Ahead (next One week) | Issues/Help Required | Overall Target
Bank ability | Asset team maturing the 6 screened opportunities. Awaiting volumes endorsement and cost assessment. Finance Team completed reverse bankability assessment. Currently undergoing review for alignment. | TA2 volumes and cost endorsement. Update of reverse bankability assessment based on results of alignment | Swamp Asset Team support for cost and volume ranges for STOG opportunities Alignment on bankability | Conclude internal bankability assessment: Feb 19th
ITR3/ SAR3 | Continuing the Schedule Assurance Review. Concluded functional review of draft Production Promise. Awaiting draft report. Subsurface Fact Sheet (SSFS) undergoing SME review. Held pre-Review meeting with ITR3/SAR3 Review Team Lead. Updated TOR and Review agenda. Project Execution Strategy draft completed. Currently undergoing functional review. Preparing pre-reads for ITR3/SAR3. | C&P Strategy Workshop with JV Partners & NCDMB only planned for week of 15-Feb. Engagement on alignment will be held subsequently with NAPIMS. Issue draft Project Execution Strategy Issue draft Production Promise Conclude Level 2 schedule Prepare Type 2 Cost Estimates ITR3/SAR3 Dry Run Feb 17th. Collate and send off pre-reads to JV Partners Stakeholder Mapping Review Feb 15th. | C&P Strategy Workshop contingent on successful alignment with JV Partners on Clustering initiative (Clear C&P plan for actualization desired) Successful conclusion of Type 2 Cost Estimate | ITR3/SAR3: Feb 24-26
FDP | Continue input to the Seibou (~80%) and Kanbo (~70%) | Progress input to the Seibou (~85%) and Kanbo (~75%) FDPs | Effective functional inputs | Internal FDP signoff: Mar 5th FDPs to DPR: Mar 19th
IPA Bench marking | Alignment held with IPA analyst on timing for IPA workbook delivery and interviews. | IPA workbook collation meeting Feb 15th. Continue input and collation to IPA workbooks (90%) (Expected delivery date to IPA team Feb 19th) IPA interviews tentatively fixed for Mar 1-2 | Workbook submission to IPA hinged on early completion of Type 2 cost estimates | Submission of final IPA report: 31st March
Compet. Review | Fixed kickoff meeting with PMO for Feb 23rd | Hold CR input kickoff meeting with PMO Feb 23rd. | Early and effective functional inputs | CR with VPs April 15th
 |  |  |  | DG3: end-April 2021

## Slide 11: SSAGS Step 3A, Week #5
Activity | Last week Promise and Actual Status | Look Ahead (next One week) | Issues/Help Required | Overall Target
Bank ability | Asset Leadership endorsed the 15 selected opportunities Opportunities further reduced to 11 and roadmap developed by Asset Team to mature the opportunities in time for ITR3/SAR3 Held meeting with Internal Finance Team to align on path to final Select Phase assessment | AF team to prepare reverse bankability schedule Asset Team to progress maturation of opportunities | Swamp Asset Team support for cost and volume ranges for STOG opportunities AF resource availability | Conclude internal bankability assessment: Feb 19th
ITR3/ SAR3 | Working to align final project scope for selected concept with CE in line with conclusions from the Competitive Scoping Workshop Obtain assurance for deterministic base case schedule (Awaiting Head Planning & Project Controls signoff after implementation of steers) Continued functional review of draft Production Promise Completed internal review of draft Subsurface Fact Sheet (SSFS). To be reviewed by SME Basis-for-Design: Invites and template sent for functional inputs ITR3/SAR3 Review Team selected. TOR send and pre-Review engagement planned for this week Held Brownfield Healthcheck Feb 3rd Held joint Technology Planning Workshop Feb 4th Draft Project Execution Strategy draft in progress (50%). Completion and review planned for this week | Contracting & Procurement Strategy Workshop with JV Partners & NCDMB. Date to be agreed with NAPIMS/BGR Complete and review Project Execution Strategy Signoff of Deterministic schedule Conclude Production Promise documentation Prepare Level 2 schedule Prepare Type 2 Cost Estimates Start to prepare pre-reads for ITR3/SAR3 | C&P Strategy Workshop contingent on successful alignment with JV Partners on Clustering initiative (Clear C&P plan for actualization desired) Alignment on final project scope | ITR3/SAR3: Feb 23-26
FDP | Continue input to the Seibou (~75%) and Kanbo (~60%) | Progress input to the Seibou (~85%) and Kanbo (~70%) FDPs | Effective functional inputs | Internal FDP signoff: Mar 5th FDPs to DPR: Mar 19th
IPA Bench marking | Continue input and collation to IPA workbooks (70%). Awaiting Cost and Schedule inputs. Analyst assigned from IPA team | Continue input and collation to IPA workbooks (80%) (Expected delivery date to IPA team Feb 19th) | Workbook submission to IPA hinged on early completion of Type 2 cost estimates | Submission of final IPA report: 31st March
Compet. Review | Focal points assigned to slides in overall CR pack. Will engage PMO for kickoff meeting | Hold CR input kickoff meeting with PMO | Early and effective functional inputs | CR with VPs April 15th
 |  |  |  | DG3: end-April 2021

## Slide 12: SSAGS Step 3A, Week #4
Activity | Last week Promise and Actual Status | Look Ahead (next One week) | Issues/Help Required | Overall Target
Bank ability | STOG Alignment Session held with Asset Team Asset team currently screening available basket of STOG opportunities for alignment with project timeline (15 opportunities identified) | Asset Leadership to validate identified opportunities AF team meeting for reverse bankability | Swamp Asset Team support for cost and volume ranges for STOG opportunities | Conclude internal bankability assessment: Feb 19th
ITR3/ SAR3 | Agree final scope for selected concept with CE Review and quantification of outstanding project risks (NTR-Q) Obtain assurance for deterministic base case schedule (Schedule sent to Head Planning & Project Controls. Implementing reviews) Production Promise (PP): Production forecast and project scope sent to OR&A Lead. Activity-Based Cost Model (ABCM) created. PP being developed (50%). Completed draft Subsurface Fact Sheet (SSFS) Basis-for-Design: Invites and template sent for functional inputs Clustering Campaign Workshop with JV Partners Jan 26th. CSRA Workshop Jan 27-28 Working with Assurance Team to select ITR3/SAR3 Review Team. TOR sent and awaiting team selection update. | Contracting & Procurement Strategy Workshop with JV Partners & NCDMB Feb 2nd Complete and review Production Promise Brownfield Healthcheck Feb 3rd SME review of draft SSFS Technology Planning Workshop Feb 4th Send out ITR3/SAR3 invitations to JV Partners | C&P Strategy Workshop contingent on successful alignment with JV Partners on Clustering initiative (Clear C&P plan for actualization desired) Alignment on final project scope | ITR3/SAR3: Feb 23-26
FDP | Continue FDP Sprint huddles for input to the Seibou (~75%) and Kanbo (~60%) FDPs | Progress input to the Seibou (~85%) and Kanbo (~70%) FDPs | Effective huddle participation | Internal FDP signoff: Mar 5th FDPs to DPR: Mar 19th
IPA Bench marking | Continue input and collation to IPA workbooks (70%) Extended PO to cover adjusted benchmarking duration. | Continue input and collation to IPA workbooks (80%) (Expected delivery date to IPA team Feb 19th) | Workbook submission to IPA hinged on early completion of Type 2 cost estimates | Submission of final IPA report: 31st March
Compet. Review | Received CR template from PMO and shared same with focal points Worked with PMO to update Review level to VPs. Initial invitations sent out for April 15th CR | Assign focal points to slides in overall CR pack |  | CR with VPs April 15th
 |  |  |  | DG3: end-April 2021

## Slide 13: SSAGS Step 3A, Week #3
Activity | Last week Promise and Actual Status | Look Ahead (next One week) | Issues/Help Required | Overall Target
ITR3/SAR3 | Agree final scope for selected concept with CE Close out review and quantification of outstanding project risks (NTR-Q) Conclude draft ITR3/SAR3 TOR and issue for review Obtain assurance for deterministic base case schedule (Schedule sent to Head Planning & Project Controls) | SPDC Portfolio Clustering Campaign & Standardization Initiative Workshop with JV Partners & NCDMB Jan 26th Contracting & Procurement Strategy Workshop with JV Partners & NCDMB Jan 29th (Feb 2nd) Work with Assurance Team to select Review Team Hold CSRA Workshop Jan 27th Initiate Production Promise documentation Initiate Basis-for-Design documentation | CSRA hinged on closure of NTR-Q (ER resource support key) C&P Strategy Workshop contingent on successful alignment with JV Partners on Clustering initiative (Clear C&P plan for actualization desired) | ITR3/SAR3: Feb 23-26
IPA Benchmarking | Obtain BOM signoff & submit commercial agreement to IPA team | Continue input and collation to IPA workbooks (Expected delivery date to IPA team Feb 19th) | Workbook submission to IPA hinged on early/ successful completion of CSRA/Type 2 cost estimates (ambitious timeline with Project Services support) | Submission of final IPA report: 31st March
Competitiveness Review | Agree week of April 15th with Local PMO for Competitiveness Review with EVPs | Engage PMO for updated CR template |  | CR with EVPs April 15th
FDP | Continue FDP Sprint huddles for input to the Seibou (~65%) and Kanbo (~55%) FDPs | Progress input to the Seibou (~75%) and Kanbo (~65%) FDPs | Effective huddle participation | Internal FDP signoff: Mar 5th FDPs to DPR: Mar 19th
 |  |  |  | DG3: end-April 2021