## SSAGS3A_Roadmap_Revised
SSAGS 3A Project: Revised Roadmap to DG3
|  |  | 2020-12-01 |  |  |  |  | 2021-01-01 |  |  |  | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  |  | 2021-04-01 |  |  |  | 2021-05-01
|  | Focal point | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4
Activity Description
| Well Concept Design Endorsement Session | Ajao/WE | 2020-12-01 Wk1: 3
| HAZID Workshop |  | 2020-12-01 Wk1: 3
| Social Performance Workshop |  | 2020-12-01 Wk2: 11
| NTR-Q Workshop |  | 2020-12-01 Wk3: 17
| Competitive scoping | Uju/CE | 2020-12-01 Wk4: 21
| Agree final scope for selected concept | Uju/CE | 2021-01-01 Wk3: 22
| Non-EPC cost modeling (manning profile, security requirements, logistics requirements, etc) | Uju/CE | 2021-01-01 Wk3: 22
| Close out NTR-Q | Idowu/ER | 2021-01-01 Wk3: 22
| Contracting & Procurement Strategy Workshop | Toni/CP | bar: 2021-01-01 Wk3
| ITR3/SAR3 TOR preparation and approval | Emeka/BOM | 2021-01-01 Wk3: 22
| Assurance team to select ITR3/SAR3 Review Team | Elliot/FEDM | 2021-01-01 Wk4: 29
| Assurance of deterministic schedule | Blessing/PS | 2021-01-01 Wk3: 22
| Risk Review and NTR-Q output | Kemi/PS | 2021-01-01 Wk4: 26
| CSRA Workshop | Kemi/PS | 2021-01-01 Wk4: 29
| SRA = Level 2 Schedule | Blessing/PS | 2021-02-01 Wk2: 12
| CRA (based on output of SRA) = Type 2 Cost Estimate | Lolade/PS | 2021-02-01 Wk2: 12
| IPA Benchmarking (submit commercial agreement) | Elliot/FEDM | 2021-01-01 Wk3: 20
| IPA Benchmarking (submission of workbooks) | Elliot/FEDM | 2021-02-01 Wk2: 12
| IPA Benchmarking (Conduct interviews) | Elliot/FEDM | 2021-02-01 Wk4: 26
| IPA Benchmarking (Issue Draft Report) | Elliot/FEDM | 2021-03-01 Wk4: 26
| IPA Benchmarking (Issue Final Report) | Elliot/FEDM | 2021-03-01 Wk5: 31
| Kanbo & Seibou FDP completion & endorsement | Emeka/BOM | 2021-03-01 Wk1: 5
| Submission of Kanbo and Seibou FDPs to DPR | Emeka/BOM | 2021-03-01 Wk3: 19
| Brownfield Healthcheck | Uju/CE | 2021-02-01 Wk1: 5
| Component-Level Benchmarking | Seun/FEE | 2021-02-01 Wk2: 12
| Update Cost Improvement Staircase | Tarryla/DP | 2021-02-01 Wk2: 12
| Basis for Design (BfD) | Uju/CE | 2021-02-01 Wk3: 19
| Selection of STOG candidate(s) | Emeka/BOM | 2021-02-01 Wk2: 12
| Prepare updated project economics | Ebong/Econs | 2021-02-01 Wk3: 19
| Run final Select Phase bankability | Elliot/FEDM | 2021-02-01 Wk3: 19
| ITR3/SAR3 invitations to JV Partners & DPR | Emeka/BOM | 2021-02-01 Wk1: 5
| Preparation of ITR3/SAR3 pre-reads | Emeka/BOM | 2021-02-01 Wk2: 12
| ITR3/SAR3 Dry-run | Tarryla/DP | 2021-02-01 Wk3: 19
| Project Execution Strategy (PES) | Alozie/PM | 2021-02-01 Wk2: 12
| RCCN | Nike/SSL | 2021-02-01 Wk1: 5
| Production Promise | Ahmadu/ORA | 2021-02-01 Wk1: 5
| Estimate and Schedule Fact Sheet (ESFS) | Akinbile/PS | 2021-03-01 Wk2: 12
| Subsurface Fact Sheet (SSFS) | Nike/SSL | 2021-03-01 Wk2: 12
| ITR3/SAR3 | Emeka/BOM | 2021-02-01 Wk4: 23-26
| PCP-Lite preparation & endorsement | Emeka/BOM | 2021-03-01 Wk1: 5
| PCP-Lite approval | Emeka/BOM | 2021-03-01 Wk3: 19
| Partner Engagement on Project Funding | Emeka/BOM | 2021-03-01 Wk4: 26
| Preparation of Competitiveness Review Slidepacks | Elliot/FEDM | 2021-03-01 Wk5: 31
| Competitiveness Review with in-country GMs | Elliot/FEDM | 2021-04-01 Wk1: 8
| Competitiveness Review with EVPs | Elliot/FEDM | 2021-04-01 Wk2: 15
| Preparation of DG3 DRB slidepack | Emeka/BOM | 2021-04-01 Wk3: 22
| DG3 | Emeka/BOM | bar: 2021-04-01 Wk4
| PCAP Closeout Statement | Emeka/BOM | 2021-05-01 Wk2: 14
| Project Handover | Elliot/FEDM | 2021-05-01 Wk3: 21
| DPR approval of FDPs | Emeka/BOM | 2021-05-01 Wk4: 28