## ActionLog
IMO RIVER GAS LIFT HEALTH CHECK / OPTIMIZATION WORKSHOP - ACTION LOG
Date of Workshop
2018-03-07
Agreed Time frames
Very Short Term: 2 weeks
Short term: 30 - 90 days
Medium term: 120 days
Long term: 6 months - 1 year
S/N | Issues | Actions to Address Isues | Action Party | WRFM Loop Pie | Timeline | No of Days to Due Date | Due Date
1 | GL Manifold In Place, Flow control loop not being maintained effectively | Create a maintenance plan for the Flow control loop (FCVs, transmitters, etc) | Udo Uzochukwu | Physical | 1 week | 7 | 2018-03-14
2 | Challenge in measuring Gas Lift rates during well test due to inability to integrate Delta V and SMART systems | Explore possibility of integrating Delta V and SMART System for Well Test volume measurement | Martins | Physical | 3 mnths | 90 | 2018-06-05
3 | Only 2 FCV Valves are automated | Revamping of IMOR Gaslift automation system (22 FCVs) Carry out system re-evaluation to be clear on what is required to totally automate the system, in terms of Cost, etc | Udo/Amos | Physical | 3 Mnths | 90 | 2018-06-05
5 | Conduit Stock | Identify conduits that have been on GL before and also provide a list of NF conduits for PTs to access the benefit of placing such NF conduits on GL | Mamoke/Success | Physical | 1 week | 7 | 2018-03-14
6 | GLL lines to wells in place; some leaking | Check GLL and FL integrity for all wells that can be Gaslifted | Idowu | Physical | 1 Month | 30 | 2018-04-06
7 | Cost of Restoring Vmonitors, CAO and SCADA not functional | Cost of Restoring Vmonitors, CAO and SCADA | Kevwe Okpubuluku | Physical | 14 Days | 14 | 2018-03-21
8 | Wet gas injected into wells | GL Manifold line flushing to prevent wet gas injection to wells | Operations, Uche | Physical | 30 Days | 30 | 2018-04-06
9 | BHP (FG) Survey | Identify wells on which BHP(FGs) are required | Gloria | Data Acquisition | 1 week | 7 | 2018-03-14
10 | Surface Data Gathering | Share standard GL surface data check list | Hassan | Data Acquisition | 2 days | 10 | 2018-03-17
12 | Metering & Production Allocation | Programmer to ensure that all identified GL candidates are coded properly in EC and ensure that allocation are done properly | Mamoke | Data Acquisition | Ongoing - continuous
13 | Gas Lift wells are choked back | Review list of GL wells in Imo and advice wells with chokes, and recommend if the wells can be operated on fully open choke setting | Gloria / Miete | Physical | 1 Week | 7 | 2018-03-14
14 | Well test Corollis meter cannot provide WCT readings | Configure Corollis well test meters to ensure it can read WCT | Udo | Data Acquisition | 30 Days | 30 | 2018-04-06
14.8077 | Validated GOR vs Rsi | Validate the GOR in the gaslifted wells relative to the modelled GOR/Rsi | Miete/Mamoke | Data | 30 Days | 30 | 2018-04-06
15.8901 | Lack of regular feedback for Wellhead pressure data | Production Ops teams should enusre that wellhead pressure data are regularly measured and reported to support all teams. | Obong Ben | Data | 2 Wks - Continuous |  | 2018-03-07
16.9725 | Skills development required for interpreting and modelling data | Ensure the availability of field ware gaslift, PU-RTO in place | Martins | Interpretation and modelling | continuous
18.0549 | Skills development required for interpreting and modelling data | Ensure Exception Based Surveillance (EBS) is implemented in the facility | Martins | Interpretation and modelling | 6 Mnths | 180 | 2018-09-03
19.1374 | Risk of omitting data acquistion points on GLL and FL | Scoping of data acquisition points on gaslift lines and flowines | Nmamkoche | Interpretation and modelling | 2 wks | 14 | 2018-03-21
20.2198 | PU and RTM models not updated | Build PU and RTM models as data becomes available | Mamoke | Interpretation and modelling | 6 mnths to 1 Year | 365 | 2019-03-07
21.3022 | Generating opportunities | Kick off gaslift in identified candidate wells (especially the quick wins, with minimal or no additional hardware requirement) | Miete / Idowu | Evaluating opportunities | 30 Days | 30 | 2018-04-06
22.3846 | There needs to be a clear strategy for realising the gaslift opportunities | Develop the staircase for the gaslift opportunities based on time, budget, execution capability and all other support required. | Gloria / Ben | Evaluating opportunities | 2 Wks | 14 | 2018-03-21
23.467 | Gaslift training for field production staff | Organise a handson training for the production ops staff | Ben | Evaluating opportunities | 30 Days | 30 | 2018-04-06
24.5495 | Coorporate gaslift training for field and office staff | Organise a handson gaslift training for all relevant staff facilitated by the coroporate Gaslift training course | Ben | Evaluating opportunities | 30 - 90 days | 90 | 2018-06-05
25.6319 | Snapshot of all production figures for Imo Rive conduits. | Mamoke to take a snapshot of all producing conduits as at today (14 Feb 2018) with all associated production data and share with all participants | Mamoke | Making decisions | 2 Days | 2 | 2018-03-09
26.7143 | Provision of integrated activity plan | Provide an integrated acitivity plan for the gaslift work | Ben / Gloria | Making decisions | 30 Days | 30 | 2018-04-06
27.7967 | Reactivation of automated gaslift system | Upload automated Gas lift volume into HMI and re-activate the automated gaslift system | Amos Martins/Udo | Making decisions | 30 Days | 30 | 2018-04-06
28.8791 | NO opt/rationalization strategy for GL | Develop Optimization / rationalization strategy for GL | Amos Martins | Making decisions | 30 Days | 30 | 2018-04-06
29.9615 | Lift Gas Metering | Lift Gas metering for individual wells | Udo | Making decisions | 30 Days | 30 | 2018-04-06
31.044 | WH accessories Check | Check WH accessories status of identified GL Candidates | Ogini | Execution | 30 Days | 30 | 2018-04-06
32.1264 | WH accessories cost estimation | CWI to provide cost estimate of WH accessories requiring repair/servicing/replacement | Conrad | Execution | 30 Days | 30 | 2018-04-06
33.2088 | RTO Critical spares - delay in delivery after odering | Develop a sparing philosophy for RTO critical spares and implement through C&P | Odu and Kevwe | Execution | 30 Days | 30 | 2018-04-06
34.2912 | GL Well Ops Envelop | Complete GL wells operating envelop | Miete | Execution | 30 Days | 30 | 2018-04-06
35.3736 | Project Delivery monitoring | Run this as a Cadence Action project with owners being BEN and GLORIA. Project to be feeding back weekly to management. Every one in this meeting is a part of the project delivery team. | Gloria and Ben | Execution | Effective now and Continuous
Formulas:
Due Date = +D8+[No of Days to Due Date]

## Attendance
| Venue of Workshop: | Shell RA, Conf Room
| Time | 9.00am - 4.00pm
ATTENDANCE
S/N | Name | Role
1 | Attoni, Success D SPDC-UPO/G/DNL | Reservoir Engineer
2 | Obong, Benjamin U SPDC-UPO/G/PLI | Production
3 | Akporuno, Mamoke SPDC-UPO/G/PSSH | Snr Programmer
4 | Oamen, Christopher A SPDC-UPO/G/PLI | PUM
5 | Udo, Uzochukwu SPDC-UPO/G/PLI | PACO
6 | Oginni, Abiodun I SPDC-UPO/G/PLI | Ops Supv
7 | Uche, Nduka J SPDC-UPO/G/PLI | OPS
8 | Offurum, Nmamkoche A SPDC-PTE/EUPE | Process WRFM
9 | Oboro, Richardson O SPDC-UPO/G/PLI | Production
10 | Famofo-Idowu, Olasunkanmi J SPDC-PTP/O/NA | Engineering
11 | Anyanwu, Chinedu SPDC-UPO/G/PSSH | Smartfield Engr
12 | Otoakhia, Iroboudu R SPDC-UPO/G/PSSH | Smartfield Engr
13 | Okpubuluku, Kevwe B SPDC-UPO/G/PSSH | Head PMC
14 | Erivona, Gloria O SPDC-UPO/G/DNL | IMOR FMT / Production Technologist
15 | Oruambo, Tamunomiete J SPDC-UPO/G/DNL | Production Technologist
16 | Nongo, Boniface T SPDC-UPO/G/PL | WRFM Lead
17 | Amos, Martins SPDC-UPO/G/PSSH | Smartfield Lead
18 | Jamabo, Ibinabo SPDC-UPO/G/PL | WRFM Support
19 | Aribisala, Ayodeji A SPDC-UPO/G/PLI | Operations
20 | Salisu, Hassan S SPDC-UPO/G/PLI | Operations
21 | Ezugworie, Chibogwu S SPDC-UPO/G/PL | Asset Mgr