## Opportunity Summary () (hidden)
[5 empty] | H1 2018 | Stretch 2018 | 2019-2020
| Tranche | Total | Activtity Type | Total | Immediate | Short Term | Mid Term | Long Term | Comments
Optimization (Flowing Wells) | Obigbo | 1250 | Bean Optimization | 250 | 250 | -
|  |  | Gas Lift Optimzation | WIP |  | -
| Agbada |  | Bean Optimization
|  |  | Gas Lift Optimzation | 1000 | 1000
Deferment Management (Within 90 day window) | Obigbo | 1600 | PSO (OGBN 38L/S, 20T) | 800 | 800
| Agbada |  | PSO | 800 | 800
Closed-in Well Reviews (Outside 90 day window) | Base AF | 10470 | Encroachment | 0 |  | 0
|  |  | FLRR/WHM | 3960 |  | 3960
|  |  | Rigless Well Intervention | 3810 |  | 3810
|  |  | Rig Activities | 2700 |  | 2700
| AF Emerging | 700 | Encroachment | 0 |  | 0
|  |  | FLRR/WHM | 700 |  | 700
|  |  | Rigless Well Intervention | 0 |  | 0
|  |  | Rig Activities | 0 |  | 0
| Others-Signed Proposal | 6315 | Encroachment | 0
|  |  | FLRR/WHM | 940 |  | 940
|  |  | Rigless Well Intervention | 4025 |  |  | 4025
|  |  | Rig Activities | 1350 |  |  |  | 1350
| Others-FUP (Unrisked) | 20940 | Encroachment | 7460 |  |  | 7460
|  |  | FLRR/WHM | 1130 |  |  | 1130
|  |  | Rigless Well Intervention | 8150 |  |  | 8150
|  |  | Rig Activities | 4200 |  |  |  | 4200
Type of Opportunity | Potential
Immediate | 2850 kbopd
Short Term | 12110 kbopd
Medium Term | 20765 kbopd
Long Term | 5550 kbopd

## Sheet1 (hidden)
WHM | Activity TYPE
CO LOG
FLRR
SCSSV
FLRR
CO LOG
CO LOG

## Analysis (hidden)
Field | (All)
Activity Type (Rig / Rigless) | (All)
Signed off? | (All)
Funding Vehicle (Base AF, AF Emerging, Other) | (All)
Recommended Activity | (All)
Row Labels | Sum of Potential, Oil (bopd)
Long Term | 2750
AGBD014L | 250
AGBD037T | 100
OBEL002T
OBEL005T | 500
OBGN014L | 50
OBGN017L | 250
OBGN028L | 350
OBGN028S | 0
OBGN029T | 350
OBGN032S | 250
OBGN049L | 200
OTAM001L | 250
OTAM001S | 200
Medium Term | 11240
AGBD004L | 50
AGBD004S | 100
AGBD006L | 150
AGBD006V | 75
AGBD010L | 50
AGBD010V | 75
AGBD012L | 50
AGBD015L | 50
AGBD015S | 0
AGBD019S | 250
AGBD025S | 700
AGBD030L | 100
AGBD031L | 250
AGBD032T | 1000
AGBD033L | 1000
AGBD036L | 100
AGBD038L | 100
AGBD046L | 100
AGBD053L | 75
ELWA016S | 800
ELWA017S | 400
ELWA018S | 550
OBEL003S | 150
OBGN005L | 240
OBGN005S | 150
OBGN009L | 90
OBGN009S | 80
OBGN010T | 600
OBGN024L | 150
OBGN024S | 300
OBGN026T | 40
OBGN027T | 350
OBGN033L | 250
OBGN035S | 15
OBGN036L | 40
OBGN037S | 30
OBGN039T | 115
OBGN045L | 35
OBGN048L | 400
OBGN051L | 100
OBGN051S | 130
OBGN054T | 250
OBGN055T | 200
OTAM006S | 50
UMUE004T | 1250
UMUE005L | 200
Short Term | 9280
AGBD013L | 100
AGBD013S | 250
AGBD016T | 400
AGBD018L | 150
AGBD018S | 150
AGBD026S | 400
AGBD034S | 250
AGBD035T | 150
AGBD039L | 350
AGBD041L | 350
AGBD041S | 100
AGBD042L | 300
AGBD042S | 400
AGBD043L | 350
AGBD043S | 200
AGBD044L | 300
AGBD050L | 410
AGBD050S | 90
AGBD054L | 100
AGBD054S | 100
AGBD056L | 250
AGBD058L | 500
AGBD070S | 400
ISUZ001L | 600
ISUZ001S | 200
OBGN025T | 400
OTAM007S | 120
UMUE005S | 500
UMUE015L | 300
UMUE022T | 150
AGBD024L | 400
OTAM007L | 560
Immediate Term | 3810
OBGN013L | 200
OBGN013S | 260
OBGN015T | 600
OBGN045S | 450
OBGN | 1000
AGBD | 1300
Grand Total | 27080

## PRJ2.5.30.36.44.48.51.55
IMOR Closed in Wells: 5S, 30L, 36L, 44L/S, 48L/S, 51L & 55S ) STOG Restoration Project Tracker(CIWR - 2).
S/N | Conduit | Pot Est (Bopd) | Well Status / Activity Summary | Scope | Action /Help required | Note
1 | IMOR005S | 200 | WHM and FLRR required. | 1. AVA ( Com-unit) vandalised). 2. No FL contiunity - Circa 1800 ft X 3" FL vandalised. | 1. Confirm scope / Cost and Carry out repairs / replacement of damaged line. (PLI/Asset Engrg) 2. Cost and Restore missing WHD accessories and 3. Open well to production and Test (PLI/WRFM/CWI ) (PLI/WRFM/CWI )
2 | IMOR036L | 350 | WHM and FLRR required. (A Quick win) | 1. WHD Accessories (AVA accessories, 3” FLSV Pilot) 2. No FL contiunity - Requires repairs at wellhead | 1.Cost and Restore missing WHD accessories and open well to production (PLI/WRFM/CWI ) 2. Confirm scope / Cost and Carry out repairs / replacement of damaged flowline. (PLI/Asset Engrg) | Make up 3'' FLSV'
3 | IMOR051L | 390 | FLRR & WHM (GLVI, Sand wash, wax Cut) required. | 1.No xmas tree 2.Full FL vandalised | 1. Replace flowline (Full Replacement) 2. Replace WHD and Accessoried. 3. Maintain enhanced surveillance and sustain production (WRFM/PLI) 4.Test well to confirm actual production.(PLI OPS)
4 | IMOR030L | 280 | WHM and FLRR required. | 1.Xmass tree valves ( Wing and survey valves) 2. Com-unit vandalised 3. 3" flowline gate valve. 4.Bean box 5. No FL contiunity - Circa 200 ft X 6" FL vandalised. | 1. Confirm scope / Cost and Carry out repairs / replacement of damaged Flowline. (PLI/Asset Engrg) 2.Cost and Restore missing WHD accessories and 3. Open well to production and Test (PLI/WRFM/CWI) | Swab from W/23S & 65L to fix Xma as tree v/vs, bn box
5 | IMOR044S | 235 | WHM and FLRR required. | 1. Ava-unit vandalised 2 Cameron safety valve Vandalised 3. Flowline completely vandalised | 1. Confirm scope / Cost and Carry out repairs / replacement of vandalised flowline line. (PLI/Asset Engrg) 2.Restore missing WHD accessories. 4. Open well to production and Test (WRFM/CWI ) | swab 2@FLSV from w/20
6 | IMOR055S | 150 | WHM required. (A Quick win) | 1.Xmass tree valves ( Wing and survey valves) 2. Com-unit vandalised 3. WHD Accessories | 1. Confirm Flowline Integrity. (PLI/Asset Engrg) 2. Confirm WHD eqipment Integrity; Cost and restore missing accessories; and open well to production (PLI/WRFM/CWI ) NB: FL: pressure tested with Well Gas from 8bar to 12 bar - holding. A dual Modified CoM unit would be sufficient to flow 55S & 57L wells.
7 | IMOR044L | 35 | WHM and FLRR required. | 1. Flowline completely removed. 2. WH valves and COM Unit vadalised. | 1. Confirm scope / Cost and Carry out repairs / replacement of damaged line. (PLI/Asset Engrg) 2.Cost and Restore missing WHD accessories and 3. Open well to production and Test (PLI/WRFM/CWI)
8 | IMOR048L | 250 | WHM and FLRR required. | 1.Xmass tree valves (Wing and survey valves) 2. Com-unit vandalised 3.WHD Accessories 4. No FL contiunity - Circa 800ft FL vandalised. | 1. Confirm scope / Cost and Carry out repairs / replacement of damaged Flowline. (PLI/Asset Engrg) 2.Cost and Restore missing WHD accessories and 3. Open well to production and Test (PLI/WRFM/CWI)
9 | IMOR048S | 280 | AF: Well closed in . WHM and FLRR required. | 1.Xmass tree valves (Wing and survey valves) 2. Com-unit vandalised 3. WHD Accessories 4. No FL contiunity - Circa 80 ft FL vandalised. | 1. Confirm scope / Cost and Carry out repairs / replacement of damaged Flowline. (PLI/Asset Engrg) 2.Cost and Restore missing WHD accessories and 3. Open well to production and Test (PLI/WRFM/CWI)
| Quickwins | 1015
|  | 2170 |  | Last Updated | 2018-01-06
Note on D3: Est based on last well test of 25/02/16.
Note on D4: Est based on last well test of 01/10/15.
Note on D7: Est based on the Last well test 05/04 15
Note on D8: Last tested: 12/11/16
Note on D9: Est based on the Last well test 05/04 15
Note on E11: Last Tested: 08/04/15

## PRJ1. 31.57.59 Tracker
IMOR Closed in Wells: 31S, 57L and 59T STOG Restoration Project Tracker(CIWR - 1).
S/N | Conduit | Tranches (Basket) | Pot Est (Bopd) | Well Status / Activity Summary | Scope | Action /Help required | Additional Note | Cost Estimate (=N=)
1 | IMOR057L | STOG (JV) | 500 | NON-AF. Well closed in. WHM required. A Quick win | 1. AVA ( Pump and Pilot vandalised) | 1.Cost and Restore missing WHD accessories and Open well to production and Test (PLI OPS/WRFM/CWI ): NB: FL pressure tested with Well Gas from 4bar to 5 bar. Gaslift line Pressurized at 50bar (holding). | A Modified CoM unit proposed to flow 57L wells. | TBA
2 | IMOR031S | NFW (JV) | 360 | NON-AF: Well closed in . FLRR required. | No FL contiunity - Leaking bunkering valve on 6" FL | 1. Confirm scope / Cost and Carry out repairs / replacement of vandalised Flowline. (PLI/Asset Engrg) 2. Open well to production and Test (PLI/WRFM/CWI) NB: Engineering work request signed off. To be closed out by rerouting Asset Eng'g team on site ASAP | Engineering Request Raised for repairs; Scoped awaiting feedback | TBA
3 | IMOR059T | NFW (JV) | 1300 | NON-AF: Well closed in . FLRR required. | No FL contiunity - Leaking Point reported on 08/05/18 FIM 2156045. | 1. Confirm scope / Cost and Carry out repairs / replacement of vandalised Flowline. (PLI/Asset Engrg) 2. Open well to production and Test (PLI/WRFM/CWI) Temporary repairs by clamping proposed for repairs after JIV pending Scoping and repaires by Asset Enginnering | Engineering Request to be raised for repairs; after JIV on 11/05/19 | TBA
| Total | Non-AF (2) | 2160 |  |  |  |  | TBA
| Total | AF (1) | 0
| Total | Total | 2160 |  | Last Updated | 2018-08-05
Note on F3: Est based on valid test 08/04/15
Note on E4: Based on last validated test of 9/12/2017
Note on E5: Based on last validated test of April 2018

## IMOR PU Original STOG LIST
IMO RIVER PU DNL Supported Strategy Workshop Candidates
Node | Field | Well | Conduit | Reservoir | FL available | GLL in place? | Xmas tree in place? | Revised Scope | Tranche_Dipo | Activity | Timing | Doability in 2018 | Time Frame | Revised Potential (bopd) | DNL Supported (Y/N) | Proposal Ready | Comment
Imo River | ISIMIRI | ISIM001 | ISIM001L | M6000D | N | N/A | Y | Flowline Replacement (0.4 km) [WHM Mantenance Required] | Base AF | FLRR/WHM | Immediate | Y | ST | 500 | Y | Signed-off
Imo River | IMO RIVER | IMOR004 | IMOR004T | D2000X | Y | N/A | Y | WHM [Pressure Test the FL and carryout sectional replacement if required] | Base AF | FLRR/WHM | Immediate | Y | ST | 400 | Y | Signed-off
Imo River | IMO RIVER | IMOR033 | IMOR033L | D2000X | N | Y [Status unknown] | Y | Vandalized Line. Full Replacement Agreed. WHM required | Base AF | FLRR/WHM | Immediate | Y | ST | 180 | Y | Signed-off
Imo River | IMO RIVER | IMOR048 | IMOR048L | D3000X | N | N/A | Y | Integrity Is Suspect Due To Age, No Active Use. Full Replacement Agreed. WHM Required | Base AF | FLRR/WHM | Immediate | Y | ST | 260 | Y | Signed-off
Imo River | IMO RIVER | IMOR036 | IMOR036L | D6000A | N | N/A | Y | WHM, FL Replacement/repair | Base AF | FLRR/WHM | Immediate | Y | ST | 300 | Y | Signed-off
Imo River | IMO RIVER | IMOR056 | IMOR056L | E3000A | N | N/A | N | Xmas Tree Replacement, FL Replacement | Base AF | FLRR/WHM | Immediate | Y | ST | 160 | Y | Signed-off
Imo River | NKALI | NKAL004 | NKAL004L | F2000P | N | N/A | N | Unsecuring, Xmas Tree Installation, CO Log, Re-perforation & Perforation Extension, Flowline Replacement | AF Emerging | Rigless Well Intervention | ST | Y | ST | 300 | Y | Signed-off
Imo River | IMO RIVER | IMOR005 | IMOR005S | D1000X | Y | N/A | Y | WHM, FL requires continuity checks and scoping | Wells Removed from IPSC | FLRR/WHM | Immediate | Y | ST | 177 | Y | N
Imo River | IMO RIVER | IMOR002 | IMOR002T | D3000X | Y | N/A | Y | WHM, FL requires continuity checks and scoping | Wells Removed from IPSC | FLRR/WHM | Immediate | Y | ST | 34 | Y | N
Imo River | IMO RIVER | IMOR036 | IMOR036S | D4000X | TBC | N/A | Y | WHM, FL requires continuity checks and scoping | Wells Removed from IPSC | FLRR/WHM | Immediate | Y | ST | 200 | Y | N
Imo River | IMO RIVER | IMOR013 | IMOR013L | D6000A | Y | N/A | Y | WHM, Sand wash and open up with optimized bean | Wells Removed from IPSC | Rigless Well Intervention | Immediate | Y | ST | 200 | Y | N
Imo River | IMO RIVER | IMOR057 | IMOR057L | D6000P | TBC | N/A | Y | WHM, FL requires continuity checks and scoping | Wells Removed from IPSC | FLRR/WHM | Immediate | Y | ST | 500 | Y | N
Imo River | IMO RIVER | IMOR018 | IMOR018L | D8000A | TBC | N/A | Y | WHM, FL requires continuity checks and scoping | Wells Removed from IPSC | FLRR/WHM | Immediate | Y | ST | 61 | Y | N
Imo River | IMO RIVER | IMOR030 | IMOR030L | D8000N | TBC | N/A | Y | WHM, FL requires continuity checks and scoping | Wells Removed from IPSC | FLRR/WHM | Immediate | Y | ST | 250 | Y | N
Imo River | IMO RIVER | IMOR044 | IMOR044S | D9000N | TBC | N/A | Y | WHM, FL requires continuity checks and scoping | Wells Removed from IPSC | FLRR/WHM | Immediate | Y | ST | 200 | Y | N
Imo River | IMO RIVER | IMOR055 | IMOR055S | D1000X | TBC | N/A | Y | WHM, FL requires continuity checks and scoping | Wells Removed from IPSC | FLRR/WHM | Immediate | Y | ST | 150 | Y | N
Imo River | IMO RIVER | IMOR013 | IMOR013S | D3200X | TBC | N/A | Y | WHM, FL requires continuity checks and scoping | Wells Removed from IPSC | FLRR/WHM | Immediate | Y | ST | 100 | Y | N
[13 empty] | Total | 1872