## Slide 1
Key milestones: Date
PI Server Remediation 20th Aug.2020
Mobilization(OTC) 24th Aug. 2020
Server Installation 1st Sept. 2020
Configuration 8th Sept. 2020
Integration to PI 15th Sept.2020
PI Process Book Creation 22nd Sept 2020
Data Validation 1st Oct. 2020
Project Sponsor: Meshach Maichibi (West Asset Manager)
Project Owner: Busari Abiodun (Project OPS Mgr West)
Project Lead: Martins Amos (Lead Smart Field)
Project Members: Otoakhia Iroboudu
Vincent Levi
    Okolie Emmanuel
    Oboh John
Escravos Production and Rotating Equipment Real time data integration to PI is an enabler for the deployment of SmartConnect and other real time application.
This integration to PI will actualize the opportunity to reduce unscheduled deferment associated with equipment failure as a result of Real time data availability to enhance the capability to measure equipment status and performance in the above facilities
Early warning capability associated with the data acquisition in the implemented facility reduces the possibility of catastrophic breakdown of equipment which would result in high cost of corrective maintenance.
Background / Business Case
ENABLER (Carryout ESCRAVOS Production and Equipment Realtime Data Integration to PI ) by October 2020
Availability of Equipment Real time data for Smart connect implementation
Improved reliability from proactive process monitoring
Production and Equipment Performance remote monitoring anywhere + PMC surveillance
Sign Off
Milestone Deliverables
Current Condition
Potential Benefits
Gas production data from the main fuel gas scrubber are currently inputted manually into the Energy Component (EC) by the field operators and supported by the various Asset Programmers who then enter key data on web Xplore for EC. This approach is laborious and prone to error.
This change aim to equip the main fuel gas scrubber to enable remote monitoring of the following process parameters: temperature, pressure and flow rates for gas used.