## Slide 1
Key milestones: Date
WO/PO Creation 4th May 2020
Mobilization 8th Jun 2020
Tunu Integration 15th Jun 2020
Benisede Integration 22nd Jun 2020
Opukushi Integration 8th Jul 2020
Ogbotogbo Integration 3rd Aug 2020
Data Validation 17th Aug 2020
Project Sponsor: Meshach Maichibi (West Asset Manager)
Project Owner: Busari Abiodun (Project OPS Mgr West)
Project Lead: Martins Amos (Lead Smart Field)
Project Members: Otoakhia Iroboudu
Vincent Levi
    Okolie Emmanuel
    Oboh John
Tunu Node Rotating Equipment Real time data integration to PI is an enabler for the deployment of SmartConnect in Tunu node critical rotating rotating equipment’.
The Reliability Engineering team has identified a total of 1463 tags ( For Gas Turbine ,Generator, Screw /Centrifugal /Reciprocating Compressor to be integrated.
This integration to PI will actualize the opportunity to reduce unscheduled deferment associated with equipment failure as a result of Real time data availability to enhance the capability to measure equipment status and performance in the above facilities
Early warning capability associated with the data acquisition in the implemented facilities reduces the possibility of catastrophic breakdown of equipment which would result in high cost of corrective maintenance.
Background / Business Case
Integrate Tunu Node Rotating Equipment Realtime Data into PI by August 2020
Availability of Equipment Real time data for Smart connect implementation
Equipment Performance surveillance in PMC
Sign Off
Milestone Deliverables
 | Facility | Tags on DCS not on PI | Tags not DCS & PI
Condensate Flash Gas Compressor | Tunu | 21 | 43
 | Benisede | 21 | 30
 | Okpukushi | 21 | 1
 | Ogbotobo | 21 | 30
AG Gas Compressor | Tunu | 100 | 53
Export Gas Compressor | Tunu | 86 | 46
Gas Generator ( Engine Driven) | Benisede | 60 | 96
 | Okpukushi | 60 | 96
 | Ogbotobo | 45 | 90
GTG | Tunu | 96 | 145
AG Booster Compressor | Tunu | 0 | 58
 | Benisede | 0 | 75
 | Okpukushi | 0 | 105
 | Ogbotobo | 0 | 64
Total |  | 531 | 932
Current Condition
Potential Benefits