## ProjectSchedule
| Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | FMS/EFMS Phase 1 and 2 Project Implementation Plan | [5 empty] | * These actions will be continuous
Group 1 - PILOT 18 security vessels (EFMS) Group 2 -PILOT 7 Vessels (EFMS) Group 3 - PILOT 13 Vessels (FMS) Group 4 - Rest of the SPDC fleet (112 vessels)
| Enter Company Name in cell B2. | [31 empty] | Completed
| Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  | Project Start: |  | 2020-06-15
| The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2020-06-15 | [6 empty] | 2020-06-22 | [6 empty] | 2020-06-29 | [6 empty] | 2020-07-06 | [6 empty] | 2020-07-13 | [6 empty] | 2020-07-20 | [6 empty] | 2020-07-27 | [6 empty] | 2020-08-03 | [6 empty] | 2020-08-10 | [6 empty] | 2020-08-17 | [6 empty] | 2020-08-24 | [6 empty] | 2020-08-31 | [6 empty] | 2020-09-07 | [6 empty] | 2020-09-14 | [6 empty] | 2020-09-21 | [6 empty] | 2020-09-28 | [6 empty] | 2020-10-05 | [6 empty] | 2020-10-12 | [6 empty] | 2020-10-19 | [6 empty] | 2020-10-26 | [6 empty] | 2020-11-02 | [6 empty] | 2020-11-09 | [6 empty] | 2020-11-16 | [6 empty] | 2020-11-23 | [6 empty] | 2020-11-30 | [6 empty] | 2020-12-07 | [6 empty] | 2020-12-14 | [6 empty] | 2020-12-21 | [6 empty] | 2020-12-28 | [6 empty] | 2021-01-04 | [6 empty] | 2021-01-11 | [6 empty] | 2021-01-18 | [6 empty] | 2021-01-25 | [6 empty] | 2021-02-01 | [6 empty] | 2021-02-08 | [6 empty] | 2021-02-15 | [6 empty] | 2021-02-22 | [6 empty] | 2021-03-01 | [6 empty] | 2021-03-08 | [6 empty] | 2021-03-15 | [6 empty] | 2021-03-22 | [6 empty] | 2021-03-29 | [6 empty] | 2021-04-05 | [6 empty] | 2021-04-12 | [6 empty] | 2021-04-19 | [6 empty] | 2021-04-26 | [6 empty] | 2021-05-03 | [6 empty] | 2021-05-10
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2020-06-15 to 2021-05-16
S/N | s/n | KEY ACTIONS | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2020-06-15 to 2021-05-16
L3 Movement
1 |  | Conclude implementation Plan | Amina and Jonathan.B | 0% | 2020-06-19 | 2020-06-24
2 |  | Secure approval to move to L3 | Amina | 0% | 2020-06-24 | 2020-06-25
Group 1 - 18 security vessels (EFMS) Phase 1 Wave 23003
EFMS reporting
1 |  | Advise Shell EFMS focal point to receive data from vendor and commence training | Tony Woghiren | 100% | 2020-06-22 | 2020-06-25
2 |  | Provide March and mid-June monthly fuel consumption data from manual input * | Paul Eaton | 50% | 2020-06-19 | 2020-06-30
3 |  | Start receiving EFMS data and share information with the team | Paul Eaton | 0% | 2020-06-26 | 2020-07-03
4 |  | Review EFMS data with the logistics and data analytics team to determine gap between best practice and performance* | Tony Woghiren, Johan and Ikemefula | 0% | 2020-06-03 | 2020-07-10
5 |  | Work with the vendor to close the gap | Yemi.O and Tony.W | 0% | 2020-07-10 | 2020-08-03
6 |  | Ratify savings figure with Finance before banking | Tony Woghiren | 0% | 2020-08-07 | 2020-08-10
7 |  | Start Banking savings of identified gaps in Wave | Tony Woghiren | 0% | 2020-08-10 | 2020-08-15
8 |  | Placement of Contract for an independent Opsealog system | Tony Woghiren | 0% | 2020-06-01 | 2020-07-15
9 |  | Implementing Opsealog solution | Jonathan. B and Tony.W | 0% | 2020-08-01 | 2020-11-06
10 |  | Monitoring and Reporting of remote independent output | Jonathan. B and Tony.W | 0% | 2020-11-06 | 2020-11-23
EFMS Installation and activation
|  | Ensure 3 vessels (A20, A80 and Avery) have EFMS installed and activated | Yemi.O | 80% | 2020-06-01 | 2020-06-30
|  | Secure 100% Installation and activation of eFMS on the remaining 6 vessels | Yemi.O | 67% | 2020-07-10 | 2020-07-17
|  | Provide list of EFMS systems being used by contracted vessel owners | Yemi.O & Tony.W | 10% | 2020-06-25 | 2020-07-05
Group 2 -7 Vessels (EFMS) Phase 2 Wave 22885
EFMS reporting
1 |  | Nominate Shell focal points that will be receiving EFMS data | Jonathan. B | 100% | 2020-06-19 | 2020-06-26
2 |  | Provide March, April, May and June monthly fuel consumption data from manual input for PSVs and AHTS | Paul E | 50% | 2020-06-19 | 2020-06-30
3 |  | Start receiving EFMS data and share information with the team | Paul E | 0% | 2020-06-22 | 2020-06-30
4 |  | Review EFMS data with the logistics and data analytics team to determine KPI* | Tony Woghiren, Johan and Ikemefula | 0% | 2020-06-22 | 2020-06-30
5 |  | Work with the vendor to close the gap | Kunle.M and Tony.W | 0% | 2020-07-03 | 2020-08-03
6 |  | Ratify savings figure with Finance before banking | Amina.S | 0% | 2020-07-06 | 2020-07-07
7 |  | Start Banking savings of identified gaps in Wave | Amina.S | 0% | 2020-07-07 | 2020-07-10
EFMS Installation and activation
1 |  | Issue EFMS implementation instruction letters to PSVs and AHTS vessel owners | Emmanuel. A | 100% | 2020-06-19 | 2020-06-22
2 |  | Secure 100% Installation and activation of eFMS on the remaining 4 vessels | Kunle.M | 67% | 2020-06-01 | 2020-07-17
Group 3 -13 Vessels (FMS) - Phase 2 Wave 22885
FMS reporting, Design and VSM
1 |  | Provide March, April, May and June monthly fuel consumption data from manual input for LHT and PCs* | Kunle.M | 50% | 2020-06-19 | 2020-06-30
2 |  | Review 1st level FMS data with the logistics and data analytics team | Amina, Johan and Ikemefula | 0% | 2020-06-22 | 2020-07-13
3 |  | Conduct SIPOC on the terminal vessel fuel management process (working with the transformation team) to identify key stakeholders | Elomense. A, Valentine. O, Amina and Fasakin | 0% | 2020-06-26 | 2020-07-07
4 |  | Conduct value stream mapping session on the terminal vessel fuel management process (working with the transformation team) to identify the opportunities to eliminate waste in the fuel management system. | Elomense. A, Valentine. O, Amina and Fasakin | 0% | 2020-07-01 | 2020-07-03
5 |  | Share documented findings from the VSM workshop | Elomense. A, Valentine. O, Amina and Fasakin | 0% | 2020-07-03 | 2020-07-08
6 |  | Braing storming - Develop fuel monitoring and reporting process for the non-EFMS compatible vessels relying on insights from the VSM | Elomense. A and Fasakin | 0% | 2020-07-08 | 2020-07-15
7 |  | Engage key stakeholders with findings | Jonathan Boyle, Valentine. O and Amina | 0% | 2020-07-17 | 2020-07-22
8 |  | Management of change on existing process | Jonathan Boyle and Valentine.O | 0% | 2020-07-23 | 2020-08-01
9 |  | Ratify savings figure with Finance before banking | Amina.S | 0% | 2020-07-24 | 2020-07-29
10 |  | Start Banking savings of identified gaps in Wave | Amina.S | 0% | 2020-07-29 | 2020-07-31
FMS Installation and activation
1 |  | Secure 100% Installation of New FMS on all 13 vessels | Yemi.O | 0% | 2020-07-10 | 2020-07-21
Group 4 - Rest of the fleet (112 vessels) - Phase 2 Wave 22885
EFMS/FMS EFMS reporting
1 |  | Verify the full list of vessels that don't require EFMS | Olamide. O and Daniel. A | 0% | 2020-06-23 | 2020-07-26
2 |  | Confirm which of the non-EFMS compatible vessels have existing fuel monitoring and reporting system | Olamide. O and Daniel. A | 0% | 2020-06-26 | 2020-07-03
3 |  | Discussions on required resource (e.g Full/Part time, Collation and analytics) and securing management support | Jonathan, Amina and Tony | 30% | 2020-06-26 | 2020-07-10
EFMS/FMS installation and activation
1 |  | Issue EFMS implementation instruction letters to the identified vendors that are EFMS compatible | Emmanuel. A | 30% | 2020-06-30 | 2020-07-03
2 |  | Secure 100% Installation of New FMS on identified vessels | Jonathan, Yemi and Kunle | 0% | 2020-07-10 | 2020-11-01
3 |  | Secure 100% Installation of EFMS on identified vessels | Jonathan, Yemi and Kunle | 0% | 2020-07-10 | 2020-09-21
4 |  | Engage key stakeholders with findings | Jonathan Boyle, Valentine. O and Amina | 0% | 2020-07-17 | 2020-07-22
5 |  | Management of change on existing process | Jonathan Boyle and Valentine.O | 0% | 2020-07-23 | 2020-08-05
This is an empty row
| This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one