## Sequence Details
April 2024 Signed WRFM Sequence: Fit4 LiP Activity Update
Description | Status | Type | Spread | Sub Spread | Asset | Asset Node | Pot (bopd/MMscfd) | Well Name | Hydrocarbon (HC) Type | Activity Legend | Activity Duration | Planned Start Date | Planned Finish Date | Column1 | Column2
WIRELINE | Ongoing | WL | 7 | WIRELINE | East |  |  |  | OIL | CWI Well Integrity | 240 | 2024-03-17 | 2024-11-12
OGUT 14 AC9 | Completed | WL | 7 | WIRELINE | East | Rumuahia |  |  | OIL | CWI Well Integrity | 8 | 2023-04-23 | 2023-05-01
RUMU 3L CM | Completed | WL | 7 | WIRELINE | East | Rumuahia |  |  | OIL | CWI Well Integrity | 15 | 2023-07-16 | 2023-07-31
2 CMs (OBEL 1,6) | Completed | WL | 7 | WIRELINE | East | Rumuahia |  |  | OIL | CWI Well Integrity | 7 | 2023-10-29 | 2023-11-05
RUMU 3L Well Kill & Chemical Plug Placement | Completed | WL | 7 | WIRELINE | East | Rumuahia |  | RUMU003L | OIL | CWI Well Integrity | 9 | 2023-11-26 | 2023-12-05
7 SECURING (OGUT12,14,16,23,27,28): 4 CM (OGUT2,26,28);OGUT17S - Well kill & Chem. Plug; OGUT16 SG | Completed | WL | 7 | WIRELINE | East | Rumuahia | 0 |  | OIL | CWI Well Integrity | 77 | 2023-12-31 | 2024-03-17
5 SECURING (AHIA1,2,4,5,7): 2 CM (AHIA7,13) | L3 - Doable | WL | 7 | WIRELINE | East | Rumuahia | 0 |  | OIL | CWI Well Integrity | 15 | 2024-03-17 | 2024-04-01
10 SECURING (OGUT 1,2, 3,4,5,6,7,8,10, 26) | L3 - Doable | WL | 7 | WIRELINE | East | Rumuahia | 0 |  | OIL | CWI Well Integrity | 45 | 2024-04-01 | 2024-05-16
MINI 8/9 TRSCSSV/Straddle | L3 - Doable | WL | 7 | WIRELINE | East | Rumuahia | 0 |  | OIL | CWI Well Integrity | 16 | 2024-06-28 | 2024-07-14
ETEL 9T Xmas-tree Replacement (N2 Lift Contingency) [NOT DELIVERED IN 2024] | Completed | CT | 7 | COILED TUBING (1.25") | East | GBAR/KC | 350 | ETEL009T | OIL | CWI STOG | 8 | 2023-12-24 | 2024-01-01
27 wells CM (7 Ahia, 4 Minita, 3 Obele, 12 Oguta) | L3 - Doable | WL | 7 | WIRELINE | East | Rumuahia |  |  | OIL | CWI Well Integrity | 36 | 2024-05-23 | 2024-06-28
AHIA 3S SG | L3 - Doable | WL | 7 | WIRELINE | East | Rumuahia | 0 | AHIA003S | OIL | CWI Data Acquisition | 8 | 2024-10-21 | 2024-10-29
KOMA 2 Nitrogen lift Injection (GNC) [NOT REPORTED BY WRFM, ALLOCATED TO GNC PROJECT TEAM] | Completed | CT | 9 | COILED TUBING (1.75", 1.50") | East | GBAR/KC | 1 | KOMA002T | GAS | CWI STOG | 9 | 2024-01-07 | 2024-01-16
COILED TUBING (1.25") | Ongoing | CT | 7 | COILED TUBING (1.25") | East |  |  |  | OIL | CWI STOG | 364 | 2024-05-13 | 2025-05-12
KOMA 5 Nitrogen lift Injection (GNC | Completed | CT | 9 | COILED TUBING (1.75", 1.50") | East | GBAR/KC | 1 | KOMA005T | GAS | CWI STOG | 9 | 2024-01-16 | 2024-01-25
KOMA 6 Nitrogen lift Injection (GNC) [NOT REPORTED BY WRFM, ALLOCATED TO GNC PROJECT TEAM] | Completed | CT | 9 | COILED TUBING (1.75", 1.50") | East | GBAR/KC | 1 | KOMA006T | GAS | CWI STOG | 9 | 2024-01-25 | 2024-02-03
OPNO 21T [LiP Restoration] | Completed | WL | 6 | SLICKLINE | West | Southern Swamp | 600 | OPNO021T | OIL | CWI STOG | 6 | 2024-01-30 | 2024-02-05
OPNO 5S Quit Well Rest. | Completed | WL | 6 | SLICKLINE | West | Southern Swamp | 500 | OPNO005S | OIL | CWI STOG | 9 | 2024-02-01 | 2024-02-10
FORC 84L GLVCO (LAND) | Completed | WL | 3 | WIRELINE | West | Forcados | 200 | FORC084L | OIL | CWI STOG AF Maintenance | 6 | 2024-02-05 | 2024-02-11
KOMA 7 Nitrogen lift Injection (GNC) [NOT REPORTED BY WRFM, ALLOCATED TO GNC PROJECT TEAM] | Completed | CT | 9 | COILED TUBING (1.75", 1.50") | East | GBAR/KC | 1 | KOMA007T | GAS | CWI STOG | 9 | 2024-02-03 | 2024-02-12
FORC 66S Bulkline 3 Sectional Replacement | Completed | FL | 2 | FLOWLINE | West | Forcados | 230 | FORC066S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 11 | 2024-02-01 | 2024-02-12
KOMA 8 Nitrogen lift Injection (GNC) [NOT REPORTED BY WRFM, ALLOCATED TO GNC PROJECT TEAM] | Completed | CT | 9 | COILED TUBING (1.75", 1.50") | East | GBAR/KC | 1 | KOMA008T | GAS | CWI STOG | 9 | 2024-02-12 | 2024-02-21
FORC 48L Sand Clean-out/SCON/Perf Extension | Completed | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 500 | FORC048L | OIL | CWI STOG | 71 | 2023-12-18 | 2024-02-27
MINI 4L WHM, Milling, Sand Clean-out,WSO, Perf. Ext., TTSAS | L3 - Doable | CT | 7 | COILED TUBING (1.25") | East | Rumuahia | 300 | MINI004L | OIL | CWI STOG | 28 | 2024-12-23 | 2025-01-20
MINI 3S WHM, N2 lifting and open-up | L3 - Doable | CT | 7 | COILED TUBING (1.25") | East | Rumuahia | 200 | MINI003S | OIL | CWI STOG | 21 | 2025-01-20 | 2025-02-10
OBEL 1L WHM, SCON,Perforation Extension,N2 lifting | L3 - Doable | CT | 7 | COILED TUBING (1.25") | East | Rumuahia | 350 | OBEL001L | OIL | CWI STOG | 28 | 2025-02-10 | 2025-03-10
Move to OGUT: OGUT 25T Usecuring, N2 lifting, WRSCSSV, Open-up | L3 - Doable | CT | 7 | COILED TUBING (1.25") | East | Rumuahia | 500 | OGUT025T | OIL | CWI STOG | 28 | 2025-03-10 | 2025-04-07
OGUT 16S WHM, with repaired one, N2 lifting and Open up | L3 - Doable | CT | 7 | COILED TUBING (1.25") | East | Rumuahia | 200 | OGUT016S | OIL | CWI STOG | 21 | 2025-04-07 | 2025-04-28
OGUT 12T WHM, Xmas Tree C/O, Unsecuring and N2 lift | L3 - Doable | CT | 7 | COILED TUBING (1.25") | East | Rumuahia | 200 | OGUT012T | OIL | CWI STOG | 14 | 2025-04-28 | 2025-05-12
EMBEDDED CREW | Ongoing | WH | 7 | EMBEDDED CREW | East |  |  |  | OIL | CWI Well Integrity | 92 | 2024-02-25 | 2024-05-27
56 PMs: AHIA, ANOH, MINI, OBEL, RUMUAHIA, UBIE, OGUT, ONITE | Ongoing | WH | 7 | EMBEDDED CREW | East | Rumuahia |  |  | OIL | CWI Well Integrity | 92 | 2024-02-25 | 2024-05-27
FLOWLINE 1 | Ongoing | FL | 7 | FLOWLINE 1 | East |  |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 307 | 2024-05-02 | 2025-03-05
UBIE 8T and 3L Flowline Integrity Tests | L3 - Doable | FL | 7 | FLOWLINE 1 | East | Rumuahia | 0 |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 14 | 2024-05-02 | 2024-05-16
AHIA 3S FLOWLINE REPAIR | L3 - Doable | FL | 7 | FLOWLINE 1 | East | Rumuahia | 0 | AHIA003S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 22 | 2024-09-23 | 2024-10-15
AHIA 7L FLOWLINE REPAIR | L3 - Doable | FL | 7 | FLOWLINE 1 | East | Rumuahia | 0 | AHIA007L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 29 | 2024-10-14 | 2024-11-12
AHIA 11L FLOWLINE REPAIR | L3 - Doable | FL | 7 | FLOWLINE 1 | East | Rumuahia | 0 | AHIA011L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 29 | 2024-11-11 | 2024-12-10
MINI 4L FLOWLINE REPAIR | L3 - Doable | FL | 7 | FLOWLINE 1 | East | Rumuahia | 0 | MINI004L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 29 | 2024-12-09 | 2025-01-07
MINI 3S FLOWLINE REPAIR | L3 - Doable | FL | 7 | FLOWLINE 1 | East | Rumuahia | 0 | MINI003S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 36 | 2025-01-06 | 2025-02-11
OGUT 16S FLOWLINE REPAIR | L3 - Doable | FL | 7 | FLOWLINE 1 | East | Rumuahia |  | OGUT016S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 23 | 2025-02-10 | 2025-03-05
FLOWLINE 2 | Ongoing | FL | 7 | FLOWLINE 2 | East |  |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 85 | 2024-09-23 | 2024-12-17
AHIA 14S INTEGRITY TEST | L4 - Certain | FL | 7 | FLOWLINE 2 | East | Rumuahia | 0 | AHIA014S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 8 | 2024-09-23 | 2024-10-01
AHIA 1S FLOWLINE REPAIR | L3 - Doable | FL | 7 | FLOWLINE 2 | East | Rumuahia | 0 | AHIA001S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 36 | 2024-09-30 | 2024-11-05
AHIA 9S FLOWLINE REPAIR | L3 - Doable | FL | 7 | FLOWLINE 2 | East | Rumuahia | 0 | AHIA009S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 43 | 2024-11-04 | 2024-12-17
FLOWLINE 3 | Ongoing | FL | 7 | FLOWLINE 3 | East |  |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 194 | 2024-05-02 | 2024-11-12
OBEL 3L FLOWLINE HOOK UP ARM FAB/INSTALL | L3 - Doable | FL | 7 | FLOWLINE 3 | East | Rumuahia | 0 | OBEL003L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 16 | 2024-05-02 | 2024-05-18
AHIA 5L FLOWLINE REPAIR | L3 - Doable | FL | 7 | FLOWLINE 3 | East | Rumuahia | 0 | AHIA005L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 29 | 2024-10-14 | 2024-11-12
E-LINE & SLICKLINE | Ongoing | WL | 8 | E-LINE & SLICKLINE | East |  |  |  | OIL | CWI Well Integrity | 88 | 2024-04-26 | 2024-07-23
SOKU 31 WELL KILL/SECURING | Completed | WL | 8 | E-LINE & SLICKLINE | East | Soku/NunR |  | SOKU031L | OIL | CWI Well Integrity | 6 | 2023-01-06 | 2023-01-12
SOKU: 13 SGs | Completed | WL | 8 | E-LINE & SLICKLINE | East | Soku/NunR |  |  | OIL | CWI Data Acquisition | 26 | 2023-02-05 | 2023-03-03
DBUC 1L, 2T SGs | Completed | WL | 8 | E-LINE & SLICKLINE | East | Soku/NunR |  |  | OIL | CWI Data Acquisition | 7 | 2023-10-15 | 2023-10-22
DBUC9/15T SCSSSV Changeout | Completed | WL | 8 | E-LINE & SLICKLINE | East | Soku/NunR |  |  | OIL | CWI Well Integrity | 6 | 2023-10-08 | 2023-10-14
SOKU 48L, Corrosion Logs | Completed | WL | 8 | E-LINE & SLICKLINE | East | Soku/NunR |  | SOKU048L | OIL | CWI Well Integrity | 7 | 2023-12-03 | 2023-12-10
17 SECURING (SOKU4,5,6,9,10,11,12,16,19,25,26,32,35,40,44,55,56,) 6 CM (SOKU28,29,36,47,55,56) | Completed | WL | 8 | E-LINE & SLICKLINE | East | Soku/NunR |  |  | OIL | CWI Well Integrity | 42 | 2023-10-22 | 2023-12-03
SECURING: BELE 2, 3, 5, 7, 8, 9, 10; CM: 6 Wells | L3 - Doable | WL | 8 | E-LINE & SLICKLINE | East | Soku/NunR | 0 |  | OIL | CWI Well Integrity | 28 | 2024-06-25 | 2024-07-23
SOKU 46T (SG/FG/BHP) | Completed | WL | 8 | E-LINE & SLICKLINE | East | Soku/NunR | 0 | SOKU046T | OIL | CWI Data Acquisition | 8 | 2024-03-12 | 2024-03-20
SOKU 53T (SG/FG/BHP) | Completed | WL | 8 | E-LINE & SLICKLINE | East | Soku/NunR | 0 | SOKU053T | OIL | CWI Data Acquisition | 8 | 2024-03-19 | 2024-03-27
SOKU 17T NPL log | L3 - Doable | WL | 8 | E-LINE & SLICKLINE | East | Soku/NunR | 0 | SOKU017T | OIL | CWI Data Acquisition | 8 | 2024-04-26 | 2024-05-04
SOKU 10L CO log | L3 - Doable | WL | 8 | E-LINE & SLICKLINE | East | Soku/NunR | 0 | SOKU010L | OIL | CWI Data Acquisition | 8 | 2024-05-03 | 2024-05-11
SOKU 34T, 41T, 42T, 45T, 47T, 51T, 52T SG | Completed | WL | 8 | E-LINE & SLICKLINE | East | Soku/NunR | 0 |  | OIL | CWI Data Acquisition | 17 | 2024-03-26 | 2024-04-12
CM: SOKU 47, 49S & 30 Wells | L3 - Doable | WL | 8 | E-LINE & SLICKLINE | East | Soku/NunR | 0 |  | OIL | CWI Well Integrity | 10 | 2024-05-17 | 2024-05-27
CM: 9 DBUC Wells | L3 - Doable | WL | 8 | E-LINE & SLICKLINE | East | Soku/NunR | 0 |  | OIL | CWI Well Integrity | 15 | 2024-06-10 | 2024-06-25
COILED TUBING (1.5") | Ongoing | CT | 8 | COILED TUBING (1.5") | East |  |  |  | OIL | CWI STOG | 300 | 2024-04-26 | 2025-02-20
DBUC 2T WSO, PERF, SCON, N2 LIFT | Completed | CT | 8 | COILED TUBING (1.5") | East | Soku/NunR | 650 | DBUC002T | OIL | CWI STOG AF Maintenance | 35 | 2023-10-29 | 2023-12-03
DBUC 1L WHM, PERF, SCON, N2 LIFT | Completed | CT | 8 | COILED TUBING (1.5") | East | Soku/NunR | 450 | DBUC001L | OIL | CWI STOG | 28 | 2023-12-03 | 2023-12-31
2 SECURING (SOKU 16, 19) Well Kill | Completed | CT | 8 | COILED TUBING (1.5") | East | Soku/NunR | 0 |  | OIL | CWI Well Integrity | 28 | 2024-03-29 | 2024-04-26
SOKU 17T Repeat Stimulation | L3 - Doable | CT | 8 | COILED TUBING (1.5") | East | Soku/NunR | 0 | SOKU017T | OIL | CWI STOG | 20 | 2024-04-26 | 2024-05-16
EMBEDDED CREW | Ongoing | WH | 8 | EMBEDDED CREW | East |  |  |  | OIL | CWI Well Integrity | 112 | 2024-01-14 | 2024-05-05
85 PMs: BELE, SOKU, DBUC | L3 - Doable | WH | 8 | EMBEDDED CREW | East | Soku/NunR |  |  | OIL | CWI Well Integrity | 112 | 2024-01-14 | 2024-05-05
E-LINE & WIRELINE | Ongoing | WL | 9 | E-LINE & WIRELINE | East |  |  |  | OIL | CWI STOG | 213 | 2024-05-02 | 2024-12-01
KOMA 4T, 5T SGs | Completed | WL | 9 | E-LINE & WIRELINE | East | GBAR/KC |  |  | OIL | CWI Data Acquisition | 4 | 2023-02-17 | 2023-02-21
ENWH 7T SG, EPU 3T SG | Completed | WL | 9 | E-LINE & WIRELINE | East | GBAR/KC |  |  | OIL | CWI Data Acquisition | 7 | 2023-03-25 | 2023-04-01
KOCR 23T CO log | Completed | WL | 9 | E-LINE & WIRELINE | East | GBAR/KC |  | KOCR023T | OIL | CWI Data Acquisition | 14 | 2023-06-04 | 2023-01-29
KOMA8T, GBAR 25, KOCR 39T SG, KOMA 3 CO log | Completed | WL | 9 | E-LINE & WIRELINE | East | GBAR/KC |  |  | OIL | CWI Data Acquisition | 20 | 2023-07-02 | 2023-07-22
EPU 4T, KOMA 2T, 11T BHP | Completed | WL | 9 | E-LINE & WIRELINE | East | GBAR/KC |  |  | OIL | CWI Data Acquisition | 7 | 2023-07-09 | 2023-07-16
GBAR 13 TRSCSSV Exercising; GBAR13, 15, 16 SG; GBAR 4, 22 FBHP | L3 - Doable | WL | 9 | E-LINE & WIRELINE | East | GBAR/KC | 0 |  | OIL | CWI Data Acquisition | 10 | 2024-05-02 | 2024-05-12
Move to ETEL: ETEL 13T (SG/FG/BHP) | L3 - Doable | WL | 9 | E-LINE & WIRELINE | East | GBAR/KC | 0 | ETEL013T | OIL | CWI Data Acquisition | 8 | 2024-05-12 | 2024-05-20
ETEL 8T CO log | L3 - Doable | WL | 9 | E-LINE & WIRELINE | East | GBAR/KC | 0 | ETEL008T | OIL | CWI Data Acquisition | 8 | 2024-05-19 | 2024-05-27
KOCR 39T SG + CO log | L3 - Doable | WL | 9 | E-LINE & WIRELINE | East | GBAR/KC | 0 | KOCR039T | OIL | CWI Data Acquisition | 13 | 2024-05-26 | 2024-06-08
Move to ENWH: ENWH 7T, 8T, 9T SG | L3 - Doable | WL | 9 | E-LINE & WIRELINE | East | GBAR/KC | 0 |  | OIL | CWI Data Acquisition | 10 | 2024-06-07 | 2024-06-17
ZARA 12S SG | L3 - Doable | WL | 9 | E-LINE & WIRELINE | East | GBAR/KC | 0 | ZARA012S | OIL | CWI Data Acquisition | 8 | 2024-07-22 | 2024-07-30
KOMA 2T, 3T, 4T, 7T SG; KOMA 2T CO log + KOMA 3,9,10, GBAR28T Deliquification (Foamer Trial) | L3 - Doable | WL | 9 | E-LINE & WIRELINE | East | GBAR/KC | 0 |  | OIL | CWI Data Acquisition | 21 | 2024-06-17 | 2024-07-08
EPU 3T, 4T SG | L3 - Doable | WL | 9 | E-LINE & WIRELINE | East | GBAR/KC | 0 |  | OIL | CWI Data Acquisition | 7 | 2024-07-29 | 2024-08-05
FORC 25T Bulkline 3 Sectional Replacement | Completed | FL | 2 | FLOWLINE | West | Forcados | 300 | FORC025T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 16 | 2024-02-12 | 2024-02-28
KOMA 11 Nitrogen lift Injection (GNC) [NOT REPORTED BY WRFM, ALLOCATED TO GNC PROJECT TEAM] | Completed | CT | 9 | COILED TUBING (1.75", 1.50") | East | GBAR/KC | 1 | KOMA011T | GAS | CWI STOG | 9 | 2024-02-21 | 2024-03-01
WIRELINE | Ongoing | WL | 9 | WIRELINE | East |  |  |  | OIL | CWI Well Integrity | 329 | 2024-04-24 | 2025-03-19
ADIB, ADNE, ETEL, GBAR, KOCR, KOMA, UBIE CMs (21 WELLS); | Completed | WL | 9 | WIRELINE | East | GBAR/KC |  |  | OIL | CWI Well Integrity | 104 | 2023-06-04 | 2023-09-16
GBAR 12 TRSCSSV Investigation | Completed | WL | 9 | WIRELINE | East | GBAR/KC |  | GBAR012T | OIL | CWI Well Integrity | 7 | 2023-09-03 | 2023-09-10
1 CM (KOMA 9) | Completed | WL | 9 | WIRELINE | East | GBAR/KC |  | KOMA009T | OIL | CWI Well Integrity | 8 | 2023-12-03 | 2023-12-11
3 SECURING: ADIB 4, 7, 26 | L4 - Certain | WL | 9 | WIRELINE | East | Soku/NunR | 0 |  | OIL | CWI Well Integrity | 14 | 2024-06-25 | 2024-07-09
1 SECURING: ADNE 2 | L4 - Certain | WL | 9 | WIRELINE | East | Soku/NunR | 0 | ADNE002L | OIL | CWI Well Integrity | 8 | 2024-07-09 | 2024-07-17
CM: GBAR 5 (Secure & Spool Meamnt.) + Contingent Well Kill | L3 - Doable | WL | 9 | WIRELINE | East | GBAR/KC | 0 | GBAR005T | OIL | CWI Well Integrity | 9 | 2024-05-01 | 2024-05-10
GBAR 12T TRSCSSSV Straddle | L3 - Doable | WL | 9 | WIRELINE | East | GBAR/KC | 0 | GBAR012T | OIL | CWI Well Integrity | 8 | 2024-08-10 | 2024-08-18
CM: ENWHE 9 | L3 - Doable | WL | 9 | WIRELINE | East | GBAR/KC | 0 | ENWH009T | OIL | CWI Well Integrity | 8 | 2024-07-18 | 2024-07-26
71 CMs: (ADIB/ADNE - 11, ETEL - 7, GBAR - 13, KOCR - 23, UBIE - 5, ZARA - 7, KOMA - 5 | L3 - Doable | WL | 9 | WIRELINE | East | GBAR/KC | 0 |  | OIL | CWI Well Integrity | 70 | 2024-05-09 | 2024-07-18
COILED TUBING (1.75", 1.50") | Ongoing | CT | 9 | COILED TUBING (1.75", 1.50") | East |  |  |  | GAS | CWI STOG | 323 | 2024-05-29 | 2025-04-17
GBAR028T Unloading | Completed | CT | 9 | COILED TUBING (1.75", 1.50") | East | GBAR/KC |  | GBAR028T | GAS | CWI STOG | 13 | 2023-09-24 | 2023-10-07
GBAR022T ZONE CHANGE/TUBING PUNCH/ Cont N2 lift | Completed | CT | 9 | COILED TUBING (1.75", 1.50") | East | GBAR/KC | 35 | GBAR022T | GAS | CWI STOG | 13 | 2023-10-22 | 2023-11-04
FORC 22T WRSCSSSV Change Out (QUIT WELL RESTORATION, NOT LIP) | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 1650 | FORC022T | OIL | CWI STOG | 7 | 2024-02-25 | 2024-03-03
OPUK 26T Xmas Tree Installation/Unsecure & Open Up | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 920 | OPUK026T | OIL | CWI STOG | 7 | 2024-04-21 | 2024-04-28
FORC 43S: Sand Cleanout & Acid Stimulation/ScSSSV Changeout | Completed | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 2500 | FORC043S | OIL | CWI STOG | 29 | 2024-04-04 | 2024-05-03
OTUM 22S GLLR (Quit Well) | Completed | FL | 5 | FLOWLINE 2 | West | EA/OTUM | 500 | OTUM022S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 14 | 2024-04-25 | 2024-05-09
KANB 8T / KANB 4S FLOWLINE REPAIR [KANB008T is a Quit Well with 900 bopd potential, KANB004S is LiP with 250 bopd] | L3 - Doable | FL | 6 | FLOWLINE 6 | West | Southern Swamp | 250 |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 40 | 2024-04-04 | 2024-05-14
Move to BENS: BENS 13T Acid Wash | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 560 | BENS013T | OIL | CWI STOG | 18 | 2024-04-28 | 2024-05-16
OTUM 2L Wax Remediation- Enhanced Solvent | L3 - Doable | CT | 5 | COILED TUBING (1.25") | West | EA/OTUM | 150 | OTUM002L | OIL | CWI STOG | 15 | 2024-05-07 | 2024-05-22
GBAR 7T Contingency Acid Stimulation | L5 - Ready | CT | 9 | COILED TUBING (1.75", 1.50") | East | GBAR/KC | 0 | GBAR007T | OIL | CWI STOG | 12 | 2024-06-05 | 2024-06-17
OBEL 3L WHM/SCSSSV C/O | L5 - Ready | WL | 7 | WIRELINE | East | Rumuahia | 500 | OBEL003L | OIL | CWI STOG AF Maintenance | 7 | 2024-05-16 | 2024-05-23 |  |  | Q1 | Q2 (May) | Q2 (June) | Q3 (July) | Q3 9Aug) | Q3 (Sept) | Q4 (Oct) | Q4 (Nov) | Q4 Dec
EMBEDDED CREW | Ongoing | WH | 9 | EMBEDDED CREW | East |  |  |  | OIL | CWI Well Integrity | 105 | 2024-02-25 | 2024-06-09
92 PMs: (ADIB/ADNE, GBAR, ZARA, ETEL, ENWH, KOMA, KOCR) | L4 - Certain | WH | 9 | EMBEDDED CREW | East | GBAR/KC |  |  | OIL | CWI Well Integrity | 105 | 2024-02-25 | 2024-06-09
FLOWLINE 1 | Ongoing | FL | 9 | FLOWLINE 1 | East |  |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 281 | 2024-05-02 | 2025-02-07
NUNR 3L FLOWLINE REPAIR | L3 - Doable | FL | 9 | FLOWLINE 1 | East | Soku/NunR | 0 | NUNR003L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 61 | 2024-05-02 | 2024-07-02
FLOWLINE 2 | Ongoing | FL | 9 | FLOWLINE 2 | East |  |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 181 | 2024-01-25 | 2024-07-24
UBIE 5S PBV re-calibration | L5 - Ready | CT | 7 | COILED TUBING (1.25") | East | Soku/NunR | 850 | UBIE005S | OIL | CWI STOG AF Maintenance | 10 | 2024-05-13 | 2024-05-23 |  |  | 0 | 0 | 1350 | 1350 | 3100 | 5150 | 5150 | 5620 | 7115
GBAR 5T FLOWLINE INTEGRITY TEST | L3 - Doable | FL | 9 | FLOWLINE 2 | East | GBAR/KC |  | GBAR005T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 23 | 2024-07-01 | 2024-07-24
OTUM 29L/S GLLR (Quit Well) | L3 - Doable | FL | 5 | FLOWLINE 2 | West | EA/OTUM | 500 |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 29 | 2024-04-24 | 2024-05-23
FORC 141L PB Valve recalibration (ACTIVITY DROPPED) | L3 - Doable | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 1600 | FORC141L | OIL | CWI STOG | 7 | 2024-05-20 | 2024-05-27
SOKU 45 Securing | L5 - Ready | WL | 8 | E-LINE & SLICKLINE | East | Soku/NunR | 0 | SOKU045T | OIL | CWI Well Integrity | 8 | 2024-05-10 | 2024-05-18
Move to DBUC: DBUC 010T: Sand Cleanout and SCON (pending execution doability) | L3 - Doable | CT | 8 | COILED TUBING (1.5") | East | Soku/NunR | 400 | DBUC010T | OIL | CWI STOG | 21 | 2025-01-02 | 2025-01-23
DBUC 008T: Perforation Extension and SCON (pending execution doability) | L3 - Doable | CT | 8 | COILED TUBING (1.5") | East | Soku/NunR | 300 | DBUC008T | OIL | CWI STOG | 28 | 2025-01-23 | 2025-02-20
ETEL 002S: WHM | L3 - Doable | WL | 9 | WIRELINE | East | GBAR/KC | 246 | ETEL002S | OIL | CWI STOG | 10 | 2025-01-02 | 2025-01-12
ETEL 007S: Open up post re-routing | L3 - Doable | WL | 9 | WIRELINE | East | GBAR/KC | 147 | ETEL007S | OIL | CWI STOG | 5 | 2025-01-12 | 2025-01-17
ETEL 003S: Drift Run, Fishing/Tubing punch & PB valve calibration | L3 - Doable | WL | 9 | WIRELINE | East | GBAR/KC | 120 | ETEL003S | OIL | CWI STOG | 21 | 2025-01-17 | 2025-02-07
KOCR 012T: Dewaxing, WHM and Open up(Contingent on well 13 CO log) | L3 - Doable | WL | 9 | WIRELINE | East | GBAR/KC | 200 | KOCR012T | OIL | CWI STOG | 14 | 2025-02-07 | 2025-02-21
NUNR 001T: Ann. Investigation and Restoration | L3 - Doable | WL | 9 | WIRELINE | East | Soku/NunR | 633 | NUNR001T | OIL | CWI STOG | 21 | 2025-02-21 | 2025-03-14
ADIB 019L: WHM | L3 - Doable | WL | 9 | WIRELINE | East | Soku/NunR | 160 | ADIB019L | OIL | CWI STOG | 5 | 2025-03-14 | 2025-03-19
ADNE 002L: Stimulation/Reperforation | L3 - Doable | CT | 9 | COILED TUBING (1.75", 1.50") | East | Soku/NunR | 250 | ADNE002L | OIL | CWI STOG | 28 | 2025-01-02 | 2025-01-30
ADIB 027L: Fishing/Sand Clean-out | L3 - Doable | CT | 9 | COILED TUBING (1.75", 1.50") | East | Soku/NunR | 100 | ADIB027L | OIL | CWI STOG | 21 | 2025-01-30 | 2025-02-20
NUNR 010T: Water shut Off | L3 - Doable | CT | 9 | COILED TUBING (1.75", 1.50") | East | Soku/NunR | 353 | NUNR010T | OIL | CWI STOG | 28 | 2025-02-20 | 2025-03-20
GBAR 001L: Perforation extension (N2 lift contingency) | L3 - Doable | CT | 9 | COILED TUBING (1.75", 1.50") | East | GBAR/KC | 300 | GBAR001L | OIL | CWI STOG | 28 | 2025-03-20 | 2025-04-17
ETEL 3L FLRR | L3 - Doable | FL | 9 | FLOWLINE 3 | East | GBAR/KC | 0 | ETEL003L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 46 | 2024-06-01 | 2024-07-17
SOKU 38T TRSCSSV Straddle/Ambient valve installation | L3 - Doable | CT | 8 | COILED TUBING (1.5") | East | Soku/NunR | 60 | SOKU038T | GAS | CWI STOG | 14 | 2024-05-16 | 2024-05-30 | [5 empty] | 1750 | 2050 | 0 | 470 | 1495 | 1300
KANB 6T FLOWLINE REPAIR | L3 - Doable | FL | 6 | FLOWLINE 5 | West | Southern Swamp | 540 | KANB006T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 57 | 2024-04-06 | 2024-06-02
DREDGING | Ongoing | DG | 8 | DREDGING | East | Soku/NunR | 0 |  | OIL | CIVIL/GEOMATICS Location Preparation | 55 | 2024-05-06 | 2024-06-30
Belema Dredging | L3 - Doable | DG | 8 | DREDGING | East | Soku/NunR | 0 |  | OIL | CIVIL/GEOMATICS Location Preparation | 55 | 2024-05-06 | 2024-06-30
Move to BENS: BENS 9L SCON wash + BENS 9 CO log. | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 410 | BENS009L | OIL | CWI STOG | 18 | 2024-05-16 | 2024-06-03
SOKU 38T SG + Corrosion Log | L3 - Doable | WL | 8 | COILED TUBING (1.5") | East | Soku/NunR | 0 | SOKU038T | OIL | CWI Data Acquisition | 8 | 2024-05-30 | 2024-06-07
ETEL 002S FL Pinhole Repair | L3 - Doable | FL | 9 | FLOWLINE 1 | East | GBAR/KC | 0 | ETEL002S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 11 | 2024-12-23 | 2025-01-03
KOCR 012T FLRR | L3 - Doable | FL | 9 | FLOWLINE 1 | East | GBAR/KC |  | KOCR012T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 31 | 2025-01-07 | 2025-02-07
OTUM 43L Fishing + Sand cleanout + Attic perforation + SCON; FLRR | L3 - Doable | CT | 5 | COILED TUBING (1.25") | East |  | 350 | OTUM043L | OIL | CWI STOG | 30 | 2025-01-23 | 2025-02-22
DBUC 2T Unsecuring & DBUC 3T SCSSSV repair | L3 - Doable | WL | 8 | E-LINE & SLICKLINE | East | Soku/NunR | 0 |  | OIL | CWI Well Integrity | 15 | 2024-05-27 | 2024-06-11
OPUK 4S FLRR | L3 - Doable | FL | 6 | FLOWLINE 3 | West | Southern Swamp | 0 | OPUK004S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 31 | 2024-08-05 | 2024-09-05
OPUK 22T FLRR | L3 - Doable | FL | 6 | FLOWLINE 3 | West | Southern Swamp | 0 | OPUK022T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 31 | 2024-09-04 | 2024-10-05
OPUK 15T FLRR | L3 - Doable | FL | 6 | FLOWLINE 8 | West | Southern Swamp | 0 | OPUK015T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 31 | 2024-08-17 | 2024-09-17
OTUM 18T Sand Clean out + SCON | L3 - Doable | CT | 5 | COILED TUBING (1.25") | West | EA/OTUM | 250 | OTUM018T | OIL | CWI STOG | 21 | 2025-02-22 | 2025-03-15
OTUM 41L Sand Clean out + SCON | L3 - Doable | CT | 5 | COILED TUBING (1.25") | West | EA/OTUM | 250 | OTUM041L | OIL | CWI STOG | 21 | 2025-03-15 | 2025-04-05
OTUM 42S Sectional FLRR | L3 - Doable | FL | 5 | FLOWLINE 1 | West | EA/OTUM | 120 | OTUM042S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 30 | 2025-01-10 | 2025-02-09
OTUM 42L Sectional FLRR | L3 - Doable | FL | 5 | FLOWLINE 1 | West | EA/OTUM | 100 | OTUM042L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 30 | 2025-02-09 | 2025-03-11
SLICKLINE | Ongoing | WL | 4 | SLICKLINE | West | EA/OTUM |  |  | OIL | CWI STOG | 423 | 2025-03-01 | 2026-04-28
EAZZ 19S GLVCO + Gaslift Kick Off | L3 - Doable | WL | 4 | SLICKLINE | West | EA/OTUM | 800 | EAZZ019S | OIL | CWI STOG | 10 | 2025-03-01 | 2025-03-11
EAZZ 19L GLVCO + Gaslift Kick Off | L3 - Doable | WL | 4 | SLICKLINE | West | EA/OTUM | 630 | EAZZ019L | OIL | CWI STOG | 10 | 2025-03-11 | 2025-03-21
EAZZ 56T GLVCO + Gaslift Kick Off | L3 - Doable | WL | 4 | SLICKLINE | West | EA/OTUM | 500 | EAZZ056T | OIL | CWI STOG | 10 | 2025-03-21 | 2025-03-31
EJAZ 6T PB Valve Recalibration | L3 - Doable | WL | 4 | SLICKLINE | West | EA/OTUM | 400 | EJAZ006T | OIL | CWI STOG | 10 | 2025-03-31 | 2025-04-10
EAZZ 54T Descale + Zone Change to F3000E | L3 - Doable | WL | 4 | SLICKLINE | West | EA/OTUM |  | EAZZ054T | OIL | CWI STOG | 28 | 2026-03-10 | 2026-04-07
EAZZ 55T Zone Change from C9200B to C9100B | L3 - Doable | WL | 4 | SLICKLINE | West | EA/OTUM | 0 | EAZZ055T | OIL | CWI STOG | 21 | 2026-04-07 | 2026-04-28
FLOWLINE 8 | Ongoing | FL | 6 | FLOWLINE 8 | West | Southern Swamp |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 1 | 2024-05-07 | 2024-05-08
AJAT 1L FLOWLINE REPAIR (6" Line) | L3 - Doable | FL | 6 | FLOWLINE 8 | West | Southern Swamp | 0 | AJAT001L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 60 | 2024-06-01 | 2024-07-31
OPUK 25T FLOWLINE REPLACEMENT (6" Line) | L3 - Doable | FL | 6 | FLOWLINE 8 | West | Southern Swamp | 0 | OPUK025T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 61 | 2025-01-24 | 2025-03-26
GBAR 13T contingent N2 lift | L5 - Ready | CT | 9 | COILED TUBING (1.75", 1.50") | East | GBAR/KC | 1 | GBAR013T | GAS | CWI STOG | 7 | 2024-05-29 | 2024-06-05 | [5 empty] | 3100 | 5150 | 5150 | 5620 | 7115 | 8415
OPUK 10S FLOWLINE REPLACEMENT | L3 - Doable | FL | 6 | FLOWLINE 7 | West | Southern Swamp |  | OPUK010S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 61 | 2024-07-16 | 2024-09-15
TUNU 15T/17T FLRR | L3 - Doable | FL | 6 | FLOWLINE 5 | West | Southern Swamp |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 48 | 2024-05-14 | 2024-07-01
TUNU 3T FLRR | L3 - Doable | FL | 6 | FLOWLINE 5 | West | Southern Swamp | 0 | TUNU003T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 26 | 2024-07-19 | 2024-08-14
KANB 9T FLRR | L3 - Doable | FL | 6 | FLOWLINE 6 | West | Southern Swamp | 0 | KANB009T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 44 | 2024-06-01 | 2024-07-15
KANB 3S Unsecuring | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 0 | KANB003S | OIL | CWI Well Integrity | 8 | 2024-10-06 | 2024-10-14
KANB 6T, 7S, 9T SG | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp |  |  | OIL | CWI Data Acquisition | 7 | 2024-05-25 | 2024-06-01
OPUK022T HUD/Fishing + Noise log | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp |  | OPUK022T | OIL | CWI Data Acquisition | 7 | 2024-06-16 | 2024-06-23
Move to BENS: BENS 16T, 22T SG | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp |  |  | OIL | CWI Data Acquisition | 7 | 2024-07-10 | 2024-07-17
Move to Execute SSW CT Activities | L3 - Doable | CT | 5 | COILED TUBING (1.25") | West |  | 0 |  | OIL | CWI STOG | 113 | 2024-07-05 | 2024-10-26
GBAR 23T Securing | Ongoing | WL | 9 | WIRELINE | West |  |  | GBAR023T | OIL | CWI Well Integrity | 8 | 2024-04-24 | 2024-05-02
Move to OPUK: OPUK 2T SCON Cleanout | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 600 | OPUK002T | OIL | CWI STOG | 14 | 2025-01-02 | 2025-01-16
OPUK 11L Zone Change + Reperf to the E1000A | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 600 | OPUK011L | OIL | CWI STOG | 30 | 2025-01-16 | 2025-02-15
Move to BENS: BENS 20T Acid Wash | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 300 | BENS020T | OIL | CWI STOG | 21 | 2025-04-09 | 2025-04-30
BENS 14L Tubing Drift + SCON Cleanout | L3 - Doable | WL | 6 | COILED TUBING (1.25") | West | Southern Swamp | 200 | BENS014L | OIL | CWI STOG | 21 | 2025-04-30 | 2025-05-21
Move to KANB: KANB 2T Screen Wash | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 600 | KANB002T | OIL | CWI STOG | 21 | 2028-01-02 | 2028-01-23
KANB 2T FLRR | L3 - Doable | FL | 6 | FLOWLINE 1 | West | Southern Swamp |  | KANB002T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 33 | 2027-12-01 | 2028-01-03
KANB 10T Gas Lift Opportunity | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 300 | KANB010T | OIL | CWI STOG | 10 | 2028-01-02 | 2028-01-12
KANB 10T FLRR | L3 - Doable | FL | 6 | FLOWLINE 2 | West | Southern Swamp |  | KANB010T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 32 | 2027-12-02 | 2028-01-03
Move to OPNO: OPNO 001L Acid Stimulation + Future Gaslift | L3 - Doable | CT | 6 | COILED TUBING (1.5") | West | Southern Swamp | 300 | OPNO001L | OIL | CWI STOG | 24 | 2030-02-01 | 2030-02-25
OPNO 29T Acid Stimulation + Future Gaslift | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 150 | OPNO029T | OIL | CWI STOG | 24 | 2030-02-25 | 2030-03-21
Move to OPUK: OPUK 33L Zone Change to E7300D | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 400 | OPUK033L | OIL | CWI STOG | 21 | 2030-03-21 | 2030-04-11
Move to OTUM: OTUM 33L Sand Cleanout + SCON | L3 - Doable | CT | 5 | COILED TUBING (1.25") | West | EA/OTUM | 450 | OTUM033L | OIL | CWI STOG | 21 | 2025-01-02 | 2025-01-23
UBIE 3L TBG PUNCH & PB VALVE INSTALLATION (New scope- Sand wash and open sleeve) | L5 - Ready | CT | 7 | COILED TUBING (1.25") | East | Soku/NunR | 350 | UBIE003L | OIL | CWI STOG AF Maintenance | 21 | 2024-05-23 | 2024-06-13
Move to Kanbo: KANB 3 Securing | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 0 | KANB003L | OIL | CWI Well Integrity | 10 | 2024-05-15 | 2024-05-25
5 Wells CM: ESCB | L3 - Doable | WL | 5 | WIRELINE | West | EA/OTUM | 0 |  | OIL | CWI Well Integrity | 25 | 2024-05-02 | 2024-05-27
Move to SAGR: SAGR 2, 1 Well Kill + Securing | L3 - Doable | WL | 8 | COILED TUBING (1.5") | West | EA/OTUM | 0 |  | OIL | CWI Well Integrity | 21 | 2024-06-06 | 2024-06-27
FLOWLINE | Ongoing | FL | 1 | FLOWLINE | West | Forcados | 0 |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 20 | 2024-06-20 | 2024-07-10
FORC 102L Onshore FL Repair | L3 - Doable | FL | 1 | FLOWLINE | West | Forcados | 0 | FORC102L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 26 | 2024-06-28 | 2024-07-24
KANB 3L: Unsecuring | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 0 | KANB003L | OIL | CWI Well Integrity | 8 | 2024-09-29 | 2024-10-07
KANB 3S: Unsecuring | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 0 | KANB003S | OIL | CWI Well Integrity | 6 | 2024-10-14 | 2024-10-20
OTUM 40T Hi Clay SCON Treatment | L3 - Doable | CT | 5 | COILED TUBING (1.25") | West | EA/OTUM | 500 | OTUM040T | OIL | CWI STOG | 22 | 2024-05-22 | 2024-06-13
Move to CL 9:FORC 055T: WSO & Perforation extension | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 350 | FORC058L | OIL | CWI STOG | 30 | 2025-09-29 | 2025-10-29
Move to CL 3:FORC 026L: ST- Fishing, Sand clean-out, stimulation & SCON on D9000L | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 600 | FORC026L | OIL | CWI STOG | 28 | 2025-06-05 | 2025-07-03
Move to CL 3A:FORC 145T: Motorised Milling - Rigless | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 600 | FORC145T | OIL | CWI STOG | 28 | 2025-07-03 | 2025-07-31
Move to CL 5A:FORC 132L: H2Zero/BackStop + WSO reperforation and SCON | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 600 | FORC132L | OIL | CWI STOG | 30 | 2025-07-31 | 2025-08-30
Move to CL 1:FORC 037S: WSO and Perforation extension | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 400 | FORC037S | OIL | CWI STOG | 30 | 2025-08-30 | 2025-09-29
Move to CL 20:FORC 046S: Stimulation | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 350 | FORC046S | OIL | CWI STOG | 21 | 2025-10-29 | 2025-11-19
Move to FODPA:FORC 123L: Attic perforation on the D8000L and PBV Installation | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 300 | FORC123L | OIL | CWI STOG | 30 | 2025-11-19 | 2025-12-19
Move to KANB:KANB 005S: Fishing | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 650 | KANB005S | OIL | CWI STOG | 15 | 2025-01-02 | 2025-01-17
KANB 005L: PB Valve | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 600 | KANB005L | OIL | CWI STOG | 10 | 2025-01-17 | 2025-01-27
Move to OPUK:OPUK 1T: Unsecuring + Flow trial | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 200 | OPUK001T | OIL | CWI STOG | 10 | 2027-01-02 | 2027-01-12
Move to AKON:AKON 001S: WHM + FLRR | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 150 | AKON001S | OIL | CWI STOG | 10 | 2027-01-12 | 2027-01-22
Move to BENS:BENS 010S: Sand Cleanout + WSO + Attic Perf | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 650 | BENS010S | OIL | CWI STOG | 30 | 2030-01-02 | 2030-02-01
BENS 021S: WSO, Perforation Extension & SCON | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 250 | BENS021S | OIL | CWI STOG | 30 | 2028-01-23 | 2028-02-22
Move to OPUK:OPUK 033L: Integrity Restoration + Sand Cleanout + Attic Perforation + Bulking | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 500 | OPUK033L | OIL | CWI STOG | 28 | 2025-02-15 | 2025-03-15
Move to CL 51: FORC 090T: Retrieve NRV and perform flow trial /Attic perforation | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 750 | FORC090T | OIL | CWI STOG | 28 | 2026-01-02 | 2026-01-30
Move to CL 1: FORC 089T: WSO and Perforation extension | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 600 | FORC089T | OIL | CWI STOG | 30 | 2026-01-30 | 2026-03-01
Move to CL 5: FORC 024S: Sand Clean out and SCON (perf Tube milling) & Attic Perforation | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 600 | FORC024S | OIL | CWI STOG | 28 | 2026-03-01 | 2026-03-29
Move to CL 52:FORC 052S: Reperforation and Sand Control | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 600 | FORC052S | OIL | CWI STOG | 30 | 2026-04-28 | 2026-05-28
Move to CL 93:FORC 094S: WSO & Attic perforation | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 600 | FORC094S | OIL | CWI STOG | 30 | 2026-05-28 | 2026-06-27
Move to CL 69:FORC 082S: Attic Perforation | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 500 | FORC082S | OIL | CWI STOG | 30 | 2028-01-02 | 2028-02-01
Move to CL 42:FORC 061L: Zone change from E4000L to E1000L | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 300 | FORC061L | OIL | CWI STOG | 28 | 2028-02-01 | 2028-02-29
Move to CL 69:FORC 082L: Bulkline Repair and open up | L3 - Doable | FL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 800 | FORC082L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 20 | 2028-01-02 | 2028-01-22
Move to CL 103: FORC 104T: GLVCO and Gas-line Installation | L3 - Doable | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 500 | FORC104T | OIL | CWI STOG | 30 | 2027-01-02 | 2027-02-01
FORC 103L: GLVCO and Gas-line Installation | L3 - Doable | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 400 | FORC103L | OIL | CWI STOG | 30 | 2027-02-01 | 2027-03-03
FORC 107T: GLVCO and Gas-line Installation | L3 - Doable | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 250 | FORC107T | OIL | CWI STOG | 30 | 2027-04-02 | 2027-05-02
FORC 103S: GLVCO and Gas-line Installation | L3 - Doable | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 200 | FORC103S | OIL | CWI STOG | 30 | 2027-03-03 | 2027-04-02
Move to CL 31:FORC 050S: ST: Attempt Open up; LT: Gaslift Opportunity | L3 - Doable | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 350 | FORC050S | OIL | CWI STOG | 30 | 2027-05-02 | 2027-06-01
FORC 132L: Recompletion Cement packer and SCON | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 900 | FORC132L | OIL | CWI STOG | 30 | 2027-01-02 | 2027-02-01
FORC 005S: Recompletion with Cement packer | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 200 | FORC005S | OIL | CWI STOG | 30 | 2026-03-29 | 2026-04-28
Transfer to AFRE B: AFRE 7L SG | Ongoing | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | EA/OTUM | 0 | AFRE007L | OIL | CWI Data Acquisition | 6 | 2024-06-11 | 2024-06-17
1 SECURING (AFRE 5) | Ongoing | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | EA/OTUM | 0 | AFRE005L | OIL | CWI Well Integrity | 6 | 2024-06-16 | 2024-06-22
OPUK 13L/S Flowline Repair (Bulked) | L3 - Doable | FL | 6 | FLOWLINE 4 | West | Southern Swamp | 0 |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 62 | 2024-09-01 | 2024-11-02
OTUM 41S CM | Completed | WL | 5 | WIRELINE | West | EA/OTUM | 0 | OTUM041S | OIL | CWI Well Integrity | 7 | 2024-02-29 | 2024-03-07
OTUM 5S Securing | Completed | WL | 5 | WIRELINE | West | EA/OTUM | 0 | OTUM005S | OIL | CWI Well Integrity | 7 | 2024-03-06 | 2024-03-13
Transfer to AFRE A: AFRE 13 Annulus investigation + Cont. Well Kill | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | EA/OTUM | 0 | AFRE013S | OIL | CWI Well Integrity | 9 | 2024-05-27 | 2024-06-05
BENS 9L CO log | L4 - Certain | WL | 6 | COILED TUBING (1.25") | West | Southern Swamp | 0 | BENS009L | OIL | CWI Data Acquisition | 8 | 2024-05-08 | 2024-05-16
COILED TUBING 2 (1.25") | Ongoing | CT | 6 | COILED TUBING 2 (1.25") | West |  | 0 |  | OIL | CWI STOG | 113 | 2024-05-20 | 2024-09-10
Move to OPUK: OPUK 24T CCU, TRSSV Straddle | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 495 | OPUK024T | OIL | CWI STOG AF | 15 | 2024-06-01 | 2024-06-16
BENS 9S Acid Wash | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 780 | BENS009S | OIL | CWI STOG | 18 | 2024-06-03 | 2024-06-21
ADIB 10S FLOWLINE REPAIR | Ongoing | FL | 9 | FLOWLINE 2 | East | Soku/NunR | 1400 | ADIB010S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 157 | 2024-01-25 | 2024-06-30 | Q2
NUNR 16T Solvent Soak | L4 - Certain | CT | 9 | COILED TUBING (1.75", 1.50") | East | Soku/NunR | 220 | NUNR016T | OIL | CWI STOG | 14 | 2024-06-17 | 2024-07-01
SEIB 2L, 3L WHM | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 0 |  | OIL | CWI STOG AF | 8 | 2024-10-08 | 2024-10-16
OPUK 34T FLOWLINE REPAIR | Ongoing | FL | 6 | FLOWLINE 2 | West | Southern Swamp | 0 | OPUK034T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 30 | 2024-05-10 | 2024-06-09
FORC 130S WHM, Sand wash, PERF, N2 lift | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 900 | FORC130S | OIL | CWI STOG | 23 | 2024-06-09 | 2024-07-02
UBIE 8T ZONE CHANGE/ACID STIMULATION | L5 - Ready | CT | 7 | COILED TUBING (1.25") | East | Soku/NunR | 430 | UBIE008T | OIL | CWI STOG AF Maintenance | 21 | 2024-06-13 | 2024-07-04
JUB (LAYEMAMUS) WIRELINE/SLICKLINE | Ongoing | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West |  |  |  | OIL | CWI Well Integrity | 287 | 2024-01-28 | 2024-11-10
FORC 47S SG | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados |  | FORC047S | OIL | CWI Data Acquisition | 3 | 2023-03-28 | 2023-03-31
FORC 131L SGs | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados |  | FORC131L | OIL | CWI Data Acquisition | 3 | 2023-04-27 | 2023-04-30
AFRE 6 Casing Expander + AFRE7 CM | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | EA/OTUM |  |  | OIL | CWI Well Integrity | 14 | 2023-07-02 | 2023-07-16
FORC 37S SG | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados |  | FORC037S | OIL | CWI Data Acquisition | 3 | 2023-09-10 | 2023-09-13
Transfer to CL 95: 3 SECURING (FORC95,100,102) 3 CMs (FORC95,100,102) | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados |  |  | OIL | CWI Well Integrity | 14 | 2023-10-15 | 2023-10-29
Transfer to CL 2: 3 CMs (FORC2, 27, 29) | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados |  |  | OIL | CWI Well Integrity | 19 | 2023-10-29 | 2023-11-17
FORC 2L SG | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados |  | FORC002L | OIL | CWI Data Acquisition | 3 | 2023-11-17 | 2023-11-20
Transfer to FODPA:2 CMs (FORC121, 123) | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 |  | OIL | CWI Well Integrity | 9 | 2023-11-26 | 2023-12-05
FORC 122L, 123S SG | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 |  | OIL | CWI Data Acquisition | 5 | 2023-12-06 | 2023-12-11
Transfer to CL 52: 2 SECURING (FORC65,68) | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 |  | OIL | CWI Well Integrity | 15 | 2023-12-10 | 2023-12-25
Transfer to CL 52A: CM (FORC129) | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 | FORC129S | OIL | CWI Well Integrity | 16 | 2023-12-24 | 2024-01-09
TRANSFER TO CL JB & CM: FORC150 | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados |  | FORC150T | OIL | CWI Well Integrity | 17 | 2024-01-07 | 2024-01-24
Transfer to CL 3: 4 CMs (FORC3, 25, 26, 66) | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 |  | OIL | CWI Well Integrity | 13 | 2024-01-29 | 2024-02-11
Transfer to CL 5: CM (FORC5) | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 | FORC005S | OIL | CWI Well Integrity | 15 | 2024-02-11 | 2024-02-26
OTUM 46S Dewaxing, MFC & N2 lift | L3 - Doable | CT | 5 | COILED TUBING (1.25") | West | EA/OTUM | 400 | OTUM046S | OIL | CWI STOG | 22 | 2024-06-13 | 2024-07-05
Transfer to CL JA: CM (FORC153) | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 | FORC153T | OIL | CWI Well Integrity | 32 | 2024-03-03 | 2024-04-04
FORC 135L, 153T SG | Completed | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 |  | OIL | CWI Data Acquisition | 4 | 2024-04-03 | 2024-04-07
Transfer to CL 69: CM (FORC69T) | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados |  | FORC069T | OIL | CWI Well Integrity | 8 | 2024-04-22 | 2024-04-30
Transfer to CL 42: CM (FORC62) | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados |  | FORC062T | OIL | CWI Well Integrity | 8 | 2024-04-29 | 2024-05-07
Transfer to CL 3A: 1 SECURING (FORC145T) | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados |  | FORC145T | OIL | CWI Well Integrity | 8 | 2024-05-13 | 2024-05-21
BENS 1L Perf Extension & SCON + N2 Lift | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 385 | BENS001L | OIL | CWI STOG | 28 | 2024-06-21 | 2024-07-19
Transfer to CL 4: CM (FORC33) | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados |  | FORC033L | OIL | CWI Well Integrity | 8 | 2024-05-06 | 2024-05-14
Transfer to CL 95: | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 |  | OIL | CWI Well Integrity | 7 | 2024-06-21 | 2024-06-28
FORC 102L Riser Repair | L3 - Doable | FL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 | FORC102L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 33 | 2024-06-28 | 2024-07-31
1 SECURING (AFRE 8) | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | EA/OTUM | 0 | AFRE008L | OIL | CWI Well Integrity | 5 | 2024-06-04 | 2024-06-09
AFRE 4S SG; | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | EA/OTUM | 0 | AFRE004S | OIL | CWI Data Acquisition | 4 | 2024-06-08 | 2024-06-12
Transfer to CL 52: 1 CM (FORC 65) | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 | FORC065S | OIL | CWI Well Integrity | 15 | 2024-07-30 | 2024-08-14
FORC 52L CO log | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 | FORC052L | OIL | CWI Data Acquisition | 7 | 2024-08-13 | 2024-08-20
Transfer to CL 2: | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 |  | OIL | CWI Well Integrity | 7 | 2024-08-20 | 2024-08-27
FORC 28L SG | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 | FORC028L | OIL | CWI Data Acquisition | 8 | 2024-08-27 | 2024-09-04
Transfer to CL 3A: | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 |  | OIL | CWI Well Integrity | 7 | 2024-09-03 | 2024-09-10
FORC 141L SG | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 | FORC141L | OIL | CWI Data Acquisition | 8 | 2024-09-10 | 2024-09-18
Transfer to CL 51: | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 |  | OIL | CWI Well Integrity | 7 | 2024-09-17 | 2024-09-24
FORC 72T SG | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 | FORC072T | OIL | CWI Data Acquisition | 8 | 2024-09-24 | 2024-10-02
Transfer to CL 52A: | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 |  | OIL | CWI Well Integrity | 7 | 2024-10-01 | 2024-10-08
FORC 129S SG | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 | FORC129S | OIL | CWI Data Acquisition | 8 | 2024-10-08 | 2024-10-16
Transfer to CL JB: | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 |  | OIL | CWI Well Integrity | 7 | 2024-10-15 | 2024-10-22
FORC 148T, 151L/S SG | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 |  | OIL | CWI Data Acquisition | 7 | 2024-10-22 | 2024-10-29
35 Wells CM | L4 - Certain | WL | 1 | JUB (LAYEMAMUS) WIRELINE/SLICKLINE | West | Forcados | 0 |  | OIL | CWI Well Integrity | 28 | 2024-10-29 | 2024-11-26
EMBEDDED CREW | Ongoing | WH | 1 | EMBEDDED CREW | West |  |  |  | OIL | CWI Well Integrity | 70 | 2024-03-17 | 2024-05-26
74 PM Wells: Afremo, Forcados | Ongoing | WH | 1 | EMBEDDED CREW | West | Forcados | 0 |  | OIL | CWI Well Integrity | 102 | 2024-03-11 | 2024-06-21
JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | Ongoing | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West |  |  |  | OIL | CWI STOG AF | 228 | 2023-12-17 | 2024-08-01
FORC 136 SAND CLEAN OUT, STIM & SCRN INSTALL (CL JA), SG | Completed | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados |  | FORC136T | OIL | CWI STOG | 16 | 2023-01-19 | 2023-02-04
FORC 135L REPERF & SCON/N2 Lift (CL JA) | Completed | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 760 | FORC138T | OIL | CWI STOG AF | 18 | 2023-02-04 | 2023-02-22
FORC 138T TRScSSV L/O, PBV (CL JA) | Completed | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 650 | FORC140T | OIL | CWI STOG | 30 | 2023-02-23 | 2023-03-25
FORC 140T Fishing, Sand Clean Out, Stim (CL JA) | Completed | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados |  | FORC140T | OIL | CWI Data Acquisition | 3 | 2023-03-26 | 2023-03-29
FORC 140 SG (CL JA) | Completed | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 740 | FORC139T | OIL | CWI STOG AF Maintenance | 10 | 2023-03-26 | 2023-04-05
FORC 139 TRSCSSV L/O, PBV Installation (CL JA) | Completed | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados |  | FORC139T | OIL | CWI Data Acquisition | 3 | 2023-04-05 | 2023-04-08
FORC 139T SG (CL JA) | Completed | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 760 | FORC139T | OIL | CWI STOG | 22 | 2023-04-09 | 2023-05-01
FORC 135L ZONE CHANGE (CL JA) (REPEAT) | Completed | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 1000 | FORC135L | OIL | CWI STOG | 36 | 2023-05-21 | 2023-06-26
FORC 142S Sand Clean Out/TT Screen/N2 Lift (CL 3A) | Completed | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados |  | FORC142S | OIL | CWI Well Integrity | 8 | 2023-06-25 | 2023-07-03
Cluster 3A (1) SECURING, CMs | Completed | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados |  |  | OIL | CWI Data Acquisition | 2 | 2023-07-04 | 2023-07-06
FORC 144T SG | Completed | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados |  | FORC144T | OIL | CWI Well Integrity | 3 | 2023-08-04 | 2023-08-07
AFRE CMs (AFRE4,10,14) | Completed | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | EA/OTUM |  |  | OIL | CWI Data Acquisition | 2 | 2023-08-06 | 2023-08-08
AFRE 14L & 14S SGs | Completed | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | EA/OTUM |  |  | OIL | CWI STOG | 4 | 2023-08-20 | 2023-08-24
AFRE 13S Restoration | Completed | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | EA/OTUM | 1200 | AFRE013S | OIL | CWI STOG | 30 | 2023-08-24 | 2023-09-23
AFRE 10L Stimulation/N2 lift/PB Valve recalibration | Completed | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | EA/OTUM | 300 | AFRE010L | OIL | CWI STOG AF Maintenance | 13 | 2023-10-08 | 2023-10-21
AFRE 14L Chemical Descaling | Completed | PC | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | EA/OTUM | 300 | AFRE014L | OIL | Production Chemistry Crew | 8 | 2023-10-22 | 2023-10-30
AFRE 14L PB Valve recalibration | Completed | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | EA/OTUM |  | AFRE014L | OIL | CWI STOG | 8 | 2023-10-30 | 2023-11-07
ETEL 3L WHM,PB valve re-calibration | L3 - Doable | WL | 9 | E-LINE & WIRELINE | East | GBAR/KC | 1000 | ETEL003L | OIL | CWI STOG | 14 | 2024-07-08 | 2024-07-22
FORC CL 31 Bulkline 1 Riser Repair | Completed | FL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 0 |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 14 | 2024-03-05 | 2024-03-19
Transfer to FORC CL 20: CMs (4 wells - FORC 3, 25, 26, 66) | Completed | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 0 |  | OIL | CWI Well Integrity | 11 | 2024-03-19 | 2024-03-30
FORC 43S, 47L SG | Completed | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 0 |  | OIL | CWI Data Acquisition | 5 | 2024-03-30 | 2024-04-04
NUNR 3L Perforation SCON/TT Screen | L3 - Doable | WL | 9 | COILED TUBING (1.75", 1.50") | East | Soku/NunR | 400 | NUNR003L | OIL | CWI STOG | 24 | 2024-07-01 | 2024-07-25 |  | Q2
Transfer to FORC CL 5A: CM (FORC 131 - CT Fishing) | L4 - Certain | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 0 | FORC131S | OIL | CWI Well Integrity | 23 | 2024-05-03 | 2024-05-26
Transfer to FORC CL 51A: CM (FORC 130) | L4 - Certain | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 0 | FORC130L | OIL | CWI Well Integrity | 16 | 2024-05-25 | 2024-06-10
FORC 130L WHM, Perforation and SCON | L4 - Certain | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 500 | FORC130L | OIL | CWI STOG | 23 | 2024-07-02 | 2024-07-25
Move to OPUK: OPUK 35T Xmas Tree Replacement/Unsecure | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 400 | OPUK035T | OIL | CWI STOG | 14 | 2024-07-17 | 2024-07-31
OPUK 16T WSO, Re-Perforation & SCON | L3 - Doable | CT | 6 | COILED TUBING 2 (1.25") | West | Southern Swamp | 600 | OPUK016T | OIL | CWI STOG | 30 | 2024-07-05 | 2024-08-04
Transfer to CL 31: FORC 31L CO log | L4 - Certain | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 0 | FORC031L | OIL | CWI Data Acquisition | 16 | 2024-08-23 | 2024-09-08
FLOWLINE | Completed | FL | 2 | FLOWLINE | West |  | 0 |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 22 | 2024-02-01 | 2024-02-23
FORC 3 BULKLINE REPAIR | Completed | FL | 2 | FLOWLINE | West | Forcados |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 63 | 2023-08-27 | 2023-10-29
FORC 28L Hook-Up Arm Repair | Completed | FL | 2 | FLOWLINE | West | Forcados | 1000 | FORC028L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 7 | 2023-12-17 | 2023-12-24
Move to AJAT: AJAT 1S Unsecure/Acid Wash; AJAT 1L XMT Installation/WHM | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 300 | AJAT001S | OIL | CWI STOG | 16 | 2024-07-19 | 2024-08-04
OPUK 37T Xmas Tree Replacement/Unsecure | Ongoing | WL | 6 | SLICKLINE | West | Southern Swamp | 400 | OPUK037T | OIL | CWI STOG | 12 | 2024-07-31 | 2024-08-12
WIRELINE | Ongoing | WL | 3 | WIRELINE | West |  |  |  | OIL | CWI STOG | 217 | 2024-01-28 | 2024-09-01
FORC 127,152 TRSCSSV Offline Investigation | Completed | WL | 3 | WIRELINE | West | Forcados |  |  | OIL | CWI Well Integrity | 7 | 2023-08-27 | 2023-09-03
FORC 75T, 112T BHPs | Completed | WL | 3 | WIRELINE | West | Forcados |  |  | OIL | CWI Data Acquisition | 6 | 2023-10-22 | 2023-10-28
FORC 112T GLVCO/Full BHP (LAND) | Completed | WL | 3 | WIRELINE | West | Forcados | 150 | FORC112T | OIL | CWI STOG | 6 | 2023-10-29 | 2023-11-04
FORC 75T GLVCO/Full BHP (LAND) | Completed | WL | 3 | WIRELINE | West | Forcados | 150 | FORC075T | OIL | CWI STOG | 6 | 2023-11-05 | 2023-11-11
FORC 84S(SG)/L(FBHP) | Completed | WL | 3 | WIRELINE | West | Forcados |  |  | OIL | CWI Data Acquisition | 6 | 2023-11-12 | 2023-11-18
FORC LAND CMs | Completed | WL | 3 | WIRELINE | West | Forcados | 0 |  | OIL | CWI Well Integrity | 13 | 2023-11-26 | 2023-12-09
FORC 125T BHPs | Completed | WL | 3 | WIRELINE | West | Forcados | 0 | FORC125T | OIL | CWI Data Acquisition | 9 | 2023-11-26 | 2023-12-05
FORC 119; FORC 79, 114 AC9 SECURING | Completed | WL | 3 | WIRELINE | West | Forcados | 0 |  | OIL | CWI Well Integrity | 36 | 2023-12-24 | 2024-01-29
FORC 84L FBHP | Completed | WL | 3 | WIRELINE | West | Forcados | 0 | FORC084L | OIL | CWI Data Acquisition | 9 | 2024-01-28 | 2024-02-06
DBUC 12T Isolate lower zone (Nippless plug or Bimuth alloy plug )/WSO, Perf & SCON (Sandtrap XL) [Activity Deprioritized for 2024] | L4 - Certain | CT | 8 | COILED TUBING (1.5") | East | Soku/NunR | 700 | DBUC012T | OIL | CWI STOG | 23 | 2024-07-30 | 2024-08-22
FORC 87 Securing | Completed | WL | 3 | WIRELINE | West | Forcados | 0 | FORC087T | OIL | CWI Well Integrity | 8 | 2024-01-29 | 2024-02-06
FORC 127 TRSCSSV Straddle/PB Valve | Completed | WL | 3 | WIRELINE | West | Forcados | 0 | FORC127T | OIL | CWI Well Integrity | 16 | 2024-03-25 | 2024-04-10
FORC 117L Stuck MV Repair | Completed | WL | 3 | WIRELINE | West | Forcados | 0 | FORC117L | OIL | CWI Well Integrity | 23 | 2024-02-26 | 2024-03-20
EMBEDDED CREW | Ongoing | WH | 3 | EMBEDDED CREW | West |  |  |  | OIL | CWI Well Integrity | 105 | 2024-03-31 | 2024-07-14
85 Wells PM: FORC North/South Bank & Yokri Land | Ongoing | WH | 3 | EMBEDDED CREW | West | Forcados | 0 |  | OIL | CWI Well Integrity | 105 | 2024-04-01 | 2024-07-15
FLOWLINE | Completed | FL | 3 | FLOWLINE | West |  | 0 |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 22 | 2024-02-23 | 2024-03-16
FORC 84L INTEGRITY TEST | Completed | FL | 3 | FLOWLINE | West | Forcados |  | FORC084L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 16 | 2023-11-26 | 2023-12-12
FORC 113 GLL Repair (Quit Well) | Completed | FL | 3 | FLOWLINE | West | Forcados | 0 | FORC113T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 23 | 2024-02-23 | 2024-03-17
WIRELINE | Ongoing | WL | 5 | WIRELINE | West |  |  |  | OIL | CWI STOG | 189 | 2024-01-15 | 2024-07-22
OTUM 35L GLVCO | Completed | WL | 5 | WIRELINE (SPUD BARGE) | West | EA/OTUM | 324 | OTUM035L | OIL | CWI STOG AF Maintenance | 5 | 2023-01-22 | 2023-01-27
OTUM 39L GLVCO | Completed | WL | 5 | WIRELINE (SPUD BARGE) | West | EA/OTUM | 386 | OTUM039L | OIL | CWI STOG AF Maintenance | 5 | 2023-01-28 | 2023-02-02
OTUM 22S Gaslift GLVCO | Completed | WL | 5 | WIRELINE (SPUD BARGE) | West | EA/OTUM | 100 | OTUM022S | OIL | CWI STOG AF Maintenance | 6 | 2023-02-03 | 2023-02-09
OTUM 10S Gaslift GLVCO | Completed | WL | 5 | WIRELINE (SPUD BARGE) | West | EA/OTUM | 100 | OTUM010S | OIL | CWI STOG | 6 | 2023-02-19 | 2023-02-25
OTUM 8S Gaslift GLVCO | Completed | WL | 5 | WIRELINE (SPUD BARGE) | West | EA/OTUM | 100 | OTUM008S | OIL | CWI STOG | 6 | 2023-02-26 | 2023-03-04
OTUM 49T TRSCSSV Offline Investigation | Completed | WL | 5 | WIRELINE (SPUD BARGE) | West | EA/OTUM |  | OTUM049T | OIL | CWI Well Integrity | 8 | 2023-08-13 | 2023-08-21
OTUM 41L SG | Completed | WL | 5 | WIRELINE | West | EA/OTUM | 0 | OTUM041L | OIL | CWI Data Acquisition | 3 | 2023-12-01 | 2023-12-04
OTUM 41L Drift Run & SG | Completed | WL | 5 | WIRELINE | West | EA/OTUM |  | OTUM041L | OIL | CWI STOG AF Maintenance | 6 | 2023-11-26 | 2023-12-02
OTUM 29L GL Deepening | Completed | WL | 5 | WIRELINE | West | EA/OTUM | 250 | OTUM029L | OIL | CWI STOG | 7 | 2023-12-03 | 2023-12-10
OTUM 17T Gaslift GLVCO | Completed | WL | 5 | WIRELINE | West | EA/OTUM | 200 | OTUM017T | OIL | CWI STOG | 7 | 2023-12-10 | 2023-12-17
OTUM 12S Gaslift GLVCO/Deepening | Completed | WL | 5 | WIRELINE | West | EA/OTUM | 200 | OTUM012S | OIL | CWI STOG | 7 | 2023-12-17 | 2023-12-24
OTUM 48T TRSCSSV Straddle/PB Valve | Completed | WL | 5 | WIRELINE | West | EA/OTUM | 0 | OTUM048T | OIL | CWI Well Integrity | 16 | 2024-01-15 | 2024-01-31
OTUM 49T TRSCSSV Straddle/PB Valve | Completed | WL | 5 | WIRELINE | West | EA/OTUM | 0 | OTUM049T | OIL | CWI Well Integrity | 9 | 2024-01-30 | 2024-02-08
OTUM 5L/S Ssecuring (Deep Set Plug) | Completed | WL | 5 | WIRELINE | West | EA/OTUM | 0 |  | OIL | CWI Well Integrity | 8 | 2024-02-07 | 2024-02-15
OTUM 11T Deep Set Plug | Completed | WL | 5 | WIRELINE | West | EA/OTUM | 0 | OTUM011T | OIL | CWI Well Integrity | 8 | 2024-02-22 | 2024-03-01
OTUM 30L/S, 7S, 17T SG | Completed | WL | 5 | WIRELINE | West | EA/OTUM | 0 |  | OIL | CWI Data Acquisition | 12 | 2024-03-13 | 2024-03-25
Move to ESCB: ESCB 2L, 6L/S, 14L SG | L3 - Doable | WL | 5 | WIRELINE | West | EA/OTUM | 0 |  | OIL | CWI Data Acquisition | 22 | 2024-05-27 | 2024-06-18
CM: SAGR 3 & 5 | Completed | WL | 5 | WIRELINE | West | EA/OTUM | 0 |  | OIL | CWI Well Integrity | 7 | 2024-04-23 | 2024-04-30
CM: OTUM 34, 46, 54, 56 & 30 | Completed | WL | 5 | WIRELINE | West | EA/OTUM | 0 |  | OIL | CWI Well Integrity | 21 | 2024-03-25 | 2024-04-15
COILED TUBING (1.25") | L3 - Doable | CT | 5 | COILED TUBING (1.25") | West |  |  |  | OIL | CWI STOG | 57 | 2024-03-25 | 2024-05-21
Transfer to FODPA: FORC 124L WHM, Zone change (Plugging/ Reperforation, SCON, N2 lift) | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 550 | FORC124L | OIL | CWI STOG | 29 | 2024-07-25 | 2024-08-23
Move to OPUK: OPUK 32T Zone Change + Re-perf +SCON | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 500 | OPUK032T | OIL | CWI STOG | 21 | 2024-08-04 | 2024-08-25
Move to OPUK: OPUK 14T Re-Perforation & SCON | L3 - Doable | CT | 6 | COILED TUBING 2 (1.25") | West | Southern Swamp | 400 | OPUK014T | OIL | CWI STOG | 36 | 2024-08-04 | 2024-09-09
EMBEDDED CREW | Ongoing | WH | 5 | EMBEDDED CREW | West |  |  |  | OIL | CWI Well Integrity | 56 | 2024-01-21 | 2024-03-17
57 Wells PM: OTUM | Completed | WH | 5 | EMBEDDED CREW | West | EA/OTUM | 0 |  | OIL | CWI Well Integrity | 56 | 2024-01-21 | 2024-03-17
FLOWLINE 1 | Ongoing | FL | 5 | FLOWLINE 1 | West |  |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 169 | 2024-02-11 | 2024-07-29
OTUM 35L GAS LINE REPLACEMENT | Completed | FL | 5 | FLOWLINE 1 | West | EA/OTUM | 0 | OTUM035L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 15 | 2022-12-14 | 2022-12-29
OTUM 39L GAS LINE REPLACEMENT | Completed | FL | 5 | FLOWLINE 1 | West | EA/OTUM | 0 | OTUM039L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 15 | 2022-12-29 | 2023-01-13
OTUM 29S Flowline Repair | Completed | FL | 5 | FLOWLINE 1 | West | EA/OTUM | 350 | OTUM029S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 5 | 2023-01-14 | 2023-01-19
OTUM 8S FLOWLINE REPAIR | Completed | FL | 5 | FLOWLINE 1 | West | EA/OTUM |  | OTUM008S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 70 | 2023-07-30 | 2023-10-08
OTUM 19T Flowline Repair | Completed | FL | 5 | FLOWLINE 1 | West | EA/OTUM | 500 | OTUM019T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 13 | 2023-04-16 | 2023-04-29
ESCB 15L Flowline Repair | Completed | FL | 5 | FLOWLINE 1 | West | EA/OTUM | 750 | ESCB015L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 27 | 2023-04-30 | 2023-05-27
ESCB 15L Flowline Repair | Completed | FL | 5 | FLOWLINE 1 | West | EA/OTUM | 750 | ESCB015S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 27 | 2023-04-30 | 2023-05-27
OTUM 41L FLOWLINE REPAIR | Completed | FL | 5 | FLOWLINE 1 | West | EA/OTUM |  | OTUM041L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 63 | 2023-04-30 | 2023-07-02
OTUM 2L FLOWLINE REPLACEMENT (1KM) | Completed | FL | 5 | FLOWLINE 1 | West | EA/OTUM |  | OTUM002L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 49 | 2023-05-28 | 2023-07-16
OTUM 17T GASLINE REPAIR | Completed | FL | 5 | FLOWLINE 1 | West | EA/OTUM |  | OTUM017T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 56 | 2023-07-16 | 2023-09-10
OTUM 57T GASLINE REPAIR | Completed | FL | 5 | FLOWLINE 1 | West | EA/OTUM | 470 | OTUM057T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 63 | 2023-10-15 | 2023-12-17
OTUM 48T GLLR (Quit Well) | Completed | FL | 5 | FLOWLINE 1 | West | EA/OTUM | 0 | OTUM048T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 16 | 2024-04-24 | 2024-05-10
OTUM 46S FL Replacement | L3 - Doable | FL | 5 | FLOWLINE 1 | West | EA/OTUM | 0 | OTUM046S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 29 | 2024-05-09 | 2024-06-07
SEIB 2L/S & SEIB 3L/S BULKLINE REPLACEMENT | L3 - Doable | FL | 6 | FLOWLINE 2 | West | Southern Swamp | 504 | SEIB002L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 15 | 2024-08-27 | 2024-09-11
FLOWLINE 2 | Ongoing | FL | 5 | FLOWLINE 2 | West |  |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 63 | 2024-02-11 | 2024-04-14
KANB 3L FLOWLINE REPAIR | L3 - Doable | FL | 6 | FLOWLINE 6 | West | Southern Swamp | 314 | KANB003L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 62 | 2024-07-14 | 2024-09-14
OPUK 10S Contingency Tbg wash/Reperf/SCON | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 500 | OPUK010S | OIL | CWI STOG | 22 | 2024-08-25 | 2024-09-16
SAGR 5S GLLR (Quit Well) | Completed | FL | 5 | FLOWLINE 2 | West | EA/OTUM | 0 | SAGR005S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 14 | 2024-05-09 | 2024-05-23
SLICKLINE | Ongoing | WL | 6 | SLICKLINE | West |  |  |  | OIL | CWI STOG | 259 | 2024-01-26 | 2024-10-11
CO Logs: BENS 1L, 10L; OGBO (1); SGs: TUNU 14L | Completed | WL | 6 | SLICKLINE | West | Southern Swamp |  |  | OIL | CWI Data Acquisition | 24 | 2022-12-21 | 2023-01-14
TUNU 14 FBHP, AJAT 1 SG | Completed | WL | 6 | SLICKLINE | West | Southern Swamp |  |  | OIL | CWI Data Acquisition | 17 | 2023-05-21 | 2023-06-07
OPUK 12L WHM | Completed | WL | 6 | SLICKLINE | West | Southern Swamp | 110 | OPUK012L | OIL | CWI STOG | 7 | 2023-06-18 | 2023-06-25
BENS 6S DRIFT RUN | Completed | WL | 6 | SLICKLINE | West | Southern Swamp | 350 | BENS006S | OIL | CWI STOG AF Maintenance | 5 | 2023-06-28 | 2023-07-03
5 CMs (OPUK7,16,32,33 & OPNO28) Quit Well Rest (OPUK 12, 18 & 36; OPNO28) | Ongoing | WL | 6 | SLICKLINE | West | Southern Swamp | 0 |  | OIL | CWI Well Integrity | 14 | 2024-03-28 | 2024-04-11
OPUK 33 Noise log | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 0 | OPUK033L | OIL | CWI Data Acquisition | 8 | 2024-06-23 | 2024-07-01
OPUK 33S, 9T, 18L SG | Completed | WL | 6 | SLICKLINE | West | Southern Swamp | 0 |  | OIL | CWI Data Acquisition | 10 | 2024-01-22 | 2024-02-01
DODN 3T, 4T SG | Completed | WL | 6 | SLICKLINE | West | Southern Swamp | 0 |  | OIL | CWI Data Acquisition | 8 | 2024-03-04 | 2024-03-12
Move to Akono: AKON 1 Securing | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 0 | AKON001L | OIL | CWI Well Integrity | 11 | 2024-08-12 | 2024-08-23
Move to Benisede: BENS 4, 15, 19 Securing: CM: BENS 20 & 30 Wells | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 0 |  | OIL | CWI Well Integrity | 21 | 2024-04-11 | 2024-05-02
Move to Opukushi North: OPNO 30 Securing | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 0 | OPNO030S | OIL | CWI Well Integrity | 14 | 2024-05-02 | 2024-05-16
OBEL 5T Tubing Clean out ( Sand and SCON), RePerf, SCON (sandtrapXL) and PBV Installation | L5 - Ready | CT | 7 | COILED TUBING (1.25") | East | Rumuahia | 470 | OBEL005T | OIL | CWI STOG AF Maintenance | 30 | 2024-08-26 | 2024-09-25 | Q3
Move to Tunu: TUNU 6, 9 Securing | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 0 |  | OIL | CWI Well Integrity | 14 | 2024-08-22 | 2024-09-05
CM: TUNU 8S, 19 | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 0 |  | OIL | CWI Well Integrity | 10 | 2024-09-05 | 2024-09-15
Move to KANB: CM: KANB 5, 4 | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 0 |  | OIL | CWI Well Integrity | 14 | 2024-09-15 | 2024-09-29
CM: OPNO 28S, 26 OPUK Wells; OPUK 4 upfront Drift Run/Integrity confirmation | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 0 |  | OIL | CWI Well Integrity | 10 | 2024-06-30 | 2024-07-10
Move to Benisede: CM: BENS 20 & 30 Wells | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 0 |  | OIL | CWI Well Integrity | 28 | 2024-10-13 | 2024-11-10
CM: 12 Ogbotobo Wells | L3 - Doable | WL | 6 | SLICKLINE | West | Southern Swamp | 0 |  | OIL | CWI Well Integrity | 22 | 2024-11-10 | 2024-12-02
SLICKLINE 2 | Ongoing | WL | 6 | SLICKLINE 2 | West |  |  |  | OIL | CWI STOG | 78 | 2024-05-27 | 2024-08-13
SEIB 2L/S & SEIB 3L/S BULKLINE REPLACEMENT | L3 - Doable | FL | 6 | FLOWLINE 2 | West | Southern Swamp | 1109 | SEIB002S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 15 | 2024-09-11 | 2024-09-26
FORC 31L WHM, Sand wash, PERF, SCON, N2 lift | L3 - Doable | CT | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 400 | FORC031L | OIL | CWI STOG | 21 | 2024-09-07 | 2024-09-28
ESCB 13S FLOWLINE REPAIR | L3 - Doable | FL | 5 | FLOWLINE 1 | West | EA/OTUM | 800 | ESCB013S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 29 | 2024-08-30 | 2024-09-28
COILED TUBING (1.25") | Ongoing | CT | 6 | COILED TUBING (1.25") | West |  |  |  | OIL | CWI STOG | 324 | 2024-01-07 | 2024-11-26
BENS 2T GSO + Reperf, SCON, WHM | Completed | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 500 | BENS002T | OIL | CWI STOG AF Maintenance | 76 | 2023-03-19 | 2023-06-03
BENS 17L SCON Cleanout. | Completed | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 420 | BENS017L | OIL | CWI STOG AF Maintenance | 20 | 2023-07-16 | 2023-08-05
BENS 18L SCON Cleanou/XA Sleeve open up. | Completed | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 400 | BENS018L | OIL | CWI STOG AF Maintenance | 27 | 2023-08-06 | 2023-09-02
BENS 10S Acid Wash, WHM (Install CCU) & Open Up | Completed | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 300 | BENS010S | OIL | CWI STOG | 34 | 2023-09-03 | 2023-10-07
New Oil PDHG (TUNU 18T) + Equipment Change Out | Completed | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 0 | TUNU018T | OIL | CWI STOG | 22 | 2024-01-07 | 2024-01-29
Move to OPUK: OPUK 35T Xmas Tree Replacement/Unsecure/Tubing Wash/Secure & Retrieve Xmas Tree | Completed | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 0 | OPUK035T | OIL | CWI STOG | 61 | 2024-02-20 | 2024-04-21
OPUK 4S Attic Perforation | L3 - Doable | CT | 6 | COILED TUBING 2 (1.25") | West | Southern Swamp | 550 | OPUK004S | OIL | CWI STOG | 24 | 2024-09-09 | 2024-10-03
AHIA 14S N2 LIFT | L5 - Ready | CT | 7 | COILED TUBING (1.25") | East | Rumuahia | 495 | AHIA014S | OIL | CWI STOG | 7 | 2024-09-30 | 2024-10-07
KANB 3S FLOWLINE REPAIR (6" Line) | L3 - Doable | FL | 6 | FLOWLINE 5 | West | Southern Swamp | 500 | KANB003S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 36 | 2024-09-01 | 2024-10-07
OPUK 15T Perforation & SCON | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 400 | OPUK015T | OIL | CWI STOG | 22 | 2024-09-16 | 2024-10-08
SEIB 2L/S & SEIB 3L/S BULKLINE REPLACEMENT | L3 - Doable | FL | 6 | FLOWLINE 2 | West | Southern Swamp | 919 | SEIB003S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 15 | 2024-09-26 | 2024-10-11
AHIA 3S HUD Investigation, Fishing, Solvent Soak & MFC | L3 - Doable | CT | 7 | COILED TUBING (1.25") | East | Rumuahia | 1000 | AHIA003S | OIL | CWI STOG | 14 | 2024-10-07 | 2024-10-21
OPUK 25T XMT REPLACEMENT & N2 LIFT | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 400 | OPUK025T | OIL | CWI STOG AF Maintenance | 15 | 2025-03-25 | 2025-04-09
OPUK 34T Tubbing straddle | L3 - Doable | WL | 6 | SLICKLINE 2 | West | Southern Swamp | 500 | OPUK034T | OIL | CWI STOG | 15 | 2024-10-07 | 2024-10-22
SEIB 1T DEWAXING/WHM | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 394 | SEIB001T | OIL | CWI STOG AF Maintenance | 8 | 2024-10-16 | 2024-10-24
OPUK 22T Screen Wash + N2 lift | L3 - Doable | CT | 6 | COILED TUBING 2 (1.25") | West | Southern Swamp | 500 | OPUK022T | OIL | CWI STOG | 23 | 2024-10-03 | 2024-10-26
SEIB 2L/S & SEIB 3L/S BULKLINE REPLACEMENT | L3 - Doable | FL | 6 | FLOWLINE 2 | West | Southern Swamp | 1335 | SEIB003L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 15 | 2024-10-11 | 2024-10-26
SEIB 2S DEWAXING/WHM | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 0 | SEIB002S | OIL | CWI STOG AF Maintenance | 9 | 2024-10-24 | 2024-11-02
SEIB 3S DEWAXING/WHM | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 0 | SEIB003S | OIL | CWI STOG AF Maintenance | 9 | 2024-11-01 | 2024-11-10
DREDGING | L3 - Doable | DG | 6 | DREDGING | West |  |  |  | OIL | CIVIL/GEOMATICS Location Preparation | 80 | 2024-05-15 | 2024-08-03
BENS Dredging: (BENS 9L/S; 1L; BENS CMs) | L3 - Doable | DG | 6 | DREDGING | West | Southern Swamp | 0 |  | OIL | CIVIL/GEOMATICS Location Preparation | 170 | 2024-02-12 | 2024-07-31
EMBEDDED CREW | Ongoing | WH | 6 | EMBEDDED CREW | West |  |  |  | OIL | CWI Well Integrity | 98 | 2024-02-04 | 2024-05-12
PM (98 Wells): BENS, KANB, OPUK, OPNO, OGBO, TUNU | Ongoing | WH | 6 | EMBEDDED CREW | West | Southern Swamp |  |  | OIL | CWI Well Integrity | 98 | 2024-02-04 | 2024-05-12
FLOWLINE 1 | Ongoing | FL | 6 | FLOWLINE 1 | West |  |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 178 | 2024-02-20 | 2024-08-16
OPUK 12S FLOWLINE REPAIR | Completed | FL | 6 | FLOWLINE 1 | West | Southern Swamp | 446 | OPUK012S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 10 | 2023-01-02 | 2023-01-12
OPUK 12L FLOWLINE REPAIR | Completed | FL | 6 | FLOWLINE 1 | West | Southern Swamp |  | OPUK012L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 11 | 2023-01-13 | 2023-01-24
KANB 3L, 4S, 5L, 6T SCOPING | Completed | FL | 6 | FLOWLINE 1 | West | Southern Swamp |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 20 | 2023-01-15 | 2023-02-04
BENS 6S PLATFORM REPAIR, FLOWLINE TEST | Completed | FL | 6 | FLOWLINE 1 | West | Southern Swamp |  | BENS006S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 15 | 2023-10-01 | 2023-10-16
BENS 18L FLOWLINE REPLACEMENT | Completed | FL | 6 | FLOWLINE 1 | West | Southern Swamp |  | BENS018L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 42 | 2023-06-25 | 2023-08-06
OPUK 13L/S/35T/37T FLOWLINE INTEGRITY TEST | Completed | FL | 6 | FLOWLINE 1 | West | Southern Swamp |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 20 | 2023-10-29 | 2023-11-18
BENS 9S & 9L FLOWLINE INTEGRITY TEST | L3 - Doable | FL | 6 | FLOWLINE 1 | West | Southern Swamp | 0 |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 14 | 2024-04-27 | 2024-05-11
BENS 1L FL Replacement | L3 - Doable | FL | 6 | FLOWLINE 1 | West | Southern Swamp | 0 | BENS001L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 30 | 2024-05-11 | 2024-06-10
OPUK 34T FLOWLINE REPLACEMENT | L3 - Doable | FL | 6 | FLOWLINE 1 | West | Southern Swamp | 0 | OPUK034T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 91 | 2024-07-08 | 2024-10-07
FLOWLINE 2 | Ongoing | FL | 6 | FLOWLINE 2 | West |  |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 258 | 2024-02-09 | 2024-10-24
OPNO 21T FLOWLINE REPLACEMENT | Completed | FL | 6 | FLOWLINE 2 | West | Southern Swamp | 600 | OPNO021T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 35 | 2023-10-29 | 2023-12-03
OPUK 26T FLOWLINE REPLACEMENT | L3 - Doable | FL | 6 | FLOWLINE 2 | West | Southern Swamp | 0 | OPUK026T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 80 | 2024-02-09 | 2024-04-29
OPUK 7T FLOWLINE REPLACEMENT /OPUK 14 & 16 FL Integrity Test | L3 - Doable | FL | 6 | FLOWLINE 2 | West | Southern Swamp | 0 | OPUK007T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 48 | 2024-04-28 | 2024-06-15
SEIB 1T FLOWLINE REPLACEMENT | L3 - Doable | FL | 6 | FLOWLINE 2 | West | Southern Swamp | 0 | SEIB001T | OIL | OABP JV/OABP AF/OABP AF Maintenance | 21 | 2024-08-07 | 2024-08-28
OPUK 13L Unsecure, Xmas Tree Replacement & Open Up | L3 - Doable | WL | 6 | SLICKLINE 2 | West | Southern Swamp | 300 | OPUK013L | OIL | CWI STOG | 13 | 2024-10-22 | 2024-11-04
AHIA 1S WHM, Unsecuring, Solvent Soak, MFC, PB Valve Installation & N2 Lift. | L3 - Doable | CT | 7 | COILED TUBING (1.25") | East | Rumuahia | 200 | AHIA001S | OIL | CWI STOG | 21 | 2024-10-21 | 2024-11-11
KANB 4L: FL SECTIONAL REPLACEMENT | L3 - Doable | FL | 6 | FLOWLINE 6 | West | Southern Swamp | 500 | KANB004L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 58 | 2024-09-14 | 2024-11-11
AHIA 7L WHM, Annulus Investigation, Unsecuring & PB Valve Installation | L3 - Doable | WL | 7 | WIRELINE | East | Rumuahia | 250 | AHIA007L | OIL | CWI STOG | 15 | 2024-10-28 | 2024-11-12
FLOWLINE 3 | Ongoing | FL | 6 | FLOWLINE 3 | West |  |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 94 | 2024-02-09 | 2024-05-13
OPUK 24T FLOWLINE REPAIR/OPNO005L Surface Bulking | L3 - Doable | FL | 6 | FLOWLINE 3 | West | Southern Swamp | 0 |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 94 | 2024-03-11 | 2024-06-13
FLOWLINE 4 | Ongoing | FL | 6 | FLOWLINE 4 | West |  |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 186 | 2024-04-09 | 2024-10-12
OPUK 35/37 FLOWLINE REPAIR (6" Line) | L3 - Doable | FL | 6 | FLOWLINE 4 | West | Southern Swamp | 0 |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 75 | 2024-05-21 | 2024-08-04
FLOWLINE 5 | Ongoing | FL | 6 | FLOWLINE 5 | West |  |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 179 | 2024-02-20 | 2024-08-17
OPUK 13S Unsecure, Xmas Tree Replacement & Open Up | L3 - Doable | WL | 6 | SLICKLINE 2 | West | Southern Swamp | 300 | OPUK013S | OIL | CWI STOG | 13 | 2024-11-04 | 2024-11-17
AHIA 5L WHM/Unsecuring / Sand bailing/Straddle/ N2 lifting | L3 - Doable | CT | 7 | COILED TUBING (1.25") | East | Rumuahia | 350 | AHIA005L | OIL | CWI STOG | 14 | 2024-11-11 | 2024-11-25
FLOWLINE 6 | Ongoing | FL | 6 | FLOWLINE 6 | West |  |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 127 | 2024-02-20 | 2024-06-26
GBAR 5T XMT& ADAPTER SPOOL INSTALLATION, TRSCSSV LOCK-OUT and PB VALVE | L3 - Doable | WL | 9 | E-LINE & WIRELINE | East | GBAR/KC | 500 | GBAR005T | OIL | CWI STOG | 21 | 2024-11-10 | 2024-12-01
Move to OPOM: OPOM 1S WRSCSSV redress scope + contingent PBV installation + N2 Lift | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 817 | OPOM001S | OIL | CWI STOG AF Maintenance | 25 | 2024-11-09 | 2024-12-04
FLOWLINE 7 | Ongoing | FL | 6 | FLOWLINE 7 | West |  |  |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 85 | 2024-07-15 | 2024-10-08
OPOM 1L/S FLOWLINE REPAIR (6" Line) | L3 - Doable | FL | 6 | FLOWLINE 7 | West | Southern Swamp | 0 |  | OIL | OABP JV/OABP AF/OABP AF Maintenance | 120 | 2024-09-21 | 2025-01-19
Transfer to FORC CL 31 2 SECURING (FORC31,50) 2 CMs (FORC31,50) | Completed | WL | 2 | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE | West | Forcados | 0 |  | OIL | CWI Well Integrity | 15 | 2023-12-03 | 2023-12-18
AHIA 11L WHM, Zone Change | L3 - Doable | CT | 7 | COILED TUBING (1.25") | East | Rumuahia | 480 | AHIA011L | OIL | CWI STOG | 14 | 2024-11-25 | 2024-12-09
AHIA 9S WHM, Unsecuring, Milling, SCON, N2 lifting, TT screen | L3 - Doable | CT | 7 | COILED TUBING (1.25") | East | Rumuahia | 200 | AHIA009S | OIL | CWI STOG | 14 | 2024-12-09 | 2024-12-23 | Q4
KANB 005S FLRR | L3 - Doable | FL | 6 | FLOWLINE 1 | West | Southern Swamp | 0 | KANB005S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 21 | 2024-12-10 | 2024-12-31
KANB 005L FLRR | L3 - Doable | FL | 6 | FLOWLINE 1 | West | Southern Swamp | 0 | KANB005L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 21 | 2024-12-30 | 2025-01-20
AKON 001S FLRR | L3 - Doable | FL | 6 | FLOWLINE 1 | West | Southern Swamp | 0 | AKON001S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 21 | 2026-12-23 | 2027-01-13
OPUK 033S FLRR | L3 - Doable | FL | 6 | FLOWLINE 2 | West | Southern Swamp | 0 | OPUK033S | OIL | OABP JV/OABP AF/OABP AF Maintenance | 21 | 2025-01-26 | 2025-02-16
OPUK 033S: Integrity Restoration + WHM + FLRR | L3 - Doable | CT | 6 | COILED TUBING (1.25") | West | Southern Swamp | 350 | OPUK033S | OIL | CWI STOG | 10 | 2025-03-15 | 2025-03-25
OPUK 033L Bulking | L3 - Doable | FL | 6 | FLOWLINE 2 | West | Southern Swamp | 0 | OPUK033L | OIL | OABP JV/OABP AF/OABP AF Maintenance | 11 | 2025-02-15 | 2025-02-26
Dummy | L3 - Doable | WL | 5 | EMBEDDED CREW | West | EA/OTUM |  |  | OIL | CWI Well Integrity | 1 | 2030-01-21 | 2030-01-22
Dummy Wireline | Ongoing | WL | 3 | WIRELINE | West | Forcados |  |  | OIL | CWI Well Integrity | 1 | 2027-12-30 | 2027-12-31
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
[11 empty] | 1 | 2024-06-06 | 2024-06-07
Formulas:
Planned Finish Date = +Table33[[#This Row],[Planned Start Date]]+Table33[[#This Row],[Activity Duration]]

## Notes
No
Forcados Node
| Q1 2024 | 2880 | bopd
| Q2 2024 | 4100 | bopd
| Q3 2024 | 2350 | bopd

## LIST (hidden)
Completed | CT | 1 | CARACAL PIONEERCOILED TUBING (1.75")/E-Line/WL | East | EA/OTUM | ADIB001L | GAS | CIVIL/GEOMATICS Location Preparation
Executed | DG | 2 | COILED TUBING (1.25") | West | Forcados | ADIB001S | OIL | CWI Data Acquisition
L3 - Doable | FL | 3 | COILED TUBING (1.5") |  | GBAR/KC | ADIB002L |  | CWI STOG
L4 - Certain | GEO | 4 | COILED TUBING (1.75", 1.50") |  | Rumuahia | ADIB002S |  | CWI STOG AF
L4 - Doable | PC | 5 | COILED TUBING 2 (1.25") |  | Soku/NunR | ADIB003T |  | CWI STOG AF Maintenance
L5 - Ready | WH | 6 | DREDGING |  | Southern Swamp | ADIB004L |  | CWI Well Integrity
Ongoing | WL | 7 | E-LINE |  |  | ADIB004S |  | OABP JV/OABP AF/OABP AF Maintenance
|  | 8 | E-LINE & SLICKLINE |  |  | ADIB005L |  | Production Chemistry Crew
|  | 9 | E-LINE & WIRELINE |  |  | ADIB005S
|  |  | EMBEDDED CREW |  |  | ADIB006T
|  |  | FLOWLINE |  |  | ADIB007T
|  |  | FLOWLINE (LB Grande) |  |  | ADIB008L
|  |  | FLOWLINE 1 |  |  | ADIB008S
|  |  | FLOWLINE 2 |  |  | ADIB010L
|  |  | FLOWLINE 3 |  |  | ADIB010S
|  |  | FLOWLINE 4 |  |  | ADIB012T
|  |  | FLOWLINE 5 |  |  | ADIB013T
|  |  | FLOWLINE 6 |  |  | ADIB016T
|  |  | FLOWLINE 7 |  |  | ADIB017T
|  |  | FLOWLINE 8 |  |  | ADIB018T
|  |  | JUB (LAYEMAMUS) |  |  | ADIB019L
|  |  | JUB (LAYEMAMUS) WIRELINE/SLICKLINE |  |  | ADIB019S
|  |  | JUB (WSXIX)COILED TUBING (1.5")/ WIRELINE |  |  | ADIB021T
|  |  | PC |  |  | ADIB023L
|  |  | SLICKLINE |  |  | ADIB023S
|  |  | SLICKLINE 2 |  |  | ADIB024L
|  |  | WIRELINE |  |  | ADIB024S
|  |  | WIRELINE (LAND) |  |  | ADIB025L
|  |  | WIRELINE (SPUD BARGE) |  |  | ADIB025S
ADIB026L
ADIB026S
ADIB027L
ADIB027S
ADNE001L
ADNE001S
ADNE002L
ADNE002S
ADNE004L
ADNE004S
AFRE004L
AFRE004S
AFRE005L
AFRE005S
AFRE006T
AFRE007L
AFRE007S
AFRE008L
AFRE008S
AFRE009L
AFRE009S
AFRE010L
AFRE010S
AFRE011L
AFRE011S
AFRE013L
AFRE013S
AFRE014L
AFRE014S
AFRE015T
AGBA001L
AGBA001S
AHIA001L
AHIA001S
AHIA002L
AHIA002S
AHIA003L
AHIA003S
AHIA004L
AHIA004S
AHIA005L
AHIA005S
AHIA006L
AHIA006S
AHIA007L
AHIA007S
AHIA008L
AHIA008S
AHIA009C
AHIA009L
AHIA009S
AHIA009T
AHIA010L
AHIA010S
AHIA011L
AHIA011S
AHIA012L
AHIA012S
AHIA013T
AHIA014L
AHIA014S
AJAT001L
AJAT001S
AKON001L
AKON001S
BELE001L
BELE001S
BELE002T
BELE003L
BELE003S
BELE004T
BELE005L
BELE005S
BELE006L
BELE006S
BELE007L
BELE007S
BELE008T
BELE009T
BELE010L
BELE010S
BELE011T
BELN001T
BENS001L
BENS001S
BENS002T
BENS003T
BENS004L
BENS004S
BENS005T
BENS006L
BENS006S
BENS009L
BENS009S
BENS010L
BENS010S
BENS011L
BENS011S
BENS013T
BENS014L
BENS014S
BENS015L
BENS015S
BENS016T
BENS017L
BENS017S
BENS018L
BENS018S
BENS019L
BENS019S
BENS020T
BENS021L
BENS021S
BENS022T
BENS023L
BENS023S
BENS024L
BENS024S
DBUC001L
DBUC001S
DBUC002T
DBUC003T
DBUC006T
DBUC008T
DBUC009T
DBUC010T
DBUC011T
DBUC012T
DBUC013T
DBUC014T
DBUC015T
DODN003T
DODN004T
EAZZ019L
EAZZ019S
EAZZ019T
EAZZ020T
EAZZ021T
EAZZ022T
EAZZ023T
EAZZ024T
EAZZ025T
EAZZ026T
EAZZ027T
EAZZ028T
EAZZ029T
EAZZ030T
EAZZ031T
EAZZ032T
EAZZ033T
EAZZ034T
EAZZ035T
EAZZ036T
EAZZ037T
EAZZ038T
EAZZ042T
EAZZ043T
EAZZ045T
EAZZ046T
EAZZ047T
EAZZ048T
EAZZ049T
EAZZ050T
EAZZ051T
EAZZ053T
EAZZ054T
EAZZ055T
EAZZ056T
EAZZ057L
EAZZ057S
EAZZ058L
EAZZ058S
EAZZ059T
EGBM001L
EGBM001S
EGBM002C
EGBM002L
EGBM003C
EGBM003L
EGBM003S
EGBM004L
EGBM004S
EGBM006L
EGBM006S
EGBM007L
EGBM007S
EGBM008L
EGBM008S
EGBM009L
EGBM009S
EGBW001L
EGBW001S
EGBW002T
EGBW004L
EGBW004S
EGBW005T
EGBW006L
EGBW006S
EGBW007T
EGBW009S
EGBW010T
EGBW011L
EGBW011S
EGBW012L
EGBW012S
EGBW013T
EGBW014L
EGBW014S
EGBW015T
EGBW016T
EGBW017T
EGBW018T
EGBW020T
EJAZ006T
EJAZ007T
EJAZ008T
EJAZ009T
EJAZ010T
EJAZ012T
ENWH001T
ENWH002T
ENWH007T
ENWH008T
ENWH009T
EPUZ002T
EPUZ003T
EPUZ004T
ESCB001L
ESCB001S
ESCB002L
ESCB002S
ESCB003T
ESCB004L
ESCB004S
ESCB005L
ESCB005S
ESCB006L
ESCB006S
ESCB007L
ESCB007S
ESCB008L
ESCB008S
ESCB010L
ESCB010S
ESCB011L
ESCB011S
ESCB012L
ESCB012S
ESCB013L
ESCB013S
ESCB014L
ESCB014S
ESCB015L
ESCB015S
ETEL001L
ETEL001S
ETEL002L
ETEL002S
ETEL003L
ETEL003S
ETEL006T
ETEL007L
ETEL007S
ETEL008L
ETEL008S
ETEL008T
ETEL009T
ETEL010L
ETEL010S
ETEL011T
ETEL012T
ETEL013T
ETEL014T
ETEL015L
ETEL015S
FORC002L
FORC002S
FORC003L
FORC003S
FORC004L
FORC004S
FORC005L
FORC005S
FORC006C
FORC007C
FORC008C
FORC009L
FORC009S
FORC011L
FORC011S
FORC013C
FORC014C
FORC015L
FORC015S
FORC016T
FORC017C
FORC019L
FORC019S
FORC020L
FORC020S
FORC022T
FORC023L
FORC023S
FORC024L
FORC024S
FORC025T
FORC026L
FORC026S
FORC027L
FORC027S
FORC028L
FORC028S
FORC029L
FORC029S
FORC030L
FORC030S
FORC031L
FORC031S
FORC032L
FORC032S
FORC033L
FORC033S
FORC034L
FORC034S
FORC037L
FORC037S
FORC038T
FORC041L
FORC041S
FORC043L
FORC043S
FORC046L
FORC046S
FORC047L
FORC047S
FORC048L
FORC048S
FORC049T
FORC050L
FORC050S
FORC051T
FORC052L
FORC052S
FORC054L
FORC054S
FORC056L
FORC056S
FORC058L
FORC058S
FORC059L
FORC059S
FORC061L
FORC061S
FORC062T
FORC063L
FORC063S
FORC064L
FORC064S
FORC064T
FORC065L
FORC065S
FORC066L
FORC066S
FORC068T
FORC069T
FORC071T
FORC072T
FORC073L
FORC073S
FORC074T
FORC075T
FORC076T
FORC078T
FORC079T
FORC080C
FORC081L
FORC081S
FORC082L
FORC082S
FORC083T
FORC084L
FORC084S
FORC085T
FORC086T
FORC087T
FORC088T
FORC089T
FORC090T
FORC091L
FORC091S
FORC093T
FORC094L
FORC094S
FORC095T
FORC100L
FORC100S
FORC101T
FORC102L
FORC102S
FORC103L
FORC103S
FORC104T
FORC107T
FORC109T
FORC110T
FORC111T
FORC112T
FORC113T
FORC114L
FORC114S
FORC115T
FORC117L
FORC117S
FORC119L
FORC119S
FORC121T
FORC122L
FORC122S
FORC123L
FORC123S
FORC124L
FORC124S
FORC125T
FORC126L
FORC126S
FORC127T
FORC129L
FORC129S
FORC130L
FORC130S
FORC131L
FORC131S
FORC132L
FORC132S
FORC133T
FORC134L
FORC134S
FORC135L
FORC135S
FORC136T
FORC137T
FORC138T
FORC139T
FORC140T
FORC141L
FORC141S
FORC142L
FORC142S
FORC143T
FORC144T
FORC145T
FORC146T
FORC147T
FORC148T
FORC150T
FORC151L
FORC151S
FORC152T
FORC153T
GBAR001L
GBAR001S
GBAR004T
GBAR005T
GBAR006T
GBAR007T
GBAR008T
GBAR009T
GBAR010T
GBAR011T
GBAR012T
GBAR013T
GBAR014T
GBAR015T
GBAR016T
GBAR017T
GBAR019T
GBAR020T
GBAR021T
GBAR022T
GBAR023T
GBAR024T
GBAR025T
GBAR028T
KANB002T
KANB003L
KANB003S
KANB004L
KANB004S
KANB005L
KANB005S
KANB006T
KANB007L
KANB007S
KANB008T
KANB009T
KANB010T
KOCR002T
KOCR003T
KOCR005T
KOCR006T
KOCR007T
KOCR009T
KOCR010T
KOCR011T
KOCR012T
KOCR013T
KOCR014T
KOCR015T
KOCR016T
KOCR017T
KOCR018T
KOCR019T
KOCR020T
KOCR021T
KOCR022T
KOCR023T
KOCR024T
KOCR025T
KOCR026T
KOCR027T
KOCR028T
KOCR029T
KOCR030T
KOCR031T
KOCR032T
KOCR034L
KOCR035T
KOCR037T
KOCR039T
KOCR040T
KOCR043T
KOCR044T
KOCR045T
KOCR046T
KOCR047T
KOCR048T
KOCR049T
KOMA002T
KOMA003T
KOMA004T
KOMA005T
KOMA006T
KOMA007T
KOMA008T
KOMA009T
KOMA010T
KOMA011T
MINI001L
MINI001S
MINI002T
MINI003L
MINI003S
MINI004L
MINI004S
MINI005L
MINI005S
MINI008T
MINI009T
NUNR001T
NUNR003L
NUNR003S
NUNR004L
NUNR004S
NUNR005T
NUNR006L
NUNR006S
NUNR007L
NUNR007S
NUNR010T
NUNR011L
NUNR011S
NUNR012L
NUNR012S
NUNR013T
NUNR015L
NUNR015S
NUNR016T
NUNR017L
NUNR017S
OBEL001L
OBEL001S
OBEL002T
OBEL003C
OBEL003L
OBEL004L
OBEL004S
OBEL005T
OBEL006T
OGBO001T
OGBO005T
OGBO008T
OGBO009T
OGBO010T
OGBO011T
OGBO012T
OGBO013T
OGBO014T
OGBO015T
OGBO016T
OGBO017T
OGBO018T
OGUT001L
OGUT001S
OGUT002L
OGUT002S
OGUT003L
OGUT003S
OGUT004L
OGUT004S
OGUT005L
OGUT005S
OGUT006L
OGUT006S
OGUT007L
OGUT007S
OGUT008T
OGUT010T
OGUT011L
OGUT011S
OGUT012T
OGUT013T
OGUT014T
OGUT016L
OGUT016S
OGUT017L
OGUT017S
OGUT020T
OGUT023L
OGUT023S
OGUT024T
OGUT025T
OGUT026T
OGUT027L
OGUT027S
OGUT028T
OPNO001L
OPNO001S
OPNO002T
OPNO003L
OPNO003S
OPNO005L
OPNO005S
OPNO021T
OPNO028T
OPNO029T
OPNO030L
OPNO030S
OPOM001L
OPOM001S
OPUK001C
OPUK001T
OPUK002T
OPUK004L
OPUK004S
OPUK005L
OPUK005S
OPUK006L
OPUK006S
OPUK007T
OPUK008L
OPUK008S
OPUK009T
OPUK010L
OPUK010S
OPUK011L
OPUK011S
OPUK012L
OPUK012L
OPUK012S
OPUK013L
OPUK013S
OPUK014T
OPUK015T
OPUK016T
OPUK017L
OPUK017S
OPUK018L
OPUK018S
OPUK020T
OPUK021T
OPUK022T
OPUK024T
OPUK025T
OPUK026T
OPUK027T
OPUK028T
OPUK029T
OPUK030L
OPUK030S
OPUK032T
OPUK033L
OPUK033S
OPUK034T
OPUK035T
OPUK036T
OPUK037T
OPUK038T
OPUK039T
OPUK040T
OTUM002L
OTUM002S
OTUM004L
OTUM004S
OTUM005L
OTUM005S
OTUM006L
OTUM006S
OTUM007L
OTUM007S
OTUM008L
OTUM008S
OTUM009T
OTUM010L
OTUM010S
OTUM011T
OTUM012L
OTUM012S
OTUM013L
OTUM013S
OTUM015L
OTUM015S
OTUM016T
OTUM017T
OTUM018T
OTUM019T
OTUM020L
OTUM020S
OTUM021L
OTUM021S
OTUM022L
OTUM022S
OTUM025L
OTUM025S
OTUM026L
OTUM026S
OTUM027L
OTUM027S
OTUM028L
OTUM028S
OTUM029L
OTUM029S
OTUM030L
OTUM030S
OTUM031L
OTUM031S
OTUM032L
OTUM032S
OTUM033L
OTUM033S
OTUM034L
OTUM034S
OTUM035L
OTUM035S
OTUM036L
OTUM036S
OTUM037L
OTUM037S
OTUM038L
OTUM038S
OTUM039L
OTUM039S
OTUM040T
OTUM041L
OTUM041S
OTUM042L
OTUM042S
OTUM043L
OTUM043S
OTUM044L
OTUM044S
OTUM045L
OTUM045S
OTUM046L
OTUM046S
OTUM047T
OTUM048T
OTUM049T
OTUM050T
OTUM051T
OTUM052T
OTUM053T
OTUM054T
OTUM055T
OTUM056T
OTUM057T
RUMU001T
RUMU003L
RUMU003S
RUMU004L
RUMU004S
SAGR001L
SAGR001S
SAGR002L
SAGR002S
SAGR003L
SAGR003S
SAGR005L
SAGR005S
SAGR007L
SAGR007S
SAGR008L
SAGR008S
SEIB001T
SEIB002L
SEIB002S
SEIB003L
SEIB003S
SOKU001T
SOKU002T
SOKU004L
SOKU004S
SOKU005T
SOKU006L
SOKU006S
SOKU007L
SOKU007S
SOKU008T
SOKU009L
SOKU009S
SOKU010L
SOKU010S
SOKU011L
SOKU011S
SOKU013L
SOKU013S
SOKU014L
SOKU014S
SOKU015L
SOKU015S
SOKU016L
SOKU016S
SOKU017T
SOKU018L
SOKU018S
SOKU019L
SOKU019S
SOKU020L
SOKU020S
SOKU021L
SOKU021S
SOKU022L
SOKU022S
SOKU023L
SOKU023S
SOKU025T
SOKU027L
SOKU027S
SOKU028L
SOKU028S
SOKU029L
SOKU029S
SOKU030L
SOKU030S
SOKU031L
SOKU031S
SOKU032T
SOKU033T
SOKU034T
SOKU035T
SOKU036T
SOKU037T
SOKU038T
SOKU039T
SOKU040T
SOKU041T
SOKU042T
SOKU043T
SOKU044T
SOKU045T
SOKU046T
SOKU047T
SOKU048L
SOKU048S
SOKU049T
SOKU050T
SOKU051T
SOKU052T
SOKU053T
SOKU054T
TUNU001L
TUNU001S
TUNU002L
TUNU002S
TUNU003T
TUNU004L
TUNU004S
TUNU005T
TUNU006T
TUNU007T
TUNU008T
TUNU009T
TUNU010T
TUNU011T
TUNU012L
TUNU012S
TUNU013T
TUNU014L
TUNU014S
TUNU015L
TUNU015S
TUNU016T
TUNU017T
TUNU018T
UBIE003L
UBIE003S
UBIE004L
UBIE004S
UBIE005L
UBIE005S
UBIE006L
UBIE006S
UBIE008T
UBIE009L
UBIE009S
UBIE010T
UGAD001L
UGAD001S
UGAD002T
ZARA007T
ZARA008T
ZARA009T
ZARA010T
ZARA011T
ZARA012L
ZARA012S
ZARA013T