## Cadence
| Opportunity/Objective: | Driving efficiency through improved SE and Line alignment and integration | MW Summary:
| Project Sponsor | GM SE
Project Champion
| Project Lead | Chukwuka Amos-Ejesi
| Project Team Members | Izu Iloma Olatunde Ojeyinka Titilayo Ajayi Line Reps - TBD
Cadence Meeting | Achieved Last Week | Promised for Next Week | Due Date | Help Needed | Resolutions | Unresolved Actions
12th March | Engaged SE Budget and integration lead and secured commitment as alternater team member | Develop draft ToR for Business Planning Framing session | 2021-03-12 | None
| Progressed from L1 to L2 | Organise individual challenge session with budget owners on outcome from team deep dive into different Line / SE ER budgets (possible duplication in ER budgeting) | 2021-03-19
Identified and engaged Line Representatives/stakeholders (Technical Planing, Finance Planing) and secure commitement for framing session
Analyzed different Line budgets / SE budget and identified potential duplications in ER budgeting
19th March | Developed and shared draft ToR for Business Planning Framing session | Agree and finalise framing session ToR and send meeting invite | 2021-03-12 | None
| Held initial challenge session with CER manager | Hold challenge session with: - GM SE/budget support - BFM SE | 2021-03-19 | Could not get breakdown of potential $8m cost duplication
Engage DE on WS scope
Update Fit4 with activity plan and milestones
8th April | SE Business planning and integration framing session to hold this week. | Finalize proposals on SE budget optimisation Engage Financial Planning on levers to pull for ER provisional budget - Provide final recommendation to DE Develop 10% of the SE Business Planning roadmap based on initial insights from framing session | 15th April
100% of challenge sessions on identified spend completed Insights: - 8m ER budget is provisional based on incidents. Cost savings cannot be banked until Dec 31.
3-yearly budget analysis for SE carried out - Insights to be distilled and proposal/recommendations sent to DE/GM SE
Activity plan has been finalised with milestones and inputted into Fit4. - L3 date to change based on current insights
A generic charter has been developed for the opportunity work scope and sent to Lanre