## Slide 1: Business processes | Enabler
Implementation Timelines
Sponsor: GM SE
Key issues/dilemmas:
Initiative name: SE Business Alignment
Deliverables (Point B)
Identify example potential duplicated spend (ER, learning etc) and optimize.
Defined and operationalized process for SE business planning including process for integrating activities across liferent lines (PUs, projects etc).
Teams impacted/interdependencies
Teams impacted: SPDC Assets, Projects and RE, Business Planning.
Dependencies: Asset teams, LOB SE support, Corporate ER team.
Problem Statement (Point A)
Lack of alignment between SE must wins and overall line business planning.
Potential inefficiency in SE budgeting across LOBs and SE function leading to duplicated spend/budgeting e.g., multiple ER or learning related budget items.
Lack of integration on SE Activity planning across lines e.g integrating statutory audits in different assets to optimize resources.
Key Benefits:
Save at least 10% of ER total ER budget (to further scope the opportunity).
Improved alignment and efficiency between SE and Line business plans
Initiative level: OU
Implementation Deadline: End of 2021
  2021
  Dec
  Jan
  Feb
  Mar
  Apr
  May
  Jun
  Jul
  Aug
  Sep
  Oct
  Nov
  Dec
  Identify and quantify optimization areas
  Obtain granular details of SE spend
  Activity
Issue: Multiple assets and projects with competing business needs
Dilemma: Impact of Reshape/Boundary conditions for the team.
Implementation Team
Chukwuka Amos-Ejesi
Olatunde Ojeyinka
Izu Iloma
Titilayo Ajayi
Line Reps - TBD
Governance Team
SE LT
Lanre Ogunsakin
  Develop implementation plans
  Implement plans
  Deep dive on current business planning
  Develop SE planning process map with
  ASCI charts
  Cascade, refine and operationalize
Objective: Driving efficiency through improved SE and Line alignment and integration

## Slide 2
Detailed Steps(1)
Secure Line representatives into the workstream
Obtain granular details of SE spend/budget by line teams and Corporate SE (including ER and learning)
Deep dive to identify optimization opportunities.
Engage lines and corporate SE to align on optimization opportunities
Develop implementation plans for identified opportunities
Implement.
Steps (2)
Identify key stakeholders in the business planning process
Develop a SIPOC with help from CI Coach/team
Secure availability of all stakeholders for a workshop
Hold Deep dive workshop on current business planning process (identify hold points for S & E input)
Develop SE planning process map including RASCI charts that plug into the existing business planning process.
Cascade, refine and operationalize.