## Sheet3
Deliverables | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | Aug
| 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27
PMO
Finalise and upload charter on Fit4
Update uploaded charter on Fit4
Progress from L0 to L1
Develop Activity Plan
Clarify cost optimization target
Progress from L1 to L2
Line SE Spend Optimisation
Engage SE Budget and integration lead for workstream stakeholder alignment
Engage Line Representative and secure commitement for 3 alternate reps
Obtain granular details of Line SE spend (focus on ER, Learning)
Carry out deep dive session on spend to identify optimization opportunities
Engage lines and corporate SE to align on optimization opportunities
Develop draft implementation proposal for opportunities
Agree implementation proposals with the Line
Handover implementation proposals to Line Rep/Finance
Line SE Business Planning Alignment
Identify key stakeholders in busines planning process
Organize 'Walk the Process' session
Develop SE planning process map
Develop SE Business planning Quick Reference Guide (QRG)
Agree process map with SE LT
Carry out multi-level engagement sessions across SE