## OnePager
QPA - Q4 2022 - Nigeria (SPDC+Snepco)
HSE Highlights: - GRST & LRST for new start-ups- OES Respect/Geoplex T80, Soku TRSSV, EA STOG and barge inspections. - Wells V&A, Contractor HSSE Management and Regulatory Compliance LOD 2 audits. - Strength of Controls review - Line of Fire- DS10 - Regulatory Compliance LOD 2 Audit Lowlights: - Personnel struck on the leg by cable bridge- HL 29 (Aug 2022) - Suspected NAD- HL 19 (Aug 2022) Focus Areas: - Safe start-up - OES Respect, HL-19 |  | People & Recognition - BR301 Team for delivering over $2m (100%) savings in Completions PIP (Coiled-tubing free Well lift by using breaker fluid). - WHD Maintenance team for restoring 1,500 bpd production from the FORC022T well, with an accompanying cost savings of ca $300k - WI-East team for successful retrieval of the stuck e-line dummy tool string from SOKU 27L, thus avoiding a possible junking of the well - WI team for successful investigation of Bonny 31T well, leading to opening the well to production after 7 years with an additional production of 38MMscf/d + ca. 1300 bpd condensate, and a value savings of over $600k SS - CT team for successful well lift of Forc 150 & 147 after deploying an innovative solution to open the flapper of a dysfunctional TRSCSSV, thus adding ca 3,000 bopd production and saving $500K cost of Lock open tool - Snepco team for saving ca. $1.5m (100%) in Bonga 71 PIP (Formation evaluation scope optimization) | Last Quarter Highlight & Lowlight Highlights - Received management approval to continue execution of Assa North Wells HYZN-003 and H1D5 on Hilong 19. - Completed Gbaran 16 PWD well. - Restored the production of four quit wells in FORC and LIP in BONN 31T unlocking potential 4.1kbopd - Secured additional 5 strings in the last quarter, and reduced red well count to +/-50. - Safe delivery of KOCR-43 WI activity at <5% NPT and savings of over $3mln Lowlights - Impact of flooding on Well operations. - Delay in FORC intra-field movements - Bonga DIF challenge** - BLU packer**
Metric | Below/ Above/ On Plan | Narrative (and actions if needed) | Next Quarter Lookahead: Critical Well Activities, GIPs, CRs, etc - Startup of OES Respect. - WEIS Migration from OP21 to OP22 - Execute BENS 2T, SEIB 1T, AHIA 14S STOG; Commence FORC STOG Campaign - Execution of Assa North Wells HYZN-003 H1D5 on Hilong 19. - 2023 JV Budget Defence.
New Production (FYLE kboepd) | On Plan (Snepco) Below Plan (SPDC) | SPDC: Wells delivered, however CYC impacted by delay in start up of export gas wells and FYIP wells due to unavailability of JUB. ENWH Wells: All Enwhe West wells now in 2023.
Well Count (FYLE#) | Above Plan (Snepco) Below Plan (SPDC) | SPDC: Prior security lockdown in Assa North. BOP Recertification on BR301. Flooding impact on ENWHE location readiness. OES Respect rig intake delay.
WRFM Budget % Utilization (SOV Only) | On Plan (Snepco) Below Plan (SPDC) | SPDC: Late mobilization for EA campaign etc. PM/CM execution activities in FORC suffered 1-month set back (with NPT implication). | Issues and Interventions - Delay in execution of ESCB activities due to legacy issues (bad jetty, access to location)
Wells Opt & Rest (FYLE kboepd) | On Plan (Snepco) Below Plan (SPDC) | Planned activities re-prioritized to adjust for continued TNP outage. Drop in volume vs Q2 explained by scope drop for planned activities in the east.
Wells Opt & Rest (FYLE USD SS) | On Plan (Snepco) Below Plan (SPDC) | Do not enter the data in this cell

## 5+3 SOV SPDC
2022 GM Ops Scorecard
SPDC
| Category | Metric | TARGET 2022 | AMBITION 2022 | Q1 LE | Q2 LE | Q3 LE | Q4 LE
Business Delivery Goals | Industry Leading Competitiveness | % better than OP21 Plan in Net Capital Efficiency % better than OP21 Plan for WI in $/boe (Restoration and Optimization) | 3% 3% | 5% 5% | 3% 3% | 3% 3% | 0.6% 0% | 2% 11%
Business Delivery Goals | Continuous Improvement | % Gap to BCC for the complete portfolio % Coverage of Gap to Ambition versus OP21 % Overall NPT | 20% 120% 20% | 15% 150% <20% | 20% 243% 19% | 20% 254% 20% | 25% >250% 25% | 25% 139% 22%
Business Delivery Goals | Transforming Partnerships for Value | Value created with suppliers - through joint continuous improvement efforts (NOV, VSMs, franchise approach, SCT, etc.) | $21mln | $23mln | $21mln | $21mln | $12.3mln | $12.3mln
Business Delivery Goals | Cash Generation | *New Oil Production (kb/d CYC) / # Oil Wells executed *New Gas Production (MMscf/d CYC) / # Gas Wells executed *WRFM – Additional oil from closed-in strings (kboe/d 12MDA) / # of activities Number of Exploration Wells Delivered | 4.54 / 12 136 / 7 13.94 / 11 NA | 4.54 / 12 156 / 8 33.3 / 26 NA | 4.54/8 156/12 13.94 / 11 NA | 7.3/7 103/7 52.9/40 NA | 4.7/6 92/6 17.6/50 NA | 4.7/10 92/7 16.9/62 NA
Business Delivery Goals | Delivering our Global Wells Franchise Model | % of new Wells dWIDs following a Franchise Standard Well Delivery Plan (Drill, Complete, Intervention or P&A). | 75% | >80% | 75% | 75% | 75% | 75%
|  |  | TARGET 2022 | AMBITION 2022 | Q1 LE | Q2 LE | Q3 LE | Q4 LE
Foundation Goals | I Am Goal Zero (Deliver Safely) | HPI Frequency (In support of Zero SIF) Ratio HPE/(HPI+HPE) | 1.2 Monitor | 0.8 Monitor | 0 Monitor | 0 Monitor | 0 Monitor | 0 Monitor
Foundation Goals | Process Safety | Well control incidents (WCI) – Level 1 and Level 2 RED Well Reduction # of HRW/Legacy Abandonments Executed | 0 <100 2 / 4 | 0 <80 2 / 9 | 0 <100 2/9 | 0 98 1/5 | 0 66 0/4 | 0 <70 0/5
Foundation Goals | Best Place to Work & Invest in Your Future | Reduction in Wells GHG Emission vs OP21 baseline by YE 2022 | 5% | 8% | 5% | 11% | 11% | 21%
|  | People Agenda Rolled out and Implemented Employee Engagement, Organizational Leadership, Operational Excellence Total E&C Compliance Training Overdue | 80% +2% <2% | 100% +3% 0 | 80% +2% <2% | 90% +2% <2% | 90% +2% <2% | 93% -5% <2%
Note on F7: Adedinsewo, Tosoye I SPDC-PTW/O/NG: Error with Q1LE. Should have been 7.2/7 126/9 13.94/11** NA
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WRFM values are CYC(100%)
Note on I7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CYC values for both LiP and quit wells
Note on F11: Adedinsewo, Tosoye I SPDC-PTW/O/NG: Error with #HRW Should have been 1/5

## 5+3 SOV Snepco
2022 GM Ops Scorecard
SNEPCo
| Category | Metric | TARGET 2022 | AMBITION 2022 | Q1 LE | Q2 LE | Q3 LE | Q4 LE
Business Delivery Goals | Industry Leading Competitiveness | % better than OP21 Plan in Net Capital Efficiency % better than OP21 Plan for WI in $/boe (Restoration and Optimization) Deploy 1 High Impact New Technology in SNEPCO Wells. | 3% 3% 1 | 5% 5% 1 | 3% 3% 1 | 0% 3% 1 | 0% 3% 1 | 0% 3% 0
Business Delivery Goals | Continuous Improvement | % Gap to BCC for the complete portfolio % Coverage of Gap to Ambition versus OP21 % Overall NPT | 20% 120% 20% | 15% 150% <20% | 20% 120% 20% | 20% 120% 20% | 20% 190% 29% | 20% 190% 29%
Business Delivery Goals | Transforming Partnerships for Value | *Value created with suppliers - through joint continuous improvement efforts (NOV, VSMs, franchise approach, SCT, etc.) | $6mln | $7mln | $6mln | $0.5mln | $5.5mln | $6.8mln
Business Delivery Goals | Cash Generation | *New Oil Production (kb/d CYC) / # Wells *New Gas Production (MMscf/d CYC) / # Wells *WRFM – Additional oil from closed-in strings (kboe/d 12MDA) / # of activities | 1.5 / 5 NA 3Kbopd | 1.5 / 7 NA 3Kbopd | 1.5 / 5 NA 3Kbopd | 1.5 / 6 NA 3Kbopd | 1.5 / 6 NA 3Kbopd | 1.5 / 6 NA 3Kbopd
Business Delivery Goals | Delivering our Global Wells Franchise Model | % of new Wells dWIDs following a Franchise Standard Well Delivery Plan (Drill, Complete, Intervention or P&A). | 0.75 | >80% | 0.75 | 0.75 | 0.75 | 1
|  |  | TARGET 2022 | AMBITION 2022 | Q1 LE | Q2 LE | Q3 LE | Q4 LE
Foundation Goals | I Am Goal Zero (Deliver Safely) | HPI Frequency (In support of Zero SIF) Ratio HPE/(HPI+HPE) | 1.2 Monitor | 0.8 Monitor | 1.2 Monitor | 1.2 Monitor | 1.2 Monitor | 1.2 Monitor
Foundation Goals | Process Safety | Well control incidents (WCI) – Level 1 and Level 2 RED Well Reduction # of HRW/Legacy Abandonments Executed | 0 NA 0 / 0 | 0 NA 0 / 0 | 0 NA 0 / 0 | 0 NA 0 / 0 | 0 NA 0 / 0 | 0 NA 0 / 0
Foundation Goals | Best Place to Work & Invest in Your Future | Reduction in Wells GHG Emission vs OP21 baseline by YE 2022 | 0.05 | 0.08 | 0.05 | 0.11 | 0.11 | 0.01
|  | People Agenda Rolled out and Implemented Employee Engagement, Organizational Leadership, Operational Excellence Total E&C Compliance Training Overdue | 80% +2% <2% | 100% +3% 0 | 80% +2% <2% | 80% +2% <2% | 80% +2% <2% | 93% -5% <2%
Note on I6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Most value captured through SCT and reflected on WEIS

## R1 Input file SPDC
| DVA Acc | DVA Accounts Dsc | DVA MI Dsc | Values; m$; SS | Comments
Cash Capex=Capex+Capitalized Expex+Fin Lease Adj |  | Cash Capex - Wells OP21 (P1) | Cash Capex - OP21 - TGT | 120.38
| D41001 | Wells - Portfolio Management/Scope Change | Scope Change - Portfolio Management | -11.4 | Kocr 44 +11mln (WO vs ST), Okoloma Dev LLI scope -$-13mln, AF STOG -$9mln
| D41002 | Wells - Capex-Slipp/Reph/Acc into current year | Scope Change - Slipp/Reph/Acc into current year | 9.31 | SSAGS2 $3 (part scope of Tunu CDRY3), Gbaran 14 Replacement $2mln, ANOH $1mln (Assa North 3&4 Completions), K2S $2mln (Kocr 48), Enwhe $1mln (Enwhe 8 & 9 Well test), STOG $0.3mln (Additional dredging scope).
| D41003 | Wells - Slipp/Reph/Acc out of current year | Scope Change - Slipp/Reph/Acc out of current year | -96.87 | SSAGS2 -$29mln, Uzu -$8mln (Funding -$4mln, & Slippage of LLI delivery -$4mln), K2S -$13nln (Kocr 46), Gbaran SWO -15mln (Gbaran F1B & Gbaran 26IC (HPHT)), Expex -$5mln, Enwhe -$21mln (BNSV 1, 2 & 3), ANOH -$4mln (HXZN-001-H4 and part scope of H1D5), STOG -$2mln (TNP outage, LLI delivery)
| D41004 | Wells - Cost Performance | Cost Performance SAVINGS | -8.27 | SSAGS2 -$3mln (Completions & Well lift Technology, STCS, Rig rate reduction, optimization on Logging & Downhole Gauges), K2S -$3mln (Elimination of Rigless Well Kill, CaBr2, Reduction of NPT by 10%), ANOH -$0.5mln (Xmas Tree Design Optimization, Replacement of Calcium Formate brine with Calcium Bromide), Gbaran 016 -$0.8mln (Execute with HWU instead of HL 29 Rig), Gbaran 28 -$0.6mln (Optimization on design & trajectory), Others -$0.4mln (Optimized security outfit, optimization on well lift execution)
| D41004 | Wells - Cost Performance | Cost Performance OVERRUNS | 6.55 | K2S $4.6mln (Losses encountered on Kocr 44ST), SSAGS2 $1mln (Grounded Rig move to OGBO AOTM1, Waiting on Mast Raising Line & BOP Recertifcation), ANOH $0.6mln (degradation of drilling fluid & recovery operations), FYIP $0.2mln (Additional cost for JUB mob/demob, extended period of activity execution)
| D41005 | Wells - External Factor/Accounting Reclass | External Factor/Accounting Reclass | -0.43 | ANOH +0.45mln (Standby cost due to Security lockdown), SSAGS2 +0.9mln (Covid & Community impasse), Reclass to Exploration Opex (G&G studies) -$1.8mln. FYIP +0.2m (Market Escalations)
| D41006 | Wells - Forex | Forex
| D41008 | Wells - Other | Other | 51.22 | Finance Lease: $15mln ($16mln vs $31mln), MA $36mln ($36mln vs $0.00mln)
|  | Cash Capex - FYLE | Cash Capex - Q4 FYLE | 70.49
Abex |  | DVA Accounts Dsc | DVA MI Dsc | Values; m$; SS | Comments
|  | Abex - Wells OP21 (P1) | Abex - OP21 - TGT | 10.01
|  | Abex - Portfolio Management/Scope Change | Portfolio Management | 0.65 | Gbar14 abandonment
|  | Abex - Capex-Slipp/Reph/Acc into current year | Slipp/Reph/Acc into current year | 0
|  | Abex - Slipp/Reph/Acc out of current year | Slipp/Reph/Acc out of current year | -6.76 | Phase out of all Swamp wells due to funding -$7mln
|  | Abex - Cost Performance | Cost Performance SAVINGS | 0
|  | Abex - Cost Performance | Cost Performance OVERRUNS | 0
|  | Abex - Forex | Forex/Other | 0
|  | Abex - FYLE | Abex - Q4 FYLE | 3.9
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## R1 Input file Snepco
| DVA Acc | DVA Accounts Dsc | DVA MI Dsc | Values; m$; SS | Comments
Cash Capex=Capex+Capitalized Expex+Fin Lease Adj |  | Cash Capex - Wells OP21 (P1) | Cash Capex - OP21 - TGT | 118.07
| D41001 | Wells - Portfolio Management/Scope Change | Scope Change - Portfolio Management | 1.42 | This increase is due to additional scope in the completion strategy
| D41002 | Wells - Capex-Slipp/Reph/Acc into current year | Scope Change - Slipp/Reph/Acc into current year | 49.47 | Snepco: FD wells 702p8 and B 13RD-ST ($49.4mln) were accelerated into 2022 to boost oil volumes
| D41003 | Wells - Slipp/Reph/Acc out of current year | Scope Change - Slipp/Reph/Acc out of current year | -54 | 670B16N injector and completion ($21.2mln) was dropped from the sequence (capex part) 670B14 w4 D&C($7.36mln) slipped into 2023 due to operational issues during the 670B16N exploration drilling . Bonga Nose ($22.44mln) slipped into 2023 due to the fact that the rig started later than planned and increase in number of days of earlier wells in the sequence Drop in original ODE from the drilling gap in the sequence replaced by the two wells (702p8 and B13) which were accelerated (-$3mln).
| D41004 | Wells - Cost Performance | Cost Performance SAVINGS | -6.9 | Competitive scoping of 670b14 well pair from conventional to reduced casing scheme.
| D41004 | Wells - Cost Performance | Cost Performance OVERRUNS | 16.6 | Technical issues during cementing of 670B16N; directional drilling challenges on B57RD, more time spent during mobilization of the rig due to vessel difficulty to transfer dry bulk and other cost, and other operational challenges.
| D41005 | Wells - External Factor/Accounting Reclass | External Factor/Accounting Reclass | 5.73 | This increase is directly attributable to increased fuel rate from $0.6/ltr to $1.54/ltr
| D41006 | Wells - Forex | Forex | 0
| D41008 | Wells - Other | Other | -31.64 | Finance lease ($31.64mln)
|  | Cash Capex - FYLE | Cash Capex - Q4 FYLE | 98.75
Abex |  | DVA Accounts Dsc | DVA MI Dsc | Values; m$; SS | Comments
|  | Abex - Wells OP21 (P1) | Abex - OP21 - TGT | 4.57
|  | Abex - Portfolio Management/Scope Change | Portfolio Management | 0
|  | Abex - Capex-Slipp/Reph/Acc into current year | Slipp/Reph/Acc into current year | 16.477 | B 56 and B 26 slipped into 2022 from 2021 due to the operational challenges on the Q7000 vessel. B70 not originally planned for was abandoned.
|  | Abex - Slipp/Reph/Acc out of current year | Slipp/Reph/Acc out of current year | -4.57 | Deferral of B61 suspension to 2023 P&A Campaign due to plug validity till 2023
|  | Abex - Cost Performance | Cost Performance SAVINGS | 0
|  | Abex - Cost Performance | Cost Performance OVERRUNS | 0
|  | Abex - Forex | Forex/Other | 0
|  | Abex - FYLE | Abex - Q4 FYLE | 16.477
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Croc Plot Snepco
NOTE: Croc Plot items are over and above the LE and should show further overspend or underspend above LE to enable credible Cash CAPEX LE for a potential Upstream COG MA submission.
Please provide with Risks and Opportunities data acording to categories below, input for Unrisked value and probability required:
Increase (Positive Values) |  | $mln SS | Probability | Unrisked Value | Narrative | Guide/Instruction
Out of Plan Options and Acceleration Potential | 0 | 0
Potential Cost Overruns |  | 0 |  |  |  | Include overrun that would result in overspend above LE. E.g fuel price increases, contracts escalations
Decrease (Negative Values)
Unrisked PIP Funnel |  | 0 |  |  |  | Only include savings that could reduce FYLE. Time dependent savings may accelerate scope in case of continuous sequence, not necessarily reducing overall spend
Risked PIP Funnel |  | 0
In Plan Options and Slippage Risks | 0 | 0
Contingency | 0 | 0 |  |  |  | Similar to savings, only include contingency release that would reduce FYLE
Net Position |  | 0 |  |  | $mln Shell Share
NOT REQUIRED FOR Q4

## Croc Plot SPDC
NOTE: Croc Plot items are over and above the LE and should show further overspend or underspend above LE to enable credible Cash CAPEX LE for a potential Upstream COG MA submission.
Please provide with Risks and Opportunities data acording to categories below, input for Unrisked value and probability required:
Increase (Positive Values) |  | $mln SS | Probability | Unrisked Value | Narrative | Guide/Instruction
Out of Plan Options and Acceleration Potential | 0 | 0
Potential Cost Overruns |  | 0 |  |  |  | Include overrun that would result in overspend above LE. E.g fuel price increases, contracts escalations
Decrease (Negative Values)
Unrisked PIP Funnel |  | 0 |  |  |  | Only include savings that could reduce FYLE. Time dependent savings may accelerate scope in case of continuous sequence, not necessarily reducing overall spend
Risked PIP Funnel |  | 0
In Plan Options and Slippage Risks | 0 | 0
Contingency | 0 | 0 |  |  |  | Similar to savings, only include contingency release that would reduce FYLE
Net Position |  | 0 |  |  | $mln Shell Share
NOT REQUIRED FOR Q4

## Rig Sequence SPDC
Insert Sequence here

## Rig Sequence SNEPCo
Insert Sequence here

## KPI Dashboard
Q4 2022 QPA
| Metrics |  |  | SPDC |  |  | Snepco
Mapped to 5+3 | Name | Unit | Target | Ambition 2022 | Q4 FYLE | Target | Ambition 2022 | Q4 FYLE
I am Goal Zero | RAM4+ (All) (YTD, untill the end of previous Q) | #
I am Goal Zero | Exposure hours (YTD, untill the end of previous Q) | mln hours
I am Goal Zero | RAM4+ (All) frequency (YTD, untill the end of previous Q) | N/A
I am Goal Zero | Well Control Incidents L1 and L2 (untill the end of previous Q) | #
Industry Leading Competitiveness | Cash CAPEX (LE) | SS% $USD Mln | 120.38 |  | 70.49 | 118.07 |  | 98.75
Industry Leading Competitiveness | Cash Capex Business Performance (LE) | SS% $USD Mln |  |  | 1.72 |  |  | -9.7
Industry Leading Competitiveness | Cash Capex Business Performance (LE) | % | 3% | 5% | 2.382% | 3% | 5% | -10.89%
Industry Leading Competitiveness | Optimisation Expenditure Capex (LE in year spend) | SS% $USD Mln | 11.85 |  | 3.3 | 9.4 |  | 0
Industry Leading Competitiveness | Optimisation Expenditure Opex (LE in year spend) | SS% $USD Mln |  |  | 4.5 |  |  | 9.5
Industry Leading Competitiveness | Restoration Expenditure Capex (LE in year spend) | SS% $USD Mln | 14.37 |  | 4.5 | 0 |  | 0
Industry Leading Competitiveness | Restoration Expenditure Opex (LE in year spend) | SS% $USD Mln |  |  | 1.9 |  |  | 0
Industry Leading Competitiveness | WRM Budget %Utilization | % | 95% | 105% | 54.16% | 95% | 105% | 101.1%
Industry Leading Competitiveness | Abex (LE) | SS% $USD Mln | 10.01 |  | 3.9 | 4.57 |  | 16.477
Industry Leading Competitiveness | Abex Business Performance (LE) | SS% $USD Mln | 0 |  | 0 | 0 |  | 0
Continuous Improvement | Percentage Gap to BCC (LE) | % | 28% |  | 25% | 21% |  | 20%
Competitive Cost Base | Well Count (LE) | # | 16 |  | 9 | 6 |  | 5

## Q&A
Question |  | Action Party/Status | Response
Onepager: Can you share more updates on New Production? What is the FYIP wells hook up execution status? | Khaled | Closed | Action: Gaby to share narrative on new production
SPDC R1 input - Savings: there is 12.9 banked savings in Power Bi vs only 8.3 in R1. Can you explain the variance? - Overruns; can you confirm if any of he overuns were due the impact of floods? - Overruns: STOG $0.3mln (Additional dredging scope) - Can this be considered as scope increase? - Overruns: what is the JUB mob/demob additional cost? Is it related to escalations? | Khaled | Closed | - Action: Move STOG and JUB markect escalations to Scope and external factor respectively
SPDC R1 capex movement: Please provide a brief narrative to explain the increase in Capex spend from $62M in Q3 to $70M in Q4. What has been the financial impact of the flooding? |  |  | Add narrative on scope movement
SPDC: Which risk and opportunities from Q3 croc plot materialised in Q4?
SPDC: R1 Q4LE vs actuals How does the Q4LE compare to October YTD spend i.e. what is projected to be spent in Nov & Dec and is this credible and realistic?
SNEPCO R1 input: there is 6.9 banked savings in Power Bi and nothing reported R1. Can you explain why no savings in R1? | Khaled | Closed | - Savings now added, net savings/ overrun Performance is same. - Action: Reflect cost escalations and martket impact as external factor
KPI Dashboard: - Please include gap to BCC for Both SNPECO and SPD - Please include well count SPDC - SNPECO and PDC Q4LE for WRFM matches Q3LE, can you confirm no changes since Q3? | Khaled | Ongoing | - Action for SNEPCO to include gap to BCC - Done - Scope was concluded by end of Q2. no changes to WRFM spend since Q3 - Updare WRFM spend for SPDC. Closed
Can you share SNEPCO Sequence? | Khaled | Closed | Shared
For Completeness of the CVA, can you please fill in the rest of the Mastersheet, mainly days, NPT, WOW…etc plan and actual | Khaled |  | Action to complete
SNEPCO R1 capex movement: Please provide a brief narrative to explain the $10M increase in Capex spend from $89M in Q3 to $99M in Q4. | Monika |  | At Q3, there was MA of ca. $10m with the aim of pushing the team to optimize spend. However, with our current realities of operational challenges this can no longer be achievable so the additional $10m MA has been regretted.
SNEPCO: Which risk and opportunities from Q3 croc plot materialised in Q4?
SPDC: R1 Q4LE $70m vs actuals $55m (BR 79%) How does the Q4LE compare to October YTD spend i.e. what is projected to be spent in Nov & Dec and is this credible and realistic? | Julie/Monika
SNEPCO R1 Q4LE $99m vs actuals $79m (BR 80%) How does the Q4LE compare to October YTD spend i.e. what is projected to be spent in Nov & Dec and is this credible and realistic? | Julie/Monika
SNEPCO: 5+3 please update to reflect correct values - transforming partnerships for value reflecting 0 in WEIS, capital efficiency reflecting -15% (is this correct, please check after questions above answered) |  |  | Action: Update 5+3
|  | Closed | Action: Share Flood impact

## Cost Variance Analysis
[5 empty] | Cost Variance Analysis | [6 empty] | SOV OUs ONLY
[6 empty] | OP21 |  | AFE |  | Actual/ LE |  | Cost/ Time Variance Analysis Actual Vs OP21 |  |  |  |  | Cost/ Time Variance Analysis Actual Vs AFE
vs Major projects
vs ledger |  | Replace with Well Construction Archetype | Funding | Replace with Activity Type | Add - Well Acitivty or Project | Cost TG USD | Days | Cost TG USD | Days | Cost TG USD | Days
| Country | Well Construction Archetype | Funding | Activity Type | Well Name | Cost TG USD | Days | Cost TG USD | Days | Cost TG USD | Days | Cost | Time | NPT % | WOW% | Contingency % | Cost | Time | NPT % | WOW% | Contingency % | Comments
| Nigeria |  | EXPEX | WHOLE DRILLING | Bonga 70 | 30 | 66.2 | 32.3 | 0 | 44.4 | 0 | 14.4 |  | -41% | 0% | 0% | 12.1 |  | 0% | 0% | 0%
| Nigeria |  | CAPEX | DRILL & COMPLETE | Bonga 71 | 0 | 38.51 | 33.49 | 0 | 40.03 | 0 | 40.03 |  | -37% | 0% | 0% | 6.54 |  | 0% | 0% | 0%
| Nigeria |  | CAPEX | DRILL & COMPLETE | Bonga 72 | 0 | 25.33 | 52.17 | 0 | 31.16 | 0 | 31.16 |  | -10% | 0% | 0% | -21.01 |  | 0% | 0% | 0%
| Nigeria |  | CAPEX | DRILL & COMPLETE | Bonga 73 | 38 | 0 | 50.7 | 0 | 23.4 | 0 | -14.6 |  | 0% | 0% | 0% | -27.3 |  | 0% | 0% | 0%
| Nigeria |  | CAPEX | DRILL & COMPLETE | Opukushi 39 | 25.32 | 76 | 25.16 | 0 | 18.78 | 0 | -6.54 |  | -29% | 0% | 0% | -6.38 |  | 0% | 0% | 0%
| Nigeria |  | CAPEX | DRILL & COMPLETE | Opukushi 40 | 24.11 | 62 | 23.97 | 0 | 17.41 | 0 | -6.7 |  | -19% | -0.07% | 0% | -6.56 |  | 0% | 0% | 0%
| Nigeria |  | CAPEX | DRILL - SIDETRACK | Kolo Creek 44 S2 | 18.79 | 114 | 18.79 | 0 | 12.61 | 0 | -6.18 |  | -12% | 0% | 0% | -6.18 |  | 0% | 0% | 0%
| Nigeria |  | CAPEX | DRILL & COMPLETE | Assa North 3 | 28.9 | 188 | 28.9 | 0 | 45.6 | 0 | 16.7 |  | -47% | 0% | 0% | 16.7 |  | 0% | 0% | 0%
| Nigeria |  | CAPEX | DRILL & COMPLETE | Assa North 4 | 21.58 | 75 | 21.58 | 0 | 26.6 | 0 | 5.02 |  | -33% | 0% | 0% | 5.02 |  | 0% | 0% | 0%
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0

## Template Guide
The QBA Template (excel spreadsheet) will enable focus on the following key areas by tab:
OnePager – This is the executive summary providing the key information on HSE, Recognition, Highlights & Lowlights, Burnrate etc. Along with the progress against plan and the narrative require on the Production, Well Count and WRFM thereby eliminating the need for unnecessary additional slides and charts to demonstrate.
5+3 GM’s Only – GMs Ops & GM JV/NBD are required to review their 5+3 quarterly with COG Wells VP. Use excel version or past in picture. Include GHG reporting required.
R1 Input File – This combines the previous CAPEX, EXPEX and ABEX excel spreadsheets into the template, so that everything is in one document and automatically outputs the charts. The comments box should be used to capture the cumulative picture on each DVA elements, not the quarterly change as previously required in NOV.
Note: See the DVA Description tab for DVA Guidelines and COG clarifications.
Note: Spend increase from COVID Costs should be reflected as External Factor rather than Overrun. Try to keep a clear split between savings and scope changes, for instance faster/cheaper than planned Operations (=Savings) result in execution of more Scope than planned, this is reflected accordingly.
Rig Sequence – All SOVs to paste in the latest rig sequence to enable the FTE/Activity tracking and plotting of a combined COG Sequence. NOV to share if available but not mandatory.
Croc Plot – This tracks the Risk and Opportunity values and narrative by each category to enable an accurate and credible Cash CAPEX LE for a potential Upstream COG MA submission. The spreadsheet automatically generates the chart, stacked from the Risked WEIS/Fit4 Savings. NOV Fit4 savings values and narrative will be provided by WEMs.
KPI Dashboard – This captures the Key KPI metrics not captured elsewhere in the pack but critical for the report consolidation. Metrics that are gathered centrally or not required have the cells greyed out to save you sourcing the data unnecessarily.
Note: NOV Q3 HSSE data will use from the end of Q2 with a qualitative description in the OnePager of how things have moved since that point.
Note: Well Count: For Development wells include wells Drilled and Completed in 2022. For Exploration include wells Drilled in 2022. e.g. include development well A that is/ to be spudded in 2021/2022 and is/to be completed in 2022, excluded well B is/ to be spudded in 2022 but to be completed in 2023
Cost Variance Analysis SOV Only – In compliance with the WCEM, the SOV OUs are required to complete to monitor the Cost Estimates. This is extremely valuable in the OP Cycle to see the credibility and competitiveness of the estimates for appropriate support, challenge and defend the OP Plan.
DVA Descriptions - Official Upstream Capital Investment & Cash Capex KPI_DVA_guidlines_CI&CC_2021 with further COG clarifications to support the R1 bucket selection.

## DVA Descriptions
2022 Detailed Variance Analysis (DVA) Capital Investment and Cash CAPEX Guideance
SharePoint: KPI_DVA_guidlines_CI_2022.pptx
Objective of FYLE vs OP21 2022 variance analysis Wells EVP-VP quarterly business appraisal discussions, amongst the others, covers the execution of wells plan for capex/expex spend. For this a Capex/Expex washline (OP21 2022 vs FYLE) is prepared for the PTW/O portfolio which presents the categories of variance between the 2022 operating plan and the full year latest estimate. The variance is analyzed to provide evidence of maturing PIP initiatives and banking into FYLE (= proving the progress of closing gap to BCC), scope stability, areas which could be controlled/ influenced by Wells more efficiently, areas which are outside of Wells control and insights that could result into an potential management adjustment for downsizing/upsizing the expected Capex/Expex spend for the given year. The intent is not to reconcile the variances to very last $.
FYLE vs OP variance definitions The variance between operating plan and full year latest estimate is reported, e.g. OP21 2022 vs Q2 FYLE for 2022. OP or FYLE could be based on GIP, AFE or other, it’s important to know what the base of OP and FYLE estimate is. Couple of reference docs can be used to check what was assumed in OP (OP rig sequence, OP P1 report with details of wells capex/expex spend included in individual Wells Manager Dashboard, OP TA packs carrying additional information), they can be found on wells SharePoint within respective venture collaboration set. The expected level of spend on wells capex/expex should be aligned with Upstream/ Integrated Gas assets. During operating plan cycle, wells capex and expex spend is defined in M$, Shell Share, MOD. Operating plan numbers become a target for the year (OP21 2022 = Target for 2022). Target is loaded into assets finance system (R1), is reviewed and updated during subsequent quarterly FYLE runs. The variance between target is explained, submitted within asset finance system and used for performance appraisal by wells, assets and others.
DVA Description | Examples | COG PTW Classification Pitfalls
Portfolio Management/Scope change This DVA should be used to capture variance: • resulting from Portfolio Management i.e. swapping ceiling, farming in/out, divestments, acquisitions • due to deliberate/unplanned change of work scope: • Use a positive entry to represent newly approved activities • Use a negative entry to reflect cancelled activities. | • Increase number of wells vs target (only additional wells, not identified on drilling sequence in previous or later years); e.g. Northern Lights CCS well was not in OP at all, but it was decided to inject the well into the current year’s drilling sequence. • Target wells removed from drilling sequence and replaced by new wells (I.e. not planned for previous or later years) or left as gap on sequence. E.g. TXT wells from 2020 drilling sequence removed and replaced by MLT wells due to restricted wells crossing strategy for TXT wells. • In second half of 2019 Shell announced divestment of X. However, divestment deal was finalized mid of 2020. All work from 2020 drilling sequence after date of divestment deal finalization will be de-scoped and presented under this category. Expected cut-off date to be confirmed with asset finance team during FYLE preps. • Change in Shell working interest. | • Wells were included in wells OP for previous or later year are executed in current= analyzed year, additional scope should be classified rather as rephasing into current year instead of this category. • Divestment of asset has been announced. The whole wells target capex/expex spend for analyzed year has been descoped via this category. The accounting cut- off date for spend has not been confirmed with asset finance. Despite announced divestment still some wells spend until “cut-off date” should be shown as wells capex/expex for analyzed year. • New deal has been announced, it was not included in wells target. Wells exploration/appraisal work is executed and spend is classified under this category in analyzed year. Due to complexity of accounting classification/ deal signing progress spend should be classified as other than wells capital investment. Proper classification should be confirmed with asset finance. • After finalized OP, MOC was announced and shift of wells capex/expex spend for analyzed year is expected between wells VP ships e.g. form JV/NOV to DW. The move of the targets for analyzed year between wells LOBs should not be shown as variance between target and FYLE for analyzed period. It’s once off target increase in “receiving LOB” and offsetting target decrease in “originating LOB”.
Rephasing/Acceleration/Slippage into current year (positive entry): • Rephasing: Variance due to a deliberate and controlled shift in project spend, that does not impact the on-stream or project completion date - rephased from future or previous years into the current year • Acceleration: Variance caused by an activity being brought forward in time relative to target assumptions, resulting in earlier completion or on-stream date of a project - for CI being accelerated from future years into the current year • Slippage: Variance caused by an activity that is delayed in time relative to target assumptions, resulting in a later completion or on-stream date of a project - expenditure that is delayed from previous year into current year | • Drilling sequence changes for analyzed year, resulting in “reallocation of” wells from previous or later years (already identified and included in OP) into analyzed year. | • That kind of delta could result with recognition of other delta categories at the same time. Always consider what is your target for analysis (e.g. for 2020 it will be OP19 2020 with FX OP19 2020). • The simple move of $ spend (as it was) from one year to another would lead to lack of information transparency like e.g. if the scope is still on like for like basis, if cost performance initiatives have been built in estimates during the time, if there was FX exposure. All of that should be shown separately and not netted.
Rephasing/Acceleration/Slippage out of current year (negative entry) • Rephasing: Variance due to a deliberate and controlled shift in project spend, that does not impact the on-stream or project completion date - CI being rephased out of the current year into future years. • Acceleration: Variance caused by an activity being brought forward in time relative to target assumptions, resulting in earlier completion or on-stream date of a project - CI that has been accelerated in previous years. • Slippage: Variance caused by an activity that is delayed in time relative to target assumptions, resulting in a later completion or on-stream date of a project - expenditure that is delayed from current year into future years. | See above | See above
Cost Performance Variance caused by an activity having higher or lower costs than covered in the target, for the same scope of work. In other words: achieving the same result for more or less money. If cost performance does not result in lower spend for the current year due to acceleration/scope change (e.g. due to more efficient drilling additional wells are being drilled) they should still be recognized under cost performance with the offset being reported in the relevant DVA bucket. • Use a positive entry for a cost increase while doing the same scope of work. • Use a negative entry for a cost reduction while doing the same scope of work. | Savings e.g.: • Less days for drilling, • Negotiated better rates contracts, • Funnel initiatives banked in FYLE Overruns e.g.: • More days in execution • Issues during execution, • Hole problems • Equipment lost | • Try to keep a clear split between savings and scope changes, for instance faster/cheaper than planned Operations (=Savings) result in execution of more Scope than planned, this is to be reflected accordingly. • Savings and overruns need to be presented here, as separate line DVA. • Where additional scope has been agreed with the Asset this should be reflected in the Portfolio Management, such as the Extension of a Well Test, Additional Logging Requirements, 1000ft additional well length, Geological Sidetrack or cost increase for exceeding the Design Range. This is as per the WCEM definition of Contingent Scope. When considering Cost Overrun vs Scope Change, ask these questions: • Could we have planned for this upfront knowing what we knew? • Is this a potential walk away? • Did the asset ask us to continue for the business benefit?
External factor/Accounting Reclass External factor – variance due to overspend and/or savings without change in project scope due to external market factors beyond our control such as: increasing steel price, COVID-19 impact, sand or rig rates etc. • Use a positive entry for overspends on CI caused by external market factors. • Use a negative entry for underspends on CI caused by external market factors. Accounting Reclass – variance due to a net zero transfer of budget between categotird, e.g. Capex and True Expex or Capex to Opex or to Abex. This DVA category is also to be used to re-classify the spend between Wells and Non-Wells with net effect on total CI. • Use a positive entry for the category you want to transfer budget to. • Use a negative entry for the category you want to transfer budget out. | • Target wells spend reclassification from capex wells to opex wells. • Target wells spend reclassification to non- wells due to accounting treatment (e.g. from wells to facilities spend). • Wells spend was recognized as target for facilities spend and now during FYLE correction of classification is performed | Spend increase from COVID Costs should be reflected as External Factor rather than Cost Overrun. PDO 15% Markup on Oman SDO Cost.
Forex Variances resulting from changes in USD-local currency exchange rate. • Use a positive entry for overspends caused by exchange rate movements. • Use a negative entry for underspends caused by exchange rate movements. To calculate variances for FX refer to Capex Egine Team instruction | • Target FX (e.g. OP19 2020) is” >” or” < “FYLE FX (Q1 FYLE 2020) | • When target was moved from the other years into analysed year and was not translated with proper FX. “The $ base” to comparison with FYLE is corrupted.
Other All other variances, negative or positive that cannot be captured under one of the other DVA’s. This should be used on an exception basis only. When using this DVA category comments are obligatory. | • Minor changes to target which were not captured during OP and cannot be classified under above categories | Net of cost incurred for previous year activities and reversal of related accruals
Useful link: GR Website - Single Chart of Accounts Definitions

## Mastersheet (data entry only)
Input | Input from Drop down List | Calculated | [8 empty] | Optional | Optional | Optional | Optional | Optional | Optional | Optional | Optional
[11 empty] | Franchise | Archetype |  |  |  | WDP |  |  | OP21 | [16 empty] | OP22 | [42 empty] | AFE/ Pre-execution | [17 empty] | Actual Cost
Line of Business | Country | Asset Domain | PROJECT (if campaign) | Well Name | Activity type | Funding | In OP21 (Yes/ No) | In OP22 (Yes/ No) | 2022 Excution (Yes/ No) | Full or part of Spend in 2023 (Yes/ No) | If PROJECT enter number of activities (same archetype) | Scope specific MD drilled (ft) | Well Construction Archetype | Lower Completion Archetype | Upper Completion Archetype | Next WDP milestone | Next WDP milestone date | WDP scaling | MOD TG US$MM | Estimate Type | Shell Share | OP21 Spend in 2023 (Yes/ No) | NPT % (excluding WOW) | WOW % | Contingency Cost % | Total Time (days) | EDM (TG US$MM) | BIC Cost (MOD TG US$MM) | BCC (MOD TG US$K) | % Gap to BCC | Cost Benchmark | Time Benchmark | Activity start Date | Activity End Date | Depth (ft) | MOD TG US$MM | Estimate Type | Shell Share | Spend in 2023 (MOD TG US$MM) | Trouble free time (days) | NPT % (excluding WOW) | NPT (days) | WOW % | WOW (days) | Trouble free Cost (EDM TG US$MM) | NPT Cost (EDM TG US$MM) | WOW Cost (EDM TG US$MM) | Contingency Time (days) | Contingency Cost (EDM TG US$MM) | Contingency Cost % | Total Time (days) | CSO (EDM TG US$MM) | CSO % | EDM (TG US$MM) | Market Adjustments (Escalation) (TG US$MM) | Inflation Adjustments (TG US$MM) | P10/ D10 (MOD TG US$MM) | P90/ D90 (MOD TG US$MM) | BIC Cost (MOD TG US$MM) | BCC (MOD TG US$K) | % Gap to BCC | Benchmark Cost | Benchmark Time | Unavoided Cost Increases (EDM TG US$MM) | Scope in vs OP21 (EDM TG US$MM) | Scope out vs OP21 (EDM TG US$MM) | Unbanked Savings L1-L3 (TG US$MM) | Banked Savings L4/L5 (TG US$MM) | % LfL Savings | 2023 Like for Like Savings (TG US$MM) | MOB/DEMOB included in estimate (MOD TG US$MM) | Rig rate (TG US$k/day) | TA1 Assured? | Activity start Date | Activity End Date | Depth (ft) | Ambition Duration (days) | Ambition Cost (MOD TG US$MM) | AFE Planned Cost (TG US$MM) | P10/D10 (TG US$MM) | P90/D90 (TG US$MM) | BIC Cost (TG US$MM) | Estimate Type | NPT% (exc WOW) | WOW% | NPT Cost (TG US$MM) | WOW Cost (TG US$MM) | Contingenct Time (TG US$MM) | Contingency Cost (TG US$MM) | Congtency Cost % | AFE Planned Time (days) | Cost Benchmark | Time Benchmark | Activity start Date | Activity End Date | Depth (ft) | Actual/ LE Cost (TG US$MM) | LE/ Final | Actual/ LE Days | NPT (Days) | NPT % | WOW (days) | WOW% | NPT Cost (TG US$MM) | WOW Cost (TG US$MM) | Contingency time (days) | Contingency Cost (TG US$MM) | Contingency Cost % | Benchmark | Time Benchmark | Activity start Date | Activity End Date | Depth (ft)
COG | Nigeria | Nigeria DW Operated | Bonga | Bonga 70 | WHOLE DRILLING | EXPEX | Yes | No | Yes | No | [8 empty] | 30 |  |  |  | 41% | 0% |  | 66.2 |  |  |  | 100% |  |  | 2022-05-28 | 2022-08-02 | 18300 | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0! | [8 empty] | 32.3 | [17 empty] | 44.4
COG | Nigeria | Nigeria DW Operated | Bonga | Bonga 71 | DRILL & COMPLETE | CAPEX | No | No | Yes | No | [8 empty] | 0 |  |  |  | 37% | 0% |  | 38.51 |  |  |  | #DIV/0! |  |  | 2022-05-16 | 2022-09-05 | 9352 | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0! | [8 empty] | 33.49 | [17 empty] | 40.03
COG | Nigeria | Nigeria DW Operated | Bonga | Bonga 72 | DRILL & COMPLETE | CAPEX | No | No | Yes | No | [8 empty] | 0 |  |  |  | 10% | 0% |  | 25.33 |  |  |  | #DIV/0! |  |  | 2022-05-21 |  |  | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0! | [8 empty] | 52.17 | [17 empty] | 31.16
COG | Nigeria | Nigeria DW Operated | Bonga | Bonga 73 | DRILL & COMPLETE | CAPEX | Yes | No | Yes | Yes | [8 empty] | 38 |  |  |  |  | 0% | [5 empty] | 100% | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0! | [8 empty] | 50.7 | [17 empty] | 23.4
COG | Nigeria | SPDC West Asset | SSAGS2 | Opukushi 39 | DRILL & COMPLETE | CAPEX | Yes | No | Yes | No | [8 empty] | 25.32 |  |  |  | 29% | 0% |  | 76 |  |  |  | 100% |  |  | 2021-11-28 | 2022-02-13 | 10241 | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0! | [8 empty] | 25.16 | [17 empty] | 18.78
COG | Nigeria | SPDC West Asset | SSAGS2 | Opukushi 40 | DRILL & COMPLETE | CAPEX | Yes | No | Yes | No | [8 empty] | 24.11 |  |  |  | 19% | 0.07% |  | 62 |  |  |  | 100% |  |  | 2022-02-21 | 2022-04-15 | 10200 | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0! | [8 empty] | 23.97 | [17 empty] | 17.41
COG | Nigeria | SPDC Central East Asset | K2S | Kolo Creek 44 S2 | DRILL - SIDETRACK | CAPEX | Yes | No | Yes | No | [8 empty] | 18.79 |  |  |  | 12% | 0% |  | 114 |  |  |  | 100% |  |  | 2022-03-26 | 2022-07-17 | 8400 | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0! | [8 empty] | 18.79 | [17 empty] | 12.61
COG | Nigeria | SPDC Land Asset | ANOH | Assa North 3 | DRILL & COMPLETE | CAPEX | Yes | No | Yes | No | [8 empty] | 28.9 |  |  |  | 47% | 0% |  | 188 |  |  |  | 100% |  |  | 2021-01-22 | 2022-06-18 | 10197 | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0! | [8 empty] | 28.9 | [17 empty] | 45.6
COG | Nigeria | SPDC Land Asset | ANOH | Assa North 4 | DRILL & COMPLETE | CAPEX | Yes | No | Yes | No | [8 empty] | 21.58 |  |  |  | 33% | 0% |  | 75 |  |  |  | 100% |  |  | 2022-03-12 | 2022-08-25 | 11060 | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0! | [8 empty] | 21.58 | [17 empty] | 26.6
[30 empty] | #DIV/0! | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0!
[30 empty] | #DIV/0! | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0!
[30 empty] | #DIV/0! | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0!
[30 empty] | #DIV/0! | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0!
[30 empty] | #DIV/0! | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0!
[30 empty] | #DIV/0! | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0!
[30 empty] | #DIV/0! | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0!
[30 empty] | #DIV/0! | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0!
[30 empty] | #DIV/0! | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0!
[30 empty] | #DIV/0! | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0!
[30 empty] | #DIV/0! | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0!
[30 empty] | #DIV/0! | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0!
[30 empty] | #DIV/0! | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0!
[30 empty] | #DIV/0! | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0!
[30 empty] | #DIV/0! | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0!
[30 empty] | #DIV/0! | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | #DIV/0! | [7 empty] | #DIV/0! | #DIV/0!

## Drop Downs
Line of business | Country | Activity Entity | Activity type | Funding | Well Construction Archetype | Lower Completion Archetype | Upper Completion Archetype | Next WDP milestone | Next WDP milestone date | WDP scaling | TA1 Assured/ Yes/ no Questions | Estimate type | Estimate baked in improvement | CSO (%) | NPT Allowance (%) | Contingency (%) | Activity start | Total Duration (days) | Total Cost (TG $MM) | Total Cost (SS $MM) | Risk 1 | Section | Unmitigated Risk estimate ($MM) | Approximate possibility (%) | Benchmark | LE/ Final
Deepwater | Albania | AB LTO | WHOLE DRILLING | CAPEX | DW SS/DT 14” HPHT | 3-1/2” – 7-5/8” C&P | 3-1/2” Producer | DG1 | 2021-08-01 | FULL | Yes | Type 0 | <5% |  |  |  | 2021-12-21 |  |  |  | Added scope | ALL |  |  | BIC | LE
COG | Argentina | Abadi | WHOLE COMPLETION | EXPEX | DW SS 12-1/4” HPHT | 3-1/2” – 7-5/8” PDL | 4-1/2” Producer | DG1/2 (combination) | 2021-09-21 | Combined IDENTIFY/ASSESS | No | Type 1 | 5% < x < 10% |  |  |  | 2022-01-21 |  |  |  | Re-start | Section 1 |  |  | TQ | Final
Integrated Gas | Australia | Aera | DRILL - TOP HOLE | OTHER | DW SS NPNT | 4-1/2” P&P HPF | 5” Producer | DG2 | 2021-10-21 | Combined IDENTIFY/ASSESS/SELECT |  | Type 2 | 10% < x < 15% |  |  |  | 2022-02-21 |  |  |  | Subsurface - shallow hazards | Section 2 |  |  | Q2
Shales | Bolivia | Alaska Exploration | DRILL - SIDETRACK |  | SW SS NPNT | 7-5/8” C&P SAS | 5-1/2” Producer | DG2/3 (combination) | 2021-11-21 | Combined ASSESS/SELECT |  | Type 3 | >15% |  |  |  | 2022-03-21 |  |  |  | Subsurface - borehole | Section 3 |  |  | Q3
OTHER | Brazil | Albania Exploration | DRILL - RISERLESS |  | SW DT HPHT | 5-1/2” CH SZ FP/GP | 7” Producer | DG3 | 2021-12-21 | START IN DEFINE |  | Type 4 | OTHER |  |  |  | 2022-04-21 |  |  |  | Subsurface - losses | Section 4 |  |  | Q4
| Brunei | Albania Operated | DRILL - DEEPENING |  | SW DT NPNT | 7-5/8” CH SZ FP/GP | 9-5/8” Producer | DG4 | 2022-01-21 | OTHER | [6 empty] | 2022-05-21 |  |  |  | Subsurface - contingency liner | Section 5
| Bulgaria | Altamira | DRILL & COMPLETE |  | SW DT NPNT Slim | 7-5/8” CH DZ Commingled | 3-1/2” Injector | OTHER | 2022-02-21 | [7 empty] | 2022-06-21 |  |  |  | Subsurface - drillability | Section 6
| Canada | Argentina | PROJECT |  | Land Conventional | 7-5/8” CH DZ Selective | 4-1/2” Injector |  | 2022-03-21 | [7 empty] | 2022-07-21 |  |  |  | Subsurface - pressure events | Section 7
| Colombia | Argentina Exploration DW | OTHER |  | Land Shales | 7-5/8” CH DZ SMART | 5-1/2” Injector |  | 2022-04-21 | [7 empty] | 2022-08-21 |  |  |  | Subsurface - remedial cement | Section 8
| Egypt | Arrow |  |  | Land CBM | 7-5/8” CH MZ Selective | 6-5/8” Injector |  | 2022-05-21 | [7 empty] | 2022-09-21 |  |  |  | Subsurface - completion treatment | Section 9
| Malaysia | Atlantic LNG Marketing |  |  | N/A | 9-5/8” CH MZ Selective | N/A |  | 2022-06-21 | [7 empty] | 2022-10-21 |  |  |  | Subsurface - contaminants | Section 10
| Mauritania | Atlantic LNG T1 |  |  | OTHER | 7” OH GP/SAS/ESS | OTHER |  | 2022-07-21 | [7 empty] | 2022-11-21 |  |  |  | Subsurface - other | Section 11
| Mexico | Atlantic LNG T2&3 |  |  |  | 7-5/8” OH GP/SAS |  |  | 2022-08-21 | [7 empty] | 2022-12-21 |  |  |  | Performance - Drilling | Section 12
| Namibia | Atlantic LNG T4 |  |  |  | 8-5/8” OH GP/SAS |  |  | 2022-09-21 | [7 empty] | 2023-01-21 |  |  |  | Performance - Flat time | Section 13
| Netherlands | Atlantic Shores |  |  |  | 9-5/8” OH GP/SAS |  |  | 2022-10-21 | [7 empty] | 2023-02-21 |  |  |  | Performance - Work unit | Section 14
| Nigeria | Australia Corporate |  |  |  | N/A |  |  | 2022-11-21 | [7 empty] | 2023-03-21 |  |  |  | Performance - Suppliers | N/A
| Norway | Australia Exploration |  |  |  | OTHER |  |  | 2022-12-21 | [7 empty] | 2023-04-21 |  |  |  | Performance - other | OTHER
| Phillipines | BG Royalties | [6 empty] | 2023-01-21 | [7 empty] | 2023-05-21 |  |  |  | Supply chain - upselling
| Qatar | Bintulu GTL | [6 empty] | 2023-02-21 | [7 empty] | 2023-06-21 |  |  |  | Supply chain - uncertain rates
| Russia | Blauwwind | [6 empty] | 2023-03-21 | [7 empty] | 2023-07-21 |  |  |  | OTHER
| Sao Tome | Bolivia Corporate | [6 empty] | 2023-04-21 | [7 empty] | 2023-08-21
| Suriname | Brazil Corporate | [6 empty] | 2023-05-21 | [7 empty] | 2023-09-21
| Trinidad & Tobago | Brazil Exploration | [6 empty] | 2023-06-21 | [7 empty] | 2023-10-21
| Tunisia | Brent | [6 empty] | 2023-07-21 | [7 empty] | 2023-11-21
| Turkey | Bridge I&II | [6 empty] | 2023-08-21 | [7 empty] | 2023-12-21
| United Kingdom | Browse | [6 empty] | 2023-09-21 | [7 empty] | OTHER
| United States | Brunei Corporate | [6 empty] | 2023-10-21
| OTHER | Brunei LNG | [6 empty] | 2023-11-21
|  | BSP | [6 empty] | 2023-12-21
|  | Bulgaria Exploration | [6 empty] | OTHER
Caipipendi
CASA IG Corporate
Caspian Pipeline Consortium
Changbei
China Corporate
City Solutions Americas
City Solutions Asia
City Solutions EMEA
City Solutions Global
Clean Tech
COG MA
COG Provisions
Colombia Exploration
Crux
Cyprus
Dragon LNG
DW Brazil Operated
DW Brazil Operated Development
DW Central COG
DW Corporate Historic
DW Crude Oil Trading
DW GOM Corporate
DW GOM Mars Corridor
DW GOM Norphlet
DW GOM South
DW GOM West
DW MA COG
DW Mexico
DW Offloading Adjustment
DW Production GOM Other
DW Venezuela Corporate
DW Vent Dev Growth
East Coast Marine Area (ECMA)
Egypt LNG
Elba LNG
E-Mobility Americas
E-Mobility EMEA
E-Mobility Global
Environmental Products - UK
ERM B2BC
ERM Generation
Esenin Gydan
Fast Gen
Gas & Power Australia
Gas & Power Brazil
Gas & Power Chile
Gas & Power India
Gas & Power Mexico
Gas & Power United Kingdom
Gas & Power United States
GASCO
Gasnor
GasTerra
Geothermal NL
Germany NOV
GOM Exploration
Gorgon
Greater Groundbirch
Greenlots
GTL Holding Companies
GTL P&T Allocated
GTL P&T CRI
GTL PSP
H2M Operations Americas
H2M Operations EMEA
Hasdrubal
Huacareta
Hydrogen Americas
Hydrogen Asia
Hydrogen EMEA
Hydrogen Global
IG Central MA
IG Corporate
IG Gas Strategy & Advisory
IG Holding Companies
IG Namibia Exploration
IG NBD
IG NBD Functions
IG P&T Allocated
IG P&T Holding Co
IG Pension
IG PSP
IG Shell Energy Other
IG Shell LNG Gibraltar
IGB Tanzania
IGD Base
IGD Cafetero
IGD Corporate
IGD NZT
IGD Rubix
IGD Tanzania
IGN Australia Solar
IGN Nature Based Solutions
IGV Corporate & Functions
IGX Central IG
IGX IG MA
Indonesia Exploration
Iniguazu
Italy Corporate
Itau
Karachaganak
Karoo
Kazakhstan Exploration
Kenya Exploration
KMPA
Kuwait
La Vertiente
Libra & Iara
Limejump
LNG Canada
LNG Canada Expansion
LUSIL
Malaysia Exploration NOV
Malaysia Exploration Sabah DW
Malaysia Exploration Sabah DW NOV
Malaysia Exploration Sarawak
Malaysia NOV
Malaysia Sabah Deepwater CSP
Mauritania Exploration
Mauritania Exploration COG
Mauritania Exploration DW
Mayflower Wind
Mexico Exploration DW
Mexico Exploration SW
Miskar
Morocco Exploration
Mozambique NBD
MP2
Myanmar Exploration
NBS Global
NE Corporate
Netherlands Corporate
Netherlands Exploration
New Motion
New Zealand Corporate
Nigeria Corporate
Nigeria DW Corporate
Nigeria DW Exploration
Nigeria DW NOV
Nigeria DW Operated
Nigeria Exploration
Nigeria LNG
NoordzeeWind
Nord Stream 2
North America Exploration Corporate
North Caspian Sea PSA (NCSPSA)
North Coast Marine Area (NCMA)
North West Shelf
Norway Corporate
Norway Exploration
Norway NOV
Norway SOV
Offshore Wind Americas
Offshore Wind Asia
Offshore Wind EMEA
Offshore Wind Global
Oman Exploration COG
Oman Gas
Oman LNG
Oman Other
Oman Pink
OneGas East
OneGas West
Onshore NL Groningen
Onshore NL Land
Onshore Wind Operations
PDO
PDO Adjustments
Pearl GTL
Pearls PSA
Permian
Peru LNG
Philippines Corporate
Philippines Exploration
Power Corporate
Power Holding Companies
Power P&T Allocated
Power Pension
Power PSP
Prelude
Qatar Corporate
Qatargas 4
QDN
QGC
Rashpetco
RES Distributed Energy Americas
RES Distributed Energy Australia
RES Distributed Energy EMEA
RES Distributed Energy Global
RES Energy Access Global
RES Onshore Power Americas
RES Onshore Power Asia
RES Onshore Power Australia
RES Onshore Power EMEA
RES Onshore Power Global
RES Retail Americas
RES Retail Asia
RES Retail Australia
RES Retail EMEA
Russia Corporate
Sabah DW
Sabah DW NOV
Salym Exploration
Sao Tome Exploration DW
Sarawak
SDB
SDB Central Corporate
SDB Exploration
SEA Generation
SEAU
SEB
SE-EE B2B-C
SE-EE Generation
SEI
SEIC
SEIC Corporate
SEIPL
SENV
SEPB
SEPB Exploration
SGI-BGC
Shales Central
Shales MA
Shales Other
Shell Caspian
Shell Energy Retail
Shell Ventures
Silicon Ranch Corporation
SLMT LNG
SNG Asset
SOIFI Rigs
Solar Operations Australia
Solar Operations EMEA
Somalia Exploration
Sonnen EMEA
South Africa Exploration DW
Southern Cross pipeline
SPD
SPDC Central East Asset
SPDC Land Asset
SPDC NOV
SPDC Pipelines Asset
SPDC West Asset
Spectrum
SPEX
T&T Central Block
T&T Corporate
T&T Cross Border
T&T Development
T&T Exploration
T&T Manatee
Taiyang
Tempa Rossa
Thailand Exploration
Trading Allocation - Shell Energy
Tunisia Corporate
Turkey Exploration
UK Corporate
UK Exploration NOV
UK Exploration Operated
UK NOV
UK Operated
Ukraine Corporate
UP COG Projects
UP Corp Ult Sh hld SPNV-STT COG
UP Corp Ult Sh hld SPNV-STT DW
UP Corp Ult Sh hld SPNV-STT Shales
UP Corporate Other COG
UP Corporate Other DW
UP Corporate Other Shales
UP Corporate Service COG
UP Corporate Service DW
UP Corporate Service Shales
UP Director MA COG
UP Director MA DW
UP Director MA Shales
UP Divestment COG
UP Divestment DW
UP Divestment Shales
UP MA COG
UP MA Shales
UP P&T COG
UP P&T DW
UP P&T Rigs
UP P&T Shales
UP Pensions COG
UP Pensions DW
UP Pensions Shales
UP Provisions COG
UP Provisions DW
UP Provisions Shales
UP PSP COG
UP PSP DW
UP PSP Shales
UP SIEP Servco Plan COG
UP SIEP Servco Plan DW
UP SIEP Servco Plan Shales
UP Trading COG
UPD Central
UPD Management Adjustment
UPN Central
UPN Other
Upstream India PMT
UPU MA
UPX Central COG
UPX Central DW
UPX COG MA
UPX DW MA
Val D Agri
WAPCo