## Plan (3)
BOGT Crude Export Master Meter Recertification Plan
S/N | Activity | Start Date | End Date | Action Party
1 | Confirmation of verification agent | 2021-07-02 | 2021-07-05 | Bernard/Sotonye
2 | PO creation/issue to IVA | 2021-07-05 | 2021-07-06 | Bernard/Sotonye
3 | Submission of letter and associated docements to DPR | 2021-07-07 | 2021-07-07 | Bernard/Sotonye
4 | Calibration of Meters | 2021-07-12 | 2021-07-16 | Krohne
5 | Post-calibration activities/ packaging | 2021-07-19 | 2021-07-23 | Krohne
6 | Shipment of equipment to Nigeria (Air Freight) | 2021-07-23 | 2021-07-31 | Krohne
7 | Custom clearing | 2021-08-01 | 2021-08-15 | Krohne
8 | Invitation of DPR for master meter changeout | 2021-08-01 | 2021-08-15 | Bernard/Sotonye
9 | Movement of meter from Onne to Bonny | 2021-08-20 | 2021-08-22 | Bernard/Sotonye
10 | Master meter changeout/ Linearity test | 2021-08-23 | 2021-08-30 | Bernard/Sotonye
11 | Report preparation and transmission to DPR | 2021-08-31 | 2021-09-02 | Bernard/Sotonye
Note on C7: Actual date is subject to confirmation from calibration facility