## Q2-Q3 LIP
S/N | Asset | Conduit | DP-Type | Funding Tranche | WRFM Category | Potential (boepd) | Activity | Activity Cost $mln | Status | Execution Date | LIP Restoration
1 | West | EAZZ042T | Oil | JV | Optimisation | 0.58877 | Attic perforation addition on the C92E reservoir - CO log dependent | 5.1759 | Executed | 2022-09-01 | Q2/Q3
2 | West | EAZZ035T | Oil | JV | Restoration | 0.24 | GLV C/O - DPA | 0.45 | Executed | 2022-05-01 | Q2/Q3
3 | West | EAZZ058S | Oil | AF | Restoration | 0.3 | WRSCSSSV Change Out | 0.161 | Executed | 2022-05-01 | Q2/Q3
4 | West | EAZZ020T | Oil | AF | Optimisation | 0.6 | Perforation, Through Tubing Screen Installation and Gas Lift Valve Change Out_Dependent on EA33 CO log | 3.833 | Executed | 2022-06-01 | Q2/Q3
5 | West | KANB005L | Oil | AF | Restoration | 0.54 | Sectional flowline replacment and PB valve installation | 0.68607 | Executed | 2022-09-01 | Q2/Q3
6 | West | KANB005S | Oil | AF | Restoration | 0.5 | Sectional flowline replacement and SCSSSV Redress | 0.78607 | Executed | 2022-07-01 | Q2/Q3
| Month | Plan Production | Implementation Cost ( USD) | Production Days | Plan Calculated FCF ( USD) | Actual Production | Actual FCF
| June | 0.54 | 610 | 30 | 29440 |  | 0
| July | 1.14 | 3830 | 31 | -235680 | 0.25 | -22900
| Aug | 1.14 | 0 | 31 | 223920 |  | 49100
| Sept | 1.14 | 0 | 30 | 216690 |  | 47520
| Oct | 1.14 | 0 | 31 | 223920 |  | 49100
| Nov | 2.77 | 6650 | 30 | -271470 | 0.56 | -562430
| Dec | 2.77 | 0 | 31 | 544080 |  | 159100