## Sheet1
S/No | Asset | Well Name | Fluid | Scope | Potential, bopd | LEC (L4) | OSD (L5)
1 | West | EJAZ006T | Oil | ScSSSV lockout & PB valve installation. Lockout tool ordered now on site | 380 | 2023-01-10 | 2023-02-09
2 | West | OPUK012S | Oil | Flowline repairs – contingent on the GSA in place; flood delay | 365 | 2023-01-12 | 2023-02-11
3 | West | OTUM046S | Oil | Flowline Repair | 700 | 2023-01-13 | 2023-02-12
4 | West | FORC136T | Oil | Sand Cleanout | 650 | 2023-01-18 | 2023-02-17
5 | West | OTUM029S | Oil | Flowline Repair | 350 | 2023-01-19 | 2023-02-18
6 | West | EJAZ008T | Oil | Drift run/ScSSSV investigation | 650 | 2023-01-26 | 2023-02-25
7 | West | OTUM035L | Oil | Gas lift line repair + GLVCO | 324 | 2023-01-27 | 2023-02-26
8 | West | OTUM039L | Oil | Gas lift line repair + GLVCO | 386 | 2023-02-02 | 2023-03-04
9 | West | OPUK012L | Oil | Wellhead repairs | 134 | 2023-02-03 | 2023-03-05
10 | West | FORC135L | Oil | PBV Installation/N2 lift | 600 | 2023-02-03 | 2023-03-05
11 | West | OTUM022S | Oil | GLVCO | 100 | 2023-02-09 | 2023-03-11
12 | West | FORC073S | Oil | PBV Recalibration | 1000 | 2023-02-12 | 2023-03-14
13 | West | OTUM019T | Oil | GLVCO | 100 | 2023-02-12 | 2023-03-14
14 | West | OTUM010S | Oil | GLVCO | 100 | 2023-02-16 | 2023-03-18
15 | West | OTUM008S | Oil | GLVCO | 324 | 2023-02-23 | 2023-03-25
16 | West | BENS002T | Oil | GSO & Reperf - lined up behind Bens & Ogbo CO log campaign | 397 | 2023-03-05 | 2023-04-04
17 | West | FORC140T | Oil | Heel perforation and SCON | 655 | 2023-03-06 | 2023-04-05
18 | West | FORC139T | Oil | TRSCSSV LOCK OUT + PB VALVE | 500 | 2023-03-25 | 2023-04-24
19 | West | AJAT001L | Oil | AJAT 1L FLOWLINE REPLACEMENT | 1600 | 2023-04-02 | 2023-05-02
20 | West | FORC138T | Oil | Foam lift Opportunity (Foam stick) | 760 | 2023-04-16 | 2023-05-16
21 | West | AFRE010L | Oil | PB Valve recalibration | 380 | 2023-04-23 | 2023-05-23
22 | West | AFRE015T | Oil | AFRE 15T PB Valve recalibration | 300 | 2023-05-02 | 2023-06-01
23 | West | FORC142S | Oil | Sand Clean Out/TT Screen/N2 Lift | 1242 | 2023-05-23 | 2023-06-22
24 | West | OPUK033S | Oil | Flow line repair – check with Asset | 374 | 2023-05-31 | 2023-06-30
25 | West | OPUK007T | Oil | Wellhead repairs – replace vandalized accessories | 451 | 2023-05-31 | 2023-06-30
26 | West | OPUK038T | Oil | Wellhead repairs – replace vandalized accessories | 1265 | 2023-05-31 | 2023-06-30
27 | West | AFRE014L | Oil | Chemical Descaling | 300 | 2023-06-13 | 2023-07-13
28 | West | FORC048L | Oil | Sand Cleanout/SCON/Perf Extension | 500 | 2023-07-10 | 2023-08-09
29 | West | FORC084L | Oil | GLVCO/FBHP | 200 | 2023-07-19 | 2023-08-18
30 | West | BENS018L | Oil | AF maintenance activity. Clean out , Reperforation. | 403 | 2023-07-20 | 2023-08-19
31 | West | OTUM002L | Oil | Otumara 002L Wax Remediation Enhanced Solvent | 150 | 2023-07-23 | 2023-08-22
32 | West | FORC112T | Oil | GLVCO/FBHP | 197 | 2023-07-24 | 2023-08-23
33 | West | FORC075T | Oil | GLVCO/FBHP | 150 | 2023-07-29 | 2023-08-28
34 | West | OPUK025T | Oil | OPUK 25T XMT REPLACEMENT & N2 LIFT | 400 | 2023-08-05 | 2023-09-04
35 | West | OTUM041L | Oil | FL repairs and Sand cleanout / SCON | 231 | 2023-08-07 | 2023-09-06
36 | West | FORC003L | Oil | Water shutoff / Reperforation / SCON 2 bulkline on cluster 3 | 300 | 2023-08-16 | 2023-09-15
37 | West | OPUK026T | Oil | Heel perforation | 700 | 2023-08-27 | 2023-09-26
38 | West | AFRE013L | Oil | Rigless Cement packer on D5000B | 600 | 2023-09-13 | 2023-10-13
39 | West | KANB005L | Oil | FL Repair completed, PB valve installation pending | 593 | 2023-11-15 | 2023-12-15
40 | West | OTUM029L | Oil | Flow line integrity issues, GL deepening | 250 | 2023-11-25 | 2023-12-25
41 | West | KANB006T | Oil | Flowline Repair | 460 | 2023-11-30 | 2023-12-30
42 | West | OTUM017T | Oil | GLVCO | 150 | 2023-12-02 | 2024-01-01
43 | West | OTUM054T | Oil | GLVCO | 100 | 2023-12-09 | 2024-01-08
44 | West | OPUK024T | Oil | CCU, TRSSV L/O | 493 | 2023-12-13 | 2024-01-12
45 | West | KANB003L | Oil | Flowline Replacement | 314 | 2023-12-15 | 2024-01-14
46 | West | BENS017L | Oil | AF maintenance activity. SCON Cleanout. | 420 | 2023-12-15 | 2024-01-14
47 | West | OTUM043L | Oil | Sand cleanout, attic perforation, SCON | 298 | 2023-12-17 | 2024-01-16
48 | West | OPNO021T | Oil | Flowline repairs – contingent on the GSA in place; flood delay | 432 | 2023-12-22 | 2024-01-21
49 | West | OPUK034T | Oil | Tubbing straddle (LLI) | 500 | 2023-12-28 | 2024-01-27
50 | West | KANB004S | Oil | Flowline Replacement | 250 | 2023-12-30 | 2024-01-29
51 | West | OPOM001S | Oil | WRSCSSV redress scope + contingent PBV installation + N2 Lift (+ FLRR) | 817 | 2023-12-31 | 2024-01-30