## Sheet1
Order | Order Type | Basic start date | Description | System status | User Status | Latest Allowed Finish Date | Notification | Total actual costs | Estimated costs | Total planned costs | FunctLocDescrip.
22929219 | 72FC | 2021-06-30 | GTC STG2 A/COOLER FAN C UNUSUAL NOISE | TECO CNF ESTC CSER NMAT PRC SETC | XCNF WPOK XGI | 2021-08-11 | 11858557 | 0 | 1824 | 0 | STG2 AFTERCOOLER,STG2 COMPRESSOR,OTUG1
22956143 | 72RE | 2021-11-30 | REPAIR DRY COOLER MOTOR BEARING FAILURE | REL GMPS PRC SETC | APPR MANX |  |  | 60.32 | 73.66 | 1731.26 | ELECTRIC MOTOR,DRY GAS COOLER,OTUG1
22936783 | 72FC | 2021-12-12 | OTUCPF DRY GAS COOLER-FANC UNUSUAL NOISE | REL CNF ESTC NMAT PRC SETC | EXEC WPOK | 2022-01-05 | 11862462 | 313.2 | 210 | 313.2 | ELECTRIC MOTOR,DRY GAS COOLER,OTUG1
22982040 | 71PO | 2022-02-12 | Procurement Of 2Pc Dry Gas El. Motors | REL ESTC PRC SETC | APPR |  |  | 0 | 6738.18 | 6738.19 | ELECTRIC MOTOR,DRY GAS COOLER,OTUG1
22941738 | 72RE | 2022-02-18 | Repair faulty bearing, carry out check | REL CNF ESTC GMPS PRC SETC | APPR MANX |  |  | 7.07 | 70.09 | 1890.09 | ELECTRIC MOTOR,DRY GAS COOLER,OTUG1
23000579 | 72RE | 2022-03-28 | REPLACE FAILED BEARINGS OF OTUG1 GTC COO | REL GMPS NMAT PRC SETC | APPR |  |  | 961.7 | 961.5 | 961.5 | MOTOR,LUBE OIL COOLER FAN,OTUG1
22999441 | 72FC | 2022-05-13 | RECTIFY GTC LUBE OIL COOLER NOISE: UNIT | TECO CNF ESTC NMAT PRC SETC | XCNF XGI | 2022-05-15 | 11904087 | 108.78 | 108.78 | 108.78 | MOTOR,LUBE OIL COOLER FAN,OTUG1
22998496 | 72RE | 2022-05-23 | Repair Dry Gas motor C | TECO CNF NMAT PRC SETC | XCNF XGI |  |  | 2072 | 2072 | 2072 | ELECTRIC MOTOR,DRY GAS COOLER,OTUG1
23021730 | 72FC | 2022-10-20 | OTUG1 4TH STG FAN C MAKING UNUSUAL NOISE | REL ESTC NMAT PRC SETC | EXEC | 2022-12-17 | 11920340 | 0 | 207.2 | 207.2 | ELEC MOTOR,4TH STAGE AFTERCOOLER,OTUG1
14022.22