## 2022 AGG Aspiration CostSavings
2022 AGG Aspiration Cost Saving Plan
S/N | Activity Description | Qty | Duration (Days) | optimized scope / reduced material cost | FSR Unit Rate | Total | Timeline
|  |  |  | $ | $ | $
1 | Soku LP NAG Midlife Inspections (Midlife Inspection in place of Core engine exchange) | 1 | 14 | 1638102.93 | 3000 | 1638102.93 | Feb - Nov
2 | AGG Team DIY intervention (4K Solar Turbine Inspections) | 12 | 5 |  | 2690 | 161400 | Feb - Dec
3 | AGG Team DIY intervention (8K Inspections) | 13 | 7 |  | 2690 | 244790 | Mar - Dec
4 | AGG Team DIY intervention (Replacement LPC vanes for Soku AG2/LP NAG) | 4 | 5 |  | 3000 | 60000 | Mar - Aug
5 | AGG Team Scope Optimization | 5 | 1 |  | 2500 | 12500 | Feb - Dec
6 | OTC savings from Solar (42%) | 0.42 | 100 |  | 2690 | 112980 | Feb - Dec
7 | OTC savings from Siemens (50%) | 0.5 | 100 |  | 2500 | 125000 | Feb - Dec
8 | OTC savings from Excel (50%) | 0.5 | 50 |  | 3000 | 75000 | Mar - Dec
9 | OTC savings from GE (50%) | 0.5 | 20 |  | 3200 | 32000 | Feb - Dec
10 | Interventions (medium troubleshootings) | 50 | 2 |  | 2500 | 250000 | Feb - Dec
[5 empty] | TOTAL | 2711772.93