## Slide 1: Civil Structures DIY Design, Training and Implementation
PROPOSED SOLUTION
Perform inhouse training for civil inspectors using TA 2 as trainer
Estimate the cost of savings in terms of using In house and online training resources.
Achieve TA certification for at least 2 contract personnel
PROBLEM STATEMENT
The skillset for civil structural asset integrity are relatively new and not easily assessable in textbooks
Civil Inspectors perform many structural integrity assessments, and their skill sets vary for different civil SCEs
There is an opportunity to perform upskilling and training using inhouse solution
POTENTIAL BENEFIT
Cost savings from inhouse trainings_N200,000 x 4 = N800,000 = $1904.76
Improved competence level for inspectors
Achieve TA certification and in role performance for contractor staff
CIVIL META TEAM
IMPLEMENTATION PLAN & VALUE DRIVERS
Identify training gaps for civil inspection team (L1) – End Feb
Design and build up training plan (L2) - End Apr
Execute training plan and achieve cost savings (L3) - End June
Receive feedback on training improvement areas (L4) - End August