## Otumara
OTUMARA CPF ALARM MANAGEMENT ACTIVITY COMPLETION TIMELINES
Phase | Work Scope | Critical Milestone | Days | Target End Date | Resource required | Comments
Phase 2 | 1. Update MoC list with TA comments and submit to TAs and Asset team | Secure CCMP approval | 1 | 22nd May |  | DONE
| 2. Sign-off Cover page |  | 2 | 26th May |  | DONE
| 3. Create E-MoC |  | 3 | 29th May |  | DONE
| 4. Schedule CCMP date |  | 3 | 29th May |  | DONE
| 5. Secure CCMP approval |  | 3 | 4th June |  | DONE
Phase 3 | 1. Engage Vendor; finalise contract |  | 14 | 12th June |  | P.O. releases and sent to Vendor
| 2. Alarm priority change list / suppression list sent to the Vendor |  | 1 | 12th June |  | DONE
| 3. Mobilize required personnel to site |  | 12 | 24th June |  | Offsite work ongoing
| 4. Carry out implementation and download to Controllers | DCS Implementation of approved changes | 8 | 2nd July | *Vendor Availability *Emergency contract in place for Vendor * Facility shutdown from Asset Manager
| 5. Asset (PACO Personnel) to send DCS download after implementation |  | 1 | 3rd July
| 6. Verify implementation of approved changes (QA/QC) |  | 2 | 8th July
| 7. Update VT with new alarm tags & changes |  | 2 | 10th July
| Total Estimated Time (TET): |  | 46 Days

## Benisede
BENISEDE ALARM MANAGEMENT ACTIVITY COMPLETION TIMELINES
Phase | Work Scope | Critical Milestone | Days | Target End Date | Resource required | Comments
Phase 2 | 1. Update MoC list with TA comments and submit to TAs and Asset team | Secure CCMP approval | 1 | 22nd Jan |  | DONE
| 2. Sign-off Cover page |  | 2 | 26th Jan |  | DONE
| 3. Create E-MoC |  | 3 | 29th Jan |  | DONE
| 4. Schedule CCMP date |  | 3 | 29th Feb |  | DONE
| 5. Secure CCMP approval |  | 3 | 4th Feb |  | DONE
Phase 3 | 1. Engage Vendor; finalise contract |  | 14 | 12th Feb |  | P.O. releases and sent to Vendor
| 2. Alarm priority change list / suppression list sent to the Vendor |  | 1 | 12th Feb |  | DONE
| 3. Mobilize required personnel to site |  | 12 | 24th April |  | Offsite work ongoing
| 4. Carry out implementation and download to Controllers | DCS Implementation of approved changes | 16 | 15th May | *Vendor Availability *Emergency contract in place for Vendor * Facility shutdown from Asset Manager
| 5. Asset (PACO Personnel) to send DCS download after implementation |  | 1 | 16th May
| 6. Verify implementation of approved changes (QA/QC) |  | 3 | 20th May
| 7. Update VT with new alarm tags & changes |  | 2 | 29th May
| Total Estimated Time (TET): |  | 61 Days