## ORIGINAL VS ACTUAL
META CIVIL PM MOBILIZATION COST ESTIMATE (PLANNED & ACTUAL)
|  |  | ORIGINAL PM PLANS |  |  |  | ACTUAL OPTIMIZED VISIT |  |  |  | RATES (NGN) |  |  |  |  | PLANNED, TARGET & ACTUAL INSPECTION COST ($)
S/NO | MONTH | LOCATION | N0. OF PLANNED VISITS | N0 OF PLANNED PERSONNEL | ETC (DAYS) | SITE ACCOMODATION (DAYS) | N0. OF ACTUAL VISITS | ACTUAL N0 OF PERSONNEL | ACTUAL ETC (DAYS) | ACTUAL SITE ACCOMODATION (DAYS) | LAND TRANSPORT RATE (NGN) | AIR TRANSPORT RATE (NGN) | ALLOWANCES, FEEDING & ACCOMODATION RATE (NGN) | REDUCTION FACTOR (To account for unforseen circumstances) | TOTAL PLANNED AMOUNT NGN | COST PLANNED ($) | PLANNED MONTHLY COST ($) | ACTUAL INSPECTION COST (NGN) | ACTUAL COST ($) | ACTUAL SAVINGS ($) | REMARKS
1 | JAN | OTUMARA FIELD | 3 | 2 |  | 7 | 1 | 2 |  | 7 |  | 119200 | 28016 | 1 | 1891872 | 4618.1516 |  | 630624 | 1539.3839 | 3078.7678 | 5187
2 |  | GBARAN FIELD | 3 | 2 |  | 21 | 1 | 2 |  | 16 | 42438.53 |  | 25937 | 1 | 3522693.18 | 8599.0655 |  | 829984 | 2026.0313 | 6573.0342
|  | YOKRI & NBK | 3 | 2 |  | 7 | 1 | 1 |  | 11 |  | 119200 | 28016 | 1 | 1891872 | 4618.1516 |  | 427376 | 1043.2456 | 3574.906
3 |  | RUMUAHIA | 2 | 2 |  | 7 | 1 | 2 |  | 11 | 42438.53 |  | 25937 | 1 | 895990.12 | 2187.1555 | 12174.4425 | 570614 | 1392.8965 | 794.2589
4 | FEB | NUN RIVER & DIEBU CREEK | 4 | 2 |  | 14 | 1 | 2 |  | 7 |  | 119200 | 28016 | 1 | 4091392 | 9987.287 |  | 630624 | 1539.3839 | 8447.9031
5 | [13 empty] | 1 | 0 | 0 |  | 0 | 0 | 0
6 | [16 empty] | 0 | 0 | 0 | 0
7 | [17 empty] | 0 | 0 | 0
8 | [16 empty] | 0 | 0 | 0 | 0
9 | [16 empty] | 0 | 0 | 0 | 0
10 | [17 empty] | 0 | 0 | 0
11 | [16 empty] | 0 | 0 | 0 | 0
12 | [17 empty] | 0 | 0 | 0
|  | TOTAL COST OF PM INSPECTION MOBILIZATION (2023) | [13 empty] | 30009.8113 | 12174.4425 |  | 7540.9413 | 22468.87

## ADIBAWA (hidden)
COST SAVING FROM STRUCTURAL INTEGRITY ASSESSMENT OF FLARE STRUCTURE INSPECTION IN ADIBAWA FLOWSTATION
| No | Month rate |  | Per head | Subtotal
|  | US $ | Naira |  | US $ | Naira | Naira
1
Feeding & Accm | 7 |  | 20750 | 6 |  | 145250 | 145250
ETC/OTC | 5 |  | 20750 |  |  | 103750 | 103750
0
0
0
0
0
0
0
0
0
0
|  |  | Total in Naira |  |  | 249000 | 249000
|  |  | F$ |  |  |  | 816.3934

## ETELEBOU (hidden)
COST SAVING FROM STRUCTURAL INTEGRITY ASSESSMENT OF FLARE STRUCTURE INSPECTION IN ETELEBUO
| No | Month rate |  | Per head | Subtotal
|  | US $ | Naira |  | US $ | Naira | Naira
Feeding & Accm | 7 |  | 20750 | 2 |  | 145250 | 145250
ETC/OTC | 5 |  | 20750 |  |  | 103750 | 103750
0
0
0
0
0
0
0
0
0
0
|  |  | Total in Naira |  |  | 249000 | 249000
|  |  | F$ |  |  | 816.3934 | 816.3934

## OKOLOMS GP (hidden)
COST SAVING FROM STRUCTURAL INTEGRITY ASSESSMENT OF CONCRETE/WOODEN ELECTRIC POLES AT OKOLOMA GP
| No | Month rate |  | Per head | Subtotal
|  | US $ | Naira |  | US $ | Naira | Naira
Feeding & Accm | 7 |  | 20750 | 2 |  | 145250 | 145250
ETC/OTC | 5 |  | 20750 |  |  | 103750 | 103750
0
0
0
0
0
0
0
0
0
0
|  |  | Total in Naira |  |  | 249000 | 249000
|  |  | F$ |  |  | 816.3934 | 816.3934
#REF!

## BONNY (hidden)
COST SAVING FROM STRUCTURAL INTEGRITY ASSESSMENT OF CIVIL SCEs AT BONNY TERMINAL AND OLOMA FLOWSTATION
| No | Month rate |  | Per head | Subtotal
|  | US $ | Naira |  | US $ | Naira | Naira
Flight | 2 |  | 59600 | 2 |  | 119200 | 119200
Feeding & Accm | 7 |  | 20750 |  |  | 145250 | 145250
ETC/OTC | 5 |  | 20750 |  |  | 103750 | 103750
0
0
0
0
0
0
0
0
0
|  |  | Total in Naira |  |  | 368200 | 368200
|  |  | F$ |  |  | 1207.2131 | 1207.2131

## BENISEDE (hidden)
COST SAVING FROM STRUCTURAL INTEGRITY ASSESSMENT OF STEEL SUPPORT STRUCTURE AT BENISEDE FLOWSTATION
| No | Month rate |  | Per head | Subtotal
|  | US $ | Naira |  | US $ | Naira | Naira
Flight | 2 |  | 59600 | 2 |  | 119200 | 119200
Feeding & Accm | 7 |  | 20750 |  |  | 145250 | 145250
ETC/OTC | 5 |  | 20750 |  |  | 103750 | 103750
0
0
0
0
0
0
0
0
0
|  |  | Total in Naira |  |  | 368200 | 368200
|  |  | F$ |  |  | 1207.2131 | 1207.2131

## KOLO CREEK (hidden)
COST SAVING FROM STRUCTURAL INTEGRITY ASSESSMENT OF FLARE STRUCTURE INSPECTION IN KOLO CREEK
| No | Month rate |  | Per head | Subtotal
|  | US $ | Naira |  | US $ | Naira | Naira
Feeding & Accm | 7 |  | 20750 | 2 |  | 145250 | 145250
ETC/OTC | 5 |  | 20750 |  |  | 103750 | 103750
0
0
0
0
0
0
0
0
0
0
|  |  | Total in Naira |  |  | 249000 | 249000
|  |  | F$ |  |  | 816.3934 | 816.3934

## Land Transport Rates (hidden)
Land transportation per day: Logistics
Salon cars | SPDC | 16000
| Temile | 22950
| Petronella | 36835.38
Pickup | SPDC | 20000
| Temile | 22950
| Petronella | 40272.16
HIACE | SPDC Mini bus | 35000
| Temile | 27540
| Petronella | 42438.53
Coaster buses | SPDC Mini bus | 65000
| Temile | 45370
| Petronella | 70915.98
SUV | SPDC big | 50000
| SPDC small | 45000