## Slide 1: Terminal Integrity Improvement
Business Case:
There is a significant amount of pressurized equipment at the Forcados and Bonny terminals, with in-house inspectors responsible for managing all inspection activities. Unfortunately, the majority of the corrosion barriers are currently in RED status, and our personnel on the ground are not adequately equipped to handle this. Due to limited resources, the scope of inspection has not been fully covered, leaving the asset's integrity largely unknown. Given the critical role these terminals play in SPDC's revenue, it is essential to investigate and deploy measures to improve the health status to GREEN with minimal production interruption.
Objective:
Ascertain Pressurized Equipment Integrity Status – Vessels, Tanks, Piping, heat exchangers and relief valves
Generate Corrosion Management Plan to manage corrosion barriers
Ensure all equipment data are captured on IMS for analysis
An Effective organogram is in place
Reduce tank out of service by use of Robotics
Asset awareness of corrosion barrier status
High-level Timeline:
Site barrier assessment and interviews: February 2025
Implement Organogram: June 2025
Tank Robotics Inspection :Nov 2025
Terminal Integrity report Q2 & Q4: Dec 2025
Potential Benefits & Measurement:
Predictive approach to corrosion barrier management
Risk optimization driven approach to degradation management thru use of integrated management system
A green health corrosion barrier supporting life extension assessment
Optimized Inspection personnel
Minimize Tank out of service and man entry requirement
Project Scope/Actions:
Conduct Facility corrosion barrier assessment for the terminals; February 2025
Engagement with terminal leaders on barrier status and recommendations; FEB 2025
Carry out recommended inspection to acquire relevant data for assessment; Dec 2025
Continuously integrate acquired data into IMS for analysis: Dec 2025
Roll out of facility Organogram and responsibilities ; June 2025
Deploy Tank robotics inspection; Nov 2025
Generate and issue out Facility integrity reports; Dec 2025
Critical Success Factors:
Leadership commitment
Budget availability;
Data & personnel Availability
Contract management
Technical Authority Availability
  Project Sponsor: Emeka Obi
  Implementation Lead: Akanni Joseph
  Project Team:
  Orajaka Chinenye
  Paschal Odinde
  Ohia Chibueze
  Joel Nwosu
  Somto Obi
  Felix Akunwanne
  Ojeri Chinedu
  Lawal kamar
  Overo Ogheneakpobo
Notes: Activity list
Rig-Up Equipment To Roof
Quick-Look –Visual Inspection
Online floor scanning using UT Method.
Annular Plates SRUT
Shell Course, Roof Plates Scanning with UT Crawler
Rig-Down Equipment
Analysis and Reporting