## Deliverables
PU | Process Steps | Activity | Action Lead | Pillars | Deliverables | Equipment | Weight | Close out Date | % Completion | Comment | Comment Date | Column1
Tunu | System Selection And Scope | Resource the IVD plan | Ndukwe Victor | Proactive Technical Monitoring | Engage the task owners to conform resources needed and readiness to deliver |  | 1 | 2022-04-30 | 100%
Tunu | System Selection And Scope | Identify Improvement Goal | Kebin Ofori |  | Outline clear targets |  | 1 | 2022-04-30 | 100% | 1. Reduction of trips from 35trips 2021 by 50% by Dec 2022. 2. Improvement in availability of Compressor by 5% from 89% 2021 performance (Best in Class for West based asset is 95%) 3. Reduce total unscheduled deferment by 25% from 1644kboe in 2021 by Dec 2022 4. Reduce flare by 25% in 2022
Tunu | System Selection And Scope | Kick Off meeting stakeholders | Ndukwe Victor |  | Engage AGG team on IVD |  | 1 | 2022-04-30 | 100%
Tunu | System Selection And Scope | Kick Off meeting stakeholders | Ndukwe Victor |  | Engage PS LT on IVD plans |  | 1 | 2022-04-30 | 100%
Tunu | System Selection And Scope | Kick Off meeting stakeholders | Ndukwe Victor |  | Engage Asset Manager IVD plans |  | 1 | 2022-04-30 | 100%
Tunu | System Selection And Scope | Kick Off meeting stakeholders | Ndukwe Victor |  | Name System Owners on IVD plans |  | 1 | 2022-04-30 | 100%
Tunu | System Selection And Scope | Kick Off meeting stakeholders | Ndukwe Victor |  | Agree Cadence, DRB and Success measures |  | 1 | 2022-04-30 | 100%
Tunu | MTO | Identify Threats on Fit4MTO database | Ndukwe Victor |  | Download threats and actions on MTO with impact on system |  | 1 | 2022-04-30 | 100%
Tunu | MTO | Identify Threats on Fit4MTO database | Ndukwe Victor |  | Analyse data and identify threats with deferment, flaring impact, equipment with low availability |  | 1 | 2022-04-30 | 100%
Tunu | MTO | Identify Bad actors (Review past trips and RCAs) | Ndukwe Victor |  | Review historical trip logs |  | 1 | 2022-04-30 | 100%
Tunu | MTO | Identify Bad actors (Review past trips and RCAs) | Ndukwe Victor |  | Identify causes of trips |  | 1 | 2022-04-30 | 100%
Tunu | MTO | Identify Bad actors (Review past trips and RCAs) | Ndukwe Victor |  | Review completed RCAs from past events |  | 1 | 2022-04-30 | 100%
Tunu | MTO | Identify Bad actors (Review past trips and RCAs) | Ndukwe Victor |  | Download and review failure history on SAP |  | 1 | 2022-04-30 | 100%
Tunu | MTO | Identify Bad actors (Review past trips and RCAs) | Ndukwe Victor |  | Enumerate common themes |  | 1 | 2022-04-30 | 100%
Tunu | MTO | Capture and Resolve corrective actions from EPST Causal Learning Investigation on Tunu frequent facility trips | Ndukwe Victor |  | 1. Capture learnings and threats for future trips | All | 1 | 2022-09-30 | 100% | Learning Session Completed.
Tunu | MTO | Capture and Resolve corrective actions from EPST Causal Learning Investigation on Tunu frequent facility trips | Ndukwe Victor |  | 2. Define solutions and their development/implementation actions for sustainable threat mitigation | All | 1 | 2022-09-30 | 100% | Solution Development Completed
Tunu | MTO | Capture and Resolve corrective actions from EPST Causal Learning Investigation on Tunu frequent facility trips | Ndukwe Victor |  | Track Actions on Fit4 MTO | All | 1 | 2022-12-30 | 100%
Tunu | MEC | CMMS Build closing the gaps MJR, BoM, coding. Technical Object Type Assigment to each FuncLoc Asset Register structured by FuncLoc | Daniel Olalekan | Maintenance & Operations | Review of Current Asset Register and identify Gaps (Asset Register, Drawings physical on site) | All Copressors and Accessories in Tunu, Benisede, Opukushi and Ogbotogbo | 1 | 2022-10-30 | 100%
Tunu | MEC | CMMS Build closing the gaps MJR, BoM, coding. Technical Object Type Assigment to each FuncLoc Asset Register structured by FuncLoc | Daniel Olalekan | Maintenance & Operations | Get approval from TA’s to change/update Register | All Copressors and Accessories in Tunu, Benisede, Opukushi and Ogbotogbo | 1 | 2022-11-30 | 100%
Tunu | MEC | CMMS Build closing the gaps MJR, BoM, coding. Technical Object Type Assigment to each FuncLoc Asset Register structured by FuncLoc | Daniel Olalekan | Maintenance & Operations | Recommend update of Asset Critical documents/Drawings as needed. | All Copressors and Accessories in Tunu, Benisede, Opukushi and Ogbotogbo | 1 | 2023-07-30 | 100%
Tunu | MEC | CMMS Build closing the gaps MJR, BoM, coding. Technical Object Type Assigment to each FuncLoc Asset Register structured by FuncLoc | Daniel Olalekan | Maintenance & Operations | Implement in SAP “mass upload”: Asset Register, FLOCs, Object Type, Criticality, etc. | All Copressors and Accessories in Tunu, Benisede, Opukushi and Ogbotogbo | 1 | 2023-03-30 | 100%
Tunu | MEC | CMMS Build closing the gaps MJR, BoM, coding. Technical Object Type Assigment to each FuncLoc Asset Register structured by FuncLoc | Daniel Olalekan | Maintenance & Operations | Recommend for the update of drawings (escallate where needed) | All Copressors and Accessories in Tunu, Benisede, Opukushi and Ogbotogbo | 1 | 2022-10-30 | 100%
Tunu | MEC | Complete Functional location hierarchy incl Tech information + Criticality Assignment | Daniel Olalekan | Maintenance & Operations | For the completed asset hierarchy (colums H), review the ABC indicator; Where needed initiate change request to update ABC indicator in SAP | All Copressors and Accessories in Tunu, Benisede, Opukushi and Ogbotogbo | 1 | 2022-11-30 | 100%
Tunu | MEC | Complete Functional location hierarchy incl Tech information + Criticality Assignment | Daniel Olalekan | Maintenance & Operations | Identify which equipment/Floc needs BoM yes/no + scheduling to priority | All Copressors and Accessories in Tunu, Benisede, Opukushi and Ogbotogbo | 1 | 2022-11-30 | 100%
Tunu | MEC | Complete Functional location hierarchy incl Tech information + Criticality Assignment | Daniel Olalekan | Maintenance & Operations | For missing BoM's, collect data and update SAP BoM | All Copressors and Accessories in Tunu, Benisede, Opukushi and Ogbotogbo | 1 | 2022-11-30 | 100%
Tunu | MEC | All compression systems spares coded and loaded in BoM | Daniel Olalekan | Spares | Part lists to be collected from (1 - manuals, 2 - OEM) | All Copressors and Accessories in Tunu, Benisede, Opukushi and Ogbotogbo | 1 | 2022-11-30 | 100%
Tunu | MEC | All compression systems spares coded and loaded in BoM | Daniel Olalekan | Spares | Collect all manuals for the equipment (ref doc control) | All Copressors and Accessories in Tunu, Benisede, Opukushi and Ogbotogbo | 1 | 2022-10-30 | 100%
Tunu | MEC | All compression systems spares coded and loaded in BoM | Daniel Olalekan | Spares | Review SAP Floc Component list for completeness in line with OEM parts list | All Copressors and Accessories in Tunu, Benisede, Opukushi and Ogbotogbo | 1 | 2022-10-30 | 100%
Tunu | MEC | All compression systems spares coded and loaded in BoM | Daniel Olalekan | Spares | Adopt and register missing manuals in controlled library | All Copressors and Accessories in Tunu, Benisede, Opukushi and Ogbotogbo | 1 | 2022-10-30 | 100%
Tunu | MEC | ELECTRICAL SCE: shall meet Performance standard Req’s All MJR activated = MJR for equipment to be 100% complete. | Wisdom Osohor/ Elizabeth Idoghor | Maintenance & Operations | Make available all Electrical Switchgear MJR |  | 1 | 2022-09-28 | 100%
Tunu | MEC | ELECTRICAL SCE: shall meet Performance standard Req’s All MJR activated = MJR for equipment to be 100% complete. | Wisdom Osohor/ Elizabeth Idoghor | Maintenance & Operations | Develop Mini program to review MJR for all switchgear in Tunu Node (based on SAP) |  | 1 | 2022-09-28 | 100% | Programme is drawn up and ready
Tunu | MEC | ELECTRICAL SCE: shall meet Performance standard Req’s All MJR activated = MJR for equipment to be 100% complete. | Wisdom Osohor/ Elizabeth Idoghor | Maintenance & Operations | For the Gaps: create Z6 notification for all missing MJRs |  | 1 | 2022-09-28 | 100%
Tunu | MEC | ELECTRICAL SCE: shall meet Performance standard Req’s All MJR activated = MJR for equipment to be 100% complete. | Wisdom Osohor/ Elizabeth Idoghor | Maintenance & Operations | Approval and Action the Z6, creating MJR |  | 1 | 2022-11-28 | 100%
Tunu | MEC | MECHANICAL SCE: shall meet Performance standard Req’s All MJR activated = MJR for equipment to be 100% complete. | Fetch/Odinaka | Maintenance & Operations | Make available all required mechanical MJR |  | 1 | 2022-09-28 | 100%
Tunu | MEC | MECHANICAL SCE: shall meet Performance standard Req’s All MJR activated = MJR for equipment to be 100% complete. | Fetch/Odinaka | Maintenance & Operations | Develop Mini program to review mechanical MJR in Tunu Node (based on SAP) |  | 1 | 2022-09-28 | 100%
Tunu | MEC | MECHANICAL SCE: shall meet Performance standard Req’s All MJR activated = MJR for equipment to be 100% complete. | Fetch/Odinaka | Maintenance & Operations | For the Gaps: create Z6 notification for all missing MJRs |  | 1 | 2022-11-28 | 100%
Tunu | MEC | MECHANICAL SCE: shall meet Performance standard Req’s All MJR activated = MJR for equipment to be 100% complete. | Fetch/Odinaka | Maintenance & Operations | Approval and Action the Z6, creating MJR |  | 1 | 2022-11-28 | 100%
Tunu | MEC | PACO SCE: shall meet Performance standard Req’s All MJR activated = MJR for equipment to be 100% complete. | Ezekiel Olowofela/Akpofure David | Maintenance & Operations | Make available all required PACO MJR |  | 1 | 2022-10-30 | 100%
Tunu | MEC | PACO SCE: shall meet Performance standard Req’s All MJR activated = MJR for equipment to be 100% complete. | Ezekiel Olowofela/Akpofure David | Maintenance & Operations | Develop Mini program to review all PACO MJRs in Tunu Node (based on SAP) |  | 1 | 2022-10-30 | 100%
Tunu | MEC | PACO SCE: shall meet Performance standard Req’s All MJR activated = MJR for equipment to be 100% complete. | Ezekiel Olowofela/Akpofure David | Maintenance & Operations | For the Gaps: create Z6 notification for all missing MJRs |  | 1 | 2022-10-30 | 100%
Tunu | MEC | PACO SCE: shall meet Performance standard Req’s All MJR activated = MJR for equipment to be 100% complete. | Ezekiel Olowofela/Akpofure David | Maintenance & Operations | Approval and Action the Z6, creating MJR |  | 1 | 2022-10-30 | 100%
Tunu | ESP | PTM: activating tags in DCS and in PI | Olakunle Ajayi | Proactive Technical Monitoring | Identify and activate tags in DCS and in PI | Process Control & Comms AGC1/2 and EGC1/2 (local/UPC/DCS) | 1 | 2022-07-30 | 100%
Tunu | ESP | STGE-1 All Critical alarms identified and visible on DCS; including rationalised alarms avoiding alarm info overlad) | Ezekiel Olowofela/Akpofure David | Maintenance & Operations | Review ‘control philosophy’ and identify gap to desired state | Process Control & Comms AGC1/2 and EGC1/2 (local/UPC/DCS) | 1 | 2022-10-30 | 100% | Contact Kelechi Ikpeazu
Tunu | ESP | STGE-1 All Critical alarms identified and visible on DCS; including rationalised alarms avoiding alarm info overlad) | Ezekiel Olowofela/Akpofure David | Maintenance & Operations | Confirm the master alarm database (rationalisation) | Process Control & Comms AGC1/2 and EGC1/2 (local/UPC/DCS) | 1 | 2022-10-30 | 100%
Tunu | ESP | STGE-1 All Critical alarms identified and visible on DCS; including rationalised alarms avoiding alarm info overlad) | Ezekiel Olowofela/Akpofure David | Maintenance & Operations | Update proposal: required hardware and software changes and document updates | Process Control & Comms AGC1/2 and EGC1/2 (local/UPC/DCS) | 1 | 2022-10-30 | 100% | Part of the 900 Tag Activation Project
Tunu | ESP | STGE-1 All Critical alarms identified and visible on DCS; including rationalised alarms avoiding alarm info overlad) | Ezekiel Olowofela/Akpofure David | Maintenance & Operations | Lead the review of the proposal and enable approval | Process Control & Comms AGC1/2 and EGC1/2 (local/UPC/DCS) | 1 | 2022-10-30 | 100% | Part of the 900 Tag Activation Project. Discussion on budget ongoing for OEM to provide outstanding
Tunu | ESP | STGE-1 All Critical alarms identified and visible on DCS; including rationalised alarms avoiding alarm info overlad) | Ezekiel Olowofela/Akpofure David | Maintenance & Operations | Further prepare the adoption of missing critical alarms in DCS | Process Control & Comms AGC1/2 and EGC1/2 (local/UPC/DCS) | 1 | 2022-10-30 | 100%
Tunu | ESP | STGE-1 All Critical alarms identified and visible on DCS; including rationalised alarms avoiding alarm info overlad) | Ezekiel Olowofela/Akpofure David | Maintenance & Operations | Execute the required changes to have the missing crtical alarms visible on DCS | Process Control & Comms AGC1/2 and EGC1/2 (local/UPC/DCS) | 1 | 2022-10-30 | 100% | Part of the 900 Tag Activation Project. Discussion on budget ongoing for OEM to provide outstanding |  | Review with PACO taem
Tunu | ESP | Status of equipment based on command sent visible (feedback) | Olabode Olateju/Akpofure David | Maintenance & Operations | Ensure obsolescence/PCD-IT risks are mitigated. Develop Obsolescence Risk mitigation plan | Process Control & Comms AGC1/2 and EGC1/2 (local/UPC/DCS) | 1 | 2023-07-30 | 75% | We have used the GS to resolve some Obsolescent DD Files on our DCS system at Ogbotobo. Identification of Obsolescent PCD-IT systems is ongoing and to address this we have secured CLP budget approval for the renewal of EMERSON Guardian Support for all Tunu Node DCS DeltaV System issues. Budget for hardware upgrade captured in OP23.
Tunu | ESP | Status of equipment based on command sent should be visible (feedback) | Ezekiel Olowofela/Akpofure David | Maintenance & Operations | Identify intermediate solutions to minimise risk (how to monitor, what and by whom) – especially around Seal Gas and Lub.oil system | Process Control & Comms AGC1/2 and EGC1/2 (local/UPC/DCS) | 1 | 2022-10-30 | 100% | Both parameters can be monitored/trended from the UCP. And will be hooked up to PI
Tunu | ESP | Status of equipment based on command sent should be visible (feedback) | Ezekiel Olowofela/Akpofure David | Maintenance & Operations | Make hard/software changes and document updates | Process Control & Comms AGC1/2 and EGC1/2 (local/UPC/DCS) | 1 | 2022-12-31 | 100% | Licenses procured and signal lines hardwired and routed accordingly.
Tunu | ESP | Status of equipment based on command sent should be visible (feedback) | Ezekiel Olowofela/Akpofure David | Capabilities | Operator training and awareness. Including expected Operator health checks | Process Control & Comms AGC1/2 and EGC1/2 (local/UPC/DCS) | 1 | 2022-12-31 | 100%
Tunu | ESP | Operator tasks and PM updated | Olabode Olateju/Akpofure David | Maintenance & Operations | Identify missing operator tasks and PM to mitigate critical failure modes | Process Control & Comms AGC1/2 and EGC1/2 (local/UPC/DCS) | 1 | 2023-07-30 | 90% | Continous. Missiing tags and PMs are updated alongside period asset register verification exercise.
Tunu | ESP | Operator tasks and PM updated | Ezekiel Olowofela/Akpofure David | Maintenance & Operations | Update PM strategies in SAP (loop checks etc) for the changes | Process Control & Comms AGC1/2 and EGC1/2 (local/UPC/DCS) | 1 | 2022-12-31 | 100% | Loop check SAP PMs part of the MJR reviews.
Tunu | ESP | Operator tasks and PM updated | Ezekiel Olowofela/Akpofure David | Maintenance & Operations | Update operator task list, inform coach operators | Process Control & Comms AGC1/2 and EGC1/2 (local/UPC/DCS) | 1 | 2022-12-31 | 100% | Part of the FLM update for PI Manual Logger deployment
Tunu | ESP | Operator is capable to see key trends and equipment status drill down on screen (now only on UCP) | Ezekiel Olowofela/Akpofure David | Maintenance & Operations | PACO engineers monitor system alarms periodically |  | 1 | 2022-12-31 | 100% | Part of the 900 Tag Activation Project
Tunu | ESP | Operator is capable to see key trends and equipment status drill down on screen (now only on UCP) | Ezekiel Olowofela/Akpofure David | Maintenance & Operations | PACO engineer communicates awareness for changes |  | 1 | 2022-12-31 | 100% | Part of the 900 Tag Activation Project
Tunu | ESP | Deploy PTM and EBS on Critical Assets in Tunu | Olakunle Ajayi | Proactive Technical Monitoring | Conduct Framing Sprint Sessions |  | 1 | 2022-04-30 | 100%
Tunu | ESP | Deploy PTM and EBS on Critical Assets in Tunu | Olakunle Ajayi | Proactive Technical Monitoring | Build TMP using Global templates, RCM strategy, ARCH Surveillance, etc. |  | 1 | 2022-06-30 | 100%
Tunu | ESP | Deploy PTM and EBS on Critical Assets in Tunu | Olakunle Ajayi | Proactive Technical Monitoring | Develop & Deploy tools to support surveillance and go live. |  | 1 | 2022-07-30 | 100%
Tunu | ESP | Update FLM checksheet together with FSR and implement with operations and maintenance | Taslim Abioye | Proactive Technical Monitoring | Review FLM log sheets against critical paramaters and update for daily monitoring | Opukushi AGBC#1 & #2 and Ogbotobo AGBC#1 &#2 and Benisede AGBC#1 | 1 | 2022-08-30 | 100% | FLM Log sheets updated in prepartion for the deployment of PI Manual Logger
Tunu | ESP | Extend to PTM for inclusion in PTM | Ajayi Kunle | Proactive Technical Monitoring | Extend to PTM for inclusion in PTM | Opukushi AGBC#1 & #2 and Ogbotobo AGBC#1 &#2 and Benisede AGBC#1 | 1 | 2022-08-30 | 100%
Tunu | ESP | Deploy PI Manual Logger for FLM Data Collection | Oluwatoyin Ariyo | Proactive Technical Monitoring | Deploy PI Manual Logger for FLM Data Collection |  | 1 | 2022-09-30 | 100% | PI Manual Logger deployed
Tunu | MSC/TA/ME | Completing the full scope of the 8K overhauls, including a test run. | Taslim Abioye | Spares | Budget to be re-secured for the services, include/adjust with prev experience (duration | Opukushi AGBC#1 & #2 and Ogbotobo AGBC#1 &#2 and Benisede AGBC#1 | 1 | 2022-08-31 | 100% | Scope for 2022 completed
Tunu | MSC/TA/ME | Completing the full scope of the 8K overhauls, including a test run. | Taslim Abioye | Maintenance & Operations | Include in IAP, expected to be not a problem (N+1) | Opukushi AGBC#1 & #2 and Ogbotobo AGBC#1 &#2 and Benisede AGBC#2 | 1 | 2022-08-31 | 100%
Tunu | MSC/TA/ME | Completing the full scope of the 8K overhauls, including a test run. | Taslim Abioye | Spares | Check and confirm Spares and Tools completeness | Opukushi AGBC#1 & #2 and Ogbotobo AGBC#1 &#2 and Benisede AGBC#3 | 1 | 2022-08-31 | 100%
Tunu | MSC/TA/ME | Completing the full scope of the 8K overhauls, including a test run. | Taslim Abioye | Maintenance & Operations | Get FSR (expat) to site, logistics etc + local mechanic(s) | Opukushi AGBC#1 & #2 and Ogbotobo AGBC#1 &#2 and Benisede AGBC#4 | 1 | 2022-08-31 | 100%
Tunu | MSC/TA/ME | Having the known technical issues resolved (high vibs on Opukushi #2 and PLC issue on Opukushi #1 | Taslim Abioye | Spares | Place order for all outstanding spares for engines | Opukushi AGBC#1 & #2 and Ogbotobo AGBC#1 &#2 and Benisede AGBC#5 | 1 | 2022-08-31 | 100%
Tunu | MSC/TA/ME | Having the known technical issues resolved (high vibs on Opukushi #2 and PLC issue on Opukushi #1 | Taslim Abioye | Spares | Expedite outstanding spares for engines | Opukushi AGBC#1 & #2 and Ogbotobo AGBC#1 &#2 and Benisede AGBC#5 | 1 | 2022-11-30 | 100%
Tunu | MSC/TA/ME | Having the known technical issues resolved (high vibs on Opukushi #2 and PLC issue on Opukushi #2 | Taslim Abioye | Spares | Deliver and replace missed spares | Opukushi AGBC#1 & #2 and Ogbotobo AGBC#1 &#2 and Benisede AGBC#6 | 1 | 2022-11-30 | 100%
Tunu | MSC/TA/ME | Having the known technical issues resolved (high vibs on Opukushi #2 and PLC issue on Opukushi #2 | Taslim Abioye | Spares | Start up units | Opukushi AGBC#1 & #2 and Ogbotobo AGBC#1 &#2 and Benisede AGBC#6 | 1 | 2022-08-31 | 100% | BC 1 completed.
Tunu | MSC/TA/ME | All Service Bulletiness are available and implemented, to support safe and reliable operation of unit. | Digbani Tams | Maintenance & Operations | Obtain all SBs (for all key OEMs / equipment) + backup Check and Balance to make sure we are complete | Solar GTs but also other OEMs: Siemens, Waukesha, Cooper Cameron, Caterpillar, Howden) | 1 | 2022-08-30 | 100%
Tunu | MSC/TA/ME | All Service Bulletiness are available and implemented, to support safe and reliable operation of unit. | Digbani Tams | Maintenance & Operations | Annual check for completeness, Prioritize for Criticality (H/M/L) | Solar GTs but also other OEMs: Siemens, Waukesha, Cooper Cameron, Caterpillar, Howden) | 1 | 2022-08-30 | 100%
Tunu | MSC/TA/ME | All Service Bulletiness are available and implemented, to support safe and reliable operation of unit. | Digbani Tams | Maintenance & Operations | Engage with Assets to discuss and agree on implementation of SBs | Solar GTs but also other OEMs: Siemens, Waukesha, Cooper Cameron, Caterpillar, Howden) | 1 | 2022-08-30 | 100%
Tunu | MSC/TA/ME | All Service Bulletiness are available and implemented, to support safe and reliable operation of unit. | Digbani Tams | Maintenance & Operations | Identify window for implementation Or raise 1) SAP Notification and CM workorder for SBs | Solar GTs but also other OEMs: Siemens, Waukesha, Cooper Cameron, Caterpillar, Howden) | 1 | 2022-08-30 | 100%
Tunu | MSC/TA/ME | Tracking the Implementation of SBs (keeping record / Register) | Digbani Tams | Maintenance & Operations | Incl in Register column for TA approval and units applicable, status Y/N implemented | Solar GTs but also other OEMs: Siemens, Waukesha, Cooper Cameron, Caterpillar, Howden) | 1 | 2022-08-30 | 100%
Tunu | MSC/TA/ME | Tracking the Implementation of SBs (keeping record / Register) | Digbani Tams | Maintenance & Operations | Complete register and perform necessary checks | Solar GTs but also other OEMs: Siemens, Waukesha, Cooper Cameron, Caterpillar, Howden) | 1 | 2022-08-30 | 100%
Tunu | MSC/TA/ME | Management of Change to be adhered to BUT in an efficient manner. Sign-off by TA req’d. Consider change BoM, MJR | Digbani Tams | Maintenance & Operations | Can consult with site Process Ownder for MoC if needed | Solar GTs but also other OEMs: Siemens, Waukesha, Cooper Cameron, Caterpillar, Howden) | 1 | 2022-08-30 | 100%
Tunu | MSC/TA/ME | Management of Change to be adhered to BUT in an efficient manner. Sign-off by TA req’d. Consider change BoM, MJR | Digbani Tams | Maintenance & Operations | Raise an open generic MoC. | Solar GTs but also other OEMs: Siemens, Waukesha, Cooper Cameron, Caterpillar, Howden) | 1 | 2022-08-30 | 100%
Tunu | MSC/TA/ME | Equipment that is not running: perform req preservation tasks like periodically rotating the shaft, apply grease | Okey Obowu | Maintenance & Operations | Understand scenarios that we want to plan for, e.g TRP outage | Opukushi AGC2, FGC and BC3) | 1 | 2022-08-30 | 100% | Project team is mobilising to site soonest and may not need preservative maintenance plans.
Tunu | MSC/TA/ME | Schedule to be in place with preventive maintenance tasks for preservation. Currently none in SAP. | Okey Obowu | Project to Asset | Develop Preserv Mtce plan for equipment not yet handed over (Project reps): appoint Responsible person | Opukushi AGC2, FGC and BC3) | 1 | 2022-08-30 | 100% | Project team is mobilising to site soonest and may not need preservative maintenance plans.
Tunu | MSC/TA/ME | Schedule to be in place with preventive maintenance tasks for preservation. Currently none in SAP. | Okey Obowu | Project to Asset | Develop PM/operator tasks (collaboration between maint and TAs), applies for all relevant disciplines (REQ, PACO, elect). From Project: Quality team | Opukushi AGC2, FGC and BC3) | 1 | 2022-08-30 | 100%
Tunu | MSC/TA/ME | Schedule to be in place with preventive maintenance tasks for preservation. Currently none in SAP. | Okey Obowu | Maintenance & Operations | Maintain a list of equipment that stands idle/is unavailable | Opukushi AGC2, FGC and BC3) | 1 | 2022-08-30 | 100% | Project team is mobilising to site soonest and may not need preservative maintenance plans.
Tunu | MSC/TA/ME | Schedule to be in place with preventive maintenance tasks for preservation. Currently none in SAP. | Okey Obowu | Project to Asset | Upload Preservative Mtce tasks in SAP by CMMS team | Opukushi AGC2, FGC and BC3) | 1 | 2022-08-30 | 100% | Project team is mobilising to site soonest and may not need preservative maintenance plans.
Tunu | MSC/TA/ME | Schedule to be in place preventive maintenance tasks for preserving idle equipment. Currently none in SAP. | Okey Obowu | Project to Asset | Execute preventive maintenance activities for equipment that is idle/unavailable | Opukushi AGC2, FGC and BC3) | 1 | 2022-08-30 | 100%
Tunu | MSC/TA/ME | DEP 70.10.70.11 on Preservation (Feb ‘21). Also refer to PML. Project Doc relevant – No | Okey Obowu | Project to Asset | For equipment not yet handed over to Asset: Include clear ownership / R&R for whom responsible | Opukushi FGC and BC3) | 1 | 2022-11-30 | 100% | 30days RR completed and handed over to asset
Tunu | MSC/TA/ME | Ageing of Equipment | Ogoleh Franklyn | Project to Asset | Outcome of obsolescence plan to be included in MRP, also for budget planning | Opukushi AGBC#1 & #2 and Ogbotobo AGBC#1 &#2 and Benisede AGBC#1 | 1 | 2023-07-30 | 100% | Obsolescence Management plan updated and signed off.
Tunu | MSC/TA/ME | Ageing of Equipment | Ogoleh Franklyn | Project to Asset | Outcome of obsolescence plan to be included Asset Care Plan | Opukushi AGBC#1 & #2 and Ogbotobo AGBC#1 &#2 and Benisede AGBC#1 | 1 | 2022-12-31 | 100% | Obsolescence list from PACO supvsr entred in the ACP
Tunu | MSC/TA/ME | Replace ageing Elec LV boards ageing | Atey Vincent/Otobo Didi | Maintenance & Operations | Raise item of replacing LV boards in OP22 | Flowstations (Tunu, Benisede, Opukushi | 1 | 2022-08-30 | 100%
Tunu | MSC/TA/ME | Replace ageing Elec LV boards ageing | Atey Vincent/Otobo Didi | Maintenance & Operations | Request Tech Info to updated quote (Tech info and (old) quote available) | Flowstations (Tunu, Benisede, Opukushi | 1 | 2023-06-30 | 100% | Updated and captured in OP23 for approval.
Tunu | MSC/TA/ME | Restore Ogbotobo/ Opukushi Flash Gas Compressor to reliable operation | Atey Vincent/Otobo Didi | Maintenance & Operations | 1. Check if historic problems are resolved: see excel file with events/failures. Consider to anticipate by including scope for inspection/overhaul And cross-learning to the other FGCs | Opukushi/Ogbotobo FGC | 1 | 2023-06-30 | 40% | PR released. Expecting vendor mobilization date. AGG to add to list of criticall spares. Unit commissioned however mechanical seal was discovered defective and requires replacement.
Tunu | MSC/TA/ME | Restore Opukushi Flash Gas Compressor to reliable operation | Atey Vincent/Otobo Didi | Maintenance & Operations | Develop if needed, Order accu seal and replace | Benisede | 1 | 2022-09-30 | 100% | Completed
Tunu | MSC/TA/ME | Restore Opukushi Flash Gas Compressor to reliable operation | Atey Vincent/Otobo Didi | Maintenance & Operations | If probe is problem and resolved: start unit, If probe is not the problem: plan for inspection/overhaul | Opukushi FGC | 1 | 2023-06-30 | 30% | Overhaul planned for OP23.
Tunu | MSC/TA/ME | PLC completed with missing part = PLC Safety Partner | Olabode Olateju/Akpofure David | Spares | Missing PLC Safety Partner is on order, Install when available | Opukushi FGC | 1 | 2023-07-30 | 60% | Awaiting delivery via the AGG improvement team
Tunu | MSC/TA/ME | PLC completed with missing part = PLC Safety Partner | Olabode Olateju/Akpofure David | Maintenance & Operations | Check Probes and perform loop check for axial position (female rotor is giving trip signal) | Opukushi FGC | 1 | 2023-07-30 | 80% | Probe checked and confirmed ok by the Opukushi PACO team
Tunu | MSC/TA/ME | PLC completed with missing part = PLC Safety Partner | Olabode Olateju/Akpofure David | Maintenance & Operations | Check probes and its loops using procedure left by OEM in 2021. Current problems is related to female rotor axial position/probe. | Opukushi FGC/Ogbotobo FGC | 1 | 2023-07-30 | 80% | Probe checked and confirmed ok by the Opukushi PACO team
Tunu | MSC/TA/ME | Benisede FGC reliable operation with normal oil leakage rate across mechanical seal (normal decline of oil pressure) | Fetch/Odinaka | Maintenance & Operations | PLAN A; Replacement of mechanical seal and inspection of accumulator (Use spare mechanical seal from Opukushi (available) and order a spare | Benisede FGC | 1 | 2022-11-30 | 100% | Mech replaced.
Tunu | MSC/TA/ME | Benisede FGC reliable operation with normal oil leakage rate across mechanical seal (normal decline of oil pressure) | Fetch/Odinaka | Maintenance & Operations | PLAN B: Check Accumulator (bladder) – Charge N2 and whether it keeps pressure and Pressure Relief Valve (can be passing), charging point and rest of seal oil system to confirm no leaks | Benisede FGC | 1 | 2022-08-30 | 100%
Tunu | MSC/TA/ME | Benisede FGC reliable operation with normal oil leakage rate across mechanical seal (normal decline of oil pressure) | Fetch/Odinaka | Maintenance & Operations | If Step 1) not successful, prepare for seal change out: Order Field Service Rep (local rep) | Benisede FGC | 1 | 2022-08-30 | 100%
Tunu | MSC/TA/ME | Benisede FGC reliable operation with normal oil leakage rate across mechanical seal (normal decline of oil pressure) | Fetch/Odinaka | Spares | Order inspection kit = stock item (e.g. spares required O-rings etc) | Benisede FGC | 1 | 2022-08-30 | 100%
Tunu | MSC/TA/ME | Benisede FGC reliable operation with normal oil leakage rate across mechanical seal (normal decline of oil pressure) | Fetch Emurotu | Spares | Order new mechanical seal as spare for Opukushi/Ogbotobo | Ogbotobo FGC | 1 | 2023-06-30 | 70% | AGG team captured seal for ordering. BEAMCO Price Agreement review completed. Awaiting FSR visit to site. Budget secured for visit.- Decision to change the seal design or change only internal components being made
Tunu | Sust/Process Maturity | CPF/AGC2 (not handed over) Punch List Items | Ahmed Abubakar/Barango Alabo | Project to Asset | Close out Punch list items | AGC2- CPF / AGB3 | 1 | 2022-09-30 | 100%
Tunu | Sust/Process Maturity | CPF/AGC2 (not handed over) Punch List Items | Ahmed Abubakar/Barango Alabo | Project to Asset | Monitor integrity of repair. Understand what causes the crack? Brainstrom on causes without necessity of inspection. | AGC2- CPF / AGB3 | 1 | 2022-11-30 | 100% | Analysis done.
Tunu | Sust/Process Maturity | High T in GT enclosure, leak of exhaust plenum (recent) – after approx. 24 hour run | Ahmed Abubakar/Barango Alabo | Project to Asset | 1. Understand cause for high T (from Solar) – crack at exhaust stack (collector)Report available | AGC2- CPF | 1 | 2022-11-30 | 100% | Technical review held with Tas and Asset.
Tunu | Sust/Process Maturity | High T in GT enclosure, leak of exhaust plenum (recent) – after approx. 24 hour run | Atey Vincent/Otobo Didi | Project to Asset | Short Term: Repair plan of collector if possible (SAIPEM -> Solar)Check complete collector for cracks (by Solar) | AGC2- CPF | 1 | 2022-09-30 | 100% | Technical review held with Tas and Asset. Collector planned for changout
Tunu | Sust/Process Maturity | High T in GT enclosure, leak of exhaust plenum (recent) – after approx. 24 hour run | Ahmed Abubakar/Barango Alabo | Project to Asset | Project to place order for new collector for next engine changeout | AGC2- CPF | 1 | 2023-11-30 | 40% | Mobilization planned in March for temporary measure i.e. weld the exhaust collector. NAPIMS yet to give approval for replacement (permanent measure).
Tunu | Sust/Process Maturity | Safe and reliable compressor + GT No forces/overrides in Solar Logic | Iskil Popoola | Maintenance & Operations | Check register + field check and logic check on forces and overrides |  | 1 | 2022-09-30 | 100% | No override on AGBC3/Opukushi as at the last time we were running it before station shut down in July 2022.
Tunu | Sust/Process Maturity | Safe and reliable compressor + GT No forces/overrides in Solar Logic | Iskil Popoola | Maintenance & Operations | Resolve and remove forces/overrides (if any) |  | 1 | 2022-09-30 | 100%
Tunu | Sust/Process Maturity | Safe and reliable compressor + GT No forces/overrides in Solar Logic | Iskil Popoola | Maintenance & Operations | Include in Handover / SoF: Check no forces and overrides |  | 1 | 2022-11-30 | 100%
Tunu | Sust/Process Maturity | OR&A: Comm, Operating + Insurance spares and special tools in place. | Okey Obowu | Project to Asset | Spares and Tools: Do a gap check, include in Punch list | AGC2- CPF / AGB3 | 1 | 2022-10-30 | 100%
Tunu | Sust/Process Maturity | OR&A: Comm, Operating + Insurance spares and special tools in place. | Okey Obowu | Project to Asset | Projects to procure missing items3.Include as note in separate Parts WS with JF | AGC2- CPF / AGB4 | 1 | 2022-10-30 | 100%
Tunu | Sust/Process Maturity | CMMS build complete and loaded in SAP - Unit passed performance and reliability test with flying colours | Okey Obowu | Project to Asset | 1. CMMS: review the build (MJR, BoM’s coding) 2. Include in Punch List Item. To be actioned by Projects | AGC2- CPF / AGB5 | 1 | 2023-06-30 | 80% | CMMS completed and BoMs ongoing. LEC June 2023
Tunu | Sust/Process Maturity | Punch List Items Opukushi/AGBC3. SAIPEM did sign handover note, but Asset not (yet) | Atey Vincent/Otobo Didi | Project to Asset | Asset note: tripping on cylinder low lube oil flow | AGC2- CPF / AGB6 | 1 | 2022-09-30 | 100%
Tunu | Sust/Process Maturity | Punch List Items Opukushi/AGBC3. SAIPEM did sign handover note, but Asset not (yet) | Atey Vincent/Otobo Didi | Project to Asset | Asset note: Aux lube oil cut/out and start issue | AGC2- CPF / AGB7 | 1 | 2022-09-30 | 100% | Unit has done 30 days Reliability run and handed cert over signed

## Status
Completion Status
Completed
Ongoing
Not started

## Due Status
Due Status | Id
Overdue | 1
Due in 30 days | 2
Due 30 to 60 days | 3
Over 60 days | 4
Completed | 5

## System Owners
System Owner | PU
Didi Otobo | Tunu
Vincent Atey | Tunu
Chimuanya Onyejekwe | Soku
Musa Nabage | Soku

## Pillars
Pillars
Maintenance & Operations
Spares
Proactive Technical Monitoring
Capabilities
Project to Asset

## PUs
PU | Title
Soku | SOKU INTEGRATED VALUE DELIVERY SUSTAIN
Tunu | INTEGRATED VALUE DELIVERY TUNU NODE COMPRESSOR AVAILABILITY

## Pivot
Row Labels | Count of % Completion
30% | 1
40% | 2
60% | 1
70% | 1
75% | 1
80% | 3
90% | 1
100% | 104
(blank)
Grand Total | 114