## Deliverables
PU | Process Steps | Activity | Action Lead | Pillars | Deliverables | Equipment | Weight | Impact | Close out Date | % Completion | Comment | Comment Date
Sea Eagle | System Selection And Scope | Resource the IVD plan | Victor Ndukwe | Maintenance & Operations | Engage the external facilitators and AMIL to conform resources needed and readiness to deliver |  | 1 | NA | 2023-02-28 | 100%
Sea Eagle | System Selection And Scope | Resource the IVD plan | Victor Ndukwe | Maintenance & Operations | Identify Initiative Focal Points with the support of the AMIL |  | 1 | NA | 2023-02-28 | 100%
Sea Eagle | System Selection And Scope | Resource the IVD plan | Kebin Ofori | Maintenance & Operations | Engage the Asset and Production Services Leadership and readiness to support the initiative |  | 1 | NA | 2023-02-28 | 100%
Sea Eagle | System Selection And Scope | Identify Improvement Goal | Victor Ndukwe | Maintenance & Operations | Develop scope, Outline clear targets, include in the CTR and secure CTR approval |  | 1 | NA | 2023-02-28 | 100%
Sea Eagle | System Selection And Scope | Kick Off meeting stakeholders | Victor Ndukwe | Maintenance & Operations | Engage AGG team on IVD |  | 1 | NA | 2023-02-28 | 100%
Sea Eagle | System Selection And Scope | Kick Off meeting stakeholders | Victor Ndukwe | Maintenance & Operations | Name System Owners on IVD plans |  | 1 | NA | 2023-02-28 | 100%
Sea Eagle | System Selection And Scope | Kick Off meeting stakeholders | Kebin Ofori | Maintenance & Operations | Engage Asset Manager and PS LT on IVD plans |  | 1 | NA | 2023-02-28 | 100%
Sea Eagle | System Selection And Scope | Kick Off meeting stakeholders | Casmir Ojobor | Maintenance & Operations | Agree Cadence, DRB and Success measures |  | 1 | NA | 2023-03-06 | 100%
Sea Eagle | MTO | Identify Threats on Fit4MTO database | Victor Ndukwe | Maintenance & Operations | Download threats and actions on MTO with impact on system |  | 1 | NA | 2023-03-20 | 100%
Sea Eagle | MTO | Identify Threats on Fit4MTO database | Victor Ndukwe | Maintenance & Operations | Analyse data and identify threats with deferment, flaring impact, equipment with low availability |  | 1 | NA | 2023-03-20 | 100%
Sea Eagle | MTO | Identify Bad actors (Review past trips and RCAs) | Victor Ndukwe | Maintenance & Operations | Review historical trip logs |  | 1 | NA | 2023-03-20 | 100%
Sea Eagle | MTO | Identify Bad actors (Review past trips and RCAs) | Victor Ndukwe | Maintenance & Operations | Identify causes of trips |  | 1 | NA | 2023-03-20 | 100%
Sea Eagle | MTO | Identify Bad actors (Review past trips and RCAs) | Victor Ndukwe | Maintenance & Operations | Review completed RCAs from past events |  | 1 | NA | 2023-03-20 | 100%
Sea Eagle | MTO | Identify Bad actors (Review past trips and RCAs) | Casmir Ojobor | Maintenance & Operations | Download and review failure history of GTs and Compressors |  | 1 | NA | 2023-03-20 | 100%
Sea Eagle | System Selection And Scope | Kick Off meeting stakeholders | Victor Ndukwe | Maintenance & Operations | Organise and Hold Kickoff workshop(F2F) |  | 1 | NA | 2023-03-27 | 100%
Sea Eagle | MTO Improvement | Adequate action owners are assigned (competent and available), appreciating difference between Short and Long term. For Long term: supporting teams, not Front Line (assign by threat owner, along with required mandate) | Adetayo Funto | Maintenance & Operations | Criteria to be set (competence, available time, mandate) for action owner |  | 1 | M | 2023-06-30 | 100% | Action owners are competent and knowledgeable on diff btw long and ST threats
Sea Eagle | MTO Improvement | Adequate action owners are assigned (competent and available), appreciating difference between Short and Long term. For Long term: supporting teams, not Front Line (assign by threat owner, along with required mandate) | Adetayo Funto | Maintenance & Operations | Agree on handshake (including criteria) with Action Owner (in case of member from supporting team, i.e. Outside asset team). |  | 1 | M | 2023-05-30 | 100% | Action owners are competent and knowledgeable on MTO process. Where outside team member is required, handshake will be agreed on.
Sea Eagle | MTO Improvement | Adequate action owners are assigned (competent and available), appreciating difference between Short and Long term. For Long term: supporting teams, not Front Line (assign by threat owner, along with required mandate) | Nwachi Ogbonna / Boma Brown | Maintenance & Operations | Include agreed actions in GPA of action owner or include: Allocate 20% of time for MTO threats/actions |  | 1 | M | 2023-06-30 | 100%
Sea Eagle | MTO Improvement | Common Action for MTO: Organize Awareness session on adjustments in the process. | Adetayo Funto | Maintenance & Operations | Include as part of agenda in the Weekly MTO meeting with clear terms of reference and claritify roles of participants |  | 1 | M | 2023-06-30 | 100%
Sea Eagle | MTO Improvement | Common Action for MTO: Organize Awareness session on adjustments in the process. | Adetayo Funto | Maintenance & Operations | Threat owners (OIM) to vet the final decisions /outcomes including reasoning, risk level, mitigating actions |  | 1 | M | 2023-06-30 | 100% | EA Leaders including OIM are present at weekly MTO meetings where risk rankings, levels and mitigating actions are discussed.
Sea Eagle | MSC/TA/ME | We don’t expect tubing failures(Temperature resistant tubing available) | Duro-Oni, Simisola | Maintenance & Operations | Raise and secured an approved MOC for tubing change out on intrument Air Compressor | Intrument Air Compressor | 1 | H | 2023-10-01 | 100% | MoC raised: 134899. Risk Assessment for the MoC done
Sea Eagle | MSC/TA/ME | No spurious trip and reliable reading, Only true alarm, No flat line, No freezing of UCP/HMI | Ogbonnaya Ekelechi | Maintenance & Operations | Engage with existing project team for UCP upgrade project | AGC/GTG/IAC | 1 | H | 2023-12-30 | 100% | UCP and HMI Commissioning Completed
Sea Eagle | MSC/TA/ME | No spurious trip and reliable reading, Only true alarm, No flat line, No freezing of UCP/HMI | Ogbonnaya Ekelechi | Maintenance & Operations | Engagement to comfirm scope, loop checks for vibration | AGC/GTG/IAC | 1 | H | 2023-12-30 | 100% | UCP and HMI Commissioning Completed
Sea Eagle | MSC/TA/ME | No critical transmitter failure to cause trip( Robust and workable PM strategy) | Awe Afolabi/Phillips Oluseye | Maintenance & Operations | Identify Critical Transmitters with trip functions within the EA facility | AGC/GTG/IAC | 1 | M | 2023-10-01 | 100%
Sea Eagle | MSC/TA/ME | No critical transmitter failure to cause trip( Robust and workable PM strategy) | Awe Afolabi/Phillips Oluseye | Maintenance & Operations | Source the MTBF for the critical transmitters/ End Of Life(EOL) and hence identify transmitters for changeout. | AGC/GTG/IAC | 1 | M | 2023-10-01 | 100% | Engagement with OEM ongoing. PACO META, asset PACO and OPS teams identifying bad actors for priority replacement in phase. | OEM confirmed service life of all the transmitters in operation
Sea Eagle | MSC/TA/ME | No critical transmitter failure to cause trip( Robust and workable PM strategy) | Awe Afolabi/Phillips Oluseye | Maintenance & Operations | Review and update existing PMs and include inspection maintenance plan | AGC/GTG/IAC | 1 | M | 2023-10-01 | 100% | Review done. Z6 to be raised to update MJR and align the with maintenance plans with mechanical milestone inspections
Sea Eagle | MSC/TA/ME | No critical transmitter failure to cause trip( Robust and workable PM strategy) | Awe Afolabi/Phillips Oluseye | Maintenance & Operations | Review and Replace Transmitters due for replacement including spares for those in voting configurations. | AGC/GTG/IAC | 1 | M | 2023-10-01 | 100% | Data being sourced from OEM. Expecting feedback. Not obsolete hence due for replacement. Closed
Sea Eagle | MSC/TA/ME | ASV Operating outside the design/operating envelope. | Awe Afolabi/Phillips Oluseye | Maintenance & Operations | Review the design of the Anti surge Valve (ASV) plug with respect to current gas flow rate involving the OEM and TAs. | FGC/EGC | 1 | M | 2023-12-31 | 100% | Review carried out by study team. Reveals no need for change. Valve designed to tough, rough and turbulent processess.
Sea Eagle | MSC/TA/ME | 100% Critical spares available in stock (Realistic methodology to identify critical spares, Sustainable Min-Max levels,Preservation to requirement) | Michael Amaku / Akeem Adepoju | Spares | Develop procedues to manange non-stock goods in transit | FGC/AGC/EGC /GTG/IAC | 1 | H | 2023-10-01 | 10% | To engage the amterial folks. 02/02/24 Hawa Ajilima has started some work on this. Check for updates from her.
Sea Eagle | MSC/TA/ME | ASV Operating outside the design/operating envelope. | Henry Unuane/Barobote Stanley | Maintenance & Operations | Raise and MTO ID for continuous operation of the compressors (ASV) with current flow rate | FGC/EGC | 1 | M | 2024-06-30 | 100% | MTO ID: I-2619587
Sea Eagle | MSC/TA/ME | ASV Intrusive maintenance( Maintenance job routine is Fit for purpose) | Michael Amaku / Akeem Adepoju | Maintenance & Operations | Create work order and purchase order for intrusive maintenance of ASV. Order a spare ASV for the plant | FGC/EGC | 1 | M | 2024-06-30 | 100% | 4510476375 10.01.2023 - Goods receipt done in 06.11.2023 (delivered to EA and awaiting installation – EGC ASV) ITEMS USED
Sea Eagle | MSC/TA/ME | ASV Operating outside the design/operating envelope. | Michael Amaku / Akeem Adepoju | Maintenance & Operations | Create PM plan for ASV intrusive maintenance | FGC/EGC | 1 | M | 2024-06-30 | 100% | MJR approved and Z6 number 12007011 raised to update MJR and align the with maintenance plans Follow up on creation of Mtce plan and create WO23132036 - a 5-yearly cycle Maintenance Plan for intrusive inspection targeting next shutdown window.
Sea Eagle | MSC/TA/ME | 100% Critical spares available in stock (Realistic methodology to identify critical spares, Sustainable Min-Max levels,Preservation to requirement) | Michael Amaku / Akeem Adepoju | Spares | Review criteria for what make a critical spare | FGC/AGC/EGC /GTG/IAC | 1 | H | 2023-10-01 | 100% | Done
Sea Eagle | MSC/TA/ME | 100% Critical spares available in stock (Realistic methodology to identify critical spares, Sustainable Min-Max levels,Preservation to requirement) | Michael Amaku / Akeem Adepoju | Spares | Prioritize systems that are most vulnerable for critical spares | FGC/AGC/EGC /GTG/IAC | 1 | H | 2023-10-01 | 100% | System Prioritisation Completed.
Sea Eagle | MSC/TA/ME | 100% Critical spares available in stock (Realistic methodology to identify critical spares, Sustainable Min-Max levels,Preservation to requirement) | Michael Amaku / Akeem Adepoju | Spares | Check BOMs and MMDS plus Min-Max and update when needed | FGC/AGC/EGC /GTG/IAC | 1 | H | 2023-10-01 | 100% | Min-Max reviewed, update and captured
Sea Eagle | MSC/TA/ME | 100% Critical spares available in stock (Realistic methodology to identify critical spares, Sustainable Min-Max levels,Preservation to requirement) | Michael Amaku / Akeem Adepoju | Spares | Order spares and implement preservation requirement - (3D print alternative to be explored to optimize lead time) | FGC/AGC/EGC /GTG/IAC | 1 | H | 2023-10-01 | 80% | PO EDD 4510484359 25.09.2023 – Goods receipt done in 09.01.2024 - CONFIRMED. ITEMS USED ON GAS COMPRESSOR 4510487188 24.11.2023 - Goods receipt done in 09.01.2024 - CONFIRMED. ITEMS USED ON GAS COMPRESSOR 4510472743 29.01.2023 - Goods receipt done in 22.11.2023 (delivered to EA and installed – 2nd stage Separator LCV) ITEMS USED 4510476375 10.01.2023 - Goods receipt done in 06.11.2023 (delivered to EA and awaiting installation – EGC ASV) ITEMS USED 4510481538 13.09.2023 – Not a material but for FGC/EGC upgrade FAT 4510481492 31.12.2022 - Not a material but for FGC/EGC upgrade works 4510484397 30.04.2023 - Not a material but for GT1 engine inspection works 4510485218 30.04.2023 - Not a material but for GT1 engine inspection works
Sea Eagle | MSC/TA/ME | 100% Critical spares available in stock (Realistic methodology to identify critical spares, Sustainable Min-Max levels,Preservation to requirement) | Michael Amaku / Akeem Adepoju | Spares | Obtain approval of critical spares and raise budget | FGC/AGC/EGC /GTG/IAC | 1 | H | 2023-10-01 | 100% | Adequeate budget available and confirmed by asset mgt
Sea Eagle | MSC/TA/ME | Adequate Manning of Facility in line with the HSE Case | Chris Ugochukwu | Capability | Carry out audit of the current manning in line with the HSE Case and make recommendations | FPSO | 1 | H | 2023-12-30 | 80% | CN adequacy under review.
Sea Eagle | MSC/TA/ME | 100% Critical spares available in stock (Realistic methodology to identify critical spares, Sustainable Min-Max levels,Preservation to requirement) | Michael Amaku / Akeem Adepoju | Spares | Review the selected system for critical spares according to the criteria and define preservation requirements | FGC/AGC/EGC /GTG/IAC | 1 | H | 2023-10-01 | 100% | Preservation Process is already in place and spares are preserved as required
Sea Eagle | MSC/TA/ME | The design temperature able to maintain at all level in engine room- Adequate PM for Engine room Fan and Motor | Michael Amaku / Akeem Adepoju | Maintenance & Operations | Check Engine room design temperature and compare with current obtainable mean temperatures. | Ventillation System | 1 | M | 2023-10-31 | 100% | 1. Average temperature determination in the machinery space ongoing 2. Compare with design temperature in POPMS FINDINGS - Average operating temperature measured and compared to be within the design temperature.
Sea Eagle | MSC/TA/ME | The design temperature able to maintain at all level in engine room- Adequate PM for Engine room Fan and Motor | Michael Amaku / Akeem Adepoju | Maintenance & Operations | Create work order for checking inlet filter,Louvers, Blockages in venting, Motor fans | Ventillation System | 1 | M | 2023-10-31 | 100% | 22828837, 22848048, 22869157, 22880036, 22890022, 22891099, 23005447, 23008723
Sea Eagle | MSC/TA/ME | The design temperature able to maintain at all level in engine room- Adequate PM for Engine room Fan and Motor | Michael Amaku / Akeem Adepoju | Maintenance & Operations | Carry out recommended health checks on the existing Ventillation Fan motor. Check motor speed, etc. | Ventillation System | 1 | M | 2023-10-31 | 100% | Health checks on motors, done.
Sea Eagle | MSC/TA/ME | The design temperature able to maintain at all level in engine room- Adequate PM for Machinary space, Fan and Motor | Michael Amaku / Akeem Adepoju | Maintenance & Operations | Verify the operating design of the newly installed equipment in the machinary space. Instrument Air compressor. | IAC | 1 | M | 2023-10-01 | 100% | Operating design for newly installed IAC provided. Operating design documents already. Check SharePoint.
Sea Eagle | MSC/TA/ME | Adequate Manning of Facility in line with the HSE Case | Chris Ugochukwu | Capability | Recommend to SPDC LT the gap closure plans from the EA manning audit. | FPSO | 1 | H | 2024-06-30 | 80% | Done, vacant positions being resourced. 4 out of 6 SN Roles filled CN adequacy under review.
Sea Eagle | MSC/TA/ME | The design temperature able to maintain at all level in engine room- Adequate PM for Engine room Fan and Motor | Michael Amaku / Akeem Adepoju | Maintenance & Operations | Restore the functionality of the second draft fan. | Engine Room | 1 | M | 2023-10-01 | 100% | The fan has been repaired and installed 1. New motor available 2. Confirmation of suitability of fan by joint team of Elect/HVAC/Power Techs (after offtake) required. Two motors confirmed functional
Sea Eagle | MSC/TA/ME | Race against corrosion. | Akanni Joseph | Maintenance & Operations | Appoint focal point for fabric maintenance on board Sea Eagle. | FPSO | 1 | H | 2023-10-01 | 100% | A CN position has been resourced to focus on EA in Sea eagle and the update on the liquidation. Mail from Joe Akanni on Thu 6/1/2023 1:53 PM
Sea Eagle | MSC/TA/ME | Race against corrosion. | Akanni Joseph | Maintenance & Operations | Inspect and deliver corrosion damage report (CDR) | FPSO | 1 | H | 2023-12-31 | 100%
Sea Eagle | MSC/TA/ME | Race against corrosion. | Akanni Joseph | Maintenance & Operations | Include inspection routine/fabric maintenance in SAP at Equipment level. | FPSO | 1 | H | 2023-12-31 | 100% | There is a PM driven inspection routine to identify corroded areas.
Sea Eagle | MSC/TA/ME | Race against corrosion. | Akanni Joseph | Maintenance & Operations | Check of existing MJR's are covering inspection of non-pressurized equipments | FPSO | 1 | H | 2023-12-31 | 100% | Visual Inspection and UTM activities are routine and driven by SAP
Sea Eagle | MSC/TA/ME | Race against corrosion. | Akanni Joseph | Maintenance & Operations | Review CDR and make execution plan | FPSO | 1 | H | 2023-12-31 | 100% | The CDR exists and Implementattion ongoing.
Sea Eagle | MSC/TA/ME | Race against corrosion. | Akanni Joseph | Maintenance & Operations | Make use of corrosion damage framework | FPSO | 1 | H | 2023-12-31 | 100%
Sea Eagle | MSC/TA/ME | Race against corrosion. | Michael Amaku / Akeem Adepoju | Maintenance & Operations | Engage with BONGA to mirror manning and execution. | FPSO | 1 | H | 2023-12-31 | 100% | Manning upgraded to 6/crew as against 3/crew Staff yet to resume fully. Structure in place but dependent on POB management
Sea Eagle | MSC/TA/ME | ASV Operating outside the design/operating envelope. | Henry Unuane/Barobote Stanley | Maintenance & Operations | Raise an MOC for likely ASV plug design changes. | FGC/EGC | 1 | M | 2024-06-30 | 60% | MOC not required; This was not recommended by the Operating Envelope review. Replacement ASV on order - PO 4510476375. Replacement ASV on order - PO 4510476375. Order completed and ready for shipment 02/02/24 Spare ASV in Warehouse. | Reword
Sea Eagle | MSC/TA/ME | FGC/EGC are operating below the operating envelope due to declining gas volumes | Victor Eziyi | Maintenance & Operations | Carry out operating envelope review of EA FGC/EGC | FGC/EGC | 1 | M | 2024-06-30 | 60% | Awaiting Signed Off Report Out while recommendations from the Preliminary reports are being implemented.
Sea Eagle | MSC/TA/ME | No obsolescence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Awe Afolabi/Phillips Oluseye | Maintenance & Operations | Appoint Focal Point Develop R&R and agree on a RACI | AGC/GTG/IAC | 1 | H | 2023-06-30 | 100% | Focal Point appointed to work wit the TA.
Sea Eagle | MSC/TA/ME | No obsolescence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Michael Amaku / Akeem Adepoju | Maintenance & Operations | Compile a list of obsolete items across disciplines in EA Classify Obsolescene items | AGC/GTG/IAC | 1 | H | 2023-09-30 | 100% | Review existing obsolescence management framework in progress and update accordingly Activities commenced in the replacement of obsolete equipment. Obsolescence management plan also updated. Review existing obsolescence management framework and update in progress awaiting mech/elect input. Compare with document issued by PACO TA2 11 items (mostly PACO) are being carried in the current upgrade plans.
Sea Eagle | MSC/TA/ME | No obsolescence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Awe Afolabi/Phillips Oluseye | Maintenance & Operations | Create 5 year Obsolescence Management Plan for EA | FPSO | 1 | H | 2023-06-30 | 100% | Plan exists but to be reviewed. Awaiting final sign off by John Fraeijhoven
Sea Eagle | MSC/TA/ME | No obsolescence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Awe Afolabi/Phillips Oluseye | Maintenance & Operations | Engage key stakeholders on the obsolescence management | AGC/GTG/IAC | 1 | H | 2023-06-30 | 100%
Sea Eagle | MSC/TA/ME | No obsolescence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Michael Amaku / Akeem Adepoju | Maintenance & Operations | Prioritize critical items and include in the Fit4MTO tool | AGC/GTG/IAC | 1 | H | 2023-09-30 | 100% | Already being tracked in the Fit4MTO tool and at various stages of implementation Continue tracking vide MTO process
Sea Eagle | MSC/TA/ME | No obsolescence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Chris Ugochukwu | Maintenance & Operations | Co-present the outcome of Obsolescence study to SPDC LT | AGC/GTG/IAC | 1 | H | 2023-12-30 | 100% | Issues from the Obsolescence Management Plan been integrated with the MTO Process and loaded on Fit4MTO tool. Made submission to SPDC Obsolence Management Plan Report.
Sea Eagle | MSC/TA/ME | No obsolescence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Funto | Maintenance & Operations | Develop an Implemention plan for Obsolescence Management. Track through MTO process. | AGC/GTG/IAC | 1 | H | 2023-12-30 | 100% | 02/02/24 : Funto to load all identified obsolescence issues on MTO and track . 07/05/2024: Obsolescence issues with DCS Workstation and Power Management System captured with MTO IDs: I-0261501 and I-0056017 Obsolescence Implmentation plan created in 2023. Signed off. Reviewed Yearly.
Sea Eagle | MSC/TA/ME | No obsolescence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Awe Afolabi/Phillips Oluseye | Maintenance & Operations | Carry out Annual review of the list- Set up a workshop and collect all input and create a project report | AGC/GTG/IAC | 1 | H | 2023-06-30 | 100%
Sea Eagle | MSC/TA/ME | FGC/EGC are operating below the operating envelope due to declining gas volumes | Awe Afolabi/Phillips Oluseye | Maintenance & Operations | Highlight terms of reference for design review of FGC/EGC include avaiable and target | FGC/EGC | 1 | M | 2023-10-31 | 100% | Terms concluded. Date for review fixed.
Sea Eagle | MSC/TA/ME | FGC/EGC are operating below the operating envelope due to declining gas volumes | EA Process team | Maintenance & Operations | Organize design review workshop for the compressor | FGC/EGC | 1 | M | 2023-10-31 | 100%
Sea Eagle | MSC/TA/ME | FGC/EGC are operating below the operating envelope due to declining gas volumes | EA Process team | Maintenance & Operations | Obtain key input like production profile and field development plan, design premise | FGC/EGC | 1 | M | 2023-10-31 | 100% | This was receieved and considered during the workshop.
Sea Eagle | MSC/TA/ME | FGC/EGC are operating below the operating envelope due to declining gas volumes | EA Process team | Maintenance & Operations | Review of design limit and compare with current and future production rate | FGC/EGC | 1 | M | 2023-10-31 | 100%
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE Reuben | Maintenance & Operations | Secure budget proposal for new purifier | AGC/GTG/IAC | 1 | L | 2023-06-30 | 0%
Sea Eagle | MSC/TA/ME | We don’t expect tubing failures(Temperature resistant tubing available) | Duro-Oni, Simisola | Maintenance & Operations | Secure budget for tubing change out of Intrument Air Compressor | Intrument Air Compressor | 1 | H | 2023-11-01 | 100% | 1 Instrument Air Compressor Installed and Commissioned
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE Reuben | Maintenance & Operations | Place order for new purifier | AGC/GTG/IAC | 1 | L | 2023-06-30 | 0%
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE Reuben | Maintenance & Operations | Carry out installation of procured purifier and commission | AGC/GTG/IAC | 1 | L | 2023-06-30 | 0%
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE Reuben | Maintenance & Operations | Review and create maintenance plan in SAP | AGC/GTG/IAC | 1 | L | 2023-06-30 | 0%
Sea Eagle | MSC/TA/ME | No spurious trip and reliable reading, Only true alarm, No flat line, No freezing of UCP/HMI | Ogbonnaya Ekelechi | Maintenance & Operations | Carry out loop check from probe to UCP, DCS, BENTLEY, OS1 PI to identify any fault | AGC/GTG/IAC | 1 | H | 2023-12-30 | 100% | UCP and HMI Commissioning Completed
Sea Eagle | MSC/TA/ME | No spurious trip and reliable reading, Only true alarm, No flat line, No freezing of UCP/HMI | Ogbonnaya Ekelechi | Maintenance & Operations | Locate and confirm that Completed commissioning test sheet exists | AGC/GTG/IAC | 1 | H | 2023-12-30 | 100% | UCP and HMI Commissioning Completed
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE Reuben | Maintenance & Operations | Regular draining and cleaning of storage tank, sevice tank and create PM | AGC/GTG/IAC | 1 | H | 2023-06-30 | 100% | Regular draining and collection of sample.
Sea Eagle | MSC/TA/ME | No spurious trip and reliable reading, Only true alarm, No flat line, No freezing of UCP/HMI | Ogbonnaya Ekelechi | Maintenance & Operations | Update documentation with any identified gap from loop check and commissioning test sheet if any. | AGC/GTG/IAC | 1 | H | 2023-06-30 | 100% | UCP and HMI Commissioning Completed
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE Reuben | Maintenance & Operations | Identify specifications and build for a new purifier | AGC/GTG/IAC | 1 | L | 2023-06-30 | 50% | Specification identified, however it cannot pass through the door and a request sent to Lloyds to approve expansion of the door. Had an engagement with Lloyds to seek support for expansion of Diesel purifier room door
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE Reuben | Maintenance & Operations | Mirror Forcados terminal purifier installation or explore learning opportunities | AGC/GTG/IAC | 1 | L | 2023-06-30 | 65% | Exploring possibility of procuring the latest version of diesel purifier.
Sea Eagle | MSC/TA/ME | No spurious trip and reliable reading, Only true alarm, No flat line, No freezing of UCP/HMI | Ogbonnaya Ekelechi | Maintenance & Operations | Sign-off the updated document and handover asset | AGC/GTG/IAC | 1 | H | 2023-06-30 | 100% | UCP and HMI Commissioning Completed
Sea Eagle | MSC/TA/ME | Race against corrosion. | Akanni Joseph | Maintenance & Operations | Identify priority areas/equipments, support structures for coolers, Cowlings HV motor enclosures ETC. | FPSO | 1 | H | 2023-12-31 | 98% | Work ongoing on the cowlings (completed), the water Ballast Tanks (ongoing) and the External Hulls of the FPSO in progress (84% completed)
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE Reuben | Maintenance & Operations | Install the new relatively wider purifier on board and commission | Intrument Air Compressor | 1 | L | 2023-06-30 | 100% | Steer from the AMIL to backload the not-fit-purpose purifier and progress the procurement of new one.
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE Reuben | Maintenance & Operations | Review PM on GT line Orifice and spark plugs to address observed failures | AGC/GTG/IAC | 1 | L | 2023-06-30 | 100% | Inspection, cleaning and changeout of orifice and spark plugs during 4K and 8K services.
Sea Eagle | MSC/TA/ME | The design temperature able to maintain at all level in engine room- Adequate PM for Engine room Fan and Motor | Duro-Oni, Simisola | Maintenance & Operations | Review maintenance plan for the engine room air conditioning system | AGC/GTG/IAC | 1 | M | 2023-10-01 | 80% | Observed that no PM is in place for Suction Louvers. Draft 2Y Mtce Plan for cleaning of the Fan Suction Louvers and under review with TA (Finebone) 07/05/2024: TA Reviewed and Signed off MJR.
Sea Eagle | MSC/TA/ME | The design temperature able to maintain at all level in engine room- Adequate PM for Engine room Fan and Motor | Michael Amaku / Akeem Adepoju | Maintenance & Operations | Deliver specific equipmemts with known problems | FPSO | 1 | M | 2023-12-31 | 80% | 2Y Mtce Plan for cleaning of the Fan Suction Louvers in progress 100% done. Sent to TA for review. 07/05/2024: TA Reviewed and Signed off MJR.
Sea Eagle | MSC/TA/ME | We don’t expect tubing failures(Temperature resistant tubing available) | Michael Amaku / Akeem Adepoju | Maintenance & Operations | Create work order and execute activity (Proactive replacement of existig tubings) | Intrument Air Compressor | 1 | H | 2023-10-01 | 100% | Replacement tubings are available for replacement on site 1. Notification 11994416 and PM WO 23122195 created 2.Initiated MOC for material change MoC raised: 134899 3. Confirmed material availability 30/4/2024 - Conversion of the low heat resistant tubing the in IAC to metallic ones- Done
|  | Location | Temp | Temp (Offtake) | Average | Operating Temp
|  | M/s Lv 2 | 22.6 | 26.8 | 24.7 | 45
|  | M/s Lv 3 | 25 | 31.4 | 28.2 | 45
|  | M/s Lv 4 | 32.6 | 33.9 | 33.25 | 87
|  | M/s Lv 5 (Framo Room) | 31.8 | 36.2 | 34 | <65
|  | M/s Lv 5 | 27 | 30.9 | 28.95 | 45
|  | M/s Lv 6 | 27 | 27.6 | 27.3 | 50

## Status
Completion Status
Completed
Ongoing
Not started

## Due Status
Due Status | Id
Overdue | 1
Due in 30 days | 2
Due 30 to 60 days | 3
Over 60 days | 4
Completed | 5

## System Owners
System Owner | PU
Didi Otobo | Sea Eagle
Vincent Atey | Sea Eagle
Chimuanya Onyejekwe | Sea Eagle
Musa Nabage | Sea Eagle

## Pillars
Pillars
Maintenance & Operations
Spares
Proactive Technical Monitoring
Capabilities
Project to Asset

## PUs
PU | Title
Soku | SOKU INTEGRATED VALUE DELIVERY SUSTAIN
Tunu | INTEGRATED VALUE DELIVERY TUNU NODE COMPRESSOR AVAILABILITY
Sea Eagle | EA COMPRESSORS & POWER GENERATION IVD

## Pivot
% Completion | (Multiple Items)
Row Labels | Count of % Completion
100% Critical spares available in stock (Realistic methodology to identify critical spares, Sustainable Min-Max levels,Preservation to requirement) | 2
Adequate Manning of Facility in line with the HSE Case | 2
ASV Operating outside the design/operating envelope. | 1
FGC/EGC are operating below the operating envelope due to declining gas volumes | 1
Location
M/s Lv 2
M/s Lv 3
M/s Lv 4
M/s Lv 5
M/s Lv 5 (Framo Room)
M/s Lv 6
No obsolescence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | 1
Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | 6
Race against corrosion. | 1
The design temperature able to maintain at all level in engine room- Adequate PM for Engine room Fan and Motor | 2
We don’t expect tubing failures(Temperature resistant tubing available) | 1
(blank)
Grand Total | 17