## Deliverables
PU | Process Steps | Activity | Action Lead | Pillars | Deliverables | Equipment | Weight | Close out Date | % Completion | Comment | Comment Date
| System Selection And Scope | Resource the IVD plan | Victor Ndukwe |  | Engage the external facilitators and AMIL to conform resources needed and readiness to deliver |  | 1 | 2023-02-28 | 100%
| System Selection And Scope | Resource the IVD plan | Victor Ndukwe |  | Identify Initiative Focal Points with the support of the AMIL |  | 1 | 2023-02-28 | 100%
| System Selection And Scope | Resource the IVD plan | Kebin Ofori |  | Engage the Asset and Production Services Leadership and readiness to support the initiative |  | 1 | 2023-02-28 | 100%
| System Selection And Scope | Identify Improvement Goal | Victor Ndukwe |  | Develop scope, Outline clear targets, include in the CTR and secure CTR approval |  | 1 | 2023-02-28 | 100%
| System Selection And Scope | Kick Off meeting stakeholders | Victor Ndukwe |  | Engage AGG team on IVD |  | 1 | 2023-02-28 | 100%
| System Selection And Scope | Kick Off meeting stakeholders | Victor Ndukwe |  | Name System Owners on IVD plans |  | 1 | 2023-02-28 | 100%
| System Selection And Scope | Kick Off meeting stakeholders | Kebin Ofori |  | Engage Asset Manager and PS LT on IVD plans |  | 1 | 2023-02-28 | 100%
| System Selection And Scope | Kick Off meeting stakeholders | Casmir Ojobo |  | Agree Cadence, DRB and Success measures |  | 1 | 2023-03-06 | 100%
| MTO | Identify Threats on Fit4MTO database | Victor Ndukwe |  | Download threats and actions on MTO with impact on system |  | 1 | 2023-03-20 | 100%
| MTO | Identify Threats on Fit4MTO database | Victor Ndukwe |  | Analyse data and identify threats with deferment, flaring impact, equipment with low availability |  | 1 | 2023-03-20 | 100%
| MTO | Identify Bad actors (Review past trips and RCAs) | Victor Ndukwe |  | Review historical trip logs |  | 1 | 2023-03-20 | 100%
| MTO | Identify Bad actors (Review past trips and RCAs) | Victor Ndukwe |  | Identify causes of trips |  | 1 | 2023-03-20 | 100%
| MTO | Identify Bad actors (Review past trips and RCAs) | Victor Ndukwe |  | Review completed RCAs from past events |  | 1 | 2023-03-20 | 100%
| MTO | Identify Bad actors (Review past trips and RCAs) | Casmir Ojobo |  | Download and review failure history of GTs and Compressors |  | 1 | 2023-03-20 | 100%
| System Selection And Scope | Kick Off meeting stakeholders | Victor Ndukwe |  | Organise and Hold Kickoff workshop(F2F) |  |  | 2023-03-27 | 100%
| MTO Improvement | Adequate action owners are assigned (competent and available), appreciating difference between Short and Long term. For Long term: supporting teams, not Front Line (assign by threat owner, along with required mandate) | Olachi Olatunji/Ndukwe | Maintenance & Operations | Criteria to be set (competence, available time, mandate) for action owner |  | 1 | 2023-06-30 | 0%
| MTO Improvement | Adequate action owners are assigned (competent and available), appreciating difference between Short and Long term. For Long term: supporting teams, not Front Line (assign by threat owner, along with required mandate) | Olachi Olatunji/Ndukwe | Maintenance & Operations | Agree on handshake (including criteria) with Action Owner (in case of member from supporting team, i.e. Outside asset team). |  | 1 | 2023-05-30 | 0%
| MTO Improvement | Adequate action owners are assigned (competent and available), appreciating difference between Short and Long term. For Long term: supporting teams, not Front Line (assign by threat owner, along with required mandate) | PUM | Maintenance & Operations | Include agreed actions in GPA of action owner or include: Allocate 20% of time for MTO threats/actions |  | 1 | 2023-06-30 | 0%
| MTO Improvement | Common Action for MTO: Organize Awareness session on adjustments in the process. | Olachi Olatunji/Ndukwe | Maintenance & Operations | Include as part of agenda in the Weekly MTO meeting with clear terms of reference and claritify roles of participants |  | 1 | 2023-06-30 | 100%
| MTO Improvement | Common Action for MTO: Organize Awareness session on adjustments in the process. | Olachi Olatunji/Ndukwe | Maintenance & Operations | Threat owners (OIM) to vet the final decisions /outcomes including reasoning, risk level, mitigating actions |  | 1 | 2023-06-30 | 30%
Sea Eagle | MSC/TA/ME | We don’t expect tubing failures(Temperature resistant tubing available) | Maintenance Execution Engineer | Maintenance & Operations | Raise an MOC for tubing change out on intrument Air Compressor including stoping | Intrument Air Compressor | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | We don’t expect tubing failures(Temperature resistant tubing available) | Maintenance Execution Engineer | Maintenance & Operations | Secure budget for tubing change out of Intrument Air Compressor | Intrument Air Compressor | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | We don’t expect tubing failures(Temperature resistant tubing available) | Maintenance Execution Engineer | Maintenance & Operations | Create work order and execute activity (Proactive replacement) | Intrument Air Compressor | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | No critical transmitter failure to cause trip( Rebust and workable PM strategy) | Awe Afolabi | Maintenance & Operations | Identify Critical Transmitters with trip functions within the EA facility | AGC/GTG/IAC | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | No critical transmitter failure to cause trip( Rebust and workable PM strategy) | Awe Afolabi | Maintenance & Operations | Source the MTBF for the critical transmitters/ End Of Life(EOL) and hence identify transmitters for changeout. | AGC/GTG/IAC | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | No critical transmitter failure to cause trip( Rebust and workable PM strategy) | Awe Afolabi | Maintenance & Operations | Review and update existing PMs and include inspection maintenance plan | AGC/GTG/IAC | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | No critical transmitter failure to cause trip( Rebust and workable PM strategy) | Awe Afolabi | Maintenance & Operations | Review and Replace Transmitters due for replacement including spares for those in voting configurations. | AGC/GTG/IAC | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | ASV Intrusive maintenance( Mintenance job routine-Fit for purpose) | Process TA/Rotating Eng. TA ( Tonye,E/Unwana Ufeh) | Maintenance & Operations | Review the design of the Anti surge Valve (ASV) plug with respect to current gas flow rate involving the OEM and TAs. | FGC/EGC | 1 | 2023-12-31 | 0%
Sea Eagle | MSC/TA/ME | ASV Intrusive maintenance( Mintenance job routine-Fit for purpose) | Process TA/Rotating Eng. TA ( Tonye,E/Unwana Ufeh) | Maintenance & Operations | Raise an MOC for likely ASV plug design changes. | FGC/EGC | 1 | Turnaround 2024 | 0%
Sea Eagle | MSC/TA/ME | ASV Intrusive maintenance( Mintenance job routine-Fit for purpose) | Process TA/Rotating Eng. TA ( Tonye,E/Unwana Ufeh) | Maintenance & Operations | Raise and MTO ID for continuous operation of the compressors with current flow rate | FGC/EGC | 1 | Turnaround 2024 | 0%
Sea Eagle | MSC/TA/ME | ASV Intrusive maintenance( Mintenance job routine isFit for purpose) | Process TA/Rotating Eng. TA ( Tonye,E/Unwana Ufeh) | Capability | Create work order and purchase order for intrusive maintenance of ASV | FGC/EGC | 1 | Turnaround 2024 | 0%
Sea Eagle | MSC/TA/ME | ASV Intrusive maintenance( Mintenance job routine-Fit for purpose) | Process TA/Rotating Eng. TA ( Tonye,E/Unwana Ufeh) | Maintenance & Operations | Create PM plan for ASV intrusive maintenance | FGC/EGC | 1 | Turnaround 2024 | 0%
Sea Eagle | MSC/TA/ME | 100% Critical spares available in stock (Realistic methodology to identify critical spares, Sustainable Min-Max levels,Preservation to requirement) | AMIL support,EA (Brian Arodiogbu) | Spares | Review criteria for what make a critical spare | AGC/GTG/IAC | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | 100% Critical spares available in stock (Realistic methodology to identify critical spares, Sustainable Min-Max levels,Preservation to requirement) | Maintenance Team Leader | Spares | Prioritize systems that are most vulnerable for critical spares | AGC/GTG/IAC | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | 100% Critical spares available in stock (Realistic methodology to identify critical spares, Sustainable Min-Max levels,Preservation to requirement) | AMIL support,EA (Brian Arodiogbu) | Spares | Check BOMs and MMDS plus Min-Max and update when needed | AGC/GTG/IAC | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | 100% Critical spares available in stock (Realistic methodology to identify critical spares, Sustainable Min-Max levels,Preservation to requirement) | AMIL support,EA (Brian Arodiogbu) | Spares | Develop procedues to manange non-stock goods in transit | AGC/GTG/IAC | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | 100% Critical spares available in stock (Realistic methodology to identify critical spares, Sustainable Min-Max levels,Preservation to requirement) | AMIL support,EA (Brian Arodiogbu) | Spares | Obtain approval of critical spares and raise budget | AGC/GTG/IAC | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | 100% Critical spares available in stock (Realistic methodology to identify critical spares, Sustainable Min-Max levels,Preservation to requirement) | AMIL support,EA (Brian Arodiogbu) | Spares | Order spares and implement preservation requirement - (3D print alternative to be explored to optimize lead time) | AGC/GTG/IAC | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | 100% Critical spares available in stock (Realistic methodology to identify critical spares, Sustainable Min-Max levels,Preservation to requirement) | AMIL support,EA (Brian Arodiogbu) | Spares | Review the selected system for critical spares according to the criteria and define preservation requirements | AGC/GTG/IAC | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | The design temperature able to maintain at all level in engine room- Adequate PM for Engine room Fan and Motor | Eyitayo, B | Maintenance & Operations | Check Engine room design temperature and compare with current obtainable mean temperatures. | Ventillation System | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | The design temperature able to maintain at all level in engine room- Adequate PM for Engine room Fan and Motor | Eyitayo, B | Maintenance & Operations | Create work oreder for checking inlet filter,Louvers, Blockages in venting, Motor fans | Ventillation System | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | The design temperature able to maintain at all level in engine room- Adequate PM for Engine room Fan and Motor | Eyitayo, B | Maintenance & Operations | Carry out recommended health checks on the existing Ventillation Fan motor. Check motor speed, etc. | Ventillation System | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | The design temperature able to maintain at all level in engine room- Adequate PM for Engine room Fan and Motor | Eyitayo, B | Maintenance & Operations | Verify the operating design of the newly installed equipment in the engine room. Ei Instrument Air compressor. | IAC | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | The design temperature able to maintain at all level in engine room- Adequate PM for Engine room Fan and Motor | Eyitayo, B | Maintenance & Operations | Review maintenance plan for the engine room air conditioning system | AGC/GTG/IAC | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | The design temperature able to maintain at all level in engine room- Adequate PM for Engine room Fan and Motor | Eyitayo, B | Maintenance & Operations | Restore the functionality of the second draft fan. | Engine Room | 1 | 2023-10-01 | 0%
Sea Eagle | MSC/TA/ME | Race against corrosion. | OIM | Maintenance & Operations | Appoint focal point for fabric maintenance on board in sea eagle. | FPSO |  | 2023-10-01
Sea Eagle | MSC/TA/ME | Race against corrosion. | MTC T/L | Maintenance & Operations | Inspect and deliver corrosion damage report (CDR) | FPSO | 1 | 2023-12-31 | 0%
Sea Eagle | MSC/TA/ME | Race against corrosion. | MTC T/L | Maintenance & Operations | Include inspection routine/fabric maintenance in SAP at Equipment level. | FPSO | 1 | 2023-12-31 | 0%
Sea Eagle | MSC/TA/ME | Race against corrosion. | MTC T/L | Maintenance & Operations | Check of existing MJR's are covering inspection of non-pressurized equipments | FPSO | 1 | 2023-12-31 | 0%
Sea Eagle | MSC/TA/ME | Race against corrosion. | MTC T/L | Maintenance & Operations | Review CDR and make execution plan | FPSO | 1 | 2023-12-31 | 0%
Sea Eagle | MSC/TA/ME | Race against corrosion. | MTC T/L | Maintenance & Operations | Make use of corrosion damage framwork | FPSO | 1 | 2023-12-31 | 0%
Sea Eagle | MSC/TA/ME | The design temperature able to maintain at all level in engine room- Adequate PM for Engine room Fan and Motor | MTC T/L | Maintenance & Operations | Engage with BONGA to mirror manning and execution | FPSO | 1 | 2023-12-31 | 0%
Sea Eagle | MSC/TA/ME | The design temperature able to maintain at all level in engine room- Adequate PM for Engine room Fan and Motor | MTC T/L | Maintenance & Operations | Identify priority areas/equipments, support structures for coolers, Cowlings HV motor enclosures ETC. | FPSO | 1 | 2023-12-31 | 0%
Sea Eagle | MSC/TA/ME | The design temperature able to maintain at all level in engine room- Adequate PM for Engine room Fan and Motor | MTC T/L | Maintenance & Operations | Deliverable specific equipmemts with know problems | FPSO | 1 | 2023-12-31 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Appoint R&R Developer and Agree RACI | AGC/GTG/IAC | 1 | 06/31/2023 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Collect and check the obsolescene items | AGC/GTG/IAC | 1 | 06/31/2023 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Execution by project team | AGC/GTG/IAC | 1 | Tie into OP23 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Annual review of the list- Set up a workshop and collect all input and create a project report | AGC/GTG/IAC | 1 | 06/31/2023 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Classify Obsolescene items | AGC/GTG/IAC | 1 | 06/31/2023 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Engage key stakeholders | AGC/GTG/IAC | 1 | 06/31/2023 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Prioritize critical items and imclude into MTO tool | AGC/GTG/IAC | 1 | 06/31/2023 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Create 5 year plan, include Asset team for review | AGC/GTG/IAC | 1 | 06/31/2023 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Include Obsolescene items into ACP and IAP | AGC/GTG/IAC | 1 | 06/31/2023 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Conmpliance- Work the plan, have annual review | AGC/GTG/IAC | 1 | 06/31/2023 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Get budget | AGC/GTG/IAC | 1 | Tie into OP23 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Highlight terms of reference for design review include avaiable and terget | AGC/GTG/IAC | 1 | 2023-10-31 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Organize design review workshop | AGC/GTG/IAC | 1 | 2023-10-31 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Engage stakeholders | AGC/GTG/IAC | 1 | 2023-10-31 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Obtain key input like production profile and field development plan, design premise | AGC/GTG/IAC | 1 | 2023-10-31 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Review of design limit and compare with current and future production rate | AGC/GTG/IAC | 1 | 2023-10-31 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Reliability review | AGC/GTG/IAC | 1 | 2023-10-31 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Identify action and make project plan | AGC/GTG/IAC | 1 | 2023-10-31 | 0%
Sea Eagle | MSC/TA/ME | No osolence of equipment,parts and softwears,plan for upgrade and replacement, mitigation in place until upgrade is secured,clear line of communication, collect obselence needs and approval, Have a focal point obselence plan, Execution( In time, Bugdet, Quality, Fit for purpose) | Development team AMIL | Maintenance & Operations | Create MOC for new production envelop | AGC/GTG/IAC | 1 | 2023-10-31 | 0%
Sea Eagle | MSC/TA/ME | No spurious trip and reliable reading, Only true alarm, No flat line, No freezing of UCP/HMI | Balogun (MTC Support) | Maintenance & Operations | Engage with existing project team for UCP upgrade project | AGC/GTG/IAC | 1 | 6/31/2023 | 0%
Sea Eagle | MSC/TA/ME | No spurious trip and reliable reading, Only true alarm, No flat line, No freezing of UCP/HMI | Balogun | Maintenance & Operations | Engagement to comfirm scope, loop checks for vibration | AGC/GTG/IAC | 1 | 6/31/2023 | 0%
Sea Eagle | MSC/TA/ME | No spurious trip and reliable reading, Only true alarm, No flat line, No freezing of UCP/HMI | Balogun | Maintenance & Operations | Loop check from probe to UCP, DCS, BENTLEY, OS1 PI | AGC/GTG/IAC | 1 | 6/31/2023 | 0%
Sea Eagle | MSC/TA/ME | No spurious trip and reliable reading, Only true alarm, No flat line, No freezing of UCP/HMI | Balogun | Maintenance & Operations | Completed commissioning test sheet | AGC/GTG/IAC | 1 | 6/31/2023 | 0%
Sea Eagle | MSC/TA/ME | No spurious trip and reliable reading, Only true alarm, No flat line, No freezing of UCP/HMI | Balogun | Maintenance & Operations | Update document | AGC/GTG/IAC | 1 | 6/31/2023 | 0%
Sea Eagle | MSC/TA/ME | No spurious trip and reliable reading, Only true alarm, No flat line, No freezing of UCP/HMI | Balogun | Maintenance & Operations | Sign-off and handover | AGC/GTG/IAC | 1 | 6/31/2023 | 0%
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE | Maintenance & Operations | Regular draining and cleaning of storage tank, sevice tank and create PM | AGC/GTG/IAC | 1 | 6/31/2023 | 0%
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE | Maintenance & Operations | Secure budget proposal for new purifier | AGC/GTG/IAC | 1 | 6/31/2023 | 0%
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE | Maintenance & Operations | Identify specificationof as build pufifier for adequate specification | AGC/GTG/IAC | 1 | 6/31/2023 | 0%
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE | Maintenance & Operations | Place order for new purifier | AGC/GTG/IAC | 1 | 6/31/2023 | 0%
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE | Maintenance & Operations | Installation and commission | AGC/GTG/IAC | 1 | 6/31/2023 | 0%
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE | Maintenance & Operations | Review and create maintenance plan in SAP | AGC/GTG/IAC | 1 | 6/31/2023 | 0%
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE | Maintenance & Operations | Install new large purifier and make it work | Intrument Air Compressor | 1 | 6/31/2023 | 0%
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE | Maintenance & Operations | Review PM on GT line Oriface and spark plugs | AGC/GTG/IAC | 1 | 6/31/2023 | 0%
Sea Eagle | MSC/TA/ME | Purifier available at all time, purifier maintenance plan,diesel meets desired spec and day tank cleaning. | KITOYE | Maintenance & Operations | Mirror Forcados terminal pufifier installation | AGC/GTG/IAC | 1 | 6/31/2023 | 0%
Sea Eagle | MSC/TA/ME | Adequate Manning of Facility in line with the HSE Case |  | Capability | Audit the current manning philosphy in line with the HSE Case and make recommendations |  |  |  | 0%
Sea Eagle |  | Adequate Manning of Facility in line with the HSE Case |  | Capability | Make Recommendations based on the Manning audit findings
Sea Eagle |  | Adequate Manning of Facility in line with the HSE Case |  | Capability | Implement the gap closure plans from the manning audit

## Status
Completion Status
Completed
Ongoing
Not started

## Due Status
Due Status | Id
Overdue | 1
Due in 30 days | 2
Due 30 to 60 days | 3
Over 60 days | 4
Completed | 5

## System Owners
System Owner | PU
Didi Otobo | Sea Eagle
Vincent Atey | Sea Eagle
Chimuanya Onyejekwe | Sea Eagle
Musa Nabage | Sea Eagle

## Pillars
Pillars
Maintenance & Operations
Spares
Proactive Technical Monitoring
Capabilities
Project to Asset

## PUs
PU | Title
Soku | SOKU INTEGRATED VALUE DELIVERY SUSTAIN
Tunu | INTEGRATED VALUE DELIVERY TUNU NODE COMPRESSOR AVAILABILITY
Sea Eagle | EA COMPRESSORS & POWER GENERATION IVD