## Deliverables
PU | Process Steps | Activity | Action Lead | Pillars | Deliverables | Equipment | Weight | Close out Date | % Completion | Comment | Comment Date
Soku | System Selection And Scope | Resource the IVD plan | Kebin Ofori | Maintenance & Operations | Engage the task owners to conform resources needed and readiness to deliver |  | 1 | 2022-06-30 | 100%
Soku | System Selection And Scope | Identify Improvement Goal | Casmir Ojobor | Maintenance & Operations | Outline clear targets |  | 1 | 2022-06-30 | 100%
Soku | System Selection And Scope | Kick Off meeting stakeholders | Umunakwe Odinakachi | Maintenance & Operations | Engage AGG team on IVD |  | 1 | 2022-06-30 | 100%
Soku | System Selection And Scope | Kick Off meeting stakeholders | Umunakwe Odinakachi | Maintenance & Operations | Engage PS LT on IVD plans |  | 1 | 2022-06-30 | 100%
Soku | System Selection And Scope | Kick Off meeting stakeholders | Umunakwe Odinakachi | Maintenance & Operations | Engage Asset Manager IVD plans |  | 1 | 2022-06-30 | 100%
Soku | System Selection And Scope | Kick Off meeting stakeholders | Umunakwe Odinakachi | Maintenance & Operations | Name System Owners on IVD plans |  | 1 | 2022-06-30 | 100%
Soku | System Selection And Scope | Kick Off meeting stakeholders | Umunakwe Odinakachi | Maintenance & Operations | Agree Cadence, DRB and Success measures |  | 1 | 2022-06-30 | 100%
Soku | MTO | Identify Threats on Fit4MTO database | Umunakwe Odinakachi | Maintenance & Operations | Download threats and actions on MTO with impact on system |  | 1 | 2022-06-30 | 100%
Soku | MTO | Identify Threats on Fit4MTO database | Umunakwe Odinakachi | Maintenance & Operations | Analyse data and identify threats with deferment, flaring impact, equipment with low availability |  | 1 | 2022-06-30 | 100%
Soku | MTO | Identify Bad actors (Review past trips and RCAs) | Umunakwe Odinakachi | Maintenance & Operations | Review historical trip logs |  | 1 | 2022-06-30 | 100%
Soku | MTO | Identify Bad actors (Review past trips and RCAs) | Umunakwe Odinakachi | Maintenance & Operations | Identify causes of trips |  | 1 | 2022-06-30 | 100%
Soku | MTO | Identify Bad actors (Review past trips and RCAs) | Umunakwe Odinakachi | Maintenance & Operations | Review completed RCAs from past events |  | 1 | 2022-06-30 | 100%
Soku | MTO | Identify Bad actors (Review past trips and RCAs) | Umunakwe Odinakachi | Maintenance & Operations | Download and review failure history on SAP |  | 1 | 2022-06-30 | 100%
Soku | MTO | Identify Bad actors (Review past trips and RCAs) | Umunakwe Odinakachi | Maintenance & Operations | Enumerate common themes |  | 1 | 2022-06-30 | 100%
Soku | MTO Improvement | Adequate action owners are assigned (competent and available), appreciating difference between Short and Long term. For Long term: supporting teams, not Front Line (assign by threat owner, along with required mandate) | Kebin Ofori | Maintenance & Operations | Criteria to be set (competence, available time, mandate) for action owner |  | 1 | 2022-12-30 | 100%
Soku | MTO Improvement | Adequate action owners are assigned (competent and available), appreciating difference between Short and Long term. For Long term: supporting teams, not Front Line (assign by threat owner, along with required mandate) | Kebin Ofori | Maintenance & Operations | Agree on handshake (including criteria) with Action Owner (in case of member from supporting team, i.e. Outside asset team). |  | 1 | 2022-12-30 | 100%
Soku | MTO Improvement | Adequate action owners are assigned (competent and available), appreciating difference between Short and Long term. For Long term: supporting teams, not Front Line (assign by threat owner, along with required mandate) | Kebin Ofori | Maintenance & Operations | Include agreed actions in GPA of action owner or include: Allocate 20% of time for MTO threats/actions |  | 1 | 2022-12-30 | 100%
Soku | MTO Improvement | Common Action for MTO: Organize Awareness session on adjustments in the process. | Casmir/Uju/Victor | Maintenance & Operations | Monthly cadence to be in place with clear terms of reference and claritify of participants and their role |  | 1 | 2022-12-30 | 100%
Soku | MTO Improvement | Common Action for MTO: Organize Awareness session on adjustments in the process. | Casmir/Uju/Victor | Maintenance & Operations | Threat owners (PUM) to vet the final decisions /outcomes including reasoning, risk level, mitigating actions |  | 1 | 2023-12-30 | 50%
Soku | MTO Improvement | Common Action for MTO: Organize Awareness session on adjustments in the process. | Casmir/Uju/Victor | Maintenance & Operations | Major Actions from MTO process to be included in Asset (Care and Improvement) Plans – already covered under IVD plan/actions |  | 1 | 2023-06-30 | 35%
Soku | MSC/TA/ME | Prevent GT + Compressor Start-up delays | Kene/Lukmon/Theresa/Nsikak | Spares | Main Inlet valves: Review Actuator design with regards to travel time | LPNAG/AG2 | 1 | 2022-11-30 | 60% | Discussion with TA held, Mech TA advised we can change valve timing after confirmation of valve held – That is ongoing. 19/04/23 control sysytem to be reviewed during OEM site visit... 26/04/23 Sergio to come in today and would be engaged. 03/05/2023 to commence conversation today/tomorrow
Soku | MSC/TA/ME | Prevent GT + Compressor Start-up delays | Kene/Philip/Theresa/Nsikak | Spares | Retrieve documentation of actuator. Review details of the actuator design to confirm travel time | LPNAG/AG2 | 1 | 2022-11-30 | 100% | review
Soku | MSC/TA/ME | Prevent GT + Compressor Start-up delays | Kene/Lukmon/Theresa/Nsikak | Spares | Review travel time vs logic through AGG team, including consultation with OEM of logic (OEM = GE, now Baker Hughes) | LPNAG/AG2 | 1 | 2022-11-30 | 60% | Further reviews with TA and AGG to be held post OEM engagement (manufacturer of valve of actuator)(manufacturer of logic to be engaged later). Kene to give screenshot of logic. Asset should get original commissioning dosuments that would show specifications as per design and we can compare to current reality 26/04/2023 Shina to connect with Sam Idio and Kene on commissioning docs 03/05/23 to check in house files for this
Soku | MSC/TA/ME | Prevent GT + Compressor Start-up delays | Kene/Philip/Theresa/Nsikak | Maintenance & Operations | If margin between travel time and logic timer too little: OEM to propose modification of logic | LPNAG/AG2 | 1 | 2022-11-30 | 100% | OEM has given a general recommendation for the valve and advised on steps to boost speed of travel.
Soku | MSC/TA/ME | Prevent GT + Compressor Start-up delays | Kene/Lukmon/Theresa/Nsikak | Spares | Main Inlet valves: C) Review logic (5 sec for 18”valve open/close is very short) | LPNAG/AG2 | 1 | 2022-11-30 | 20% | TA advised to connect with other shell OU to get their practice. Valve timing can be changed according to Mech TA.
Soku | MSC/TA/ME | Prevent GT + Compressor Start-up delays | Kene/Philip/Theresa/Nsikak | Spares | Understand what has changed over the years (initially the 5 seconds seemed to be sufficient) | LPNAG/AG2 | 1 | 2022-11-30 | 100% | there is an understanding of what has happened over time
Soku | MSC/TA/ME | Prevent GT + Compressor Start-up delays | Kene/Philip/Theresa/Nsikak | Spares | Check condition of actuator through time (inspection / repair history) | LPNAG/AG2 | 1 | 2022-11-30 | 100% | Actuator needs to be rekitted, as pitting and degradation has happpened over time
Soku | MSC/TA/ME | Prevent GT + Compressor Start-up delays | Kene/Lukmon/Theresa/Nsikak | Spares | Upgrade IA package to address quality concerns (Review Maintenance history of valve and actuator), | LPNAG/AG2 | 1 | 2022-11-30 | 30% | IA has moisture. Cadence going on to make a change to Copco IA compressor package believed to give dryer air. 19/04/23 PR for repair materials out. no PO yet. C&P handling that. Dessicant to be ordered: working with commercial to get vendor for cost effective alternate dessicant as the ones presented are very expensive. Team to have connect with Idio and team to justify purchase of new compressors based on their validation of no air leaks. 26/04 gotten buy-in of one TA, awaiting buy-in of 2nd, then we proceed with MOC for getting new compressors 03/05 process engrg team to give buy-in. to have conv this week
Soku | MSC/TA/ME | Prevent GT + Compressor Start-up delays | Kene/Philip/Theresa/Nsikak | Maintenance & Operations | Conclude on what may have changed over time and solve the relevant problem or include in solution | LPNAG/AG2 | 1 | 2022-11-30 | 100% | Valves are older 24yrs, defective position sensors. These position sensors have been ordered.
Soku | MSC/TA/ME | Prevent GT + Compressor Start-up delays | Kene/Lukmon/Theresa/Nsikak | Maintenance & Operations | TAs to review and approve the modification (MOC req’d) | LPNAG/AG2 | 1 | 2023-12-31 | 50% | TAs have been engaged, gave Seye a feedbackon things to get to continue review: screenshot of logic, C&E
Soku | MSC/TA/ME | Prevent GT + Compressor Start-up delays | Kene Odunze/Musa | Capability | Conduct Mark VIe Training for Asset PACO personnel | LPNAG/AG2 | 1 | 2023-12-31 | 50% | Sent out request to capability team. PS Manager on top it
Soku | MSC/TA/ME | Main Inlet valves: B) Upgrade valve positioner – obsolete, Discontinued, not longer manufactured | Kene/Philip/Theresa/Nsikak | Maintenance & Operations | Explore for alternative type(s) / model Testing of alternative with communication system | LPNAG/AG2 | 1 | 2022-11-30 | 100%
Soku | MSC/TA/ME | Main Inlet valves: B) Upgrade valve positioner – obsolete, Discontinued, not longer manufactured | Kene/Philip/Theresa/Nsikak | Maintenance & Operations | Engage with all parties involved to frame up the solution. Involve TA's | LPNAG/AG2 | 1 | 2022-11-30 | 100% | PR10753414 ( procurement process initiated
Soku | MSC/TA/ME | Main Inlet valves: B) Upgrade valve positioner – obsolete, Discontinued, not longer manufactured | Kene/Philip/Theresa | Maintenance & Operations | Frame up technical spec and commercial quotation | LPNAG/AG2 | 1 | 2022-11-30 | 100%
Soku | MSC/TA/ME | Main Inlet valves: B) Upgrade valve positioner – obsolete, Discontinued, not longer manufactured | Kene/Philip/Theresa/Nsikak | Maintenance & Operations | Review and approve technical and quotation | LPNAG/AG2 | 1 | 2022-11-30 | 100%
Soku | MSC/TA/ME | Main Inlet valves: B) Upgrade valve positioner – obsolete, Discontinued, not longer manufactured | Kene/Lukmon/Theresa/Nsikak | Maintenance & Operations | Raise and obtain MOC including TA approval for new solution to inlet valve | LPNAG/AG2 | 1 | 2022-11-30 | 0%
Soku | MSC/TA/ME | Main Inlet valves: B) Upgrade valve positioner – obsolete, Discontinued, not longer manufactured | Kene/Lukmon/Theresa/Nsikak | Spares | Order the material, testing and installation | LPNAG/AG2 | 1 | 2022-10-31 | 60% | material ordered PO 26/04/23 so materials on site,vendors to install to be on site on friday to begin installation 03/05 action would be moved to TAM. October...
Soku | MSC/TA/ME | AG2 and LP NAG / Compressor overdue inspections | Kene Odunze | Maintenance & Operations | Carry out Overdue Bundle Change out on LPNAG | LPNAG | 1 | 2023-10-30 | 60% | planned for October. Preparation ongoing. LPNAG bundle change out -bundle is now at siemens yard here in phc. Inspection of bundle should be completed by 3rd week April. about 80% of spares ordered have arrived...20% lef
Soku | MSC/TA/ME | AG2 and LP NAG / Compressor overdue inspections | Kene Odunze | Maintenance & Operations | Carry out Overdue Bundle Change out on AG2 |  | 1 | 2022-10-31 | 100%
Soku | MSC/TA/ME | AG2 / Radial Bearing Failure | Kene Odunze | Maintenance & Operations | Mobilise OEM for the correction of the Radial Bearing Failure on AG2 | AG2 | 1 | 2022-10-31 | 100%
Soku | MSC/TA/ME | AG2 / Gearbox Inspection | Kene Odunze | Maintenance & Operations | Carry out overdue Gearbox Inspection on AG2 and close out the remedial actions. | AG2 | 1 | 2023-06-30 | 45% | 99% of Materials on site. Awaiting Contract Renewal. October
Soku | MSC/TA/ME | LP NAG / HP Comp Seal gas vent DE LL alarm | Kene Odunze | Maintenance & Operations | LP NAG / HP Comp Seal gas vent DE LL alarm | LP NAG | 1 | 2022-10-31 | 100%
Soku | IVD Sustainability | IVD Sustainability – Actions for Improvement Plan | Kebin Ofori | Maintenance & Operations | Confirm under which process IVD is captured + identify process owner |  | 1 | 2022-12-31 | 100%
Soku | IVD Sustainability | IVD Sustainability – Actions for Improvement Plan | Kebin Ofori | Maintenance & Operations | Capture IVD Ways of Working and Actions under existing process (MTO?) |  | 1 | 2022-12-31 | 100%
Soku | IVD Sustainability | IVD Sustainability – Actions for Improvement Plan | Kebin Ofori | Maintenance & Operations | Define R&R matching the WoW and Actions |  | 1 | 2022-12-31 | 100%
Soku | IVD Sustainability | IVD Sustainability – Actions for Improvement Plan | Kebin Ofori | Maintenance & Operations | In Reliability Impr Strategy Check in: add Check in on Process, incl key R&R. |  | 1 | 2022-12-31 | 10%
Soku | IVD Sustainability | IVD Sustainability – Actions for Improvement Plan | Kebin Ofori | Maintenance & Operations | Appoint and confirm persons for R&R (note: can be batch ways, may change over time) |  | 1 | 2022-12-31 | 50%
Soku | IVD Sustainability | Actions managed through existing systems/process and included in Asset plans with report out to Asset Mgt to drive accountability | Kebin Ofori | Maintenance & Operations | Tool for action management to be confirmed (likely Fit4 or IAF = Power BI = IVD tracking tool. High level actions into Fit4) |  | 1 | 2022-12-31 | 100%
Soku | IVD Sustainability | Actions managed through existing systems/process and included in Asset plans with report out to Asset Mgt to drive accountability | Casmir/Uju/Victor | Maintenance & Operations | Load the open actions in selected Tool(s |  | 1 | 2022-06-30 | 100% | Open actions are captured in Fit4MTO tool
Soku | IVD Sustainability | Actions managed through existing systems/process and included in Asset plans with report out to Asset Mgt to drive accountability | Casmir/Uju/Victor | Maintenance & Operations | Progress monitoring to be captured in 1 of the existing cadence/meetings (ref WoW) |  | 1 | 2022-12-31 | 100% | We monitor progress in weekly cadence meeting
Soku | IVD Sustainability | Budget and resources available: sufficient and in time | Casmir/Uju/Victor | Maintenance & Operations | Pull in actions from fit4 Tool into AIP and ACP including supporting info like Risk and justification |  | 1 | 2022-12-31 | 20%
Soku | IVD Sustainability | Budget and resources available: sufficient and in time | AMIL/AMIS | Maintenance & Operations | Establish longer term outlook for budget and resource for IVD actions (longer term planning at least 3 yrs ahead to give adequate time for alignment and approval) |  | 1 | 2022-12-31 | 10%
Soku | IVD Sustainability | Governance on Quality and Progress, addressing the threats in a sustainable way | Kebin Ofori | Maintenance & Operations | Ref IVD WoW / include Assurance review (cold eye review) into WoW. Confirm in R&R who sits in governance team (steering committee to review progress and quality) (includes Monitoring against set KPIs |  | 1 | 2023-06-30 | 0%
Soku | IVD Sustainability | Governance on Quality and Progress, addressing the threats in a sustainable way | Kebin Ofori | Maintenance & Operations | Consider to integrate in agenda of existing quarterly MTO steering committee. Consider specific attendees for providing the cold eyes. |  | 1 | 2023-06-30 | 50%
Soku | MTO Improvement | Adequate action owners are assigned (competent and available), appreciating difference between Short and Long term. For Long term: supporting teams, not Front Line (assign by threat owner, along with required mandate) | Chimuanya/Musa | Maintenance & Operations | Criteria to be set (competence, available time, mandate) for action owner |  | 1 | 2023-02-28 | 0% | PUM and TL to cascade criteria over some time to get all conversant with it
Soku | MTO Improvement | Adequate action owners are assigned (competent and available), appreciating difference between Short and Long term. For Long term: supporting teams, not Front Line (assign by threat owner, along with required mandate) | Chimuanya/Musa |  | Agree on handshake (including criteria) with Action Owner (in case of member from supporting team, i.e. Outside asset team). |  | 1 | 2023-02-28 | 20% | ongoing improvement process
Soku | MTO Improvement | Adequate action owners are assigned (competent and available), appreciating difference between Short and Long term. For Long term: supporting teams, not Front Line (assign by threat owner, along with required mandate) | Chimuanya/Musa |  | Include agreed actions in GPA of action owner or include: Allocate 20% of time for MTO threats/actions |  | 1 | 2023-03-30 | 20% | GPAs for year 2023 should have line item reading : 'Have 0 overdue MTO T/Os assigned to me"
Soku | MTO Improvement | Longer Term Actions are followed up in agreed timescale | Chimuanya/Musa |  | In case of challenges: escalate to Monthly meeting (Asset governance team) |  | 1 | 2022-11-30 | 100% | Completed
Soku | MTO Improvement | Common Action for MTO: Organize Awareness session on adjustments in the process. | Casmir/Uju/Victor |  | Monthly cadence to be in place with clear terms of reference and claritify of participants and their role |  | 1 | 2022-11-30 | 100% | MTO FP connects, Monthly MTO meetings, MTO Process council, all these are forums where updates are shared
Soku | MTO Improvement | Common Action for MTO: Organize Awareness session on adjustments in the process. | Casmir/Uju/Victor |  | Decisions are prepared by proposal by action owner(Actions to address threats properly) (including reasoning, risk level, mitigating actions |  | 1 | 2022-11-30 | 40% | This is drven by the Rel Engineers during MTO scoring sessions.
Soku | ACP/AIP | ACP in place in time and with right quality to serve as input for budget request and resource planning | Tamunoemi Efebeli & RES |  | Agree on content requirement and expectations (ref MEC_RP_03. Maintenance Reference Plan to be included. ACP to give 5-year outlook |  | 1 | 2023-12-30 | 40% | Discuss and engage MEC SPO to start a cadence on ACP dev. To start discussion with John on Friday. ACP is already being put together
Soku | ACP/AIP | ACP in place in time and with right quality to serve as input for budget request and resource planning | Tamunoemi Efebeli & RES |  | Appoint Lead and contributors for ACP for the other assets |  | 1 | 2022-12-30 | 100% | Identified. Emi Efebeli (Lead), Ivovi Ajiri, Sani Mukthar, Uju Okwuosa, Casmir Ojobor, Victor Ndukwe
Soku | ACP/AIP | ACP in place in time and with right quality to serve as input for budget request and resource planning | Tamunoemi Efebeli & RES |  | Set Milestone dates, in line with OP cycle |  | 1 | 2022-12-30 | 20% | This would be determined as we start cadence.
Soku | ACP/AIP | IVD to be captured as tactics in AIP (info: currently managed by ASM), milestones: M1 – M5 | Casmir/Uju/Victor |  | Include IVD tactics and its charters in AIP (M2) under related improvement theme. Tactics to be included in Fit4. |  | 1 | 2022-12-30 | 20%
Soku | ACP/AIP | IVD to be captured as tactics in AIP (info: currently managed by ASM), milestones: M1 – M6 | Casmir/Uju/Victor |  | Confirm that Critical Compressor and Power Generation is key improvement theme for AIP (M1) - check |  | 1 | 2022-12-30 | 60% | uju to check this
Soku | ACP/AIP | ACP and AIP to deliver a 5-year outlook for activities and related cost (covered under CSF). (AIP is currenlty 3-years) | Tamunoemi Efebeli & RES |  | ACP and AIP to deliver a 5-year outlook for activities and related cost (covered under CSF). (AIP is currenlty 3-years) |  | 1 | 2022-12-30 | 50%
Soku | ACP/AIP | ACP and AIP to deliver a 5-year outlook for activities and related cost (covered under CSF). (AIP is currenlty 3-years) | Tamunoemi Efebeli & RES |  | ACP Owner needs to approve ACP and AIP. |  | 1 | 2022-12-30 | 0%
Soku | ACP/AIP | Partners in agreement with plans including 5-year outlook íncl req’d budget | AMIL/AMIS |  | Capture outcome of discussion of plans with JV Partners/Regulators (MoM) ie 5-year outlooks including projected budget outlook. |  | 1 | 2022-12-30 | 0%
Soku | ACP/AIP | Approval for Deferment of activities subject to deferral process (Ref MEC_RP_06 | Chimuanya/Musa |  | Approval for Deviations of activities subject to deferral process (Ref MEC_RP_06) Procedure for Non-HSSE CE tasks: This addresses how we treat Production critical deferrments and play it back to the targets for the year. |  | 1 | 2023-06-30 | 0%
Soku | Budget Process | Budget available in time for spending (e.g. Ordering materials) (for lead time > 6 months this needs notional budget | Kene Odunze |  | Using 5-year outlook: Identify/list and earmark in ACP the items with lead time which need notional budget to place PO in time (annually) |  | 1 | 2023-03-31 | 100%
Soku | Budget Process | Budget available in time for spending (e.g. Ordering materials) (for lead time > 6 months this needs notional budget | Kene Odunze |  | Raise budget request for all items that need notional budget for the following year(s) as per list |  | 1 | 2023-03-31 | 100%
Soku | Budget Process | Budget available in time for spending (e.g. Ordering materials) (for lead time > 6 months this needs notional budget | AMIL/AMIS |  | Start request process for notional budget (consider to detail out these steps, we can do with Finance Advisor) for Mtce critical spares with long lead items |  | 1 | 2023-03-31 | 30% | Notional Budget for Mtce CAPEX 2023 has been approved.
Soku | Budget Process | Budget 3-year cycle in place | AMIL/AMIS |  | Incorporate this in the ACP and AIP multi-year cycle to take care of this |  | 1 | 2023-03-31 | 0%
Soku | Budget Process | Budget 3-year cycle in place. Notional Budgets used where applicable. | AMIL/AMIS |  | Notional Budgets: Get comfort that it has been approved internally in DRB (Wessel/Ian) b) Support from external partner with a) and b) Getting approval from finance Load in SAP |  | 1 | 2023-03-31 | 0%
Soku | Budget Process | In case of regrets: consequence to be communicated to decision maker and stakeholders and production targets to be re-calibrated (reliability impact) | AMIL/PUM |  | Key Milestone: Yearly Handshake for Production Target shall include budget position/regrets |  | 1 | 2023-03-31 | 0%
Soku | Budget Process | In case of regrets: consequence to be communicated to decision maker and stakeholders and production targets to be re-calibrated (reliability impact) | AMIL/PUM |  | Budget Regrets: pull together regrets and impact on production; Adjust production targets as neededBudget |  | 1 | 2023-03-31 | 0%
Soku | Budget Process | Budget for planned activities is spent on the planned activities, not on emerging activities | AMIL/PUM |  | Key is to make sure planned activities are mature enough to execute the activity (execution capacity/ readiness). Maturity on contracting part before budget Activitely monitor and manage execution capacity vs planned activities |  | 1 | 2023-03-31 | 40% | DRB sessions with DMD discuss the execution readiness.

## Status
Completion Status
Completed
Ongoing
Not started

## Due Status
Due Status | Id
Overdue | 1
Due in 30 days | 2
Due 30 to 60 days | 3
Over 60 days | 4
Completed | 5

## System Owners
System Owner | PU
Didi Otobo | Tunu
Vincent Atey | Tunu
Chimuanya Onyejekwe | Soku
Musa Nabage | Soku

## Pillars
Pillars
Maintenance & Operations
Spares
Proactive Technical Monitoring
Capabilities
Project to Asset

## PUs
PU | Title
Soku | SOKU INTEGRATED VALUE DELIVERY SUSTAIN
Tunu | INTEGRATED VALUE DELIVERY TUNU NODE COMPRESSOR AVAILABILITY
Sea Eagle | SEA EAGLE COMPRESSORS AND POWER GENERATION IVD