## Deliverables
PU | Process Steps | Activity | Action Lead | Pillars | Deliverables | Equipment | Weight | Close out Date | % Completion | Comment | Comment Date
Gbaran | System Selection And Scope | Resource the IVD plan | Kebin Ofori |  | Engage the task owners to conform resources needed and readiness to deliver |  | 1 | 2022-09-30 | 100%
Gbaran | System Selection And Scope | Identify Improvement Goal | Casmir Ojobor |  | Outline clear targets |  | 1 | 2022-09-30 | 100%
Gbaran | System Selection And Scope | Kick Off meeting stakeholders | Uju Okwuosa |  | Engage AGG team on IVD |  | 1 | 2022-09-30 | 100%
Gbaran | System Selection And Scope | Kick Off meeting stakeholders | Uju Okwuosa |  | Engage PS LT on IVD plans |  | 1 | 2022-09-30 | 100%
Gbaran | System Selection And Scope | Kick Off meeting stakeholders | Uju Okwuosa |  | Engage Asset Manager IVD plans |  | 1 | 2022-09-30 | 100%
Gbaran | System Selection And Scope | Kick Off meeting stakeholders | Uju Okwuosa |  | Name System Owners on IVD plans |  | 1 | 2022-09-30 | 100%
Gbaran | System Selection And Scope | Kick Off meeting stakeholders | Uju Okwuosa |  | Agree Cadence, DRB and Success measures |  | 1 | 2022-09-30 | 100%
Gbaran | MTO | Identify Threats on Fit4MTO database | Uju Okwuosa | Maintenance & Operations | Download threats and actions on MTO with impact on system |  | 1 | 2022-09-30 | 100%
Gbaran | MTO | Identify Threats on Fit4MTO database | Uju Okwuosa | Maintenance & Operations | Analyse data and identify threats with deferment, flaring impact, equipment with low availability |  | 1 | 2022-09-30 | 100%
Gbaran | MTO | Identify Bad actors (Review past trips and RCAs) | Uju Okwuosa | Maintenance & Operations | Review historical trip logs |  | 1 | 2022-09-30 | 100%
Gbaran | MTO | Identify Bad actors (Review past trips and RCAs) | Uju Okwuosa | Maintenance & Operations | Identify causes of trips |  | 1 | 2022-09-30 | 100%
Gbaran | MTO | Identify Bad actors (Review past trips and RCAs) | Uju Okwuosa | Maintenance & Operations | Review completed RCAs from past events |  | 1 | 2022-09-30 | 100%
Gbaran | MTO | Identify Bad actors (Review past trips and RCAs) | Uju Okwuosa | Maintenance & Operations | Download and review failure history on SAP |  | 1 | 2022-09-30 | 100%
Gbaran | MTO | Identify Bad actors (Review past trips and RCAs) | Uju Okwuosa | Maintenance & Operations | Enumerate common themes |  | 1 | 2022-09-30 | 100%
Gbaran | MSC/TA/ME | AGC blow down valve failure / Passing Valves / Maintenance on boundary valves Blown down valve not passing | Bosini Oghenevwogaga /Charles Ogbuehi | Maintenance & Operations | Confirm there is an active PM program for leak testing; greasing; stroke testing during plant down time |  | 1 | 2023-04-30 | 100% | 28/04/2023 we have these. greasing done in service....to confirm leak testing is part of other activities . Confirm leak test done as PM
Gbaran | MSC/TA/ME | AGC blow down valve failure / Passing Valves / Maintenance on boundary valves. Blown down valve not passing | Bosini Oghenevwogaga /Charles Ogbuehi | Maintenance & Operations | ESD/BDV maintenance strategy to be defined across unit: including PM for Overhaul valve and ACP coverage for Ultimate Replacement (end of normal life) ; maintenance covered in PM |  | 1 | 2022-04-30 | 40% | 28/04/23 Obsolescence mgt plan for these to be developed starting next month as per TA commitment. PMs available? pls confirm...
Gbaran | MSC/TA/ME | AGC blow down valve failure / Passing Valves / Maintenance on boundary valves ESD.BDV’s are covered by SIL study (IPF/SIFpro) | Bosini Oghenevwogaga /Charles Ogbuehi | Maintenance & Operations | ESD/BDV maintenance SIL. Confirm for all ESD. BDV's. |  | 1 | 2023-04-30 | 0% | 28/04/23 This looks like 100% but need to clarify...
Gbaran | MSC/TA/ME | AGC blow down valve failure / Passing Valves / Maintenance on boundary valves Start-up sequence of AGC compressor not interrupted because of malfunction proximity switch actuator BDV | IT Ekanem / Njoku Richard | Spares | Follow up for delivery of the new BDV (incl. actuator, solenoid and proximity switches) on order |  | 1 | 2023-03-30 | 100% | Delivered
Gbaran | MSC/TA/ME | AGC blow down valve failure / Passing Valves / Maintenance on boundary valves Start-up sequence of AGC compressor not interrupted because of malfunction proximity switch actuator BDV | IT Ekanem / Njoku Richard | Maintenance & Operations | Plan and carry out the installation of the new BDV; Reconfirm scope in the 2023 turnaround. |  | 1 | 2023-08-30 | 50% | in scope for July
Gbaran | MSC/TA/ME | AGC blow down valve failure / Passing Valves / Maintenance on boundary valves Stem protected against weather to avoid water and dirt build-up causing corrosion/erosion | IT Ekanem / Njoku Richard | Maintenance & Operations | Condition check (cleanliness/condition) of proximity switches covered by Operator Round FLM or task captured in PM task list. |  | 1 | 2023-06-30 | 0% | 28/04/23 check MJR for condition check in proximity switches
Gbaran | MSC/TA/ME | AGC blow down valve failure / Passing Valves / Maintenance on boundary valves Actuator has sufficient torque to close the valve | IT Ekanem / Njoku Richard | Spares | Define options to prevent water ingress (I.e Chinese cap. actuator, solenoid and proximity switches) Order and Install. |  | 1 | 2023-11-30 | 0% | 28/04/23 TL to check if necessary to have chinese caps for this. to revert by next week. VAlves built to accomodate water ingress, check what option works better
Gbaran | MSC/TA/ME | AGC Seal Gas Issues New seal gas heater avoids condensation of liquids which block up filter | Kene Odunze/Abaass Kabir/Agabi Lawson | Spares | Expedite delivery of new seal gas heater (Q1-23) for AGC1 |  | 1 | 2023-03-31 | 100% | 28/04/23 New seal Gas Heater installed.
Gbaran | MSC/TA/ME | AGC Seal Gas Issues New seal gas heater avoids condensation of liquids which block up filter | Solomon/Abass/Lawson/Chiemezie | Maintenance & Operations | Installation and commissioning of the new seal gas heater for AGC1 |  | 1 | 2023-05-31 | 100% | 28/04/23 New seal Gas Heater installed. Confirm Performance.
Gbaran | MSC/TA/ME | AGC Seal Gas Issues Seal gas liquids drain continuous in open position when in operation (continuous drain) | Akinlolu Haruna/Ibrahim Saheed | Maintenance & Operations | Check operator round (FLM) scope for seal gas filter drain valve in open position and add if necessary |  | 1 | 2023-05-31 | 0% | 28/04/2023 Mech to check with operations team to agree on right positiion of valve
Gbaran | MSC/TA/ME | AGC Seal Gas Issues Seal gas liquids drain continuous in open position when in operation (continuous drain) | Akinlolu Haruna/Ibrahim Saheed | Maintenance & Operations | Consider making valve locked open, risk assses and pursue change through MoC |  | 1 | 2023-05-31 | 0% | same as above
Gbaran | MSC/TA/ME | AGC Seal Gas Issues Seal gas flow transmitters operating in range (ability to re-calibrate in range) | IT Ekanem / Njoku Richard | Spares | Expedite delivery of new transmitters (Q1-23) |  | 1 | 2023-03-31 | 0% | 28/04/23 Seal gas transmitters not known to be faulty. Generally transmitters have been ordered, lets know the status. Uju to ask Kene
Gbaran | MSC/TA/ME | AGC Seal Gas Issues Seal gas flow transmitters operating in range (ability to re-calibrate in range) | IT Ekanem / Njoku Richard | Maintenance & Operations | Installation and commissioning of the new transmitters |  | 1 | 2023-05-31 | 0%
Gbaran | MSC/TA/ME | AGC Seal Gas Issues All instrumentation on Seal gas Systems correct design (range) and in good condition | IT Ekanem / Njoku Richard | Maintenance & Operations | Review design and condition of all instrumentations on the Seal gas Systems |  | 1 | 2023-03-31 | 0% | why this?
Gbaran | MSC/TA/ME | AGC Seal Gas Issues All instrumentation on Seal gas Systems correct design (range) and in good condition | IT Ekanem / Njoku Richard | Maintenance & Operations | List instrumentation that needs 1:1 replacement on the Seal gast systems. |  | 1 | 2023-03-31 | 0%
Gbaran | MSC/TA/ME | AGC Seal Gas Issues All instrumentation on Seal gas Systems correct design (range) and in good condition | IT Ekanem / Njoku Richard | Maintenance & Operations | Raise Notifications for the changes in instrumentations. |  | 1 | 2023-03-31 | 0%
Gbaran | MSC/TA/ME | AGC Seal Gas Issues All instrumentation on Seal gas Systems correct design (range) and in good condition | IT Ekanem / Njoku Richard | Maintenance & Operations | List instrumentation that needs modification |  | 1 | 2023-03-31 | 0%
Gbaran | MSC/TA/ME | AGC Seal Gas Issues All instrumentation on Seal gas Systems correct design (range) and in good condition | IT Ekanem / Njoku Richard | Maintenance & Operations | Obtain an approved MoC for the proposed changes in instrumentations on the seal gas system. |  | 1 | 2023-03-31 | 0%
Gbaran | MSC/TA/ME | AGC Seal Gas Issues All instrumentation on Seal gas Systems correct design (range) and in good condition | IT Ekanem / Njoku Richard | Maintenance & Operations | Obtain Specification of new modified instrumentation and place an order for procurement. |  | 1 | 2023-06-30 | 0%
Gbaran | MSC/TA/ME | Instrument Air Compressors – Freeze Common HMI Manage Reliability Existing HMI (until new HMI installed) | Uju Okwuosa/Richard | Spares | Conduct structured Investigation into issues with IA compressors (HMI freezes in 2022), to understand and confirm the causes for the problems |  | 1 | 2023-06-30 | 0% | 24/03/23: To connect with Mtce team lead to understand current stats and next steps
Gbaran | MTO | Instrument Air Compressors – Freeze Common HMI Manage Reliability Existing HMI (until new HMI installed) | Uju Okwuosa/Richard | Maintenance & Operations | HMI: Once root cause(s) are confirmed, corrective actions to be defined and captured in MTO for tracking. |  | 1 | 2023-06-30 | 0%
Gbaran | MTO | Instrument Air Compressors – Freeze Common HMI Info: issues in 2012-2020 related to OPC server 2020: OPC server upgraded to PK controller, reduced problems. | Uju Okwuosa/ Abdul | Maintenance & Operations | Investigate Electric Motor failures (2020). 1st replaced, 2nd about to be replaced. Main root cause yet to be confirmed (lubrication or other?) |  | 1 | 2023-06-30 | 10% | 24/03/23 ; decide on date to start RCA on electric motor failure New motor procured awaiting installation
Gbaran | MTO | Instrument Air Compressors – Freeze Common HMI Info: issues in 2012-2020 related to OPC server 2020: OPC server upgraded to PK controller, reduced problems. | Uju Okwuosa | Maintenance & Operations | Electric Motors: Once root cause(s) are confirmed, Define corrective actions and track to closure using MTO |  | 1 | 2023-07-03 | 0%
Gbaran | MSC/TA/ME | Fire & Gas Detection Issues #1 Accelerate the delivery of alignment piece (on order) | IT Ekanem / Njoku Richard | Maintenance & Operations | Confirm spec for the alignment piece (information to order the piece) – new model |  | 1 | 2023-01-15 | 100%
Gbaran | MSC/TA/ME | Fire & Gas Detection Issues #1 Accelerate the delivery of alignment piece (on order) | IT Ekanem / Njoku Richard | Maintenance & Operations | New model included in SAP (CMMS) – coding - DONE |  | 1 | 2023-01-15 | 100%
Gbaran | MSC/TA/ME | Fire & Gas Detection Issues #1 Accelerate the delivery of alignment piece (on order) | IT Ekanem / Njoku Richard | Maintenance & Operations | Make Requisition for alignment tool DONE |  | 1 | 2023-01-15 | 100%
Gbaran | MSC/TA/ME | Fire & Gas Detection Issues #1 Accelerate the delivery of alignment piece (on order) | IT Ekanem / Njoku Richard | Spares | Engage C&P team to expedite delivery (no issues with funding at the moment) |  | 1 | 2023-03-15 | 0% | Charles to meet with SC mgr for expedition of this
Gbaran | MSC/TA/ME | Fire & Gas Detection Issues #1 Accelerate the delivery of alignment piece (on order) | IT Ekanem / Njoku Richard | Maintenance & Operations | Demonstration on use of new model of alignment kit 1) study the manual and 2) do a demonstration to the rest of the mtc team |  | 1 | 2023-07-15 | 0%
Gbaran | MSC/TA/ME | Fire & Gas Detection Issues #2 Maintenance frequency to clean lenses and further campaign/preventive maintenance, including MJR | Uju Okwuosa | Maintenance & Operations | Review Maintenance Strategy (freq) and scope (which detectors). Consider resource/ man power availability. Current 1Y, probably better 6M. Cleaning lenses maybe need more often (3M) but resource impact. RCM |  | 1 | 2023-06-30 | 0% | 24/03/23: F&G is for SIF studies, to contact Awe and decide on plan going forward
Gbaran | MSC/TA/ME | Fire & Gas Detection Issues #2 Maintenance frequency to clean lenses and further campaign/preventive maintenance, including MJR | Uju Okwuosa | Maintenance & Operations | MJR content: Improve existing and develop new MJR, including the work preparation (e.g. requirement for manlift, or scaffold etc). Note: cleaning of lenses is already included in MJR. Include in MJR all equipment in the loop like cabling, surge protection barrier etc. |  | 1 | 2023-06-30 | 0%
Gbaran | MSC/TA/ME | Fire & Gas Detection Issues #2 Maintenance frequency to clean lenses and further campaign/preventive maintenance, including MJR | Uju Okwuosa | Maintenance & Operations | Check with Soku experience with F&G and adopt possible learnings. |  | 1 | 2023-06-30 | 0%
Gbaran | MSC/TA/ME | Fire & Gas Detection Issues #3 Scope for the optical detector replacements (On the run or during TAM) | IT Ekanem / Njoku Richard | Maintenance & Operations | Obtain Spec/datasheet for new detector (:new gas detector already installed in new section, use this |  | 1 | 2023-05-30 | 0%
Gbaran | MSC/TA/ME | Fire & Gas Detection Issues #3 Scope for the optical detector replacements (On the run or during TAM) | IT Ekanem / Njoku Richard | Maintenance & Operations | Start Simple (single discipline) MoC required, to capture documentation changes, Bill of Material and Coding and mods to fixing bracket and hangers Identify Flocs (info: between 50-100 total), also include remote locations |  | 1 | 2023-04-30 | 0%
Gbaran | MSC/TA/ME | Fire & Gas Detection Issues #3 Scope for the optical detector replacements (On the run or during TAM) | IT Ekanem / Njoku Richard | Maintenance & Operations | Update SAP info Follow normal mtc process: include Notification and do work preparation |  | 1 | 2023-06-30 | 0%
Gbaran | MSC/TA/ME | Fire & Gas Detection Issues #3 Scope for the optical detector replacements (On the run or during TAM) | IT Ekanem / Njoku Richard | Maintenance & Operations | Replacement of gas detectors on the run by Mtc team. Gas Detectors removed: keep as spare. |  | 1 | 2023-08-30 | 0% | 28/04/23...what does this mean?
Gbaran | MSC/TA/ME | Fire & Gas Detection Issues #3 Scope for the optical detector replacements (On the run or during TAM) | IT Ekanem / Njoku Richard | Maintenance & Operations | Point gas detector: obsolete, upgrade available. Phase out old detectors, order new once and install these |  | 1 | 2023-06-30 | 0%
Gbaran | MSC/TA/ME | Gas Turbine Air Flow Switches Current (old type spring): timely change out and sufficient spares available to do so | IT Ekanem/Njoku Richard/Kene Odunze | Maintenance & Operations | Confirm replacement frequency of air flow switches |  | 1 | 2023-03-31 | 0% | 28/04/23 Mtce strategy is replace when bad. we are moving to transmitter type. Ekeleme to check and confirm
Gbaran | MSC/TA/ME | Gas Turbine Air Flow Switches Current (old type spring): timely change out and sufficient spares available to do so | IT Ekanem/Njoku Richard/Kene Odunze | Maintenance & Operations | Set and provide spares needed until upgraded flow switch is installed |  | 1 | 2023-04-30 | 0% | to check
Gbaran | MSC/TA/ME | Gas Turbine Air Flow Switches Current (old type spring): timely change out and sufficient spares available to do so | IT Ekanem/Njoku Richard/Kene Odunze | Maintenance & Operations | Create a new Maintenance Plan for replacement of air flow switches with frequency |  | 1 | 2023-07-31 | 0%
Gbaran | MSC/TA/ME | Gas Turbine Air Flow Switches Current (old type spring): timely change out and sufficient spares available to do so | IT Ekanem/Njoku Richard/Kene Odunze | Maintenance & Operations | Current overdue replacements: Raise notification and replace soonest |  | 1 | 2023-03-31 | 0%
Gbaran | MSC/TA/ME | Gas Turbine Air Flow Switches Current (old type spring): timely change out and sufficient spares available to do so | IT Ekanem/Njoku Richard/Kene Odunze | Maintenance & Operations | Set spares needed until upgraded flow switch is installed |  | 1 | 2023-03-31 | 0%
Gbaran | MSC/TA/ME | Gas Turbine Air Flow Switches Current (old type spring): timely change out and sufficient spares available to do so | IT Ekanem/Njoku Richard/Kene Odunze | Maintenance & Operations | Place Order for replacement of air flow switches. |  | 1 | 2023-03-31 | 0%
Gbaran | MSC/TA/ME | Gas Turbine Air Flow Switches Current (old type spring): timely change out and sufficient spares available to do so | IT Ekanem/Njoku Richard/Kene Odunze | Maintenance & Operations | Expedite and follow up for delivery of switches |  | 1 | 2023-03-31 | 0%
Gbaran | MSC/TA/ME | Gas Turbine Air Flow Switches Upgraded Flow Switch installed and commissioned | IT Ekanem/Njoku Richard/Kene Odunze | Maintenance & Operations | Raise and approved MoC for Upgraded Flow Switch (as per Siemens recommendation) |  | 1 | 2023-03-28 | 0%
Gbaran | MSC/TA/ME | Gas Turbine Air Flow Switches Upgraded Flow Switch installed and commissioned | IT Ekanem/Njoku Richard/Kene Odunze | Maintenance & Operations | Update BoM and Coding in CMMS |  | 1 | 2023-03-01 | 0%
Gbaran | MSC/TA/ME | Gas Turbine Air Flow Switches Upgraded Flow Switch installed and commissioned | IT Ekanem/Njoku Richard/Kene Odunze | Maintenance & Operations | Get approval for Asset Budget |  | 1 | 2023-03-04 | 0% | 28/04/23... get into the CAPEX build...
Gbaran | MSC/TA/ME | Gas Turbine Air Flow Switches Upgraded Flow Switch installed and commissioned | IT Ekanem/Njoku Richard/Kene Odunze | Maintenance & Operations | Raise Notification/ Work Order for upgrade, installation and commissioning |  | 1 | 2023-05-05 | 0%
Gbaran | MSC/TA/ME | Alternators – Preventive Maintenance not planned for and not executed RCM executed PM Tasks loaded in SAP MJR defined | Mohammed Abdul /Okolo Nelson/Uju Okwuosa | Maintenance & Operations | Refer to MTO Fit 4 Initiative #21: Review Gbaran Ubie Equipment Care Plans Existing Initiative action: Develop Maintenance Strategy / Plan for GTG and all Sub-Components. This shall include the Alternators |  | 1 | 2023-06-30 | 0% | 28/04/23 Charles to check for this 05/05/23 there is a 2 yrly plan for the alternators and this is on the CMMS
Gbaran | MSC/TA/ME | Alternators – Preventive Maintenance not planned for and not executed RCM executed PM Tasks loaded in SAP MJR defined | Mohammed Abdul/Okolo Nelson /Uju Okwuosa | Maintenance & Operations | Alternator = Sub component Action shall include: Run RCM, develop MJRs, load into SAP and include in Asset Care Plan Note: SNEPCO / BONGA is conducting RCM for their alternators. |  | 1 | 2023-06-30 | 0% | 05/05/23
Gbaran | MSC/TA/ME | GTG Alternators – Preventive Maintenance not planned for and not executed | Uju Okwuosa | Maintenance & Operations | Asset Care Plan to be developed, including Maintenance Reference Plan |  | 1 | 2024-06-30 | 0% | 24/03/23: Included in budget for OP '23. Changed close out date to 2024
Gbaran | MSC/TA/ME | Alternators – Preventive Maintenance not planned for and not executed | Mohammed Abdul/ Okolo Nelson | Maintenance & Operations | Review preservation procedures for equipment (alternator) in warehouse. |  | 1 | 2023-04-30 | 0%
Gbaran | MSC/TA/ME | Alternators – Preventive Maintenance not planned for and not executed | Mohammed Abdul/ Okolo Nelson | Maintenance & Operations | Full spare alternator in warehouse: condition unknown – to be inspected + updating preservation maintenance |  | 1 | 2023-04-30 | 0% | 05/05/23 Team to develop preservative care plan for this
Gbaran | MSC/TA/ME | Alternators – Preventive Maintenance not planned for and not executed | Mohammed Abdul/ Okolo Nelson | Maintenance & Operations | Carry out Alternators A/B/C: Milestone inspections which are overdue |  | 1 | 2023-07-30 | 0%
Gbaran | MSC/TA/ME | Obsolesence management incl IA Comp HMI, C2Link Obsolesence in place as per AMS: Integrated in ACP for critical equipment (e.g. DCS and Control Systems). (note: MRP as source) | Bosini Oghenevwogaga /Charles Ogbuehi | Maintenance & Operations | 1) Proactive assessment on date when obsolescence is expected of systems/equipment (horizon: up to end of field life – Multiyear outlook) |  | 1 | 2023-06-30 | 30% | 28/04/23 vendor was on site last week...to look at obsolescence. Awaiting report post vendors visit for cost implication of upgrade
Gbaran | MSC/TA/ME | Obsolesence management incl IA Comp HMI, C2Link Obsolesence in place as per AMS: Integrated in ACP for critical equipment (e.g. DCS and Control Systems). (note: MRP as source) | Bosini Oghenevwogaga /Charles Ogbuehi | Maintenance & Operations | Info: For Long Lead Items: reference is made to IVD sustain topics for Soku. (note: phased approach). |  | 1 | 2023-07-01 | 0%
Gbaran | MSC/TA/ME | Obsolesence management incl IA Comp HMI, C2Link Obsolesence in place as per AMS: Integrated in ACP for critical equipment (e.g. DCS and Control Systems). (note: MRP as source) | Bosini Oghenevwogaga /Charles Ogbuehi | Maintenance & Operations | Approach for long lead items and budget request to be embedded in work process/system, including R&R and annual key milestones |  | 1 | 2023-07-02 | 0%
Gbaran | MSC/TA/ME | Obsolesence management incl IA Comp HMI, C2Link Budget approved and available in time | Bosini Oghenevwogaga /Charles Ogbuehi |  | On Annual basis: Collect input from Asset team as scope for the Obsolesence plan |  | 1 | 2023-04-30 | 0%
Gbaran | MSC/TA/ME | Obsolesence management incl IA Comp HMI, C2Link Budget approved and available in time | Bosini Oghenevwogaga /Charles Ogbuehi | Maintenance & Operations | Specific for Gbaran Ubie: (Info Budget for 2023 has been closed) Action: for GU obsolescence scope (e.g. IA Comp HMI and C2Link): to be included timely for 2024 budget |  | 1 | 2023-04-30 | 0%
Gbaran | MSC/TA/ME | Obsolesence management incl IA Comp HMI, C2Link ACP: annual update, also on Obsolesence management | Bosini Oghenevwogaga /Charles Ogbuehi | Maintenance & Operations | Info: OP – 5 year outlook JV partners: request for annual budget AND provide outlook for multiyear budget. Include info on business impact of elements |  | 1 | 2023-07-31 | 0%
Gbaran | MSC/TA/ME | Obsolesence management incl IA Comp HMI, C2Link ACP: annual update, also on Obsolesence management | Bosini Oghenevwogaga /Charles Ogbuehi | Maintenance & Operations | Specific for Gbaran Ubie: Explore possibility to tap into OPEX budget for 2023 |  | 1 | 2023-07-31 | 0%
Gbaran | MSC/TA/ME | Obsolesence management incl IA Comp HMI, C2Link Monitor, Track and Control implementation | Bosini Oghenevwogaga /Charles Ogbuehi | Maintenance & Operations | Outcome to be aligned with input for 2024. |  | 1 | 2023-07-31 | 0%
Gbaran | MSC/TA/ME | Export Pumps – Preventive Maintenance not planned for and not executed | Solomon/Abass/Lawson/Chiemezie | Maintenance & Operations | Refer to MTO Fit 4 Initiative #21: Review Gbaran Ubie Equipment Care Plans |  | 1 | 2023-07-31 | 100% | 28/04/23 Solomon to send mtce plan no as evidence of this availability
Gbaran | MSC/TA/ME | Export Pumps – Preventive Maintenance not planned for and not executed | Solomon/Abass/Lawson/Chiemezie | Maintenance & Operations | Include New Initiative action: Develop Maintenance Strategy / Plan for Export Pumps all Sub-Components. |  | 1 | 2023-07-31 | 100%
Gbaran | MSC/TA/ME | Export Pumps – Preventive Maintenance not planned for and not executed | Solomon/Abass/Lawson/Chiemezie | Maintenance & Operations | Action shall include: Run RCM, develop MJRs, load into SAP and include in Asset Care Plan |  | 1 | 2023-07-31 | 100%
Gbaran | MSC/TA/ME | GTG alternators – Preventive Maintenance not planned for and not executed RCM executed, PM Tasks loaded in SAP, MJR defined | Mohammed Abdul/Okolo Nelson | Maintenance & Operations | Alternator = Sub component Note: SNEPCO / BONGA is conducting RCM for their alternators |  | 1 | 2023-07-31 | 0%
Gbaran | MSC/TA/ME | Competence Enhancement / Capability Management SGT 400 Control System: Local team members trained on Control System | Kene Odunze/Romeo | Capabilities | Identify current experts on SGT400 Control System in SPDC: not available, external support needed for upgraded control system |  | 1 | 2023-03-31 | 0%
Gbaran | MSC/TA/ME | Competence Enhancement / Capability Management SGT 400 Control System: Local team members trained on Control System | Kene Odunze/Romeo | Capabilities | Engage with OEM to identify training material and trainer |  | 1 | 2023-03-31 | 0%
Gbaran | MSC/TA/ME | Competence Enhancement / Capability Management SGT 400 Control System: Local team members trained on Control System | Kene Odunze/Romeo | Capabilities | Compile Training Plan for SGT 400 and other critical equipment Note: recent control system upgrade (PLC system) |  | 1 | 2023-03-31 | 0%
Gbaran | MSC/TA/ME | Competence Enhancement / Capability Management SGT 400 Control System: Local team members trained on Control System | Kene Odunze/Romeo | Capabilities | Identify people that need to be trained |  | 1 | 2023-03-31 | 0%
Gbaran | MSC/TA/ME | Competence Enhancement / Capability Management SGT 400 Control System: Local team members trained on Control System | Kene Odunze/Romeo | Capabilities | Key Gaps: 1) Control: SGT400 Control System 2) Mech Mtc: Compressor DGS change out |  | 1 | 2023-03-31 | 0%
Gbaran | MSC/TA/ME | Competence Enhancement / Capability Management Competence Management Plan in place and actioned | Kene Odunze/Romeo | Capabilities | Mgt Plan for wider scope: including compressors and other key equipment (both PACO and Mechanical) Info: on mechanical Mtc operations: generally no gaps, but: 1 Gap exists for for Dry Gas Seals, training needed |  | 1 | 2023-04-30 | 0%
Gbaran | MSC/TA/ME | Competence Enhancement / Capability Management Competence Management Plan in place and actioned | Kene Odunze/Romeo | Capabilities | Identify activity that will be conducted by Asset Team Then: Definition of Competence Needed |  | 1 | 2023-04-30 | 0%
Gbaran | MSC/TA/ME | Competence Enhancement / Capability Management Competence Management Plan in place and actioned | Kene Odunze/Romeo | Capabilities | Take action to Identify gaps in competence |  | 1 | 2023-04-30 | 0%
Gbaran | MSC/TA/ME | Competence Enhancement / Capability Management Competence Management Plan in place and actioned | Kene Odunze/Romeo | Capabilities | Develop Capability Mgt Plan that addresses the progressing/movement of personnel and make sure multiple persons are training (backup) Gaps: Applies mainly for Mtc |  | 1 | 2023-04-30 | 0% | DRB sessions with DMD discuss the execution readiness.
Gbaran | MSC/TA/ME | Competence Enhancement / Capability Management Competence Management Plan in place and actioned | Kene Odunze/Romeo | Capabilities | Embed Sustainable: Include in Competence Management Framework, and keep it evergreen. For both Ops and Mtc |  | 1 | 2023-04-30 | 0%

## Status
Completion Status
Completed
Ongoing
Not started

## Due Status
Due Status | Id
Overdue | 1
Due in 30 days | 2
Due 30 to 60 days | 3
Over 60 days | 4
Completed | 5

## System Owners
System Owner | PU
Didi Otobo | Tunu
Vincent Atey | Tunu
Chimuanya Onyejekwe | Soku
Musa Nabage | Soku
Bosini Oghenevwogaga | Gbaran
Charles Ogbuehi | Gbaran

## Pillars
Pillars
Maintenance & Operations
Spares
Proactive Technical Monitoring
Capabilities
Project to Asset

## PUs
PU | Title
Soku | SOKU INTEGRATED VALUE DELIVERY SUSTAIN
Tunu | INTEGRATED VALUE DELIVERY TUNU NODE COMPRESSOR AVAILABILITY
Gbaran | Gbaran Ubie – Sustaining the Gains from IVD Flaring Reduction Initiative