## Slide 1: Technical improvement of BOGT LLODs Sluice Gates Operations
BOGT MECHANICAL TEAM

## Slide 2
Technical improvement of BOGT LLODs Sluice Gates Operations
  Production Unit: Central East Hub - Bonny
  Project Owner: Osita Nnajiofor/Brossa Isaac
  Process Custodian: Opel Joel / Victor Essienton.
  Process Focal Point: Okaiwele Anthony.
  Process Stakeholders: Ikechi Amaewhule, Opel Joel, Okaiwele Anthony, Bela-Zabe Dumtuaka, Ukpong Nsibiet, Goodi Emoghware, Ireti Omotoso, Opubo Tamunobarabiye.
PROCESS OWNERSHIP
OPPORTUNITY STATEMENT
Conduct Site Assessment – June 2019/ Design Reviews/Approve MOC- Sep. 2019
Secure budget cover – Nov. 2019
Procure and construct sluice gate, stem and other accessories – Nov. 2019 – April . 2020/ Site Mobilization – April - June 2020
End user Utilization and Benefit Tracking – Q3 - Q4 2020
SCOPE
BUSINESS CASE
GOAL
POTENTIAL ROADBLOCKS/ ISSUES
Gross Cost
Material Cost (NGN 250,000)
Machinist cost (NGN150,000)
Technician cost (NGN 150,000)
Soft Benefits:
- Safer unit for operators’ daily routine
- Improved Ops/Mtce. wrench time
- Stress Reduction
COST/BENEFITS
The BOGT LLOD as constructed does not meet environmental standards required for near Shore Oil and Water recovery/ discharge.
The current operations of the BOGT LLODs is challenging and poses a real risk of overflooding the LLOD or releasing of off-spec produced water (above regulatory limit) to Bonny river during periods of heavy rainfall.
Currently, increased surveillance is carried out during this period but this is an abnormal operation with potential for error and avoidable escalations.
This project will implement a medium/long term solution by construction of a rectangular weir across the inlet to the LLOD. Project cost estimate is NGN550K
Key benefits: 1. Ensure the LLOD is operated as designed.
2. Reduce the increased risk of overflooding during heavy rainfalls.
Successful resolution of this problem will:
Ensure the LLOD is operated as designed.
Reduce the increased risk of overflooding during heavy rainfalls.
Eliminate the potential for overflooding the LLOD or releasing of off-spec produced water (above regulatory limit) to Bonny river during periods of heavy rainfall.
Management Commitment.
Successful stakeholder collaboration
Budget cover/Approval
100%
0%
01/09/19
01/04/20
PROCESS STATUS
30%
100%
Health
% Compl
Completion Date
Start Date
Overall Health Status (Current)
Conduct Site Assessment
Design Review/Approve MOC
Secure Budget /assemble Sluice gate
Installation and Commissioning
01 /11/19
01/04/20
Continuous
Gross Hard Benefits*:
Cost saving ($0.8m)
Eliminate potential overflooding of LLOD and Bonny River pollution
30/09/19
30/03/19
30/10/19