## Sheet1
Facility | PO issue and Mobilization | FTO and Off-site Fabrication | Shut Down Activities | Construction | Integration | Pre-com and commissioning | Hand over
AGBD/2 | 10th Oct – 8th Nov 2018 | 25th Oct – 6th Nov, 2018 | 9th Nov- 13th Nov, 2018 | 9th Nov – 20th Dec, 2018 | 4th Jan- 13th Jan, 2019 | 14th Jan- 30th Jan, 2019 | 28th Mar, 2019
IMOR/1 | 28th June & 13th Oct, 2017 | 27th Jul & 4th Aug – 6th Nov, 2017 | 19th Nov – 26 Nov, 2017 | 16th Oct – 30th Nov, 2017 | 28th Nov – 3rd Dec, 2017 | 4th Dec, 2017 – 13th Feb, 2018
OTUM/1 | 3rd Oct, 2018 | 5th Nov – 20th Nov 2017 | 25th May – 2 June, 2018 | 6th June – 10th Aug, 2018 | 15th – 20th July, 2018 | 9th – 15 August, & 22nd Aug - 2018 | 15th Oct, 2019
FORC/4 (Yokri)
IMOR/3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BENS/1 | 10th May, 2020 & 7th June, 2020 | 4th June, 2020 & 18th – 30th July, 2020 | 8th June – 11th July, 2020 | 8th June – 27th July, 2020 | 25th July – 5th August, 2020 | 7th – 20th August, 2020 | 2020-11-01
GBAR/GP | 10th July, 2020 & 7th Aug, 2020 | 4th July, 2019 & 18th – 30th Aug, 2020 | 8th Aug – 11th Aug, 2020 | 8th Aug – 27th Sept, 2020 | 25th Sept – 5th Oct, 2020 | 7th – 20th Oct, 2020 | Feb, 2021
FORC/2 N.B.
OBGN/1 | 10th Feb, 2019 & 7th Mar, 2019 | 4th Mar, 2019 & 18th – 30th Feb, 2019 | 8th Mar – 11th Mar, 2019 | 8th Mar – 27th Apr, 2019 | 25th April – 5th May, 2019 | 7th – 20th May, 2019 | July, 2019
IMOR/2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OPUK/1
ADIB/1 | 10th July, 2020 & 7th Aug, 2020 | 4th July, 2019 & 18th – 30th Aug, 2020 | 8th Aug – 11th Aug, 2020 | 8th Aug – 27th Sept, 2020 | 25th Sept – 5th Oct, 2020 | 7th – 20th Oct, 2020 | Feb, 2021
SOKU/GP | 10th Oct – 8th Nov 2018 | 25th Oct – 6th Nov, 2018 | 9th Nov- 13th Nov, 2018 | 9th Nov – 20th Dec, 2018 | 4th Jan- 13th Jan, 2019 | 14th Jan- 30th Jan, 2019 | 28th Mar, 2019
ESCB/1 | 10th August, 2019 & 7th September, 2019 | 4th Sept, 2019 & 18th – 30th Oct, 2019 | 8th Sept – 11th Oct, 2019 | 8th Sept – 27th Oct, 2019 | 25th Oct – 5th Nov, 2019 | 7th – 20th Nov, 2019 | Mar, 2020
BONN/1 | 10th July, 2020 & 7th Aug, 2020 | 4th July, 2019 & 18th – 30th Aug, 2020 | 8th Aug – 11th Aug, 2020 | 8th Aug – 27th Sept, 2020 | 25th Sept – 5th Oct, 2020 | 7th – 20th Oct, 2020 | Feb, 2021
AHIA/1 | 10th May, 2019 & 7th June, 2019 | 4th June, 2019 & 18th – 30th July, 2019 | 8th June – 11th July, 2019 | 8th June – 27th July, 2019 | 25th July – 5th August, 2019 | 7th – 20th August, 2019 | Nov, 2019
TUNU/1
AGBD/1 | 10th Feb, 2019 & 7th Mar, 2019 | 4th Mar, 2019 & 18th – 30th Feb, 2019 | 8th Mar – 11th Mar, 2019 | 8th Mar – 27th Apr, 2019 | 25th April – 5th May, 2019 | 7th – 20th May, 2019 | July, 2019
UMUE/1 | 10th Jan, 2020 & 7th Feb, 2020 | 4th Feb, 2020 & 18th – 30th Mar, 2020 | 8th Feb – 11th Mar, 2020 | 8th Feb – 27th Mar, 2020 | 25th Mar – 5th Apr, 2020 | 7th – 20th Apr, 2020 | Aug, 2020
OBEL/1 | 10th Oct – 8th Nov 2022 | 25th Oct – 6th Nov, 2022 | 9th Nov- 13th Nov, 2022 | 9th Nov – 20th Dec, 2022 | 4th Jan- 13th Jan, 2022 | 14th Jan- 30th Jan, 2023 | 28th Mar, 2023
KOCR/1 | 10th August, 2019 & 7th September, 2019 | 4th Sept, 2019 & 18th – 30th Oct, 2019 | 8th Sept – 11th Oct, 2019 | 8th Sept – 27th Oct, 2019 | 25th Oct – 5th Nov, 2019 | 7th – 20th Nov, 2019 | Mar, 2020
ISIM/1 | 10th Oct – 8th Nov 2020 | 25th Oct – 6th Nov, 2020 | 9th Nov- 13th Nov, 2020 | 9th Nov – 20th Dec, 2020 | 4th Jan- 13th Jan, 2021 | 14th Jan- 30th Jan, 2021 | 2021-05-01
SOKU/1 | 10th Oct – 8th Nov 2018 | 25th Oct – 6th Nov, 2018 | 9th Nov- 13th Nov, 2018 | 9th Nov – 20th Dec, 2018 | 4th Jan- 13th Jan, 2019 | 14th Jan- 30th Jan, 2019 | 28th Mar, 2019
FORC/3 S.B
NKAL/1 | 10th Oct – 8th Nov 2020 | 25th Oct – 6th Nov, 2020 | 9th Nov- 13th Nov, 2020 | 9th Nov – 20th Dec, 2020 | 4th Jan- 13th Jan, 2021 | 14th Jan- 30th Jan, 2021 | 2021-05-01
OBGN/GP | 10th May, 2019 & 7th June, 2019 | 4th June, 2019 & 18th – 30th July, 2019 | 8th June – 11th July, 2019 | 8th June – 27th July, 2019 | 25th July – 5th August, 2019 | 7th – 20th August, 2019 | Nov, 2019
OGUT/1 | 10th Oct – 8th Nov 2022 | 25th Oct – 6th Nov, 2022 | 9th Nov- 13th Nov, 2022 | 9th Nov – 20th Dec, 2022 | 4th Jan- 13th Jan, 2022 | 14th Jan- 30th Jan, 2023 | 28th Mar, 2023
FORC/GP
OKOL/GP
BONN/GP1 | 10th Jan, 2020 & 7th Feb, 2020 | 4th Feb, 2020 & 18th – 30th Mar, 2020 | 8th Feb – 11th Mar, 2020 | 8th Feb – 27th Mar, 2020 | 25th Mar – 5th Apr, 2020 | 7th – 20th Apr, 2020 | Aug, 2020
OGBO/1
AGBD/GP | 10th Feb, 2019 & 7th Mar, 2019 | 4th Mar, 2019 & 18th – 30th Feb, 2019 | 8th Mar – 11th Mar, 2019 | 8th Mar – 27th Apr, 2019 | 25th April – 5th May, 2019 | 7th – 20th May, 2019 | July, 2019
2019
2018

## 2018_2019 Plan
| Facility | PO issue and Mobilization | FTO and Off-site Fabrication | Shut Down Activities | Construction | Integration | Pre-com and commissioning | Hand over
| IMOR/1 | 28th June & 13th Oct, 2017 | 27th Jul & 4th Aug – 6th Nov, 2017 | 19th Nov – 26 Nov, 2017 | 16th Oct – 30th Nov, 2017 | 28th Nov – 3rd Dec, 2017 | 4th Dec, 2017 – 13th Feb, 2018 | 30th Oct, 2018
| OTUM/1 | 3rd Oct, 2018 | 5th Nov – 20th Nov 2017 | 25th May – 2 June, 2018 | 6th June – 10th Aug, 2018 | 15th – 20th July, 2018 | 9th – 15 August, & 22nd Aug - 2018 | 15th Oct, 2018
| FORC/2 N.B. |  |  | N/A | 12th April – 30th May 2018 | 15th – 20th June 2018 | 15th – 22nd July & 24th – 30th Sept 2018 | 15th Nov., 2018
| FORC/3 S.B |  |  | N/A | 27th June – 30th Sept 2018 | 1st – 10th October, 2018 | 11th – 15th October & 28th – 30th October 2018
OGBO/1
1 | AGBD/2 | 10th May, 2019 & 7th June, 2019 | 4th June, 2019 & 18th – 30th July, 2019 | 8th June – 11th June, 2019 | 8th June – 20th Aug, 2019 | 25th Aug – 15th Sept, 2019 | 7th – 20th Oct, 2019 | Dec, 2019
2 | GBAR/GP | 10th May, 2019 & 7th June, 2019 | 4th June, 2019 & 18th – 30th July, 2019 | 8th June – 11th June, 2019 | 8th June – 27th July, 2019 | 25th July – 5th August, 2019 | 7th – 20th August, 2019 | Nov, 2019
3 | OBGN/1 | 10th Apr, 2019 & 7th June, 2019 | 2nd May, 2019 & 18th – 30th May, 2019 | 8th June – 11thJune, 2019 | 8th Junr – 27th Aug, 2019 | 23rdh Augus – 15th Sep, 2019 | 7th – 20th Oct, 2019 | Dec, 2019
4 | ADIB/1 | 10th Feb, 2019 & 7th Mar, 2019 | 4th Mar, 2019 & 18th – 30th Feb, 2019 | 8th Mar – 11th Mar, 2019 | 8th Mar – 27th Apr, 2019 | 25th April – 5th May, 2019 | 7th – 20th May, 2019 | July, 2019
5 | SOKU/GP | 10th Oct – 8th Nov 2018 | 25th Oct – 6th Nov, 2018 | 9th Nov- 13th Nov, 2018 | 9th Nov – 20th Dec, 2018 | 4th Jan- 13th Jan, 2019 | 14th Jan- 30th Jan, 2019 | 28th Mar, 2019
6 | ESCB/1 | 10th Feb, 2019 & 7th Apr 2019 | 4th Mar, 2019 & 18th – 30th Mar, 2019 | 8th Apr – 11th Apr, 2019 | 8th Apr – 27th jun, 2019 | 25th Oct – 5th Nov, 2019 | 7th – 20th Nov, 2019 | Mar, 2020
7 | BONN/1 | 10th May, 2019 & 7th June, 2019 | 4th June, 2019 & 18th – 30th July, 2019 | 8th June – 11th July, 2019 | 8th June – 27th July, 2019 | 25th July – 5th August, 2019 | 7th – 20th August, 2019 | Nov, 2019
8 | SOKU/1 | 10th Feb, 2019 & 7th Apr, 2019 | 24th Mar, 2019 & 18th – 30th Feb, 2019 | 20th Apr-29 Apr, 2019 | 8th Mar – 30th Apr, 2019 | 30th April – 10th May, 2019 | 7th – 25th May, 2019 | July, 2019
FORC/4 (Yokri)
| IMOR/3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| BENS/1 | 10th May, 2020 & 7th June, 2020 | 4th June, 2020 & 18th – 30th July, 2020 | 8th June – 11th July, 2020 | 8th June – 27th July, 2020 | 25th July – 5th August, 2020 | 7th – 20th August, 2020 | 2020-11-01
| IMOR/2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OPUK/1
| AHIA/1 | 10th Oct – 8th Nov 2020 | 25th Oct – 6th Nov, 2020 | 9th Nov- 13th Nov, 2020 | 9th Nov – 20th Dec, 2020 | 4th Jan- 13th Jan, 2021 | 14th Jan- 30th Jan, 2021 | 2021-05-01
TUNU/1
| AGBD/1 | 10th Feb, 2019 & 7th Mar, 2019 | 4th Mar, 2019 & 18th – 30th Feb, 2019 | 8th Mar – 11th Mar, 2019 | 8th Mar – 27th Apr, 2019 | 25th April – 5th May, 2019 | 7th – 20th May, 2019 | July, 2019
| UMUE/1 | 10th Jan, 2020 & 7th Feb, 2020 | 4th Feb, 2020 & 18th – 30th Mar, 2020 | 8th Feb – 11th Mar, 2020 | 8th Feb – 27th Mar, 2020 | 25th Mar – 5th Apr, 2020 | 7th – 20th Apr, 2020 | Aug, 2020
| OBEL/1 | 10th Oct – 8th Nov 2022 | 25th Oct – 6th Nov, 2022 | 9th Nov- 13th Nov, 2022 | 9th Nov – 20th Dec, 2022 | 4th Jan- 13th Jan, 2022 | 14th Jan- 30th Jan, 2023 | 28th Mar, 2023
| KOCR/1 | 10th August, 2019 & 7th September, 2019 | 4th Sept, 2019 & 18th – 30th Oct, 2019 | 8th Sept – 11th Oct, 2019 | 8th Sept – 27th Oct, 2019 | 25th Oct – 5th Nov, 2019 | 7th – 20th Nov, 2019 | Mar, 2020
| ISIM/1 | 10th Oct – 8th Nov 2020 | 25th Oct – 6th Nov, 2020 | 9th Nov- 13th Nov, 2020 | 9th Nov – 20th Dec, 2020 | 4th Jan- 13th Jan, 2021 | 14th Jan- 30th Jan, 2021 | 2021-05-01
| NKAL/1 | 10th Oct – 8th Nov 2020 | 25th Oct – 6th Nov, 2020 | 9th Nov- 13th Nov, 2020 | 9th Nov – 20th Dec, 2020 | 4th Jan- 13th Jan, 2021 | 14th Jan- 30th Jan, 2021 | 2021-05-01
| OBGN/GP | 10th May, 2019 & 7th June, 2019 | 4th June, 2019 & 18th – 30th July, 2019 | 8th June – 11th July, 2019 | 8th June – 27th July, 2019 | 25th July – 5th August, 2019 | 7th – 20th August, 2019 | Nov, 2019
| OGUT/1 | 10th Oct – 8th Nov 2022 | 25th Oct – 6th Nov, 2022 | 9th Nov- 13th Nov, 2022 | 9th Nov – 20th Dec, 2022 | 4th Jan- 13th Jan, 2022 | 14th Jan- 30th Jan, 2023 | 28th Mar, 2023
FORC/GP
OKOL/GP
| BONN/GP1 | 10th Jan, 2020 & 7th Feb, 2020 | 4th Feb, 2020 & 18th – 30th Mar, 2020 | 8th Feb – 11th Mar, 2020 | 8th Feb – 27th Mar, 2020 | 25th Mar – 5th Apr, 2020 | 7th – 20th Apr, 2020 | Aug, 2020
| AGBD/GP | 10th Feb, 2019 & 7th Mar, 2019 | 4th Mar, 2019 & 18th – 30th Feb, 2019 | 8th Mar – 11th Mar, 2019 | 8th Mar – 27th Apr, 2019 | 25th April – 5th May, 2019 | 7th – 20th May, 2019 | July, 2019
Comp 2018
Comp 2019
Start 2019
By others 2019

## 2018 volume
Facility | PO issue and Mobilization | FTO and Off-site Fabrication | Shut Down Activities | Construction | Integration | Pre-Commissioning | Commissioning | Hand over | Volume Gain BBL
IMOR/1 | 28th June & 13th Oct, 2017 | 27th Jul & 4th Aug – 6th Nov, 2017 | 19th Nov – 26 Nov, 2017 | 16th Oct – 30th Nov, 2017 | 28th Nov – 3rd Dec, 2017 | Dec, 2017 | 2018-02-01 | 30th Oct, 2018 | 30000
OTUM/1 | 3rd Oct, 2018 | 5th Nov – 20th Nov 2017 | 25th May – 2 June, 2018 | 6th June – 10th Aug, 2018 | 15th – 20th July, 2018 | 9th – 15 August | 2018-09-25 | 15th Oct, 2018 | 9000
FORC/2 N.B. |  |  | N/A | 12th April – 30th May 2018 | 15th – 20th June 2018 | 15th – 22nd July 2018 | 24th – 30th Sept 2018 | 15th Nov., 2018 | 15000
FORC/3 S.B |  |  | N/A | 27th June – 30th Sept 2018 | 1st – 10th October, 2018 | 11th – 15th October | 28th – 30th October 2018 | 10th Dec. 2018 | 16000
OGBO/1 |  |  | N/A |  |  | 15th-17th November | 10th-15th December | 20th Dec. 2018 | 1000