## Sheet1
Facility | PO issue and Mobilization | FTO and Off-site Fabrication | Shut Down Activities | Construction | Integration | Pre-com and commissioning | Hand over
AGBD/2 | 10th Oct – 8th Nov 2018 | 25th Oct – 6th Nov, 2018 | 9th Nov- 13th Nov, 2018 | 9th Nov – 20th Dec, 2018 | 4th Jan- 13th Jan, 2019 | 14th Jan- 30th Jan, 2019 | 28th Mar, 2019
IMOR/1 | 28th June & 13th Oct, 2017 | 27th Jul & 4th Aug – 6th Nov, 2017 | 19th Nov – 26 Nov, 2017 | 16th Oct – 30th Nov, 2017 | 28th Nov – 3rd Dec, 2017 | 4th Dec, 2017 – 13th Feb, 2018
OTUM/1 | 3rd Oct, 2018 | 5th Nov – 20th Nov 2017 | 25th May – 2 June, 2018 | 6th June – 10th Aug, 2018 | 15th – 20th July, 2018 | 9th – 15 August, & 22nd Aug - 2018 | 15th Oct, 2019
FORC/4 (Yokri)
IMOR/3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BENS/1 | 10th May, 2020 & 7th June, 2020 | 4th June, 2020 & 18th – 30th July, 2020 | 8th June – 11th July, 2020 | 8th June – 27th July, 2020 | 25th July – 5th August, 2020 | 7th – 20th August, 2020 | 2020-11-01
GBAR/GP | 10th July, 2020 & 7th Aug, 2020 | 4th July, 2019 & 18th – 30th Aug, 2020 | 8th Aug – 11th Aug, 2020 | 8th Aug – 27th Sept, 2020 | 25th Sept – 5th Oct, 2020 | 7th – 20th Oct, 2020 | Feb, 2021
FORC/2 N.B.
OBGN/1 | 10th Feb, 2019 & 7th Mar, 2019 | 4th Mar, 2019 & 18th – 30th Feb, 2019 | 8th Mar – 11th Mar, 2019 | 8th Mar – 27th Apr, 2019 | 25th April – 5th May, 2019 | 7th – 20th May, 2019 | July, 2019
IMOR/2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OPUK/1
ADIB/1 | 10th July, 2020 & 7th Aug, 2020 | 4th July, 2019 & 18th – 30th Aug, 2020 | 8th Aug – 11th Aug, 2020 | 8th Aug – 27th Sept, 2020 | 25th Sept – 5th Oct, 2020 | 7th – 20th Oct, 2020 | Feb, 2021
SOKU/GP | 10th Oct – 8th Nov 2018 | 25th Oct – 6th Nov, 2018 | 9th Nov- 13th Nov, 2018 | 9th Nov – 20th Dec, 2018 | 4th Jan- 13th Jan, 2019 | 14th Jan- 30th Jan, 2019 | 28th Mar, 2019
ESCB/1 | 10th August, 2019 & 7th September, 2019 | 4th Sept, 2019 & 18th – 30th Oct, 2019 | 8th Sept – 11th Oct, 2019 | 8th Sept – 27th Oct, 2019 | 25th Oct – 5th Nov, 2019 | 7th – 20th Nov, 2019 | Mar, 2020
BONN/1 | 10th July, 2020 & 7th Aug, 2020 | 4th July, 2019 & 18th – 30th Aug, 2020 | 8th Aug – 11th Aug, 2020 | 8th Aug – 27th Sept, 2020 | 25th Sept – 5th Oct, 2020 | 7th – 20th Oct, 2020 | Feb, 2021
AHIA/1 | 10th May, 2019 & 7th June, 2019 | 4th June, 2019 & 18th – 30th July, 2019 | 8th June – 11th July, 2019 | 8th June – 27th July, 2019 | 25th July – 5th August, 2019 | 7th – 20th August, 2019 | Nov, 2019
TUNU/1
AGBD/1 | 10th Feb, 2019 & 7th Mar, 2019 | 4th Mar, 2019 & 18th – 30th Feb, 2019 | 8th Mar – 11th Mar, 2019 | 8th Mar – 27th Apr, 2019 | 25th April – 5th May, 2019 | 7th – 20th May, 2019 | July, 2019
UMUE/1 | 10th Jan, 2020 & 7th Feb, 2020 | 4th Feb, 2020 & 18th – 30th Mar, 2020 | 8th Feb – 11th Mar, 2020 | 8th Feb – 27th Mar, 2020 | 25th Mar – 5th Apr, 2020 | 7th – 20th Apr, 2020 | Aug, 2020
OBEL/1 | 10th Oct – 8th Nov 2022 | 25th Oct – 6th Nov, 2022 | 9th Nov- 13th Nov, 2022 | 9th Nov – 20th Dec, 2022 | 4th Jan- 13th Jan, 2022 | 14th Jan- 30th Jan, 2023 | 28th Mar, 2023
KOCR/1 | 10th August, 2019 & 7th September, 2019 | 4th Sept, 2019 & 18th – 30th Oct, 2019 | 8th Sept – 11th Oct, 2019 | 8th Sept – 27th Oct, 2019 | 25th Oct – 5th Nov, 2019 | 7th – 20th Nov, 2019 | Mar, 2020
ISIM/1 | 10th Oct – 8th Nov 2020 | 25th Oct – 6th Nov, 2020 | 9th Nov- 13th Nov, 2020 | 9th Nov – 20th Dec, 2020 | 4th Jan- 13th Jan, 2021 | 14th Jan- 30th Jan, 2021 | 2021-05-01
SOKU/1 | 10th Oct – 8th Nov 2018 | 25th Oct – 6th Nov, 2018 | 9th Nov- 13th Nov, 2018 | 9th Nov – 20th Dec, 2018 | 4th Jan- 13th Jan, 2019 | 14th Jan- 30th Jan, 2019 | 28th Mar, 2019
FORC/3 S.B
NKAL/1 | 10th Oct – 8th Nov 2020 | 25th Oct – 6th Nov, 2020 | 9th Nov- 13th Nov, 2020 | 9th Nov – 20th Dec, 2020 | 4th Jan- 13th Jan, 2021 | 14th Jan- 30th Jan, 2021 | 2021-05-01
OBGN/GP | 10th May, 2019 & 7th June, 2019 | 4th June, 2019 & 18th – 30th July, 2019 | 8th June – 11th July, 2019 | 8th June – 27th July, 2019 | 25th July – 5th August, 2019 | 7th – 20th August, 2019 | Nov, 2019
OGUT/1 | 10th Oct – 8th Nov 2022 | 25th Oct – 6th Nov, 2022 | 9th Nov- 13th Nov, 2022 | 9th Nov – 20th Dec, 2022 | 4th Jan- 13th Jan, 2022 | 14th Jan- 30th Jan, 2023 | 28th Mar, 2023
FORC/GP
OKOL/GP
BONN/GP1 | 10th Jan, 2020 & 7th Feb, 2020 | 4th Feb, 2020 & 18th – 30th Mar, 2020 | 8th Feb – 11th Mar, 2020 | 8th Feb – 27th Mar, 2020 | 25th Mar – 5th Apr, 2020 | 7th – 20th Apr, 2020 | Aug, 2020
OGBO/1
AGBD/GP | 10th Feb, 2019 & 7th Mar, 2019 | 4th Mar, 2019 & 18th – 30th Feb, 2019 | 8th Mar – 11th Mar, 2019 | 8th Mar – 27th Apr, 2019 | 25th April – 5th May, 2019 | 7th – 20th May, 2019 | July, 2019
2019
2018

## 2018_2019 Plan
| Facility | PO issue and Mobilization | FTO and Off-site Fabrication | Shut Down Activities | Construction | Integration | Pre-com and commissioning | Hand over
| IMOR/1 | 28th June & 13th Oct, 2017 | 27th Jul & 4th Aug – 6th Nov, 2017 | 19th Nov – 26 Nov, 2017 | 16th Oct – 30th Nov, 2017 | 28th Nov – 3rd Dec, 2017 | 4th Dec, 2017 – 13th Feb, 2018 | 30th Oct, 2018
| OTUM/1 | 3rd Oct, 2018 | 5th Nov – 20th Nov 2017 | 25th May – 2 June, 2018 | 6th June – 10th Aug, 2018 | 15th – 20th July, 2018 | 9th – 15 August, & 22nd Aug - 2018 | 15th Oct, 2018
| FORC/2 N.B. |  |  | N/A | 12th April – 30th May 2018 | 15th – 20th June 2018 | 15th – 22nd July & 24th – 30th Sept 2018 | 15th Nov., 2018
| FORC/3 S.B |  |  | N/A | 27th June – 30th Sept 2018 | 1st – 10th October, 2018 | 11th – 15th October & 28th – 30th October 2018
OGBO/1
1 | AGBD/2 | 10th May, 2019 & 7th June, 2019 | 4th June, 2019 & 18th – 30th July, 2019 | 8th June – 11th June, 2019 | 8th June – 20th Aug, 2019 | 25th Aug – 15th Sept, 2019 | 7th – 20th Oct, 2019 | Dec, 2019 | xx | xx mixer available
2 | GBAR/GP | 10th May, 2019 & 7th June, 2019 | 4th June, 2019 & 18th – 30th July, 2019 | 8th June – 11th June, 2019 | 8th June – 27th July, 2019 | 25th July – 5th August, 2019 | 7th – 20th August, 2019 | Nov, 2019
3 | OBGN/1 | 10th Apr, 2019 & 7th June, 2019 | 2nd May, 2019 & 18th – 30th May, 2019 | 8th June – 11thJune, 2019 | 8th Junr – 27th Aug, 2019 | 23rdh Augus – 15th Sep, 2019 | 7th – 20th Oct, 2019 | Dec, 2019
4 | ADIB/1 | 10th Feb, 2019 & 7th Mar, 2019 | 4th Mar, 2019 & 18th – 30th Feb, 2019 | 8th Mar – 11th Mar, 2019 | 8th Mar – 27th Apr, 2019 | 25th April – 5th May, 2019 | 7th – 20th May, 2019 | July, 2019
5 | SOKU/GP | 10th Oct – 8th Nov 2018 | 25th Oct – 6th Nov, 2018 | 9th Nov- 13th Nov, 2018 | 9th Nov – 20th Dec, 2018 | 4th Jan- 13th Jan, 2019 | 14th Jan- 30th Jan, 2019 | 28th Mar, 2019
6 | ESCB/1 | 10th Feb, 2019 & 7th Apr 2019 | 4th Mar, 2019 & 18th – 30th Mar, 2019 | 8th Apr – 11th Apr, 2019 | 8th Apr – 27th jun, 2019 | 25th Oct – 5th Nov, 2019 | 7th – 20th Nov, 2019 | Mar, 2020
7 | BONN/1 | 10th May, 2019 & 7th June, 2019 | 4th June, 2019 & 18th – 30th July, 2019 | 8th June – 11th July, 2019 | 8th June – 27th July, 2019 | 25th July – 5th August, 2019 | 7th – 20th August, 2019 | Nov, 2019
8 | SOKU/1 | 10th Feb, 2019 & 7th Apr, 2019 | 24th Mar, 2019 & 18th – 30th Feb, 2019 | 20th Apr-29 Apr, 2019 | 8th Mar – 30th Apr, 2019 | 30th April – 10th May, 2019 | 7th – 25th May, 2019 | July, 2019 | xx
FORC/4 (Yokri)
| IMOR/3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| BENS/1 | 10th May, 2020 & 7th June, 2020 | 4th June, 2020 & 18th – 30th July, 2020 | 8th June – 11th July, 2020 | 8th June – 27th July, 2020 | 25th July – 5th August, 2020 | 7th – 20th August, 2020 | 2020-11-01
| IMOR/2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OPUK/1
| AHIA/1 | 10th Oct – 8th Nov 2020 | 25th Oct – 6th Nov, 2020 | 9th Nov- 13th Nov, 2020 | 9th Nov – 20th Dec, 2020 | 4th Jan- 13th Jan, 2021 | 14th Jan- 30th Jan, 2021 | 2021-05-01
TUNU/1
| AGBD/1 | 10th Feb, 2019 & 7th Mar, 2019 | 4th Mar, 2019 & 18th – 30th Feb, 2019 | 8th Mar – 11th Mar, 2019 | 8th Mar – 27th Apr, 2019 | 25th April – 5th May, 2019 | 7th – 20th May, 2019 | July, 2019
| UMUE/1 | 10th Jan, 2020 & 7th Feb, 2020 | 4th Feb, 2020 & 18th – 30th Mar, 2020 | 8th Feb – 11th Mar, 2020 | 8th Feb – 27th Mar, 2020 | 25th Mar – 5th Apr, 2020 | 7th – 20th Apr, 2020 | Aug, 2020
| OBEL/1 | 10th Oct – 8th Nov 2022 | 25th Oct – 6th Nov, 2022 | 9th Nov- 13th Nov, 2022 | 9th Nov – 20th Dec, 2022 | 4th Jan- 13th Jan, 2022 | 14th Jan- 30th Jan, 2023 | 28th Mar, 2023
| KOCR/1 | 10th August, 2019 & 7th September, 2019 | 4th Sept, 2019 & 18th – 30th Oct, 2019 | 8th Sept – 11th Oct, 2019 | 8th Sept – 27th Oct, 2019 | 25th Oct – 5th Nov, 2019 | 7th – 20th Nov, 2019 | Mar, 2020
| ISIM/1 | 10th Oct – 8th Nov 2020 | 25th Oct – 6th Nov, 2020 | 9th Nov- 13th Nov, 2020 | 9th Nov – 20th Dec, 2020 | 4th Jan- 13th Jan, 2021 | 14th Jan- 30th Jan, 2021 | 2021-05-01
| NKAL/1 | 10th Oct – 8th Nov 2020 | 25th Oct – 6th Nov, 2020 | 9th Nov- 13th Nov, 2020 | 9th Nov – 20th Dec, 2020 | 4th Jan- 13th Jan, 2021 | 14th Jan- 30th Jan, 2021 | 2021-05-01
| OBGN/GP | 10th May, 2019 & 7th June, 2019 | 4th June, 2019 & 18th – 30th July, 2019 | 8th June – 11th July, 2019 | 8th June – 27th July, 2019 | 25th July – 5th August, 2019 | 7th – 20th August, 2019 | Nov, 2019
| OGUT/1 | 10th Oct – 8th Nov 2022 | 25th Oct – 6th Nov, 2022 | 9th Nov- 13th Nov, 2022 | 9th Nov – 20th Dec, 2022 | 4th Jan- 13th Jan, 2022 | 14th Jan- 30th Jan, 2023 | 28th Mar, 2023
FORC/GP
OKOL/GP
| BONN/GP1 | 10th Jan, 2020 & 7th Feb, 2020 | 4th Feb, 2020 & 18th – 30th Mar, 2020 | 8th Feb – 11th Mar, 2020 | 8th Feb – 27th Mar, 2020 | 25th Mar – 5th Apr, 2020 | 7th – 20th Apr, 2020 | Aug, 2020
| AGBD/GP | 10th Feb, 2019 & 7th Mar, 2019 | 4th Mar, 2019 & 18th – 30th Feb, 2019 | 8th Mar – 11th Mar, 2019 | 8th Mar – 27th Apr, 2019 | 25th April – 5th May, 2019 | 7th – 20th May, 2019 | July, 2019
Comp 2018
Comp 2019
Start 2019
By others 2019

## 2018 volume
Facility | PO issue and Mobilization | FTO and Off-site Fabrication | Shut Down Activities | Construction | Integration | Pre-Commissioning + Inhouse Val. | Commissioning [DPR Visit] | Training | Hand over | Volume Gain BBL
IMOR/1 | 28th June & 13th Oct, 2017 | 27th Jul & 4th Aug – 6th Nov, 2017 | 19th Nov – 26 Nov, 2017 | 16th Oct – 30th Nov, 2017 | 28th Nov – 3rd Dec, 2017 | Dec, 2017 | 2018-02-01 | 15th Oct | 30th Oct, 2018 | 30000
OTUM/1 | 3rd Oct, 2018 | 5th Nov – 20th Nov 2017 | 25th May – 2 June, 2018 | 6th June – 10th Aug, 2018 | 15th – 20th July, 2018 | 15th-20th Sept. | 25th - 30th Sep 2018 | 30th Sep | 15th Oct, 2018 | 9000
FORC/2 N.B. |  |  | N/A | 12th April – 30th May 2018 | 15th – 20th June 2018 | 15th Sept. | October 14th 2018 | Oct 20th | 15th Nov., 2018 | 15000
FORC/3 S.B |  |  | N/A | 27th June – 12th Sept 2018 | 25th Sept. | October [waiting for oil to introduce] | TBA [project team advise by 20th] |  | 10th Dec. 2018 | 16000
OGBO/1 |  |  | N/A |  |  | October [waiting for oil to introduce] | TBA [project team advise by 20th] |  | 20th Dec. 2018 | 1000

## Oil Allocation
|  | SPDC EAST allocated | SPDC Westt allocated | Total | EAST Impact | West Impact | Total Gain
Month | Facility | 2281211 | 1844758.4354 | 4125969.4354 | [12 empty] | USD FCF
2018-10-01 | IMO River | 2312156 | 1844758.4354 | 4156914.4354 | 30945 | 0 | 30945 | 2018 |  | 1591501.35 | -318300.27 | -83737.17 | 1189463.91 | -1011044.3235 | 178419.5865 | 262156.7565 | 78647.027 | IMO River
2018-12-01 | S. Bank | 2312156 | 1850547.3821 | 4162703.3821 | 0 | 5788.9467 | 5788.9467 |  |  | 297725.5312 | -59545.1062 | 0 | 238180.425 | -202453.3612 | 35727.0637 | 35727.0637 | 10718.1191 | S. Bank
2018-11-01 | Ogbotobo | 2312156 | 1853388.9753 | 4165544.9753 | 0 | 2841.5932 | 2841.5932 |  |  | 146143.1375 | -29228.6275 | 0 | 116914.51 | -99377.3335 | 17537.1765 | 17537.1765 | 5261.1529 | Ogbotobo
2018-12-01 | N Bank | 2312156 | 1872645.2086 | 4184801.2086 | 0 | 27886.7732 | 27886.7732 |  |  | 1434216.7451 | -286843.349 | 0 | 1147373.3961 | -975267.3866 | 172106.0094 | 172106.0094 | 51631.8028 | N Bank
2018-11-01 | Otumara | 2312156 | 2008280.4681 | 4320436.4681 | 0 | 154891.4927 | 154891.4927 |  | 222353.8059 | 7966069.4716 | -1593213.8943 | 0 | 6372855.5773 | -5416927.2407 | 955928.3366 | 955928.3366 | 286778.501 | Otumara
2019-12-01 | AGBD/2 | 2369126 | 2008280.4681 | 4377406.4681 | 56970 |  | 56970 | 2019 |  | 2929967.1 | -585993.42 | -154160.82 | 2189812.86 | -1861340.931 | 328471.929 | 482632.749 | 144789.8247 | AGBD/2
2019-11-01 | GBAR/GP | 2391233 | 2008280.4681 | 4399513.4681 | 22107 |  | 22107 |  |  | 1136963.01 | -227392.602 | -59821.542 | 849748.866 | -722286.5361 | 127462.3299 | 187283.8719 | 56185.1616 | GBAR/GP
2019-12-01 | OBGN/1 | 2412889 | 2008280.4681 | 4421169.4681 | 21656 |  | 21656 |  |  | 1113768.08 | -222753.616 | -58601.136 | 832413.328 | -707551.3288 | 124861.9992 | 183463.1352 | 55038.9406 | OBGN/1
2019-08-01 | ADIB/1 | 2415691 | 2008280.4681 | 4423971.4681 | 2802 |  | 2802 |  |  | 144106.86 | -28821.372 | -7582.212 | 107703.276 | -91547.7846 | 16155.4914 | 23737.7034 | 7121.311 | ADIB/1
2019-04-01 | SOKU/GP | 2439901 | 2008280.4681 | 4448181.4681 | 24210 |  | 24210 |  |  | 1245120.3 | -249024.06 | -65512.26 | 930583.98 | -790996.383 | 139587.597 | 205099.857 | 61529.9571 | SOKU/GP
2019-05-01 | ESCB/1 | 2439901 | 2031705.5411 | 4471606.5411 | 0 | 23425.073 | 23425.073 |  |  | 1204751.5064 | -240950.3013 | 0 | 963801.2051 | -819231.0243 | 144570.1808 | 144570.1808 | 43371.0542 | ESCB/1
2019-12-01 | BONN/1 | 2450098 | 2031705.5411 | 4481803.5411 | 10197 | 10197 | 20394 |  |  | 524431.71 | -104886.342 | -27593.082 | 391952.286 | -333159.4431 | 58792.8429 | 86385.9249 | 25915.7775 | BONN/1
2019-08-01 | SOKU/1 | 2454481 | 2031705.5411 | 4486186.5411 | 4383 |  | 4383 |  | 175947.073 | 225417.69 | -45083.538 | -11860.398 | 168473.754 | -143202.6909 | 25271.0631 | 37131.4611 | 11139.4383 | SOKU/1
[5 empty] | 173270 | 225030.8789 | 398300.8789
838128.0678
Base BP price
51.43
Oil Roalty
20%
CAPEX $
50000
Depreciation /kboe
2.706
Tax
85%

## FCF Calcs
Month | Facility | Vol. KBbl/monthly | FCF Monthly/Facility - K $ | Total Monthly K$
2018-10-01 | IMO River | 30.945 | 78.647 | 78.647
2018-11-01 | Ogbotobo | 2.8416 | 5.2612 | 83.9082
2018-11-01 | Otumara | 154.8915 | 286.7785 | 370.6867
2018-12-01 | S. Bank | 5.7889 | 10.7181 | 381.4048
2018-12-01 | N Bank | 27.8868 | 51.6318 | 433.0366
2019-04-01 | SOKU/GP | 24.21 | 61.53 | 494.5666
2019-05-01 | ESCB/1 | 23.4251 | 43.3711 | 537.9376
2019-08-01 | ADIB/1 | 2.802 | 7.1213 | 545.0589
2019-08-01 | SOKU/1 | 4.383 | 11.1394 | 556.1984
2019-11-01 | GBAR/GP | 22.107 | 56.1852 | 612.3835
2019-12-01 | AGBD/2 | 56.97 | 144.7898 | 757.1733
2019-12-01 | OBGN/1 | 21.656 | 55.0389 | 812.2123
2019-12-01 | BONN/1 | 20.394 | 25.9158 | 838.1281