## Critical Materials
LP NAG E2E MSC Critical Spares
S/n | Project Title | Planned Finished Date | Step 1 |  |  | Step 2 |  |  | Step 3 |  |  | Step 4 |  |  | Overall % Progress | Comments
|  |  | SAP Data Mining |  |  | Data Analysis (MinMax) |  |  | OR&A / MRP Joint Review |  |  | MRP Implementation in SAP
|  |  | TARGET | STATUS | % PROG | TARGET | STATUS | % PROG | TARGET | STATUS | % PROG | TARGET | STATUS | % PROG | 100%
1 | LP NAG |  | 47 | 47 | 100% | 43 | 43 | 100% | 43 | 43 | 100% | 43 | 43 | 100% | 100%
2 | OTHER SOKU FACILITIES
3 | LEGACY
|  |  | 20% |  |  | 30% |  | 0% | 20% |  | 0% | 30%
[8 empty] | #DIV/0! |  |  | #DIV/0!
|  |  | Value |  |  | Volume |  | #VALUE! |  |  | #DIV/0!
|  |  | Tega - LP Separator |  |  |  |  | #DIV/0! |  |  | #DIV/0!

## Min Max Review
LP NAG E2E MSC Critical Spares
S/n | Project Title | Planned Finished Date | Step 3 |  |  | Step 4 |  |  | Overall % Progress | Comments
|  |  | OR&A / MRP Joint Review |  |  | MRP Implementation
|  |  | TARGET | STATUS | % PROG | TARGET | STATUS | % PROG | 100%
1 | LP NAG | MRP | 43 | 43 | 100% | 43 | 43 | 100% | 100%
2 | OTHER SOKU FACILITIES
3 | LEGACY
|  |  | 20% |  | 0% | 30%
#DIV/0!
#DIV/0!
#DIV/0!

## BOM
LP NAG - BOM Completion Progress
S/n | Project Title | Planned Finished Date | Step 1 |  |  | Step 2 |  |  | Step 3 |  |  | Step 4 |  |  | Overall % Progress | Comments
|  |  | Asset Register |  |  | Manufacturer of Asset |  |  | Model Number |  |  | Serial Number
|  |  | TARGET | STATUS | % PROG | TARGET | STATUS | % PROG | TARGET | STATUS | % PROG | TARGET | STATUS | % PROG | 100%
1 | LP NAG | 22/04/2020 | 47 | 47 | 100% | 47 | 47 | 100% | 47 | 47 | 100% | 47 | 47 | 100% | 100%
2 | OTHER SOKU FACILITIES
3 | LEGACY
4
5
6
6

## WO Granularity (hidden)
LP NAG - WO Granularity Progress
S/N | Project Title | Planned Finished Date | Inputs/Start | Step 1 |  |  | Step 2 |  |  | Step 3 |  |  | Step 4 |  |  | Overall % Progress | Comments
|  |  |  | Raise Work Orders |  |  | Identify/attach materials to order |  |  | Generate PRs |  |  | Stock Pull
|  |  |  | TGT | STATUS | % PROG | TGT | STATUS | % PROG | TGT | STATUS | % PROG | TGT | STATUS | % PROG | #DIV/0!
1 | LP NAG

## Stock Accuracy (hidden)
LP NAG -Stock Accuracy Process Progress
S/n | Project Title | Planned Finished Date | Inputs / Start | Step 1 | Step 2 | Step 3 | Step 4 | Overall % Progress | Comments
|  |  |  | Wall-To-Wall First / Blind Count | Wall-To-Wall Second Count | Investigation | Reconciliation / Report | #DIV/0!
1 | LP NAG |  | MRP
|  |  |  | 40 | 20 | 10 | 30

## Most Competitive (hidden)
BBIP - Develop Credible Procuremet Plan Progress
S/n | Project Title | Planned Finished Date | Inputs/Start | Step 1 | Step 2 | Step 3 | Step 4 | Step 5 | Step 6 | Step 7 | Step 8 | Step 9 | Step 10 | Step 11 | Step 12 | Overall % Progress | Comments
|  |  |  | Kick off | Contract Short list | Contract Data | One Pager | CH meet | Spend Analysis | First Iteration | First Feedback | Second Iteration | Opportunities | Category Strategy Approval | Final Version/Report Out | 84.62%
1 | Marine | xx |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 84.62%
2 | Pipelines | xx |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 84.62%
3 | Rot Equipment | xx |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 84.62%
4 | Static Equipment | xx |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 84.62%
5 | Well Const | xx |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 84.62%
6 | Produced Water System (Train 1) | xx |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 84.62%
7 | Oil Handling System | xx |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 84.62%
8 | Heating Medium System | xx | [13 empty] | 0% | bar: Step 1 to Step 12
|  |  |  | 50 | 10
Note on F4: Ejiofor, Chiedu C SNEPCO-PTP/D/NC: MRP Implemted, WO / PR Released as input for this. ROS Date Required.
Note on G4: Ejiofor, Chiedu C SNEPCO-PTP/D/NC: MRP Implemted, WO / PR Released as input for this. ROS Date Required.

## Supermarket Model
LP NAG - Supermarket Model Process Progress
S/n | Project Title | Planned Finished Date | Inputs/Start | Step 1 | Step 2 | Step 3 | Step 3 | Step 4 | Overall % Progress | Comments
|  |  |  | MRP Implementation | System Changes | Asset Changes/ Readiness | Assurance/ Sign off | Inventory | 88.76%
1 | LP NAG | xx | Critical Spares | 100% | 100% | 100% | 60% | 27.6% | 88.76% | 13 line items available in stock
2 | OTHER SOKU FACILITIES
3 | LEGACY
1.6667
Note on F4: Raji, Iyabo SNEPCO-PTP/D/N: Replenishment @Bonga & Supply base

## Credible Procurement
LP NAG - Develop Credible Procuremet Plan Progress
S/n | Project Title | Planned Finished Date | Inputs/Start | Step 1 | Step 2 | Step 3 | Step 4 | Step 5 | Step 6 | Overall % Progress | Comments
|  |  |  | Plan | Price Agreement | PR CRTD | PR RELEASED | PO ISSUED | PO DELIVERIES | 72.4%
1 | LP NAG | xx | CRITICAL SPARES | 100% | 60% | 100% | 100% | 44% | 0% | 72.4% | 13 line items available in stock. 26 line items have price agreements. PO's issued on19 line items.
2 | OTHER SOKU FACILITIES
3 | LEGACY
[5 empty] | 10 | 71
[5 empty] | 9 | 63.9

## Contract Consolidation (hidden)
BBIP - Contract Consolidation Progress
S/n | Project Title | Planned Finished Date | Step 1 | Step 2 | Step 3 | Step 4 | Overall % Progress | Comments
0%
1 | Fuel Gas System | xx | 0% | 0% | 0% | 0% | 0%
2 | Instrument Air System | xx | 0% | 0% | 0% | 0% | 0%
3 | Waterflood System Phase 1 | xx | 0% | 0% | 0% | 0% | 0%
4 | Power Generation System | xx | 0% | 0% | 0% | 0% | 0%
5 | Produced Water System (Train 1) | xx | 0% | 0% | 0% | 0% | 0%
6 | Oil Handling System | xx | 0% | 0% | 0% | 0% | 0%
7 | Heating Medium System | xx | 0% | 0% | 0% | 0% | 0%

## Removal of Duplicates (hidden)
BBIP - Removal of Duplicate Materials in SAP Progress
S/n | Project Title | Planned Finished Date | Input / Start | Step 1 | Step 2 | Step 3 | Step 4 | Step 5 | Step 6 | Overall % Progress | Comments
|  |  |  | Identify Duplicates | Analysis | User Acceptance Test | Clean up Sign Off | Upload to Production | Production Sign Off | 0%
1 | Fuel Gas System | xx | Critical Spares List | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2 | Instrument Air System | xx |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3 | Waterflood System Phase 1 | xx |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4 | Power Generation System | xx |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5 | Produced Water System (Train 1) | xx |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6 | Oil Handling System | xx |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  |  | 10 | 30 | 20 | 10 | 20 | 10
|  |  |  | 100 | 100 | 100 | 0 | 0 | 0 | 100
0
0
0
0
0
0
0
0